## Slide 1
3GPP Work Plan
Review at Plenary #105
Source: MCC / Work Plan Manager (A. Sultan)
Agenda item: Review of the Work Plan
Document for: Information
Review based on the latest available version of the Work Plan, available at: https://ftp.3gpp.org/Information/WORK_PLAN
Includes: - the progress on all WIDs, as indicated in the WG Chairs’ reports (CT & SA) and in the Status Report (RAN), - the new WIDs proposed by SA/CT WGs to TSG#105 (will be removed if not TSG-approved)
Does not include: - the company-proposed WIDs proposed/approved at TSG#105, revised WID/SID during TSG#105
Warnings :
- This review is a high-level view of the 3GPP progress. It is based on the 3GPP Work Plan, a continuously updated document.
Some misalignments might temporarily appear on some individual items.
- Some WG cannot progress because of reasons beyond their control (e.g. dependencies with other groups).
These slides shall not be used to judge the “efficiency” of whatever WG.
© 3GPP 2024
CP-242257 (rev. of CP-242012/RP-241711/SP-241065) - 3GPP TSG#105, 9 -13 September 2024, Melbourne, Australia

## Slide 2: Content of this Work Plan review
Snapshot of all ongoing/future Releases
Ongoing Releases
  Rel-19 Timeline and Progress
  Rel-20 Timeline and Progress
  Rel-21 Timeline and Progress
Background information

## Slide 3
Releases 19 to 21 timelines
#108
Release 19
Note: All starting dates are indicative
#110
#112
#114
#116
#118
#120
#122
#124
#126
2025
2026
2028
*: +3 months for RAN4
**: - 3 months for RAN1 & + 3 months for RAN4 perf
#111
#113
#115
#119
#121
#123
#125
2027
2029
5GA Stage 1
RAN Completion**
Stage 3 (CT & SA)
ASN.1
&
Open
APIs
Stage 2
#117
#109
2024
#104
#106
#107
#105
Mar.
#103
TSGs
Mar.
Mar.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Jun.
Jun.
Jun.
Sep.
Sep.
Sep.
Sep.
Sep.
Sep.
Dec.
Dec.
Dec.
Dec.
Dec.
Dec.
Now
SA1 St.1, Content Definition (RAN & SA St.2): completed Dec. 2023
Release 20 5GA
Release 20 FS_6G
5GA Stage 2
5GA RAN Completion**
5GA Stage 3
Chart showing Normative dates
(timeline for 5GA studies not shown)
Chart showing Studies dates
(no 6G normative work in Rel-20)
FS_6G Stage 1
FS_6G RAN P
FS_6G Stage 2
or
FS_6G RAN WG**
FS_6G Stage 3
TBD
Release 21 6G
Rel-21 timeline to be decided no later than June 2026
ITU deadlines for 6G: March 2029 for technology proposal, mid-2030 for specifications

## Slide 4: Content of this Work Plan review
Snapshot of all ongoing Releases
Rel-19 Timeline and Progress
Rel-20 Timeline and Progress
Rel-21 Timeline and Progress
Background information

## Slide 5
Release 19 timeline
#101
Note: All starting dates are indicative
#102
#103
#104
#105
#106
#107
#108
#109
#110
#111
#112
#99
RAN4
content def.
RAN Content def.
2024
2025
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Mar.
Dec.
Dec.
Dec.
2026
RAN4_Perf
Stage 3 (CT & SA)
RAN1
Stage 2 (SA2, SA6,…) Normative
RAN Completion (RAN2/3/4core)
ASN.1 & Open APIs
St.2 Content approval
#100
Jun.
2023
Now
100%
SA1 Stage 1 80%
TSGs
RAN Rel-19 workshop
SA Rel-19
Workshop

## Slide 6: Release 19 progress overview (1/2)
SA1 (Stage 1): completed and stable for some time
  14 Studies, 25 Normative items
SA2, SA6 (Stage 2)
  Studies:
    1 new study: Study on SEAL Phase 4. So now 24 studies in total
    OCI* = 90% (against 81% at previous TSG). Two studies below 80%:
  Normative: TARGET IS DECEMBER 2024
    62 items (against 44 at previous TSG), OCI = 46% (against 30% at previous TSG)
    Items still below 50% (not showing the TEI19_xx items) including 3 not started:
* OCI = Overall Completion Index
1050034 | Study on SEAL Phase 4 | FS_SEAL_Ph4 | S6 | 0%
1040071 | Study on MC services support on IOPS mode of operation for 5G | FS_Generic_IOPS | S6 | 40%
1050112 | (pending WA) Energy Efficiency and Energy Saving | EnergySys | S2 | 0%
1040033 | Stage 2 of Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) | AIML_CN | S2 | 15%
1040075 | Stage 2 of Application enablement for AI/ML services | AIML_App | S6 | 40%
1040027 | Integration of satellite components in the 5G architecture Phase III | 5GSAT_Ph3_ARCH | S2 | 15%
1040077 | Application enablement for satellite access Phase 3 | 5GSAT_Ph3_App | S6 | 5%
1040076 | Application enablement for mobile metaverse services | Metaverse_App | S6 | 25%
1040032 | Extended Reality and Media service (XRM) Phase 2 | XRM_Ph2 | S2 | 5%
1040074 | Application enablement for XRM Services Phase 2 | XRM_Ph2_App | S6 | 15%
1050097 | UPF enhancement for Exposure And SBA Phase 2 | UPEAS_Ph2 | S2 | 26%
1050035 | CAPIF Phase 3 | CAPIF_Ph3 | S6 | 0%
1050036 | MC services support on IOPS mode of operation | Generic_IOPS | S6 | 0%
1050050 | Stage 2 of Enhancement of support for Edge Computing in 5G Core network - Phase 3 | eEDGE_5GC_Ph3 | S2 | 30%
1050056 | Multi-Access (ATSSS_Ph4) | MASSS | S2 | 33%
1040026 | Stage 2 of System architecture for Next Generation Real time Communication services Phase 2 | NG_RTC_Ph2 | S2 | 10%
1040028 | System aspects of 5G NR Femto | 5G_Femto | S2 | 30%
1040031 | Stage 2 of Vehicle Mounted Relays Phase 2 | VMR_Ph2 | S2 | 40%
1040085 | Stage 2 of Identifying non-3GPP Devices Connecting behind a UE or 5G-RG | UIA_ARC | S2 | 15%
1040073 | Application enablement aspects for MMTel | MMTel_App | S6 | 10%
1040072 | Stage 2 of Enhanced application layer support for location services | eLSAPP | S6 | 30%
1050071 | SEAL DD (Data Delivery) Phase 2 | SEALDD_Ph2 | S6 | 31%

## Slide 7: Release 19 progress overview (2/2)
RAN
  studies: 10 studies (against 8 at previous TSG), OCI = 51 % (against 32% at previous TSG)
  RAN Core: 41 items (against 20 at previous TSG), OCI = 25 % (against 18% at previous TSG)
  RAN Perf: 26 items (against 19 at previous TSG), OCI = 6 % (against 0% at previous TSG)
SA 3/4/5 & CT
  SA3/4/5:
    Studies: Stays at 51 studies, OCI = 64 % (against 51% at previous TSG)
    Normative: 26 items (against 20 at previous TSG), OCI = 36% (against 20% at previous TSG)
  CT WG:
    Studies: 2 studies (against 1 at previous TSG), OCI = 7 % (against 0% at previous TSG)
    Normative: 62 items (against 27 at previous TSG), OCI = 13% (against 0% at previous TSG)

## Slide 8: Release 19 timeline recap - text version
Release 19 Freezes and other milestones, sorted by dates :
  June 2023: RAN workshop on Rel-19 content, SA workshop on Rel-19 content
  Sept 2023 (TSG#101):
    Stage 1: 80% normative work
    Approve 1st part of SA Stage 2 package (SA/CT)
  Dec 2023 (TSG#102):
    Stage 1: 100% normative work
    RAN1/2/3 Content Definition
    Approve final package of SA Stage 2 with RAN/CT
  Mar 2024 (TSG#103): RAN4 Content Definition
  Sept 2024: no specific milestone
  Dec 2024 (TSG#106): Stage 2 Functional work (SA2 and SA6) Freeze (working assumption)
  June 2025 (TSG#108): RAN1 freeze
  Sept 2025 (TSG#109):
    RAN2, RAN3, RAN4Core freeze
    Stage 3 (all CT WGs; SA WGs involved with Stage 3) freeze (working assumption)
  Dec 2025 (TSG#110):
    RAN4Perf freeze; “coding freeze”. Freeze of:ASN-1; Open APIs (working assumption)
Now

## Slide 9: Content of this Work Plan review
Snapshot of all ongoing Releases
Rel-19 Timeline and Progress
Rel-20 Timeline and Progress
Rel-21 Timeline and Progress
Background information

## Slide 10
2024
#103
Mar.
#111
Mar.
#107
Mar.
#104
Jun.
#108
Jun.
#112
Jun.
#105
Sep.
#109
Sep.
#102
Dec.
#106
Dec.
#110
Dec.
Now
TSGs
SA1 5GA SID definition
Workshop 6G TSGs
100%
SA1 5GA Studies + Norm 80%
100%
St. 2 (SA2, SA6, …) 5GA St.+Norm 80%
Stage 3 5GA St + Norm
Stage 3 6G SID def.
#113
Sep.
#114
Dec.
#115
Mar.
Jun
Workshop IMT-2030 use cases
RAN1
RAN Completion (RAN2/3/4core)
#116
SA1 6G Study(ies)
RAN4 C.def.
RAN4 Perf
RP Content def.
SA1 6G SID def.
RP IMT-2030 disc.
RP ITU Study
RP 6G Study(ies)
RAN1 6G Study(ies)
SA2 6G Study(ies)
Stage 3 6G Study(ies)
Rel-20 - 5GA part
Rel-20 – FS_6G part
2025
2026
2027
SA2 & RAN WGs 6G SID def.
SA3/4/5/6 SID def. and compl. TBD
5GA ASN.1 & Open APIs
RAN2/3/4 6G Study(ies)
St.2 SID def. TBD
St.3 SID def. TBD
Release 20 timeline
or
TBD
Note: All starting dates are indicative
Workshop 5GA RAN
Workshop 5GA SA

## Slide 11: Release 20: introduction
Rel-20 has 2 components: “Rel-20_5GA” and “Rel-20_6G” (or “Rel-20_FS_6G”)
  Rel-20_5GA covers 5GA studies and normative;
  Rel-20_6G covers 6G studies only (6G normative in Rel-21)
  Up to each TSG/WG how to split their time on each component (e.g. in SA1, it is 50%-50%)

## Slide 12: Release 20_5GA
The Rel-20_5GA endorsed deadlines are: (assuming no delay on Rel-19)
  Stage 1 approval of SIDs: Jun 2024; Stage 1 normative freeze : Jun 2025
  Stage 2 approval of SIDs: NYD*; Stage 2 normative freeze : Jun 2026 (80%); Sep 2026 (100%)
  Stage 3 (CT) approval of SIDs: Mar 2026 or earlier; Stage 3 CT normative freeze : Mar 2027
  Stage 3 RAN approval of SIDs:NYD*; Stage 3 RAN normative freeze : NYD*
  ASN.1/OpenAPI freeze: June 2027
  Other WGs : + 18 months compared to Rel-19 dates, i.e. for RAN:
    Content def: June 2025
    Ran1: Dec 2026
    RAN2/3/4Core: March 2027
    RAN4 Perf: June 2027
* NYD = Not Yet Defined

## Slide 13: Release 20_FS_6G
Rel-20 work on 6G will be only on studies. The endorsed deadlines are: (assuming no delay on Rel-19)
  Stage 1 approval of SIDs: Sep 2024 (TSG 105); Stage 1 (study) freeze: Mar 2026
  March 2025 (TSG#107): First TSG-wide 6G workshop
  RAN IMT-2030 discussion is expected in RAN from 09/24 to 12/24
  RP SI Rel-20 focusing on ITU– IMT-2030: approval 12/24 until 06/25
  RP SI Rel-20 focusing on 6G General: approval 03/25 (after WS), until 06/26
  SA2 and RAN-WG SIDs approval: June 2025 (TSG 108); SA2 (study) freeze: Dec 2026 or Mar 2027
  SA1/SA2 6G SI may continue beyond Stage-1/Stage-2 freeze dates for 5G-Advanced
  Other SA WG (SA3, SA4, SA5, SA6) SIDs approval: TBD at future TSG meeting
  CT WG SIDs approval: March 2026
  RAN1 starts in 3Q/25 until 1Q/27; RAN2/3/4 start in 4Q/25 until 2Q/27
  CT WG 6G SI will start 9 months after approval of SA2 SI.
Sources: SP-240192 (SA1 chair), SP-240432 from TSG Chairs

## Slide 14: Release 20 progress overview (5GA & 6G)
5GA
  Studies: Still three SA1 studies (all approved at TSG#103, no new one):
    Study on Satellite Access Phase 4 – 60% (was 30%)
    Study on FRMCS Phase 6 – 40% (was 20%)
    Study on Energy Efficiency as Service Criteria Phase 2 - 55% (was 25%)
  Normative:
    6 “miniWIDs” approved and completed in the last 3 months in SA1
    One “basket” WID on Rel-20 Lawful Interception in SA3LI
FS_6G:
  SA1 presents one SID at TSG#105 to cover all the 6G-related work – this “single-SID-approach” is the one chosen by SA1

## Slide 15: Content of this Work Plan review
Snapshot of all ongoing Releases
Rel-19 Timeline and Progress
Rel-20 Timeline and Progress
Rel-21 Timeline and Progress
Background information

## Slide 16: Release 21
Release 21 is the release for submission to IMT-2030*, aka 6G
This implies that 3GPP (normative) work will be submitted to ITU before 2030
  ASN.1/OpenAPI freeze date is no earlier than March 2029
Release 21 Freezing dates and other milestones TBD
  Rel-21 timeline is to be decided no later than June 2026
Note that, as usual in 3GPP, previous Generations will in parallel continue to be maintained & enhanced in Rel-21 and after
* source: TSG#103-endorsed CT-240307/SP-240458/RP-240823

## Slide 17: Content of this Work Plan review
Snapshot of all ongoing Releases
Rel-18 Timeline and Progress
Rel-19 Timeline and Progress
Rel-20 Timeline and Progress
Rel-21 Timeline and Progress
Background information

## Slide 18: Background information (1/2): overall background information
Dedicated e-mail list for Work Plan aspects
Open to everyone interested (rapporteus, chairs, delegates, etc.) by sending the message “Subscribe 3GPP_WORKPLAN” to the address LISTSERV@LIST.ETSI.ORG
For comments/update to the Work Plan, please use the 3GPP_WORKPLAN list
3GPP Work Plan
http://www.3gpp.org/ftp/Information/WORK_PLAN
Contains Release 1999 to Release 20; Master version in MS Project; Working versions in Excel
Tutorials on content, maintenance and other info on the Work Plan in subfolder /info
3GPP Releases Descriptions – R99 to Rel-17
http://www.3gpp.org/ftp/Information/WORK_PLAN/Description_Releases/
“Releases Descriptions” for Releases 8 to 13: limited to copy-paste of the WIDs.
“Releases Descriptions” for Releases 14 to 17: TR 21.9xx: “Release xx Description; Summary of Rel-xx Work Items”, written in collaboration with all the Rel-xx Features Rapporteurs
3GPP Releases Descriptions – Rel-18
Progressing – v.1.2.0 at TSG#105

## Slide 19: Background information (2/2): Relationship between WGs, Stages and deadlines
Most 3GPP Working Groups handle only one Stage:
  SA1  Stage 1
  SA2  Stage 2; SA6  Stage 2
  CT WGs  Stage 3 (also Stage 2 for some specific items)
SA3, SA4 and SA5 handle several Stages for some or all their WIDs:
  SA3: handles Stages 2 and 3 for all its WIDs. Stage 2 at SA3 is one quarter after SA2/SA6’s deadline, but this date is an SA3-internal date since there is no dependency (i.e. SA3 is not expecting work from any other WGs)
  SA4: handles Stage 2 for some WIDs (for which SA4 might rely on CT WGs for Stage 3), and Stage 3 for a majority of its WIDs. Stage 2 WIDs in SA4 are clearly identified as such and have the same deadline as SA2/SA6’s date.
  SA5: handles Stages 1, 2 and 3 for all its WIDs. Stage 1 for SA5 is 4 quarters after SA1’s date. Stage 2 for SA5 is 2 quarters after SA2/SA6’s date. Stage 3 for SA5 is same date as CT WGs’ date.
  For SA3, SA4 and SA5, the completion date for all WIDs dealing with Stage 3 (fully or partially) is the same as for CT WGs.
  In this Work Plan review slides, SA3, SA4 and SA5 are reported in the “Stage 3” slides since their overall completion date is aligned with (CT’s) Stage 3. Except for SA4’s Stage 2-only WIDs but this cannot be handled by the present tools.
RAN has a slightly different process. RAN defines two dates:
  The “RAN Content Definition”, which is the same date as SA Stage 1 and SA content definition
  The “RAN Completion”, which is the same date as SA/CT’s Stage 3
  Note that there is no specific RAN-equivalent date for SA/CT’s Stage 2