## Cover sheet
3GPP TSG-RAN WG5 Meeting #105 | [7 empty] | R5-247133
Orlando, Florida, Nov 18-22, 2024
Agenda Item: | 7.5.2
Source: | Qualcomm Incorporated
Title: | WP - UE Conformance - New bands and bandwidth allocation for LTE based 5G terrestrial broadcast
Work item code: | LTE_terr_bcast_bands_part2-UEConTest
Release: | Rel-18
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
<Description of work item and its scope>
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 5% (+5%) | 0 | 6 (+6)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
LTE (FR1) |  | 5% (+5%) | 0 | 6 (+6)
FR1 |  | 5% (+5%) | 0 | 6 (+6)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508 | 0% |  |  | 0%
UE specific test functions | 36.509
LTE RF/RRM
RF common parts | 36.521-1 | 0% |  |  | 0%
RF Rx test cases | 36.521-1 Rx | 0% | 0 | 3 (+3) | 0% | 0 | 3 (+3)
RF Tx test cases | 36.521-1 Tx
RF Demod test cases | 36.521-1 Demod | 0% | 0 | 3 (+3) | 0% | 0 | 3 (+3)
Applicability RF. Demod/QSI and RRM test cases | 36.521-2 | 0% |  |  | 0%
RRM test cases | 36.521-3
Test Tolerances analysis RRM test cases | 36.903
Test Tolerances analysis receiver test cases | 36.904
Test Point analysis receiver and transmitter test cases | 36.905
LTE RAN and CN protocols
Protocol test cases | 36.523-1
Applicability Protocol test cases | 36.523-2
Test suites (TTCN) | 36.523-3
5 References
[1] RP-242026 | New WID on New bands and bandwidth allocation for LTE based 5G terrestrial broadcast - UEConTest
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP - UE Conformance - New bands and bandwidth allocation for LTE based 5G terrestrial broadcast | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | LTE_terr_bcast_bands_part2-UEConTest
WP Scope: |  | This part of the work plan covers RF receiver, Demodulation, Protocol and RRM test cases for the LTE based 5G terrestrial broadcast (5GB)
WP Resp: |  | Vijay Balasubramanian |  |  | vijayb@qti.qualcomm.com | [5 empty] | WP item completion |  |  | LTE
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | LTE |  | FR1
5% (+5%)
11 (+11)
9.5 (+9.5)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
TS 36.508: Common test environment
1 |  | 36.508 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
2 |  | 36.508 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 1 | 0% | 0% |  | 0%
3 |  | 36.508 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
TS 36.509: UE specific testing functions
4 |  | 36.509 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
5 |  | 36.509 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
6 |  | 36.509 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
LTE RF/RRM
TS 36.521-1: RF test cases - Common parts (general clauses, Annexes)
7 |  | 36.521-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
8 |  | 36.521-1 | 5.5H | Operating bands for LTE based 5G terrestrial broadcast |  |  | TBD |  |  | 0.5 | 0% | 0% |  | 0%
9 |  | 36.521-1 | 5.6H | PMCH bandwidths per operating band for LTE based 5G terrestrial broadcast | <Describe task> |  | TBD |  |  | 0.5 | 0% | 0% |  | 0%
10 |  | 36.521-1 | 5.7.3H | Carrier frequency and EARFCN for LTE based 5G terrestrial broadcast | <Describe task> |  | TBD |  |  | 0.5 | 0% | 0% |  | 0%
TS 36.521-1: RF test cases - Rx
11 |  | 36.521-1 Rx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
12 |  | 36.521-1 Rx | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
16 |  | 36.521-1 Rx | 7.3 | Reference sensitivity power level | <Describe required change of the existing test case> |  | TBD |  |  | 0
17 | Y | 36.521-1 Rx | 7.3.1H | Reference sensitivity requirements for LTE based 5G terrestrial broadcast | verify Refsens requirements for LTE based 5GB |  | TBD |  |  | 1 | 0% | 0% |  | 0%
16 |  | 36.521-1 Rx | 7.4 | Maximum input level | <Describe required change of the existing test case> |  | TBD |  |  | 0
17 | Y | 36.521-1 Rx | 7.4.1H | Maximum input level requirements for LTE based 5G terrestrial broadcast | verify Max input level requirements for LTE based 5GB |  | TBD |  |  | 1 | 0% | 0% |  | 0%
16 |  | 36.521-1 Rx | 7.5 | Adjacent Channel Selectivity (ACS) | <Describe required change of the existing test case> |  | TBD |  |  | 0
17 | Y | 36.521-1 Rx | 7.5.1H | ACS requirements for LTE based 5G terrestrial broadcast | verify Max input level requirements for LTE based 5GB |  | TBD |  |  | 1 | 0% | 0% |  | 0%
TS 36.521-1: Demod/CSI reporting test cases
|  | 36.521-1 Demod |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 36.521-1 Demod | 10 | Performance requirement (MBMS) | Exiting clause |  | TBD |  |  | 0
TBD |  | 36.521-1 Demod | 10.4 | FDD with 5G terrestrial broadcast | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD |  | 36.521-1 Demod | 10.4.1 | Minimum requirement for PMCH decoding | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 36.521-1 Demod | 10.4.1.1 | PMCH decoding performance with 0.37kHz SCS for 5G terrestrial broadcast | Verifying the minimum requirements for PMCH decoding with 0.37kHz SCS |  | TBD |  |  | 1 | 0% | 0% |  | 0%
TBD | Y | 36.521-1 Demod | 10.4.1.2 | PMCH decoding performance with 2.5kHz SCS for 5G terrestrial broadcast | Verifying the minimum requirements for PMCH decoding with 2.5kHz SCS |  | TBD |  |  | 1 | 0% | 0% |  | 0%
TBD |  | 36.521-1 Demod | 10.4.2 | Minimum requirement for CAS detection | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 36.521-1 Demod | 10.4.2.1 | PBCH decoding performance for 5G terrestrial broadcast | Verifying the minimum requirements for PBCH decoding |  | TBD |  |  | 1 | 0% | 0% |  | 0%
TS 36.521-2: Applicability for RF, Demod/CSI reporting and RRM test cases
TBD |  | 36.521-2 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0.1
TBD |  | 36.521-2 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced for 36.521-1 and 38.521-3. |  | TBD |  |  | 1 | 0% | 0% |  | 0%
TS 36.521-3: RRM test cases
|  | 36.521-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 36.521-3 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 36.521-3 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 36.521-3 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TR 36.903: Test Tolerances analysis RRM test cases
|  | 36.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 36.903 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 36.903 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
TR 36.904: Test Tolerances analysis receiver test cases
|  | 36.904 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 36.904 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 36.904 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
TR 36.905: Test Point analysis receiver and transmitter test cases
|  | 36.905 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 36.905 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 36.905 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
LTE RAN and CN protocols
TS 36.523-1: Protocol test cases
|  | 36.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
Idle Mode
TBD |  | 36.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD |  | 36.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD | Y | 36.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
Layer 2
TBD |  | 36.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD |  | 36.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD | Y | 36.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
RRC
TBD |  | 36.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD |  | 36.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD | Y | 36.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
NAS
TBD |  | 36.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD |  | 36.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD | Y | 36.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TS 36.523-2: Applicability for Protocol test cases
TBD |  | 36.523-2 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0.1
TBD |  | 36.523-2 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced in 36.523-1 |  | TBD |  |  | 0.1
TS 36.523-3: Protocol test suites (TTCN)
|  | 36.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 36.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.