## Cover sheet
3GPP TSG-RAN5 Meeting #105 | [8 empty] | R5-247492
Orlando, United States, 18th Nov 2024 - 22nd Nov 2024
Agenda Item: | 7.5.2
Source: | Apple, Rohde & Schwarz, Vivo
Title: | UE Conformance - Enhancement of UE TRP and TRS requirements and test methodologies for FR1 (NR SA and EN-DC)
Work item code: | NR_FR1_TRP_TRS_enh-UEConTest
Release: | Rel-18
Document for: | Information
RAN5 WP template v2.0-8
1. Introduction
The objective of this work plan is to track contributions towards the RAN5 test specifications enable UE conformance testing for the corresponding Rel-18 NR FR1 TRP TRS Enhancement Work Items
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 30% | 0 | 0
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR1) |  | 30% | 0 | 0
FR1 |  | 0% | 0 | 0
NSA Option 3 (EN-DC) |  |  | 0 | 0 | Only placeholder and skeleton structure added as core and test requirements are not within Rel-17 scope.
FR1 |  | 0% | 0 | 0 | Only placeholder and skeleton structure added as core and test requirements are not within Rel-17 scope.
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) |  |  |  |  | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  |  |  | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases |  |  | Completion | Number of new completed test cases | Number of new test cases
5GS
NR RF TRP and TRS requirements and test methodologies for FR1 (SA and EN-DC)
TS 38.561:Common Clauses 1-5 | 38.561
TS 38.561 Clause 6 - FR1 Tx: FR1 Transmitter (TRP) Performance | 38.561 | 30% | 0 | 0 | 30% |  | 0 |  |  | 30% |  | 0
TS 38.561 Clause 7 - FR1 Rx: FR1 Receiver (TRS) Performance | 38.561 |  | 0 | 0 |  |  | 0 |  |  |  |  | 0
TS 38.561 Annexes | 38.561
5 References
[1] RP-241503 | New WID: UE Conformance - Enhancement of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC)
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance - Enhancement of UE TRP and TRS requirements and test methodologies for FR1 (NR SA and EN-DC) | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_FR1_TRP_TRS_enh-UEConTest
WP Scope: |  | The purpose of this document is to create and track development of test requirements and procedures for Rel-18 enhancements for FR1 OTA (TRP/TRS) for Standalone and EN-DC
WP Resp: |  | Ashwin Mohan, Jose Fortes, Ruixin Wang |  |  | ashwin_mohan@apple.com | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) | NSA Option 3 (EN-DC)
TS Resp: |  | Ashwin Mohan |  |  | ashwin_mohan@apple.com
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments (include where references to CTIA are included) | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) |  | FR1 | FR1
[15 empty] | 30% | 5%
0%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
NR RF TRP and TRS requirements and test methodologies for FR1 (SA and EN-DC)
TS 38.561: Scope, References, Definitions, Frequency Bands
1 |  | 38.561 | 1 | Scope |  |  | RAN5#106 (Feb-25) |  | 3GPP Defined | 0.5 | 0% | 0% |  |  | 0%
2 |  | 38.561 | 2 | References | The reference, especially of CTIA test plans, is updated to the latest active version. |  | RAN5#106 (Feb-25) |  | 3GPP Defined | 0.2 | 100% | 100% |  |  | 100%
3 |  | 38.561 | 3 | Definition of terms, symbols and abbreviations | Some Abbreviations are added |  | RAN5#106 (Feb-25) |  | 3GPP Defined | 0.2 | 100% | 100% |  |  | 100%
TS 38.561: General Information Clause
4 |  | 38.561 | 4 | General | Relationship between minimum conformance requirements and test requirements, Applicability Rules. No updates expected in Rel-18 |  |  |  | 3GPP Defined | 0.7 | 0% | 0% |  |  | 0%
5 |  | 38.561 | 5 | Frequency Bands | Clause Header |  |  |  | 3GPP Defined
6 |  | 38.561 | 5.1 | General |  |  | RAN5#106 (Feb-25) |  | 3GPP Defined | 0.7 | 80% | 80% | 80% |  | 80% | 80%
7 |  | 38.561 | 5.2 | Operating Bands | SA FR1 bands and EN-DC FR1 combinations; Updates to EN-DC decision Tree |  | RAN5#106 (Feb-25) |  | 3GPP Defined | 0.7 | 80% | 80% |  |  | 80%
8 |  | 38.561 | 5.3 | Test Parameters | Test Parameters updated as per Rel-18 | Apple | RAN5#106 (Feb-25) |  | 3GPP Defined | 0.7 | 80% | 80% |  |  | 80%
TS 38.561 FR1 Tx: FR1 Transmitter (TRP) Performance
9 |  | 38.561 FR1 Tx | 6 | FR1 Transmitter TRP Performance | Clause Header |  |  |  | TC owner completes headers and introduction
10 |  | 38.561 FR1 Tx | 6.1 | General | Introductory Description |  |  |  | TC owner completes headers and introduction | 0.1
11 |  | 38.561 FR1 Tx | 6.2 | TRP Performance for Handheld UE |  |  |  |  | TC owner completes headers and introduction | 0.1
12 |  | 38.561 FR1 Tx | 6.2.1 | TRP Performance for Handheld UE for FR1 (NR SA and EN-DC) |  |  |  |  | TC owner completes headers and introduction | 0.1
13 |  | 38.561 FR1 Tx | 6.2.1.1 | Total Radiated Power (TRP) in Browsing Mode with Hand Phantom |  |  |  |  | TC owner completes headers and introduction | 0.5
14 |  | 38.561 FR1 Tx | 6.2.1.1.1 | Total Radiated Power (TRP) for FR1 NR Standalone (SA) in Browsing Mode with Hand Phantom | Update PC3 requirements and also test requirements for new bands. The tables for TRP and TRS requiremens have been updated to reflect the bandwidth and usage scenario for easy understanding. | Apple | RAN5#106 (Feb-25) |  | 3GPP Defined | 1 | 100% | 100% |  | 90 | 100%
15 |  | 38.561 FR1 Tx | 6.2.1.1.2 | Total Radiated Power (TRP) for FR1 NR EN-DC in Browsing Mode with Hand Phantom (NOTE 1) | Update skeleton as needed and reference to updated decision tree. No details added |  | RAN5#106 (Feb-25) |  | Test Structure skeleton only. No test requirements defined in Release 18 | 1 | 0% |  | 0% |  |  | 0%
16 |  | 38.561 FR1 Tx | 6.2.1.2 | Total Radiated Power (TRP) with Beside the head and hand phantom |  |  | RAN5#106 (Feb-25) |  |  | 0.5
17 |  | 38.561 FR1 Tx | 6.2.1.2.1 | Total Radiated Power (TRP) for FR1 NR Standalone (SA) with Beside the head and hand phantom (NOTE 1) | Update test case with Rel-18 test requirements and update test procedures | Apple | RAN5#106 (Feb-25) |  |  | 1 | 10% | 10% |  |  | 10%
18 |  | 38.561 FR1 Tx | 6.2.1.2.2 | Total Radiated Power (TRP) for FR1 NR EN-DC with Beside the head and hand phantom (NOTE 1) | Update skeleton as needed and reference to updated decision tree. No details added | Vivo | RAN5#106 (Feb-25) |  | Test Structure skeleton only. No test requirements defined in Release 18 | 1 | 0% |  | 0% |  |  | 0%
TS 38.561 FR1 Rx: FR1 Receiver (TRS) Performance
19 |  | 38.561 FR1 Rx | 7 | FR1 Receiver TRS Performance | Clause Header |  |  |  | TC owner completes headers and introduction
20 |  | 38.561 FR1 Rx | 7.1 | General | Introductory Description |  |  |  | TC owner completes headers and introduction | 0.1
21 |  | 38.561 FR1 Rx | 7.2 | Total Radiated Sensitivity (TRS) Performance for Handheld UE |  |  |  |  | TC owner completes headers and introduction | 0.2
22 |  | 38.561 FR1 Rx | 7.2.1 | Total Radiated Sensitivity (TRS) Performance for Handheld UE for FR1 (NR SA and EN-DC) |  |  |  |  | TC owner completes headers and introduction | 0.2
23 |  | 38.561 FR1 Rx | 7.2.1.1 | Total Radiated Sensitivity (TRS) in Browsing Mode with Hand Phantom |  |  |  |  | Includes full test structure including Test Requirements | 0.5
24 |  | 38.561 FR1 Rx | 7.2.1.1.1 | Total Radiated Sensitivity (TRS) for FR1 NR Standalone (SA) in Browsing Mode with Hand Phantom | Update with requirements for new bands. The tables for TRP and TRS requiremens have been updated to reflect the bandwidth and usage scenario for easy understanding. | Apple | RAN5#106 (Feb-25) |  | 3GPP Defined | 1 | 100% | 100% |  | 90 | 100%
25 |  | 38.561 FR1 Rx | 7.2.1.1.2 | Total Radiated Sensitivity (TRS) for FR1 NR EN-DC in Browsing Mode with Hand Phantom (NOTE 1) | Update skeleton as needed and reference to updated decision tree. No details added |  | RAN5#106 (Feb-25) |  | Test Structure skeleton only. No test requirements defined in Release 18 | 1 | 0% |  | 0% |  |  | 0%
26 |  | 38.561 FR1 Rx | 7.2.1.2 | Total Radiated Sensitivity (TRS) with Beside the head and hand phantom | [5 empty] | 0.2
27 |  | 38.561 FR1 Rx | 7.2.1.2.1 | Total Radiated Sensitivity (TRS) for FR1 NR Standalone (SA) with Beside the head and hand phantom (NOTE 1) | Update test case with Rel-18 test requirements and update test procedures | Apple, Vivo | RAN5#106 (Feb-25) |  |  | 1 | 10% | 10% |  |  | 10%
28 |  | 38.561 FR1 Rx | 7.2.1.2.2 | Total Radiated Sensitivity (TRS) for FR1 NR EN-DC with Beside the head and hand phantom (NOTE 1) | Update skeleton as needed and reference to updated decision tree. No details added | Vivo | RAN5#106 (Feb-25) |  | Test Structure skeleton only. No core or test requirements defined in Release 17 | 1 | 0% |  | 0% |  |  | 0%
38.561 Annex A : Test Methodology
29 |  | 38.561 Annex A | Annex A.1 | General |  |  | RAN5#106 (Feb-25) |  |  | 0.5 | 0% | 0% | 0% |  | 0% | 0%
30 |  | 38.561 Annex A | Annex A.2 | UE Configuration |  |  | RAN5#106 (Feb-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
31 |  | 38.561 Annex A | Annex A.3 | Test System - Anechoic Chamber Method | - Add additional granurality from TR 38.870 after review. - Update to measurement grids - The definition of TRP and TRS for AC is clarified. - Introduce test procedures and metrics to verify performance of UEs supporting TxD and/or UL-MIMO aligned with TR 38.870 | Apple | RAN5#106 (Feb-25) | R5-245448 |  | 1 | 0% | 0% |  |  | 0%
32 |  | 38.561 Annex A | Annex A.4 | Estimation of Measurement Uncertainty | Annex Header |  |  |  | Clause owner(s) completes headers and introduction | 0
33 |  | 38.561 Annex A | Annex A.4.1 | General | Definitions and description of section | R&S | RAN5#107 (May-25) |  |  | 0.5 | 0% | 0% | 0% |  | 0% | 0%
34 |  | 38.561 Annex A | Annex A.4.2 | Measurement Uncertainty of Test System | Updates to MU of Conformance Test System for FR1 TRP/TRS; Target Date RAN5#106 (February 2025). MU Work Plan is TBD Updates for RC MU and Talk Mode for AC MU. | R&S | RAN5#107 (May-25) |  | TBD (RAN5 MU Work Plan for Rel18) | 1 | 0% | 0% | 0% |  | 0%
35 |  | 38.561 Annex A | Annex A.4.3 | Test Tolerances | TT across defined conformance tests for FR1 (SA) TRP and TRS | Apple | RAN5#106 (Feb-25) |  | Will be listed within the test case clause as well. This section is placeholder for summary within Annex | 1 | 0% | 0% | 0% |  | 0%
36 |  | 38.561 Annex A | Annex TBD | Test System - Reverberation Chamber Method (FFS Placeholder) | FFS for now. Add details of this alternate method (specific to 1Tx as per Rel-18 Core Part) from TR 38.870 after review and pending RAN4 completion | FFS | FFS |  |  | 1 | 0% | 0% |  |  | 0%
38.561 Annex B : Phantom Definitions and Positioning
37 |  | 38.561 Annex B | Annex B.1 | General |  |  | RAN5#106 (Feb-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
38 |  | 38.561 Annex B | Annex B.2 | Phantom Definitions | Add forearm phantom definition for RedCAP Ues Some corrections for Hand phantom as per R4-2318972. Addition of head and hand phantom as per R4-2318972 | Apple, R&S | RAN5#106 (Feb-25) |  | Leveraged from CTIA Definitions Aligns with TR 38.870 and TS 38.161. Additional analysis if needed, for EN-DC, will be FFS once RAN4 provides requirments or EN-DC test methodology updates in Rel-18 | 1 | 20% | 20% | 20% |  | 20% | 20%
39 |  | 38.561 Annex B | Annex B.3 | UE positioning guidelines | Update for RedCap UEs |  | RAN5#106 (Feb-25) |  | Leveraged from CTIA Definitions Aligns with TR 38.870 and TS 38.161 | 1 | 20% | 20% | 20% |  | 20% | 20%
38.561 Annex C : Environmental Requirements
40 |  | 38.561 Annex C | Annex C.1 | General |  |  | RAN5#106 (Feb-25) |  | Aligns with TR 38.870 and TS 38.161 | 1 | 0% | 0% | 0% |  | 0% | 0%
41 |  | 38.561 Annex C | Annex C.2 | Environmental |  |  | RAN5#106 (Feb-25) | R5-244444 (Email) | Aligns with TR 38.870 and TS 38.161 | 1 | 50% | 50% | 50% |  | 50% | 50%
38.561 Annex D : Maximum uncertainty of Test system and Test Tolerance
42 |  | 38.561 Annex D | Annex D.1 | Maximum uncertainty of test system | Update MU values as needed for AC for Rel-18 and add RC MU values |  | RAN5#106 (Feb-25) | R5-246004 | Earlier agreed TT/MU ratio is entered | 1 | 50% | 50% | 50% |  | 50% | 50%
43 |  | 38.561 Annex D | Annex D.2 | Test Tolerances | Update TT values as needed for AC for Rel-18 and add RC MU values |  | RAN5#106 (Feb-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
38.561 Annex E (Placeholder): Test Case Applicability or Test Point Analysis for FR1 (SA and EN-DC) TRP and TRS test cases
44 |  | 38.561 Annex E | Annex D.1 | Placeholder for FR1 SA TRP test case applicability |  | FFS | FFS |  | FFS | 0.1
45 |  | 38.561 Annex E | Annex D.2 | Placeholder for FR1 SA TRS test case applicability |  | FFS | FFS |  | FFS | 0.1
46 |  | 38.561 Annex E | Annex D.3 | Placeholder for FR1 EN-DC test case applicability (NOTE 1) |  | FFS | FFS |  | FFS | 0.1
47 |  | 38.561 Annex E | Annex D.4 | Placeholder for FR1 EN-DC test case applicability (NOTE 1) |  | FFS | FFS |  | FFS | 0.1
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
|  |  | NOTE 1 | Only placeholder and skeleton structure added as no test requirements are in Rel-18 WID scope
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.