## Slide 1: MCC TF160 Status Report
Olivier Genoud
Task Force 160 Leader, 3GPP MCC

## Slide 2
TTCN workflow Simplified view
Note: Each step above has a feedback loop to any previous step(s) (e.g. prose/TTCN bug report).
Who:
RAN5_SIG
TF160 +
SS Vendors
TF160
SS Vendor(s) +
UE Vendor(s) +
TF160
Where:
RAN5 meeting
TTCN Workshop
ETSI
SS/UE Vendor
lab
scope of this report
Notes: ASP: Abstract Service Primitive
SS: System Simulator
TTCN: Testing and Test Control Notation (version 3)
UE: User Equipment

## Slide 3
Test Models – 5G:
  Rel-15:
    NR BWP Switch: endorsed ASP updates to help SS adapter identifying the type of BWP switch being requested by TTCN.
  Rel-18:
    NR MC enh: endorsed Test Model & ASP updates to support multi-cell scheduling by a single DCI, using new DCI formats 0_3 and 1_3.
    NR NW energy savings (NES): endorsed Test Model & ASP updates to support new DCI format 2_9 and associated functionalities.
  Prose CRs to TS 38.523-3 submitted at RAN5#105 for the above.
Test models & system interface design Progress at TTCN Workshop #67 (22nd Oct’24)
Notes: ASP: Abstract Service Primitive

## Slide 4
Test Models – MCX:
  Rel-18 type definitions baseline:
    Rel-18 Jun’24 not compatible with Rel-17 => endorsed upgrading several XSDs to the corrected Rel-18 Sep’24 version.
    TS 24.581 Rel-18 not compatible with Rel-17 and earlier. CT1 decided not to change TS 24.581 Rel-18 => endorsed MCX ASP updates to deal with those incompatibilities.
  Rel-16 MCData:
    HTTP request: endorsed addition of new header field ‘Accept’, needed by TC 6.8.4.
  Prose CRs to TS 36.579-x submitted at RAN5#105 for the above.
RAN5 TTCN Workshop #67 material:
  https://portal.3gpp.org/Home.aspx#/meeting?MtgId=60813
Test models & system interface design Progress at TTCN Workshop #67 (22nd Oct’24)
Notes: ASP: Abstract Service Primitive

## Slide 5: TTCN development Progress for period: Sep to Nov’24
Completed:
  5G Rel-16:
    Redirection with MPS ind.
    DAPS handover, intra-band contiguous
  5G Rel-17:
    Multi-SIM NR devices
    NR SDT in INACTIVE state
  NB-IoT Rel-18:
    SENSE - NB-IoT
  LTE:
    Rel-14+ network policy
    Rel-16 ethernet header compression
    Rel-17 UAS conn., id., tracking
    Rel-18 SENSE - eMTC
Started:
  5G Rel-17:
    NR NTN - NGSO
    NR MBS - Broadcast
    UAS conn., id., tracking
  5G Rel-18:
    eRedCap
  NB-IoT Rel-18:
    IoT NTN enhancements
Progressed:
  5G Rel-15:
    P-CSCF restoration
  5G Rel-16:
    V2X with NR sidelink
    NR unlicensed (NR-U)
  5G Rel-17:
    NR NTN - GSO
    MR-DC further enhancements
    NR coverage enhancements
  LTE:
    Rel-9 P-CSCF restoration
    Rel-12 ACB per PLMN
  Mission Critical:
    Rel-16 MCData over LTE
Notes: Completed: The TTCN of all test cases is ready for verification.
Progressed: TTCN development ongoing, not yet completed.
Started: TTCN development has started since last report.
Suspended: TTCN development on hold due to external blocker.

## Slide 6: TTCN verification Progress for period: 14th Aug --> 13th Nov’24
Completed:
Feature | 3GPP Release | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
LTE RACS | Rel-16 | none | 4 / 4 | +1 | 
Notes: Completed: Since last report, the TTCN of all remaining test cases has been verified and agreed.

## Slide 7: TTCN verification Progress for period: 14th Aug --> 13th Nov’24
Progressed – 5G (EN-DC, NR/5GC):
Feature | 3GPP Release | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
EN-DC access stratum | Rel-15 | 503 | 96 / 102 | = | 
NR/5GC access stratum | Rel-15 | 503 | 155 / 164 | = | 
NR/5GC NR-DC | Rel-15 | 503 | 14 / 24 | = | 
NR/5GC NR CA | Rel-15 | 510 | 31 / 33 | = | 
EN-DC NR CA | Rel-15 | 512 | 14 / 18 | = | 
5G private network - SNPN | Rel-16 | 518 | 7 / 9 | = | 
NR mobility enhancements | Rel-16 | 522 | 10 / 16 | = | 
NR UE power saving | Rel-16 | 533 | 3 / 9 | = | 
IMS eCall over NR/5GC (38.523) | Rel-16 | 537 | 4 / 15 | +2 | 
MR-DC & NR CA enhancements | Rel-16 | none | 6 / 28 | +3 | +3 under verification
MPS Priority Indication | Rel-16 | none | 3 / 4 | +1 | 
NR reduced capability (RedCap) | Rel-17 | 530 | 7 / 10 | = | 
5G NW slicing enhancements - Phase 2 | Rel-17 | none | 7 / 8 | = | 
NR UE power saving enhancements | Rel-17 | 540 | 1 / 5 | = | 
NR eDRX | Rel-17 | 541 | 3 / 4 | = | 
NR RAN slicing enhancement | Rel-17 | none | 4 / 8 | = | 
Notes: Progressed: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 8: TTCN verification Progress for period: 14th Aug --> 13th Nov’24
Progressed – IMS, Positioning, MCX:
Feature | 3GPP Release | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
LTE positioning | Rel-9+ | 166, RTF-115 | 17 / 27 | = | 
MCPTT over LTE (IPCAN test model) | Rel-14 | 288, RFT-153 | 38 / 51 | = | 
IMS eCall over LTE (34.229) | Rel-14 | 298 | 5 / 12 | = | 
MCData over LTE (IPCAN test model) | Rel-14 | 329, RFT-153 | 4 / 28 | = | 
MCPTT enhancements over LTE (IPCAN test model) | Rel-15 | 330, RFT-153 | 5 / 22 | = | 
IMS over NR/5GC | Rel-15 | 505 | 93 / 95 | = | 
NR Positioning | Rel-16 | none | 10 / 29 | = | 
Notes: Progressed: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 9: TTCN verification Progress for period: 14th Aug --> 13th Nov’24
Progressed – 4G (LTE, eMTC, NB-IoT):
Feature | 3GPP Release | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
CA intra-band contiguous | Rel-11 | 162 | 20 / 21 | = | Left: TC 7.1.2.11.1(multiple TA)
SCE-PHY | Rel-12 | 245 | 6 / 9 | = | 
eDRX | Rel-13 | 253 | 4 / 5 | = | Left: TC 9.2.4.1.3(emergency call)
eMTC (CAT-M1) | Rel-13 | 254-A | 14 / 15 | = | Left: TC 7.1.4.3a(Lch prioritization)
eMTC (CIoT) | Rel-13 | 254-C | 2 / 5 | = | 
NB-IoT (CAT-NB1) | Rel-13 | 257 | 72 / 73 | = | Left: TCs 22.1.1.M2
LAA | Rel-13 | 272 | 1 / 2 | = | Left: TC 8.3.1.32(RSSI measurement)
eNB-IoT | Rel-14 | 295 | 11 / 14 | = | Left: SC-PTM (in iWD-003), IRAT with E-UTRA
IMS eCall over LTE (36.523) | Rel-14 | 298 | 4 / 9 | = | 
Notes: Progressed: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 10: TTCN verification Progress for period: 14th Aug --> 13th Nov’24
Starting:
Feature | 3GPP Release | Priority (GCF / PTCRB) | Verified TC # | Progress | Comments
MCPTT over LTE (E-UTRA test model) | Rel-14 | 288, RFT-153 | 0 / 51 |  | +1 under verification
Notes: Started: lists the features for which at least one (first) test case has been submitted and agreed since the last report.
Starting: lists the feature for which no test case has yet been verified, but at least one submission has been made, which is under review (consultation period still running).

## Slide 11
2023 Tasks (carried over) | Rel- | RAT | Prose Target | SIG TC # | TTCN Develpmt | 2024 WkLoad | TTCN Development Status (as of Nov’24) / Comments
MCX Client enhancements | R15to16 | L | Q3’24 | 79 | Q1’23-Q4’24 | 2.5 | 86% (@iwd-24wk37)
5G V2X with NR sidelink | Rel-16 | N,L | Q4’24 | 73 | Q4’20-Q1’25 | 3 | 60% (@iwd-24wk37)
NR in unlicensed spectrum (NR-U) | Rel-16 | N,L | Q4’24 | 15 | Q1’22-Q4’24 | 2 | 95% (@iwd-24wk37)
NB-IoT in non-terrestrial network (NTN) | Rel-17 | L | Q1’24 | 49 | Q1’23-Q2’24 | 1 | 100% (@iwd-24wk24)
LTE/NR multi-USIM UE (MUSIM) | Rel-17 | N,L | Q3’23 | 14 | Q4’22-Q1’25 | 1 | 50% (@iwd-24wk37)
NR & MR-DC SON/MDT enhancements | Rel-17 | N,L | Q3’23 | 11 | Q4’22-Q4’24 | 0.5 | 91% (@iwd-23wk49)
NR multi/broadcast services (MBS) | Rel-17 | N | Q4’23 | 45 | Q4’22-Q2’25 | 2.5 | 5% (@iwd-24wk37)
EN-DC user plane integrity protection | Rel-17 | L,N | Q1’24 | 5 | Q1’23-Q1’24 | 0.5 | 100% (@iwd-24wk12)
NR sidelink enhancements | Rel-17 | N | Q1’25 | 2 | Q4’22-Q1’25 | 0.5 | Not started ; no prose
NR sidelink relay | Rel-17 | N | Q1’25 | 40 | Q4’22-Q2’25 | 0.5 | Not started
NR coverage enhancements | Rel-17 | N | Q1’24 | 17 | Q1’23-Q1’25 | 2 | 47% (@iwd-24wk37)
NR SDT in INACTIVE state | Rel-17 | N | Q3’24 | 8 | Q1’23-Q3’24 | 1 | 100% (@iwd-24wk37)
NR for non-terrestrial networks (NTN) | Rel-17 | N | Q1’25 | 22 | Q1’23-Q1’25 | 3 | 86% (@iwd-24wk37)
5G non-public network enhancements | Rel-17 | N | Q3’24 | 19 | Q1’23-Q4’24 | 2 | 95% (@iwd-24wk24)
NR QoE management and optimizations | Rel-17 | N | Q3’24 | 2 | Q1’23-Q4’24 | 0.5 | 5% ; Test Model work
NR MIMO (further) enhancements | R16to17 | N | Q2’24 | 11 | Q1’23-Q1’25 | 1.5 | 18% (@iwd-24wk12)
New/extended bands & band combinations | R16to18 | L,N | Q2’25 | n/a | Q1’21-Q2’25 | 0.5 | 48% (@iwd-24wk37)
TTCN maintenance & deliveries |  |  |  |  | Q1–Q4 | 45 | 
Release & configuration management |  |  |  |  | Q1–Q4 | 6 | 
Total: |  |  |  | 412 |  | 75.5 | person-months
TTCN workplan 2024
Status of 2023 tasks carried over and maintenance
Notes: Note: TTCN of some features initially started in 2023 will only be completed in 2024 due to availability of prose late in CY2023, especially those which impacts the Test Models.
Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.

## Slide 12
2024 Tasks | Rel- | RAT | Prose Target | SIG TC # | TTCN Develpmt | 2024 WkLoad | TTCN Development Status (as of Nov’24) / Comments
MR-DC further enhancement | Rel-17 | N | Q2’24 | 4 | Q1’24-Q4’24 | 1 | 50% (@iwd-24wk37)
UAS connectivity, identification and tracking | Rel-17 | N,L | Q3’24 | 12 | Q1’24-Q4’24 | 2 | 50% (@iwd-24wk37)
IMS voice & NW usability no E-UTRA in 5GS | Rel-17 | N,L | Q2’24 | 2 | Q1’24-Q2’24 | 0.5 | 100% (@iwd-24wk24)
5G ATSSS – Phases 1 & 2 | R16to17 | N,W | Q3’24 | 15 | Q2’24-Q1’25 | 0.5 | Not started
Signal level enhanced network selection (SENSE) | Rel-18 | L | Q1’24 | 6 | Q1’24-Q3’24 | 1 | 100% (@iwd-24wk37)
Dual Tx/Rx MUSIM for NR | Rel-18 | N | Q2’25 | 4 | Q3’24-Q3’25 | 1 | Not started
IoT NTN with enhancements | Rel-18 | L | Q4’25 | 5 | Q3’24-Q4’25 | 1.5 | 20% (@iwd-24wk37)
Enhanced RedCap NR UE | Rel-18 | N | Q4’25 | 13 | Q3’24-Q4’25 | 2 | 23% (@iwd-24wk37)
NR multi-carrier enhancements | Rel-18 | N | Q4’25 | 24 | Q3’24-Q4’25 | 2 | 5% ; Test Model work
NR coverage further enhancements | Rel-18 | N | Q4’25 | 19 | Q3’24-Q4’25 | 1.5 | 2% ; Test Model work
NR network energy savings | Rel-18 | N | Q4’25 | 8 | Q3’24-Q4’25 | 1 | 5% ; Test Model work
XR enhancements for NR | Rel-18 | N | Q4’25 | 18 | Q3’24-Q4’25 | 1.5 | Not started
NR mobility further enhancements | Rel-18 | N | Q4’25 | 13 | Q4’24-Q4’25 | 1 | 10% (@iwd-24wk37)
5G non-public networks (NPN) – Phase 2 | Rel-18 | N | Q4’25 | 9 | Q4’24-Q4’25 | 0.5 | Not started ; no prose
Expanded & improved NR positioning | Rel-18 | N | Q2’26 | 9 | Q4’24-Q4’26 | 0.5 | Not started ; no prose
TEIx_Test (misc. test coverage enhancement) | Rel-9+ | All | Q4’24 | 30 | Q1’24-Q4’24 | 4 | 2024 total after RAN5#105: 26 new tests
Total: |  |  |  | 191 |  | 21.5 | person-months
TTCN workplan 2024
Status of new 2024 tasks
Notes: Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.

## Slide 13
2024 workload is estimated at 97 person-months (pm), see previous slides.
PCG#51/OP#50 approved the 3GPP funding of 58 pm for 2024 TTCN tasks.
CTIA/PTCRB and GCF have agreed to continue TF160 financial support in 2024.
Current commitments for 2024 are as follows:
3GPP companies / 3GPP MRPs committed to provide 19 pm as voluntary contributions for 2024 TTCN development.
Total resources of 97 pm  no estimated funding gap.
TTCN funding 2024
Status
Funding |  | 
Entity | Person-months | Comments
3GPP | 58 | PCG#51/OP#50 approved (decision OP50/14)
GCF | 12 | NR-NTN, NR-SDT, feMR-DC, eRedCap, NR-feMobility
CTIA/PTCRB | 6 | NR-(f)eCoverage, NR-(f)eMIMO, NR-feMobility, SENSE, NwEnergySav
Qualcomm | 2 | NR-(e)NTN, LTE/NR-eUAV
Total: | 78 | 
TTCN experts free-of-charge |  | 
Entity | Person-months | Comments
TDIA (CAICT, CATT, HiSilicon, Starpoint) | 14 | 
Adare | 3 | 
Keysight | 1 | 
Rohde&Schwarz | 1 | 
Total: | 19 | 

## Slide 14
Course of action to secure funding for TF160 work in 2025:
  Prior to RAN5#104 meeting (August), a request to identify the potential TTCN development tasks in 2025 has been made to 3GPP members.
  At RAN5#104, a provisional ‘TTCN Tasks List’ has been endorsed by RAN5.
  The TTCN Tasks List has been presented at RAN#105 (Sep) and endorsed by TSG RAN.
  The RAN Chair has presented the List to 3GPP PCG/OP (Nov) in order to support TF160 request for the TTCN funding in 2025. 3GPP PCG/OP has approved the 2025 TTCN funding request from TSG RAN of 58 person-months.
  The finalized TTCN Tasks List will be reviewed and endorsed at RAN5#105 (Nov) for TSG RAN approval at RAN#106 (Dec).
Based on inputs to RAN5#105, the updated list of TTCN tasks is presented in the next slides.
Preparing for 2025 TTCN Work
Overview

## Slide 15
2024 Tasks (carried over) | Rel- | RAT | Prose Target | SIG TC# | TTCN Develpmt | 2025 WkLoad | 3GPP related Work Item
5G V2X with NR sidelink | Rel-16 | N,L | Q4’24 | 73 | Q4’20-Q1’25 | 1.5 | 5G_V2X_NRSL_eV2XARC-UEConTest
LTE multi-USIM UE (MUSIM) | Rel-17 | L | Q3’23 | 7 | Q4’24-Q1’25 | 1 | LTE_NR_MUSIM_plus_CT1-UEConTest
NR multi/broadcast services (MBS) | Rel-17 | N | Q4’23 | 45 | Q4’22-Q2’25 | 2.5 | NR_MBS_5MBS_5MBUSA-UEConTest
NR sidelink enhancements | Rel-17 | N | Q1’25 | 2 | Q4’22-Q1’25 | 0.5 | NR_SL_enh-UEConTest
NR sidelink relay | Rel-17 | N | Q1’25 | 40 | Q4’22-Q2’25 | 2.5 | NR_SL_Relay-UEConTest
NR MIMO further enhancements | Rel-17 | N | Q2’24 | 10 | Q1’23-Q1’25 | 0.5 | NR_feMIMO-UEConTest
5G ATSSS – Phases 1 & 2 | R16to17 | N,W | Q3’24 | 15 | Q2’24-Q1’25 | 1 | ATSSS-UEConTest, ATSSS_Ph2-UEConTest
Dual Tx/Rx MUSIM for NR | Rel-18 | N | Q2’25 | 4 | Q3’24-Q3’25 | 0.5 | NR_DualTxRx_MUSIM-UEConTest
IoT NTN with enhancements | Rel-18 | L | Q4’25 | 5 | Q3’24-Q4’25 | 0.5 | IoT_NTN_enh_plus_CT1-UEConTest
Enhanced RedCap NR UE | Rel-18 | N | Q4’25 | 13 | Q3’24-Q4’25 | 1 | NR_redcap_enh_plus_CT1-UEConTest
NR multi-carrier enhancements | Rel-18 | N | Q4’25 | 24 | Q3’24-Q4’25 | 2 | NR_MC_enh-UEConTest
NR coverage (further) enhancements | R17to18 | N | Q4’25 | 28 | Q3’24-Q4’25 | 1 | NR_cov_enh(2)-UEConTest
NR network energy savings | Rel-18 | N | Q4’25 | 8 | Q3’24-Q4’25 | 0.5 | Netw_Energy_NR-UEConTest
XR enhancements for NR | Rel-18 | N | Q4’25 | 18 | Q3’24-Q4’25 | 1.5 | NR_XR_enh_plus_CT1-UEConTest
NR mobility further enhancements | Rel-18 | N | Q4’25 | 10 | Q4’24-Q4’25 | 1 | NR_Mob_enh2-UEConTest
5G non-public networks (NPN) – Phase 2 | Rel-18 | N | Q4’25 | 9 | Q4’24-Q4’25 | 1 | eNPN_Ph2-NGRAN_plus_CT1-UEConTest
Expanded & improved NR positioning | Rel-18 | N | Q2’26 | 9 | Q4’24-Q4’26 | 1 | NR_pos_enh2-UEConTest
New/extended bands & band combinations | R18to19 | L,N | Q4’26 | n/a | Q1’21-Q4’26 | 0.5 | NR_lic_bands_BW_R1x-UEConTest (new), NR_CADC_NR_LTE_DC_R1x-UEConTest (new), IoT_NTN_{extLband/FDD_LS_band}-UEConTest, NR_FDD_bands_R18_redcap-UEConTest (new)
TTCN maintenance & deliveries |  |  |  |  | Q1–Q4 | 45 | 
Release & configuration management |  |  |  |  | Q1–Q4 | 6 | 
Total: |  |  |  | 320 |  | 71 | person-months
Preparing for 2025 TTCN Work – Tasks List
2024 tasks completion and maintenance
Notes: Note: TTCN of some features initially started in 2024 will only be completed in 2025 due to availability of prose late in CY2024, especially those which impacts the Test Models.
Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.

## Slide 16
2025 Tasks | Rel- | RAT | Prose Target | SIG TC # | TTCN Develpmt | 2025 WkLoad | 3GPP related Work Item
LTE Band 106 (3 MHz BW) | Rel-18 | L | Q1’25 | n/a | Q1’25-Q2’25 | 2 | LTE_900MHz_US-UEConTest
NR FR1 less than 5MHz BW (3 MHz BW) | Rel-18 | N | Q4’25 | n/a | Q1’25-Q4’25 | 2 | NR_FR1_lessthan_5MHz_BW-UEConTest
NR MT SDT | Rel-18 | N | Q4’25 | 6 | Q1’25-Q4’25 | 1.5 | NR_MT_SDT-UEConTest
NR/MR-DC IDC enhancements | Rel-18 | N,W | Q2’26 | 5 | Q1’25-Q2’26 | 1 | NR_IDC_enh-UEConTest
NR air-to-ground network | Rel-18 | N | Q2’25 | ~2 | Q1’25-Q4’25 | 0.5 | NR_ATG-UEConTest
NR MIMO evolution for DL & UL | Rel-18 | N | Q4’25 | ~2 | Q1’25-Q4’25 | 0.5 | NR_MIMO_evo_DL_UL-UEConTest
Enhanced NR support for high-speed train scenario in FR2 | Rel-18 | N | Q4’25 | ~2 | Q1’25-Q4’25 | 0.5 | NR_HST_FR2_enh-UEConTest
MCX Client – Rel-17 enhancements | Rel-17 | L,N | Q3’25 | ~30 | Q1’25-Q4’25 | 4 | MCProtoc17_enh3MCPTT_eMCData3_ MCOver5GS-UEConTest
LTE based 5G terrestrial broadcast | Rel-18 | L | Q4’25 | ~20 | Q1’25-Q4’25 | 3 | LTE_terr_bcast_bands_part2-UEConTest
NR NTN & enhancements | R17to18 | N | Q4’25 | ~35 | Q1’25-Q4’25 | 3 | NR_NTN_solutions_plus_CT-UEConTest, NR_NTN_enh_plus_CT-UEConTest
IMS data channel | Rel-18 | N,L | Q4’25 | ~20 | Q1’25-Q4’25 | 2 | NG_RTC-UEContest
NR MBS enhancements | Rel-18 | N | Q4’25 | TBD | Q1’25-Q4’25 | 2 | NR_MBS_enh_5MBS_Ph2-UEConTest (new)
eCall over IMS alignment with CEN | Rel-19 | N,L | Q2’25 | ~16 | Q1’25-Q3’25 | 1 | eCallCEN-UEConTest (new)
5G ATSSS – Phase 3 | Rel-18 | N,W | 2025 | ~8 | 2025 | 1 | ATSSS_Ph3 / no test Work Item yet
NR support for UAV | Rel-18 | N | 2025 | TBD | 2025 | 1 | NR_UAV, UAS_Ph2 / no test Work Item yet
NR sidelink relay enhancements | Rel-18 | N | 2025 | TBD | 2025 | 1 | NR_SL_relay_enh / no test Work Item yet
Railways features for MCX Client | Rel-18 | N | 2025 | TBD | 2025 | 1 | MC_AHGC_eMCSMI_Irail-UEConTest (new)
TEIx_Test (misc. test coverage enhancement) | Rel-8+ | All | n/a | 20 | Q1’25-Q4’25 | 3 | TEIx_Test
Total: |  |  |  | >166 |  | 30 | person-months
Preparing for 2025 TTCN Work – Tasks List
New 2025 tasks
Notes: Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.

## Slide 17
2025 workload is estimated at 101 person-months (pm), see previous slides.
PCG#53/OP#52 approved the 3GPP funding of 58 pm for 2025 TTCN tasks.
GCF has agreed to continue TF160 financial support in 2025.
Current commitments for 2025 are as follows:
3GPP companies / 3GPP MRPs committed to provide 19 pm as voluntary contributions for 2025 TTCN development.
Total resources of 91 pm  estimated funding gap of 10 pm.
   3GPP member companies and 3GPP MRPs are respectfully asked to consider providing funding support for the TTCN tasks in 2025.
Preparing for 2025 TTCN Work
Funding
Funding |  | 
Entity | Person-months | Comments
3GPP | 58 | PCG#53/OP#52 approved
GCF | 12 | 
Qualcomm | 2 | eCallCEN, NR-eNTN, NR_Mob_enh2
Total: | 72 | 
TTCN experts free-of-charge |  | 
Entity | Person-months | Comments
TDIA (CAICT, CATT, HiSilicon, Starpoint) | 14 | 
Adare | 3 | 
Keysight | 1 | 
Rohde&Schwarz | 1 | 
Total: | 19 | 
Notes: MRPs: Market Representation Partners

## Slide 18: Annexes

## Slide 19: TTCN deliveries and baseline 2024 schedule
One TTCN-2 full delivery (FDD) and five TTCN-3 full deliveries.
Type definitions baseline upgrade to 3GPP Release 18 required in 2024:
  Rel-18 Stage3 freeze declared by 3GPP in March 2024.
  Rel-18 ASN.1 freeze declared by 3GPP in June 2024.
Week number | iWD delivery date | TTCN CR cut-off date | TTCN agreement status report | Type of delivery | Comment
 wk03 |  |  | 19-Jan |  | GCF CAG#77 (24-25 Jan)
 wk09 |  |  | 01-Mar |  | PTCRB PVG#104 (5-7 Mar)
 wk12 | 22-Mar | 18-Mar | 22-Mar | TTCN-3 | 
 wk16 |  |  | 19-Apr |  | GCF CAG#78 (23-24 Apr)
 wk19 |  |  | 10-May |  | PTCRB PVG#105 (14-16 May)
 wk22 |  |  | 31-May |  | GCF CAG#78bis (4 Jun)
 wk24 | 14-Jun | 10-Jun | 14-Jun | TTCN-3 | 
 wk29 |  |  | 19-Jul |  | GCF CAG#79 (23-24 Jul)
 wk32 | 09-Aug | 31-Jul |  | TTCN-3 Rel-18 Baseline upgrade | Move to Rel-18 Jun’24 baseline
 wk32 |  |  | 09-Aug |  | PTCRB PVG#106 (13-15 Aug)
 wk37 | 13-Sep | 09-Sep | 13-Sep | TTCN-3 | 
 wk41 |  |  | 11-Oct |  | GCF CAG#80 (15-16 Oct)
 wk44 |  |  | 01-Nov |  | PTCRB PVG#107 (5-7 Nov)
wk49 | 06-Dec | 02-Dec |  | TTCN2 (FDD) | 
wk50 | 13-Dec | 09-Dec | 13-Dec | TTCN-3 | 

## Slide 20: TTCN deliveries and baseline 2025 schedule
One TTCN-2 full delivery (FDD) and four TTCN-3 full deliveries.
Type definitions baseline upgrade in 2025:
  Rel-18 Phase2: partial upgrade to Rel-18 Dec’24 baseline for NR+5GC+E-UTRA+LPP due to new/updated ASN.1+tabular IEs required by Rel-18 NR/5GC, NB-IoT & POS test cases.
Week number | iWD delivery date | TTCN CR cut-off date | TTCN agreement status report | Type of delivery | Comment
wk03 |  |  | 17-Jan |  | GCF CAG#81 (21-22 Jan)
wk09 |  |  | 28-Feb |  | PTCRB PVG#108 (4-6 Mar)
wk11 | 14-Mar | 10-Mar | 14-Mar | TTCN-3 Rel-18 phase2 baseline upgrade | Partial upgrade to Rel-18 Dec'24 baseline for NR+5GC+E-UTRA+LPP
wk17 |  |  | 25-Apr |  | GCF CAG#82 (29-30 Apr)
wk19 |  |  | 09-May |  | PTCRB PVG#109 (13-15 May)
wk24 | 13-Jun | 09-Jun | 13-Jun | TTCN-3 | 
wk29 |  |  | 18-Jul |  | GCF CAG#83 (22-23 Jul)
wk32 |  |  | 08-Aug |  | PTCRB PVG#110 (12-14 Aug)
wk38 | 19-Sep | 15-Sep | 19-Sep | TTCN-3 | 
wk41 |  |  | 10-Oct |  | GCF CAG#84 (14-15 Oct)
wk44 |  |  | 31-Oct |  | PTCRB PVG#111 (4-6 Nov)
wk49 | 05-Dec | 01-Dec |  | TTCN2 (FDD) | 
wk50 | 12-Dec | 08-Dec | 12-Dec | TTCN-3 | 

## Slide 21: Minutes of TTCN Sidebar
Wednesday 20th November @8.30AM EST.
Agenda and minutes:
  See RAN5#105_TTCN_Sidebar-v3.zip