## Slide 1: SA WG5 input for Rel-20 Planning
Zou Lan, SA5 Chair, Huawei

## Slide 2
Release 20 timeline– figure with SA5 (recommended by SA5 leaders)
Reference：SP-241424
2024
#103
Mar.
#111
Mar.
#107
Mar.
#104
Jun.
#108
Jun.
#112
Jun.
#105
Sep.
#109
Sep.
#102
Dec.
#106
Dec.
#110
Dec.
Now
TSGs
SA1 5GA SID definition
Workshop 6G TSGs
100%
SA1 5GA Studies + Norm 80%
100%
St. 2 (SA2, SA6, …) 5GA St.+Norm 80%
Stage 3 5GA St + Norm
Stage 3 6G SID def.
#113
Sep.
#114
Dec.
#115
Mar.
Jun
Workshop IMT-2030 use cases
RAN1
RAN Completion (RAN2/3/4core)
#116
SA1 6G Study(ies)
RAN4 C.def.
RAN4 Perf
RP Content def.
SA1 6G SID def.
RP IMT-2030 disc.
RP ITU Study
RP 6G Study(ies)
RAN1 6G Study(ies)
SA2 6G Study(ies)
Stage 3 6G Study(ies)
Rel-20 – FS_6G part
2025
2026
2027
SA2 & RAN WGs 6G SID def.
SA3/4/6 SID def. and compl. TBD
5GA ASN.1 & Open APIs
RAN2/3/4 6G Study(ies)
St.2 SID def. TBD
St.3 SID def. TBD
Release 20 timeline
or
TBD
Note: All starting dates are indicative
Workshop 5GA RAN
Workshop 5GA SA
Management Stage 2/Stage3 St.+Norm supporting SA&RAN (SA5)
3GPP SA5
Time plan
OAM/CH prime feature:
Start of Rel-20 study: Jan.2025 (SA#107/SA5#159)
End of Rel-20 work: Mar.2027 (SA#115/SA5#172)
OAM/CH support to network feature (SA5 is ready to support network features pending the availability of inputs from other WGs. )
Start of Rel-20 study: Jun.2025 (SA#108/SA5#161)
End of Rel-20 study: Mar.2027 (SA#115/SA5#172)
SA5 6G SID def.
SA5 6G Study(ies)
Rel-20 - 5GA part
OAM/CH prime Stage1
The content of this slides is preliminary information for comments

## Slide 3: Detailed Rel-20 time plan with 5GA/6G
Overall Plan:
OAM/CH prime feature:
  Start of Rel-20 study: Jan.2025 (SA#107/SA5#159)
  End of Rel-20 work: Mar.2027 (SA#115/SA5#172)
OAM/CH support to network feature (SA5 is ready to support network features pending the availability of inputs from other WGs. )
  Start of Rel-20 study: Jun.2025 (SA#108/SA5#161)
  End of Rel-20 study: Mar.2027 (SA#115/SA5#172)
5GA:
OAM/CH Prime:
  OAM/CH prime Stage-1 freeze: Jun 2025 – (same as SA1 stage-1 freeze)
  Stage-2 freeze : Jun 2026 (>=80%); Sep 2026 (100%) – (same as SA2 stage-2 freeze)
  Stage-3 freeze : Mar 2027 – (same as CT stage-3 freeze)
OAM/CH support network features:
  OAM/CH support Stage-1 freeze : Dec 2025 – (6 months later than SA1 stage-1 freeze)
  Stage-2 freeze: Sep 2026 (>=80%); Dec 2026 (100%) – (3 months later than SA2 stage-2 freeze)
  Stage-3 freeze : Mar 2027 – (3 months earlier than CT OpenAPI/ASN.1 freeze)
6G SI Approval:
OAM/CH Prime:
  SA5 SI approval: TSG#108 (Jun 2025) – (same as SA2 SI approval)
OAM/CH support:
  SA5 SI approval: TSG#110 (Dec 2025) – (6 months later than SA2 SI approval)
6G SI completion:
OAM/CH Prime:
  SA5 6G SI completion: Dec 2026 or Mar 2027 (To be confirmed at future TSG meeting)
OAM/CH support:
  SA5 6G SI completion: Dec 2026 or Mar 2027 (To be confirmed at future TSG meeting) ·
The content of this slides is preliminary information for comments

## Slide 4: SA5 Rel-20 capacity summary
SA5 capacity:
  Max TUs: 124 (OAM) / 80 (Charging)
    Additional buffer TUs: 61(OAM)/40(CH)
  Max number of SIs/WIs: 10~15 (OAM) / 6~10 (Charging)
    Note: one feature made up of SI+WI is counted as one item
  Max TUs per Feature: 12~8 TU
Assumptions
  Start: Jun 2025, End: Mar 2027 (21 months)
  One track for OAM and One track for Charging
  Number of meetings: 10
  Expected total TUs per meeting (for all releases): 18.5 (OAM) / 12 (Charging)
  Total TUs (for all releases): 185 (OAM) / 120 (Charging)
  TUs for maintenance of past releases: 35 (OAM) / 18 (Charging)
The content of this slides is preliminary information for comments

## Slide 5: TU allocation portion of 5GA part/6G part in Rel-20
SA5 has discussed the TU allocation and hasn’t reached agreement yet. The following information are currently under discussion:
  Management support of network features:
    for management of RAN: follow the RAN2/RAN3 split allocation: e.g. x% (5GA), y%(6G)
    for management of 5GC: follow the SA2 split allocation e.g. m% (5GA), n%(6G)
  OAM Prime features:
    Option A (bottom up): Decide the TU allocation when we have a full Rel-20 feature list.
    Option B (top down): Give the budget allocation for OAM prime features with considering companies’ inputs on how to split it.
      Samsung opinion is to consider 30% of total 6G TU for 5GA for OAM prime feature.

## Slide 6: Potential Rel-20 management features workshop (planned)
Plan for management Feature Workshop (details to be updated according to the availability of inputs):
The scope of the workshops is 5GA related new management features including OAM/CH prime features and management support to new network features.
  January 2025: Online presentation on potential topics and directions (4 TUs)
  February 2025 (SA5#159): Contributions more focused on concrete topics, especially on management prime features (2 TUs)
Draft Agenda
  Opening of the workshop
  Contributions from 3GPP member companies
    Contributions on potential Rel-20 management use cases and requirements, etc.
    Up to one contribution per company
  Chairman's summary and open discussion
  Closing of the workshop
  Please feel free to contact Chair if you plan to provide presentation, and it will be helpful to make better planning for this activity.

## Slide 7: Thank you

## Slide 8: SA5 calendar with OAM TU (one track)
Time | Monday | Tuesday | Wednesday | Thursday | Friday (Closing plenary)
Q0 (8:00~8:55) (If needed) | NA | Breakout (opt.) | Breakout (opt.) | Breakout (opt.) | Closing plenary Start at 8:30am (may change depends on the host restriction)
Q1 (9:00 - 10:30) | Plenary Session#1 (1TU) [Single Stream] | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Closing plenary
10:30 - 11:00 | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break
Q2 (11:00 - 12:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Closing plenary
12:30 - 14:00 | Lunch | Lunch | Lunch | Lunch | Lunch
Q3 (14:00 - 15:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Closing plenary
15:30 - 16:00 | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break
Q4 (16:00 - 17:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Revision session | Closing plenary
17:30 - 17:40 | Break | Break | Break | Break | Break
Q5 (17:40 – 19:10) | Stream#1 (1TU) | Stream#1 (0.5 TU) Stop around 18:45 Social evening | Stream#1 (1TU) | Revision session | 
Assumption: Every day = 5 sessions (TUs), total TU in 1 ordinary meeting (exclude closing plenary TUs) = 18.5 TUs

## Slide 9: TU Budget for SA5 OAM
Assumptions for SA5 OAM :
  6 ordinary meeting per year.
  Rel-20 spans 21 months for SA5 (with early start of studies) = 10 meetings
  1 Session = 1.5 hour time window
  Max 5 sessions per meeting day
  1 Stream = 1 TU (Time Unit)
  1 TU is time (i.e., 1.5 hours) spent to discuss/handle technical contributions.
  Revisions/Drafting/offline conference call are not counted for the TU estimates.
  OAM revision sessions normally planned to be in Thursday Q4 and Q5 (initial assump.)
  1 parallel (OAM) stream per session => 18.5 TUs per meeting (incl. 2 TUs as buffer) = 185
  Assume Maintenance + Buffer = 33% as in SA2 => ~ 61 TU
  Resulting total TUs avail. f. SI/WI: 10 meetings x 18.5 sessions = 185 TU minus 61 => 124 TU
  With 15 SI/WI => Average 8 TU per SI/WI (0.8/meeting).

## Slide 10: SA5 Rel-20 OAM TU planning (Jan.2025~Mar.2027)
 | Maintenance+R18/R19 | R19 | R20 | R21 preparation | Buffer (revision session)
Jan.2025~Jun.2025: SA5#159~#161 (3 meetings) (OAM prime stage-1 freeze) | 1.5 TU*3 meetings= 4.5 TU (CRs) | 13 TU*3 meetings= 39 TU | 2 TU*3 meetings = 6 TU | NA | 2 TU*3=6 TU
Jun.2025~Sep.2025: SA5#162 (1 meeting) (Last meeting for Rel-19) | 1.5 TU (CRs) | 13 TU | 2 TU | NA | 2 TU
Oct.2025~Dec.2025: SA5#163~#164 (2 meetings) (OAM support stage-1 freeze) | 2.5 TU*2 meetings= 5 TU (CRs) | NA | 14 TU*2 meetings = 28 TU | NA | 2 TU*2=4 TU
Jan.2026~Dec.2026: SA5#165~#169 (5 meetings) (Stage-2 freeze) | 2.5 TU*5 meetings= 12.5 TU (CRs) | NA | 14 TU*5 meetings = 70 TU | NA | 2 TU*5=10 TU
Jan. 2027~Mar.2027: SA5#170~#171 (2 meetings) (stage-3 freeze) | 1.5 TU*2 meetings = 3 TU (CRs) | NA | 12 TU*2 meetings = 24 TU | 3 TU*2 meetings = 6 TU | 2 TU*2=4 TU
Total=185 TU | 22 TU | 13 TU | 124 TU | 6TU | 20 TU
Assumptions:
Every meeting day = 5 quarters (= 5 TUs)
Total TUs per meeting = 18.5 TUs
  Buffer = 2 TUs
  OAM = 16.5 TUs
    Maintenance CRs + remaining Rel-19 work (TU allocation will decrease over time )
    Rel-21 preparation work (TU allocation will be zero at the beginning and will increase over time )
    All remaining time is available for Rel-20 SIDs / WIDs
Total TUs allocated to Rel-20 SIDs / WIDs = 124 TUs

## Slide 11: SA5 calendar with CH TU (one track)
Time | Monday | Tuesday | Wednesday | Thursday | Friday (Closing plenary)
Q0 (8:00~8:55) (If needed) |  | Breakout (opt.) | Breakout (opt.) |  | Closing plenary Start at 8:30am (may change depends on the host restriction)
Q1 (9:00 - 10:30) | Plenary Session#1 (1TU) [Single Stream] | Stream#1 (1TU) | Stream#1 (1TU) | Revision session | Closing plenary
10:30 - 11:00 | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break
Q2 (11:00 - 12:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Revision session | Closing plenary
12:30 - 14:00 | Lunch | Lunch | Lunch | Lunch | Lunch
Q3 (14:00 - 15:30) | Stream#1 (1TU) | Stream#1 (1TU) | Offline session | CH Closing | Closing plenary
15:30 - 16:00 | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break
Q4 (16:00 - 17:30) | Stream#1 (1TU) | Stream#1 (1TU) | Offline session | CH Closing | Closing plenary
17:30 - 17:40 | Break | Break | Break | Break | Break
Q5 (17:40 – 19:10) | Stream#1 (1TU) | Social evening | Offline session (Opt.) | CH Closing(Opt.) | 
Assumption: Every day = 5 sessions (TUs), total TU in 1 ordinary meeting (exclude closing plenary and offline TUs) = 12 TUs

## Slide 12: TU Budget for SA5 CH
Assumptions for SA5 CH :
  6 ordinary meeting per year.
  Rel-20 spans 21 months for SA5 (with early start of studies) = 10 meetings
  1 Session = 1.5 hour time window
  Max 5 sessions per meeting day
  1 Stream = 1 TU (Time Unit)
  1 TU is time (i.e., 1.5 hours) spent to discuss/handle technical contributions.
  Revisions/Drafting/offline conference call are not counted for the TU estimates.
  CH revision sessions normally planned to be in Thursday Q1 and Q2 (initial assump.),CH closing plenary planned to be in Thursday Q3 and Q4.
  1 (CH) stream per session => 12 TUs per meeting (incl. 2 TUs as buffer) = 120
  Assume Maintenance + Buffer = 33% as in SA2 => ~ 40 TU
  Resulting total TUs avail. f. SI/WI: 10 meetings x 10 sessions = 120 TU minus 40 => 80 TU
  With 10 SI/WI => Average 8 TU per SI/WI (0.8/meeting).
  Note: TU capacity for CH could be extended if more topics are proposed.

## Slide 13: SA5 Rel-20 CH TU planning (Jan.2025~Mar.2027)
Assumptions:
Every meeting day = 5 quarters (= 5 TUs)
Total TUs per meeting = 12 TUs
  Buffer = 2 TUs
  CH = 10 TUs
    Maintenance CRs + remaining Rel-19 work (TU allocation will decrease over time )
    Rel-21 preparation work (TU allocation will be zero at the beginning and will increase over time )
    All remaining time is available for Rel-20 SIDs / WIDs
Total TUs allocated to Rel-20 SIDs / WIDs = 80 TUs
 | Maintenance+R18/R19 | R19 | R20 | R21 preparation | Buffer (revision session)
Jan.2025~Jun.2025: SA5#159~#161 (3 meetings) (CH prime stage-1 freeze) | 1.5 TU*3 meetings= 4.5 TU (CRs) | 7.5 TU*3 meetings= 22.5 TU | 1 TU*3 meetings = 3 TU | NA | 2 TU*3=6 TU
Jun.2025~Sep.2025: SA5#162 (1 meeting) (Last meeting for Rel-19) | 1.5 TU (CRs) | 6.5 TU | 2 TU | NA | 2 TU
Oct.2025~Dec.2025: SA5#163~#164 (2 meetings) (OAM support stage-1 freeze) | 1.5 TU*2 meetings= 3 TU (CRs) | NA | 8.5 TU*2 meetings = 17 TU | NA | 2 TU*2=4 TU
Jan.2026~Dec.2026: SA5#165~#169 (5 meetings) (Stage-2 freeze) | 1 TU*5 meetings= 5 TU (CRs) | NA | 9 TU*5 meetings = 45 TU | NA | 2 TU*5=10 TU
Jan. 2027~Mar.2027: SA5#170~#171 (2 meetings) (stage-3 freeze) | 1 TU*2 meetings = 2 TU (CRs) | NA | 8 TU*2 meetings = 16 TU | 1 TU*2 meetings = 2 TU | 2 TU*2=4 TU
Total=120 TU | 11.5 TU | 6.5 TU | 80 TU | 2 TU | 20 TU