## Slide 1: Guidance on exception requests
Andy Bennett
SA2 Chair
SA WG2 Meeting #166 Orlando
November 18 – November 22, 2024

## Slide 2: Guidance on exception requests
Exception requests need to be submitted to the December SA Plenary for any work items that are not 100% complete at the end of the November SA2 meeting
The template to be used is in the Templates folder for this meeting
Ultimately the SA delegates and officials are the audience for the exception sheets so we need to give them sufficient information to make a decision about whether to grant the exception, including:
  Which aspects of the work are not complete
  What functionality will be missing
  Any dependencies between the incomplete aspects of the work
  An estimate of how many TU’s will be required to complete the work
  Dependencies on other TSGs/WGs
  Any contentious issues, and the plan to resolve them

## Slide 3: Guidance on exception requests
Rapporteurs should request a tdoc number for AI 30.9
Rapporteurs should upload a draft version to the Drafts folder and aim to discuss them offline during the week and at the end of the relevant revisions session on Thursday
Rapporteurs should upload a version to the Inbox before the Thursday Q5 session
We will review them during the Thursday Q5 session and approve them if possible (if the content is not pending the outcome of discussions/CRs)
Any still open will be reviewed during the closing plenary on Friday
If any are still open after the closing plenary on Friday they will go to email approval