## Slide 1: Proposed SA WG4 Rel-20 capacity information Frédéric Gabin, SA4 Chair, Dolby France SAS (ETSI) SA4#130, Orlando, FL, USA, 18-22 November 2024 Tdoc: S4-241832

## Slide 2: Introduction
5G-Advanced in Rel-20 Workshop will take place during TSG SA#106 10-13 December 2024.
Agenda:
SA WG input is required on WG capacity for Rel-20
The next slide is the proposed input. It is based on Rel-20 planning and SA4 current ways of working. It is presented for SA4 agreement.
22 | 5G-Adv in Rel-20 Workshop
22.1 | General
22.1.1 | 5G-Adv in Rel-20 planning
22.1.2 | Incoming LSs
22.1.3 | Cross TSG Coordination
22.2 | Input Documents to the Workshop
22.2.1 | SA WG1 inputs on Rel-20 status
22.2.2 | SA WGs inputs on WG capacity for Rel-20 (e.g., TU Budget, Max# of SIDs/WIDs, Max size per SID/WID)
22.2.3 | 3GPP Member/MRP/other contributions on Rel-20 views/priority
22.3 | Output of the Workshop
22.3.1 | High-level summary report from the WS
22.3.2 | Identify the Core and Miscellaneous Rel-20 items/direction

## Slide 3: SA4 Rel-20 capacity summary
SA4 capacity:
  Max TUs: 147
  Max number of SIs/WIs: 16 – 25
    Note: one feature might result in up to 3 WI/SI: study, stage 2, stage 3, and counted separately
  Max TUs per Feature: not defined
Assumptions
  Start: September 2025, End: March 2027 (18 months)
  Number of meetings: 7
  Expected total TUs per meeting (for all releases): 27
  Total TUs (for all releases): 189
  TUs for maintenance of past releases: 28 (4 TUs per meeting)
  TUs for Rel-20 alignment with other WGs: 14 (2 TUs per meeting)
  Guidance for max. simultaneous SIs/WIs = 16
  This capacity is for Rel-20 and doesn’t indicate the workload split between 5GA and FS_6G parts