3GPP TSG-SA WG4 Meeting #130	S4-242055

# USA, Orlando, 18 – 22 November 2024

Source:	Interdigital Europe

Title:	Time Plan for the FS_HapticsMedia Study Item

Spec:	3GPP TR 26.854

Agenda item:	10.8

Document for:	Agreement

# Introduction

The study item aims to investigate and identify the data format, and potential codecs, transport protocols suitable to enhance SA4 services and enablers with haptic capabilities.

The main objectives of this study item include:

- Identify relevant use cases and requirements already defined in TR 22.847, TR 22.856 related to the integration of haptics into media streaming and communication services, and refine them as necessary.

- Collect and document market-relevant device types and technologies (for example existing APIs)  providing support for haptic playback and/or capture.

- Collect and describe the candidate input and representation formats for haptic experience, relevant to the above use cases and device types.

- Define relevant QoE metrics for suitable haptics experiences

- Identify 3GPP streaming and communication services that may benefit from the haptics media type and identify the gaps and requirements need to integrate haptics experiences.

- Identify candidate technologies that address the gaps including digital representation and compression formats, transport formats and potential QoS requirements in context with the services.

- Provide potential needs and benefits for normative work

The timeline for normative work will be considered after the study completes.  No normative work in Rel-19 is foreseen.

# Time Plan

The following time plan for the execution of the FS_HapticsMedia study item objectives numbered above is proposed in the following table.

| Meeting | Work Item Objectives |
| --- | --- |
| SA4#129-e (19 - 23 August, Online) | - Agree TR skeleton and time plan - Start (1) Identify and extract the Haptic-related use cases and requirements defined in TR22.847, TR 22.856 and/or in SA4 studies and refined them as necessary. - Start (2) Identify and describe the candidate input formats for haptic experience, relevant to the above use-cases. - Start (3) Identify relevant device types with support for haptic playback and/or capture |
| Post SA4 #129 RTC AHG Calls - (Sep 25, 2024, Wednesday, 15:00 –17:00CEST, Host Nokia) - (Oct 23, 2024, Wednesday, 15:00 –17:00 CEST, Host Nokia) | - Coontinue (1) Identify and extract the Haptic-related use cases and requirements defined in TR22.847, TR 22.856 and/or in SA4 studies and refined them as necessary. - Continue (2) Identify and describe the candidate input formats for haptic experience, relevant to the above use-cases. - Continue (3) Identify relevant device types with support for haptic playback and/or capture |
| SA4#130 (18 – 22 November 2024, Orlando, FL) | - Continue (1) Identify and extract the Haptic-related use cases and requirements defined in TR22.847, TR 22.856 and/or in SA4 studies and refined them as necessary. - Complete (2) Collect and document market-relevant device types and technologies (for example existing APIs) providing support for haptic playback and/or capture. - Complete (3) Collect and describe the candidate input and representation formats for haptic experience, relevant to the above use cases and device types. - Start (4) Define relevant QoE metrics for suitable haptics experiences - Start (5) Identify 3GPP streaming and communication services that may benefit from the haptics media type and identify the gaps and requirements need to integrate haptics experiences. - Start (6) Identify candidate technologies that address the gaps including digital representation and compression formats, transport formats and potential QoS requirements in context with the services. - Communicate with relevant 3GPP and external groups if needed. |
| SA#106 (10 – 13 December 2024, Madrid, ES) | - Submit TR26.854 for information |
| Post SA4 #130 RTC AHG Calls - Dec 17, 2024 (1500-1700 CET) - Jan 15, 2025 (1500-1700 CET) - Feb. 5, 2025 (0600-0800 CET) | - Complete (1) Identify and extract the Haptic-related use cases and requirements defined in TR22.847, TR 22.856 and/or in SA4 studies and refined them as necessary. - Continue (4) Define relevant QoE metrics for suitable haptics experiences - Continue (5) Identify 3GPP streaming and communication services that may benefit from the haptics media type and identify the gaps and requirements need to integrate haptics experiences. - Comtinue (6) Identify candidate technologies that address the gaps including digital representation and compression formats, transport formats and potential QoS requirements in context with the services. |
| SA4#131 (17 – 21 February 2025, Geneva, CH) | - Complete (4) Identify candidate technologies (codec, storage format, and transport protocols) that may be suitable for enabling haptic experiences. - Complete (5) Identify the use of existing 3GPP network APIs to assist the QoS for the delivery of haptic experiences if necessary. - Complete (6) Study, identify and document 3GPP services in which haptic experience can be integrated, including identifying potential gaps. (5GMS streaming, RTC communications, avatar representation, and broadcast.) - Complete (7) Provide potential needs and benefits for normative work - Finalize conclusions and recommendation of the TR |
| SA#107 (12 – 13 March 2025, Korea, KR) | - Submit TR26.854 for approval |

# Proposal

It is proposed to agree the time and work plan as described in Section 2.