## SA5#157
[5 empty] | Meeting | Jan 2024 （SA5#153） | April 2024 （SA5#154） | May 2024 (SA5#155) | Aug. 2024 (SA5#156) | Oct. 2024 (SA5#157) | Nov. 2024 (SA5#158) | Feb.2025 (SA5#159) | Apr.2025 (SA5#160) | May.2025 (SA5#161) | Aug. 2025 (SA5#162) | Note
[5 empty] | TU total (for planning purposes) | 19.5 | 19.5 | 19.5 | 19.5 | 19.5 | 19.5 | 19.5 | 19.5 | 19.5 | 19.5
SA5 Open plenary+ LS
|  | Planned |  |  |  | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
|  | Actual |  |  |  | 1.8 | 2.3 | 1.1 | 1.9 | 2.6
Pre-Rel-18 maintenance
|  | Planned |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
|  | Actual |  |  |  | 0.5 | 0.5 | 0.5 | 1.9 | 1
Rel-18 maintenance + Rel-19 TEI
|  | Planned |  |  |  | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1
|  | Actual |  |  |  | 2 | 4 | 2.1 | 1.7 | 1.8
Buffer (Overflow, other)
|  | Planned |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
|  | Actual |  |  |  | 4 | 2 | 2 | 2 | 3
Total of Maintenance + Buffer
|  | Planned |  |  |  | 3.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 3.5 | 3.5 | 3.5 | 3.5
|  | Actual |  |  |  | 6.5 | 6.5 | 4.6 | 5.6 | 5.8
Rel-19
|  | Planned(from the original overall plan) |  |  |  | 2 | 14 | 14 | 14 | 14 | 14 | 13 | 13 | 13 | 13
|  | Planned(sum of individual plans) |  |  |  | 2.35 | 17.6 | 16.75 | 16.82 | 11.5 | 11.08 | 3 | 2.5 | 2 | 0 | Time plan for each meeting will use TU planning in this row as input
|  | Actual |  |  |  | 1.65 | 9.78 | 12.9 | 11.04 | 10.61
Rel-20
|  | Planned(from the original overall plan) | [9 empty] | 2 | 2 | 2 | 2
Planned(sum of individual plans)
Actual
Overall total
|  | Planned |  |  |  | 5.5 | 18.5 | 18.5 | 18.5 | 18.5 | 18.5 | 16.5 | 16.5 | 16.5 | 16.5
|  | Actual |  |  |  | 9.95 | 18.58 | 18.6 | 18.54 | 16.41
|  | Rel-19 SID/WID detailed plan |  | TU estimates (from SID) |  | Jan 2024 （SA5#153） | April 2024 （SA5#154） | May 2024 (SA5#155) | Aug. 2024 (SA5#156) | Oct. 2024 (SA5#157) | Nov. 2024 (SA5#158) | Feb.2025 (SA5#159) | Apr.2025 (SA5#160) | May.2025 (SA5#161) | Aug. 2025 (SA5#162) | leftover
1 | AIML | FS_AIML_MGT_Ph2 | Study TU's planned | 6.2 | 6.2 | 0 | 1.45 | 0.95 | 1.2 | 1.3 | 1.3 |  |  |  |  | 1.3
|  | Yizhi Yao | Study TU's used |  | 5.12 | 0 | 1.67 | 0.95 | 1.2 | 1.3
|  | Hassan Al-Kanani | Normative TU's planned | 3.9 | 0 | [10 empty] | 3.9
|  |  | Normative TU's used |  | 0
2 | MDA | FS_eMDAS_Ph3 | Study TU's planned | 4.5 | 4.5 | 0 | 1.3 | 1.4 | 1.6 | 0.2 | [5 empty] | 0
|  | Brendan T Hassett | Study TU's used |  | 2.71 | 0 | 0.61 | 1.4 | 0.5 | 0.2
|  |  | Normative TU's planned | 4 | 4 | [5 empty] | 1 | 1 | 1 | 1 | 0 | 4
|  |  | Normative TU's used |  | 0
3 | IDM | FS_IDMS_MN_Ph3 | Study TU's planned | 4 | 4 | 0.5 | 1.25 | 1 | 0.75 | 0.5 | [5 empty] | 0
|  | Ruiyue Xu | Study TU's used |  | 3.24 | 0.5 | 0.84 | 1 | 0.5 | 0.4
|  | Mark Scott | Normative TU's planned | 4 | 4 | [5 empty] | 1 | 1 | 1 | 1 | 0 | 4
|  |  | Normative TU's used |  | 0
4 | CCL | FS_CCLM | Study TU's planned | 6.4 | 6.4 | 0.5 | 1.6 | 1.25 | 1.12 | 1 | 0.93 |  |  |  |  | 0.93
|  | Deepanshu Gautam | Study TU's used |  | 4.51 | 0.3 | 0.84 | 1.25 | 1.12 | 1
|  | Stephen Mwanje | Normative TU's planned | 3 | 1.5 | [6 empty] | 1 | 0.5 |  |  | 3
|  |  | Normative TU's used |  | 0
5 | NDT | FS_NDT | Study TU's planned | 3 | 3 | 0.5 | 0.5 | 0.5 | 0.8 | 0.7 | [5 empty] | 0
|  | Yushuang Hu | Study TU's used |  | 2.97 | 0.3 | 0.67 | 0.5 | 0.8 | 0.7
|  |  | Normative TU's planned | 3 | 0.3 | [5 empty] | 0.3 |  |  |  |  | 3
|  |  | Normative TU's used |  | 0
6 | CMO | FS_Cloud_OAM | Study TU's planned | 3.6 | 3.6 | 0.2 | 1 | 0.8 | 0.8 | 0.7 | 0.1 |  |  |  |  | 0.1
|  | Bahar Sadeghi | Study TU's used |  | 3.89 | 0.3 | 0.89 | 0.8 | 0.8 | 1.1
|  | Guangjing Cao | Normative TU's planned | 3 | 0 | [10 empty] | 3
|  |  | Normative TU's used |  | 0
7 | MSEC | FS_SECM | Study TU's planned | 1 | 0.7 | 0 | 0.25 | 0 | 0.25 | 0.1 | 0.1 |  |  |  |  | 0.4
|  | Clifton Fernandes | Study TU's used |  | 0.1 | 0 | 0 | 0 | 0.1 | 0
|  |  | Normative TU's planned | 0 | 0 | [10 empty] | 0
|  |  | Normative TU's used |  | 0
8 | SBMA | FS_SBMA_Ph3 | Study TU's planned | 5.5 | 5.5 | 0 | 1 | 1.35 | 1.15 | 1 | 1 |  |  |  |  | 1
|  | Kai Zhang | Study TU's used |  | 3.59 | 0 | 0.33 | 1.11 | 1.15 | 1
|  | Jan Groenendijk | Normative TU's planned | 4 | 0 | [10 empty] | 4
Normative TU's used
9 | PTM | FS_PlanM | Study TU's planned | 4 | 4 | 0 | 1.3 | 1.3 | 1.4 | [6 empty] | 0
|  | Olaf Pollakowski | Study TU's used |  | 1.02 | 0 | 0.22 | 0.5 | 0.3
|  |  | Normative TU's planned | 4 | 2 |  |  |  |  | 1 | 1 |  |  |  |  | 3
|  |  | Normative TU's used |  | 0.7 |  |  |  |  | 0.7
10 | MADCOL | MADCOL_Ph2 | Study TU's planned | 0 | 0 | [10 empty] | 0
|  | Sivaramakrishnan Swaminathan | Study TU's used |  | 0
|  |  | Normative TU's planned | 5 | 2.9 | 0 | 0.5 | 0.5 | 0.5 | 0.7 | 0.7 |  |  |  |  | 2.8
|  |  | Normative TU's used |  | 1.37 | 0 | 0.44 | 0.33 | 0.1 | 0.5
11 | SREP | FS_Data_SREP | Study TU's planned | 2 | 2 | 0 | 0.6 | 0.6 | 0.8 | [6 empty] | 0
|  | Robert Petersen | Study TU's used |  | 0.53 | 0 | 0.13 | 0.3 | 0.1
|  |  | Normative TU's planned | 2 | 0.5 |  |  |  |  | 0.2 | 0.3 |  |  |  |  | 1.8
|  |  | Normative TU's used |  | 0.05 |  |  |  |  | 0.05
12 | PM | PM_KPI_5G_Ph4 | Study TU's planned | 0 | 0 | [10 empty] | 0
|  | XiuMin Chen | Study TU's used |  | 0
|  | Xie Baoguo | Normative TU's planned | 3.5 | 2.2 | 0 | 0.5 | 0.4 | 0.5 | 0.4 | 0.4 |  |  |  |  | 1.7
|  |  | Normative TU's used |  | 1.79 | 0 | 0.56 | 0.33 | 0.5 | 0.4
13 | AdNRM | AdNRM_Ph3 | Study TU's planned | 0 | 0 | [10 empty] | 0
|  | Sean Sun | Study TU's used |  | 0
|  | Shi Xiaoli | Normative TU's planned | 4.5 | 2.8 | 0 | 0.3 | 0.5 | 0.8 | 0.6 | 0.6 |  |  |  |  | 2.3
|  |  | Normative TU's used |  | 1.68 | 0 | 0.31 | 0.27 | 0.5 | 0.6
14 | TMQ | TraceQoE_OAM | Study TU's planned | 0 | 0 | [10 empty] | 0
|  | Zu Qiang | Study TU's used |  | 0
|  |  | Normative TU's planned | 1 | 0.5 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  |  |  |  | 0.6
|  |  | Normative TU's used |  | 0.42 | 0 | 0.11 | 0.11 | 0.1 | 0.1
15 | NTNM | FS_ NTN_OAM_Ph2 | Study TU's planned | 3.5 | 3.5 | 0 | 1 | 1 | 1 | 0.5 | [5 empty] | 0
|  | MingRui Sun | Study TU's used |  | 2.15 | 0 | 0.44 | 0.55 | 0.66 | 0.5
|  | Min Shu | Normative TU's planned | 2 | 0.5 | [5 empty] | 0.5 |  |  |  |  | 2
|  |  | Normative TU's used |  | 0
16 | IABM | FS_NR_mobile_IAB_OAM | Study TU's planned | 1.6 | 1.6 | 0 | 0.5 | 0.5 | 0.4 | 0.2 | [5 empty] | 0
|  | JunFeng Wang | Study TU's used |  | 0.53 | 0 | 0.17 | 0.09 | 0.17 | 0.1
|  |  | Normative TU's planned | 3 | 0 | [10 empty] | 3
|  |  | Normative TU's used |  | 0
17 | RedcapM | FS_NR_RedCap_OAM | Study TU's planned | 3.3 | 3.3 | 0 | 0.8 | 0.8 | 0.9 | 0.5 | 0.3 |  |  |  |  | 0.3
|  | Zhen Xing | Study TU's used |  | 0.97 | 0 | 0.11 | 0.33 | 0.33 | 0.2
|  | Shoufeng Wang | Normative TU's planned | 2.2 | 0 | [10 empty] | 2.2
|  |  | Normative TU's used |  | 0
18 | NWDAFM | FS_NWDAF_OAM_Ph2 | Study TU's planned | 1.5 | 1.5 | 0 | 0.6 | 0.4 | 0.5 | [6 empty] | 0
|  | Song Zhao | Study TU's used |  | 0.64 | 0 | 0.22 | 0.22 | 0.2
|  |  | Normative TU's planned | 2 | 0.7 |  |  |  |  | 0.1 | 0.6 |  |  |  |  | 1.9
|  |  | Normative TU's used |  | 0.1 |  |  |  |  | 0.1
19 | NSM | FS_NetShare_OAM_Ph3 | Study TU's planned | 2.6 | 2.4 | 0 | 0.8 | 0.6 | 0.6 | 0.4 | [5 empty] | 0.2
|  | ZhaoNing Wang | Study TU's used |  | 0.49 | 0 | 0.11 | 0.06 | 0.26 | 0.06
|  |  | Normative TU's planned | 2.2 | 0.2 | [5 empty] | 0.2 |  |  |  |  | 2.2
|  |  | Normative TU's used |  | 0
20 | EE | FS_Energy_OAM_Ph3 | Study TU's planned | 5 | 5 | 0.4 | 1 | 1.3 | 1 | 0.8 | 0.5 |  |  |  |  | 0.5
|  | Jean-Michel Cornily | Study TU's used |  | 4.55 | 0.15 | 1 | 1.3 | 1 | 1.1
|  | Ashutosh Kaushik | Normative TU's planned | 3 | 0 | [10 empty] | 3
|  |  | Normative TU's used |  | 0
21 | Mexpo | FS_MExpo | Study TU's planned | 4.3 | 4.3 | 0.25 | 1.25 | 1.5 | 0.65 | 0.5 | 0.15 |  |  |  |  | 0.15
|  | Srilakshmi | Study TU's used |  | 2.86 | 0.1 | 0.11 | 1.5 | 0.65 | 0.5
|  |  | Normative TU's planned | 1.7 | 0 | [10 empty] | 1.7
|  |  | Normative TU's used |  | 0
|  |  |  | planned | actual used
|  | Total for Rel-19 Studies |  | 62 | 39.77 | 1.65 | 8.36 | 11.86 | 9.84 | 8.16 | 0 | 0 | 0 | 0 | 0
|  | Total for Rel-19 Normative |  | 61 | 6.11 | 0 | 1.42 | 1.04 | 1.2 | 2.45 | 0 | 0 | 0 | 0 | 0
|  | Total for Rel-19 SID/WID |  | 123 | 45.88 | 1.65 | 9.78 | 12.9 | 11.04 | 10.61 | 0 | 0 | 0 | 0 | 0
|  | Breakout sessions bonus TU used | Total |  |  | Jan 2024 （SA5#153） | April 2024 （SA5#154） | May 2024 (SA5#155) | Aug. 2024 (SA5#156) | Oct. 2024 (SA5#157) | Nov. 2024 (SA5#158) | Feb.2025 (SA5#159) | Apr.2025 (SA5#160) | May.2025 (SA5#161) | Aug. 2025 (SA5#162)
1 | AIML | FS_AIML_MGT_Ph2 |  |  |  |  | 1 | 1 | 1.7 | 2
2 | MDA | FS_eMDAS_Ph3 | [5 empty] | 0.33
3 | IDM | FS_IDMS_MN_Ph3 |  |  |  |  | 1.6 | 1.66 | 0.5
4 | CCL | FS_CCLM | [5 empty] | 1
5 | NDT | FS_NDT |  |  |  |  | 0.5 | 1 | 0.5 | 0.5
6 | CMO | FS_Cloud_OAM |  |  |  |  | 1.1 | 1.66 | 1 | 1.5
7 | MSEC | FS_SECM
8 | SBMA | FS_SBMA_Ph3
9 | PTM | FS_PlanM
10 | MADCOL | MADCOL_Ph2
11 | SREP | FS_Data_SREP
12 | PM | PM_KPI_5G_Ph4 | [6 empty] | 0.3
13 | AdNRM | AdNRM_Ph3
14 | TMQ | TraceQoE_OAM
15 | NTNM | FS_ NTN_OAM_Ph2
16 | IABM | FS_NR_mobile_IAB_OAM
17 | RedcapM | FS_NR_RedCap_OAM
18 | NWDAFM | FS_NWDAF_OAM_Ph2
19 | NSM | FS_NetShare_OAM_Ph3
20 | EE | FS_Energy_OAM_Ph3 |  |  |  |  | 0.5 | 1 | 1 | 0.5
21 | Mexpo | FS_MExpo |  |  |  |  | 0.5 | 1 |  | 0.5
| Other | [8 empty] | 1.3
|  | Rel-19 CH SID/WID detailed plan |  | TU estimates (from SID) |  | Jan 2024 （SA5#153） | April 2024 （SA5#154） | May 2024 (SA5#155) | Aug. 2024 (SA5#156) | Oct. 2024 (SA5#157) | Nov. 2024 (SA5#158) | Feb.2025 (SA5#159) | Apr.2025 (SA5#160) | May.2025 (SA5#161) | Aug. 2025 (SA5#162) | leftover
1 | SATCH | FS_5GSAT_Ph3_CH | Study TU's planned | 3
|  | Yingying Liu | Study TU's used
|  |  | Normative TU's planned | 3
Normative TU's used
2 | CAPCH | FS_CAPIF_Ph2_CH | Study TU's planned | 6
|  | João Rodrigues | Study TU's used
|  |  | Normative TU's planned | 6
Normative TU's used
3 | RTCCH | FS_NG_RTC_Ph2_CH | Study TU's planned | 5
|  | Ai Chen | Study TU's used
|  |  | Normative TU's planned | 3
Normative TU's used
4 | CHSEG | CHFSeg | Study TU's planned | 0
|  | Cetinkaya Egemen Kemal | Study TU's used
|  |  | Normative TU's planned | 4
Normative TU's used
5 | RAGCH | Ranging_SL_CH | Study TU's planned | 0
|  | Zhiwei Mo | Study TU's used
|  |  | Normative TU's planned | 3
Normative TU's used
6 | NSCH | NetShare_CH | Study TU's planned | 0
|  | Robert Törnkvist | Study TU's used
|  |  | Normative TU's planned | 1
Normative TU's used
7 | UASCH | FS_UAS_CH | Study TU's planned | 5
|  | Jia Dong | Study TU's used
|  |  | Normative TU's planned | 3
Normative TU's used
8 | EESCH | EnergySys_CH | Study TU's planned | 0
|  | YiMeng, DENG | Study TU's used
|  |  | Normative TU's planned | 6
Normative TU's used

## SA5#156
[5 empty] | Meeting | Jan 2024 （SA5#153） | April 2024 （SA5#154） | May 2024 (SA5#155) | Aug. 2024 (SA5#156) | Oct. 2024 (SA5#157) | Nov. 2024 (SA5#158) | Feb.2025 (SA5#159) | Apr.2025 (SA5#160) | May.2025 (SA5#161) | Aug. 2025 (SA5#162) | Note
[5 empty] | TU total (for planning purposes) | 19.5 | 19.5 | 19.5 | 19.5 | 19.5 | 19.5 | 19.5 | 19.5 | 19.5 | 19.5
SA5 Open plenary+ LS
|  | Planned |  |  |  | 1.5 | 1.5 | 1.5 | 1.5
|  | Actual |  |  |  | 1.8 | 2.3 | 1.1 | 1.9
Pre-Rel-18 maintenance
|  | Planned |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
|  | Actual |  |  |  | 0.5 | 0.5 | 0.5 | 1.9
Rel-18 maintenance + Rel-19 TEI
|  | Planned |  |  |  | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1
|  | Actual |  |  |  | 2 | 4 | 2.1 | 1.7
Buffer (Overflow, other)
|  | Planned |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
|  | Actual |  |  |  | 4 | 2 | 2 | 2
Total of Maintenance + Buffer
|  | Planned |  |  |  | 3.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 3.5 | 3.5 | 3.5 | 3.5
|  | Actual |  |  |  | 6.5 | 6.5 | 4.6 | 5.6
Rel-19
|  | Planned(from the original overall plan) |  |  |  | 2 | 14 | 14 | 14 | 14 | 14 | 13 | 13 | 13 | 13
|  | Planned(sum of individual plans) |  |  |  | 2.35 | 17.6 | 17.25 | 16.82 | 12.85 | 9.63 | 1.8 | 1.3 | 0.8 | 0 | Time plan for each meeting will use TU planning in this row as input
|  | Actual |  |  |  | 1.65 | 9.78 | 12.9 | 11.04
Overall total
|  | Planned |  |  |  | 5.5 | 18.5 | 18.5 | 18.5 | 18.5 | 18.5 | 16.5 | 16.5 | 16.5 | 16.5
|  | Actual |  |  |  | 9.95 | 18.58 | 18.6 | 18.54
|  | Rel-19 SID/WID detailed plan |  | TU estimates (from SID) |  | Jan 2024 （SA5#153） | April 2024 （SA5#154） | May 2024 (SA5#155) | Aug. 2024 (SA5#156) | Oct. 2024 (SA5#157) | Nov. 2024 (SA5#158) | Feb.2025 (SA5#159) | Apr.2025 (SA5#160) | May.2025 (SA5#161) | Aug. 2025 (SA5#162) | leftover
1 | AIML | FS_AIML_MGT_Ph2 | Study TU's planned | 6.2 | 6.2 | 0 | 1.45 | 0.95 | 1.2 | 1.3 | 1.3 |  |  |  |  | 3.8
|  | Yizhi Yao | Study TU's used |  | 3.82 | 0 | 1.67 | 0.95 | 1.2
|  | Hassan Al-Kanani | Normative TU's planned | 3.9 | 0 | [10 empty] | 3.9
|  |  | Normative TU's used |  | 0
2 | MDA | FS_eMDAS_Ph3 | Study TU's planned | 4.3 | 4.3 | 0 | 1.3 | 1.4 | 1.6 | [6 empty] | 1.6
|  | Brendan T Hassett | Study TU's used |  | 2.51 | 0 | 0.61 | 1.4 | 0.5
|  |  | Normative TU's planned | 4.2 | 4.2 |  |  |  |  | 0.8 | 1 | 0.8 | 0.8 | 0.8 |  | 4.2
|  |  | Normative TU's used |  | 0
3 | IDM | FS_IDMS_MN_Ph3 | Study TU's planned | 4.5 | 4.5 | 0.5 | 1.25 | 1 | 0.75 | 1 | [5 empty] | 1.75
|  | Ruiyue Xu | Study TU's used |  | 2.84 | 0.5 | 0.84 | 1 | 0.5
|  | Mark Scott | Normative TU's planned | 3.5 | 0.5 | [5 empty] | 0.5 |  |  |  |  | 3.5
|  |  | Normative TU's used |  | 0
4 | CCL | FS_CCLM | Study TU's planned | 6.4 | 6.4 | 0.5 | 1.6 | 1.25 | 1.12 | 1 | 0.93 |  |  |  |  | 3.05
|  | Deepanshu Gautam | Study TU's used |  | 3.51 | 0.3 | 0.84 | 1.25 | 1.12
|  | Stephen Mwanje | Normative TU's planned | 3 | 1.5 | [6 empty] | 1 | 0.5 |  |  | 3
|  |  | Normative TU's used |  | 0
5 | NDT | FS_NDT | Study TU's planned | 3 | 3 | 0.5 | 0.5 | 0.5 | 0.8 | 0.7 | [5 empty] | 1.5
|  | Yushuang Hu | Study TU's used |  | 2.27 | 0.3 | 0.67 | 0.5 | 0.8
|  |  | Normative TU's planned | 3 | 0.3 | [5 empty] | 0.3 |  |  |  |  | 3
|  |  | Normative TU's used |  | 0
6 | CMO | FS_Cloud_OAM | Study TU's planned | 3.6 | 3.6 | 0.2 | 1 | 0.8 | 0.8 | 0.8 | 0 |  |  |  |  | 1.6
|  | Bahar Sadeghi | Study TU's used |  | 2.79 | 0.3 | 0.89 | 0.8 | 0.8
|  | Guangjing Cao | Normative TU's planned | 2 | 0 | [10 empty] | 2
|  |  | Normative TU's used |  | 0
7 | MSEC | FS_SECM | Study TU's planned | 1 | 1 | 0 | 0.25 | 0.5 | 0.25 | [6 empty] | 0.25
|  | Clifton Fernandes | Study TU's used |  | 0.1 | 0 | 0 | 0 | 0.1
|  |  | Normative TU's planned | 0 | 0 | [10 empty] | 0
|  |  | Normative TU's used |  | 0
8 | SBMA | FS_SBMA_Ph3 | Study TU's planned | 5.5 | 5.5 | 0 | 1 | 1.35 | 1.15 | 1 | 1 |  |  |  |  | 3.15
|  | Kai Zhang | Study TU's used |  | 2.59 | 0 | 0.33 | 1.11 | 1.15
|  | Jan Groenendijk | Normative TU's planned | 4 | 0 | [10 empty] | 4
Normative TU's used
9 | PTM | FS_PlanM | Study TU's planned | 4 | 4 | 0 | 1.3 | 1.3 | 1.4 | [6 empty] | 1.4
|  | Olaf Pollakowski | Study TU's used |  | 1.02 | 0 | 0.22 | 0.5 | 0.3
|  |  | Normative TU's planned | 4 | 2 |  |  |  |  | 1 | 1 |  |  |  |  | 4
|  |  | Normative TU's used |  | 0
10 | MADCOL | MADCOL_Ph2 | Study TU's planned | 0 | 0 | [10 empty] | 0
|  | Sivaramakrishnan Swaminathan | Study TU's used |  | 0
|  |  | Normative TU's planned | 5 | 3.5 | 0 | 0.5 | 0.5 | 0.5 | 1 | 1 |  |  |  |  | 4
|  |  | Normative TU's used |  | 0.87 | 0 | 0.44 | 0.33 | 0.1
11 | SREP | FS_Data_SREP | Study TU's planned | 2 | 2 | 0 | 0.6 | 0.6 | 0.8 | [6 empty] | 0.8
|  | Robert Petersen | Study TU's used |  | 0.53 | 0 | 0.13 | 0.3 | 0.1
|  |  | Normative TU's planned | 2 | 0 | [10 empty] | 2
|  |  | Normative TU's used |  | 0
12 | PM | PM_KPI_5G_Ph4 | Study TU's planned | 0 | 0 | [10 empty] | 0
|  | XiuMin Chen | Study TU's used |  | 0
|  | Xie Baoguo | Normative TU's planned | 3.5 | 2.2 | 0 | 0.5 | 0.4 | 0.5 | 0.4 | 0.4 |  |  |  |  | 2.6
|  |  | Normative TU's used |  | 1.39 | 0 | 0.56 | 0.33 | 0.5
13 | AdNRM | AdNRM_Ph3 | Study TU's planned | 0 | 0 | [10 empty] | 0
|  | Sean Sun | Study TU's used |  | 0
|  | Shi Xiaoli | Normative TU's planned | 4.5 | 3.1 | 0 | 0.3 | 0.5 | 0.8 | 0.7 | 0.8 |  |  |  |  | 3.7
|  |  | Normative TU's used |  | 1.08 | 0 | 0.31 | 0.27 | 0.5
14 | TMQ | TraceQoE_OAM | Study TU's planned | 0 | 0 | [10 empty] | 0
|  | Zu Qiang | Study TU's used |  | 0
|  |  | Normative TU's planned | 1 | 0.5 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  |  |  |  | 0.8
|  |  | Normative TU's used |  | 0.32 | 0 | 0.11 | 0.11 | 0.1
15 | NTNM | FS_ NTN_OAM_Ph2 | Study TU's planned | 3.5 | 3.5 | 0 | 1 | 1 | 1 | 0.5 | [5 empty] | 1.5
|  | MingRui Sun | Study TU's used |  | 1.65 | 0 | 0.44 | 0.55 | 0.66
|  | Min Shu | Normative TU's planned | 2 | 0 | [10 empty] | 2
|  |  | Normative TU's used |  | 0
16 | IABM | FS_NR_mobile_IAB_OAM | Study TU's planned | 1.6 | 1.6 | 0 | 0.5 | 0.5 | 0.4 | 0.2 | [5 empty] | 0.6
|  | JunFeng Wang | Study TU's used |  | 0.43 | 0 | 0.17 | 0.09 | 0.17
|  |  | Normative TU's planned | 3 | 0 | [10 empty] | 3
|  |  | Normative TU's used |  | 0
17 | RedcapM | FS_NR_RedCap_OAM | Study TU's planned | 3 | 3 | 0 | 0.8 | 0.8 | 0.9 | 0.5 | [5 empty] | 1.4
|  | Zhen Xing | Study TU's used |  | 0.77 | 0 | 0.11 | 0.33 | 0.33
|  | Shoufeng Wang | Normative TU's planned | 2.5 | 0 | [10 empty] | 2.5
|  |  | Normative TU's used |  | 0
18 | NWDAFM | FS_NWDAF_OAM_Ph2 | Study TU's planned | 1.5 | 1.5 | 0 | 0.6 | 0.4 | 0.5 | [6 empty] | 0.5
|  | Song Zhao | Study TU's used |  | 0.64 | 0 | 0.22 | 0.22 | 0.2
|  |  | Normative TU's planned | 2 | 0.6 |  |  |  |  | 0 | 0.6 |  |  |  |  | 2
|  |  | Normative TU's used |  | 0
19 | NSM | FS_NetShare_OAM_Ph3 | Study TU's planned | 2.6 | 2 | 0 | 0.8 | 0.6 | 0.6 | [6 empty] | 1.2
|  | ZhaoNing Wang | Study TU's used |  | 0.43 | 0 | 0.11 | 0.06 | 0.26
|  |  | Normative TU's planned | 2 | 0.6 |  |  |  |  | 0.4 | 0.2 |  |  |  |  | 2
|  |  | Normative TU's used |  | 0
20 | EE | FS_Energy_OAM_Ph3 | Study TU's planned | 5 | 5 | 0.4 | 1 | 1.3 | 1 | 0.8 | 0.5 |  |  |  |  | 2.3
|  | Jean-Michel Cornily | Study TU's used |  | 3.45 | 0.15 | 1 | 1.3 | 1
|  | Ashutosh Kaushik | Normative TU's planned | 3 | 0 | [10 empty] | 3
|  |  | Normative TU's used |  | 0
21 | Mexpo | FS_MExpo | Study TU's planned | 4.3 | 4.3 | 0.25 | 1.25 | 1.5 | 0.65 | 0.65 | 0 |  |  |  |  | 1.3
|  | Srilakshmi | Study TU's used |  | 2.36 | 0.1 | 0.11 | 1.5 | 0.65
|  |  | Normative TU's planned | 1.5 | 0 | [10 empty] | 1.5
|  |  | Normative TU's used |  | 0
|  |  |  | planned | actual used
|  | Total for Rel-19 Studies |  | 62 | 31.61 | 1.65 | 8.36 | 11.86 | 9.84 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total for Rel-19 Normative |  | 59.6 | 3.66 | 0 | 1.42 | 1.04 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total for Rel-19 SID/WID |  | 121.6 | 35.27 | 1.65 | 9.78 | 12.9 | 11.04 | 0 | 0 | 0 | 0 | 0 | 0
|  | Breakout sessions bonus TU used | Total |  |  | Jan 2024 （SA5#153） | April 2024 （SA5#154） | May 2024 (SA5#155) | Aug. 2024 (SA5#156) | Oct. 2024 (SA5#157) | Nov. 2024 (SA5#158) | Feb.2025 (SA5#159) | Apr.2025 (SA5#160) | May.2025 (SA5#161) | Aug. 2025 (SA5#162)
1 | AIML | FS_AIML_MGT_Ph2 |  |  |  |  | 1 | 1 | 1.7
2 | MDA | FS_eMDAS_Ph3 | [5 empty] | 0.33
3 | IDM | FS_IDMS_MN_Ph3 |  |  |  |  | 1.6 | 1.66 | 0.5
4 | CCL | FS_CCLM | [5 empty] | 1
5 | NDT | FS_NDT |  |  |  |  | 0.5 | 1 | 0.5
6 | CMO | FS_Cloud_OAM |  |  |  |  | 1.1 | 1.66 | 1
7 | MSEC | FS_SECM
8 | SBMA | FS_SBMA_Ph3
9 | PTM | FS_PlanM
10 | MADCOL | MADCOL_Ph2
11 | SREP | FS_Data_SREP
12 | PM | PM_KPI_5G_Ph4 | [6 empty] | 0.3
13 | AdNRM | AdNRM_Ph3
14 | TMQ | TraceQoE_OAM
15 | NTNM | FS_ NTN_OAM_Ph2
16 | IABM | FS_NR_mobile_IAB_OAM
17 | RedcapM | FS_NR_RedCap_OAM
18 | NWDAFM | FS_NWDAF_OAM_Ph2
19 | NSM | FS_NetShare_OAM_Ph3
20 | EE | FS_Energy_OAM_Ph3 |  |  |  |  | 0.5 | 1 | 1
21 | Mexpo | FS_MExpo |  |  |  |  | 0.5 | 1
|  | Rel-19 CH SID/WID detailed plan |  | TU estimates (from SID) |  | Jan 2024 （SA5#153） | April 2024 （SA5#154） | May 2024 (SA5#155) | Aug. 2024 (SA5#156) | Oct. 2024 (SA5#157) | Nov. 2024 (SA5#158) | Feb.2025 (SA5#159) | Apr.2025 (SA5#160) | May.2025 (SA5#161) | Aug. 2025 (SA5#162) | leftover
1 | SATCH | FS_5GSAT_Ph3_CH | Study TU's planned | 3
|  | Yingying Liu | Study TU's used
|  |  | Normative TU's planned | 3
Normative TU's used
2 | CAPCH | FS_CAPIF_Ph2_CH | Study TU's planned | 6
|  | João Rodrigues | Study TU's used
|  |  | Normative TU's planned | 6
Normative TU's used
3 | RTCCH | FS_NG_RTC_Ph2_CH | Study TU's planned | 5
|  | Ai Chen | Study TU's used
|  |  | Normative TU's planned | 3
Normative TU's used
4 | CHSEG | CHFSeg | Study TU's planned | 0
|  | Cetinkaya Egemen Kemal | Study TU's used
|  |  | Normative TU's planned | 4
Normative TU's used
5 | RAGCH | Ranging_SL_CH | Study TU's planned | 0
|  | Zhiwei Mo | Study TU's used
|  |  | Normative TU's planned | 3
Normative TU's used
6 | NSCH | NetShare_CH | Study TU's planned | 0
|  | Robert Törnkvist | Study TU's used
|  |  | Normative TU's planned | 1
Normative TU's used
7 | UASCH | FS_UAS_CH | Study TU's planned | 5
|  | Jia Dong | Study TU's used
|  |  | Normative TU's planned | 3
Normative TU's used
8 | EESCH | EnergySys_CH | Study TU's planned | 0
|  | YiMeng, DENG | Study TU's used
|  |  | Normative TU's planned | 6
Normative TU's used

## SA5 Work Plan post
SA5#154 (Changsha, China)
15 – 19 Apr, 2024
[10 empty] | Jan 2024 | April 2024 | May 2024 | Aug. 2024 | Oct. 2024 | Nov. 2024 | Feb.2025 | Apr.2025 | May.2025 | Aug. 2025 | Total planned
[10 empty] | SA5#153 | SA5#154 | SA5#155 | SA5#156 | SA5#157 | SA5#158 | SA5#159 | SA5#160 | SA5#161 | SA5#162
[10 empty] | (planned) | (planned) | (planned) | (planned) | (planned) | (planned) | (planned) | (planned) | (planned) | (planned)
|  | Maintenance CRs + Rel-18 work | [7 empty] | 14.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 1.5 | 1.5 | 1.5 | 1.5 | 33
|  | Rel-20 Preparation | [7 empty] | SA5#159: 2; SA5#160: 2; SA5#161: 2; SA5#162: 2 | 8
|  | Buffer | [7 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 20
[10 empty] | 16.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 5.5 | 5.5 | 5.5 | 5.5 | 61
|  | Available for Rel-19 SIDs/WIDs | [7 empty] | 2 | 14 | 14 | 14 | 14 | 14 | 13 | 13 | 13 | 13 | 124
18.5
| Abbr. | Acronym | 3GPP Rel-19 SA5 Study and Work Items SID/WID Title and WT Description | Total TU (Planned) | Study TU (Planned) | Normative TU (Planned) | Total TU (adjusted) | Study TU (adjusted) | Normative TU (adjusted) | Jan 2024 （SA5#153） | April 2024 （SA5#154） | May 2024 (SA5#155) | Aug. 2024 (SA5#156) | Oct. 2024 (SA5#157) | Nov. 2024 (SA5#158) | Feb.2025 (SA5#159) | Apr.2025 (SA5#160) | May.2025 (SA5#161) | Aug. 2025 (SA5#162) | Total TU's used (SA5#153 - SA5#162) | RAN Dependency | SA Dependency | Non-3GPP Dependency | SA WID TDoc# | Rapporteurs | TR / TS | Target date | UID | Comments
1 | AIML | FS_AIML_MGT_Ph2 | Study on AI/ML management - phase 2 | 8.1 | 4.2 | 3.9 | 10.1 | 6.2 | 3.9 | 0 | 1.45 | 0.95 | 1.2 | 1.3 | 1.3 | [5 empty] | Yes | Yes | Maybe | SP-231780 | Primary Rapporteur: Yizhi Yao (Intel), yizhi.yao@intel.com Secondary Rapporteur: Hassan Al-Kanani (NEC), Hassan.Alkanani@EMEA.NEC.COM | 28.908 | Sept. 2024 | 1020007
|  |  | WT-1. Continue the study on AI/ML emulation, AI/ML inference coordination and ML knowledge transfer that are leftover from Rel-18. |  | 1 | 1 |  | 1 |  | 0 | 0.5 | 0 | 0.3 | 0.1 | 0.1 | [5 empty] | Maybe | Maybe | No
|  |  | WT-2. Study the management aspects (LCM CM and PM) of AI/ML functionalities defined by other 3GPP WGs, including WT-2.1. AI/ML model transfer in 5GS (SA1, Rel-18 WID 920037 and Rel-19 WID 1000030), Note: Whether SA5 can start work on WT-2.1 will be discussed at SA#105 (Sep. 2024) based on the outcome of the related work in the involved RAN WGs(s) |  | 0 | 0 |  | 0.2 |  | 0 | 0 | 0 | 0 | 0.1 | 0.1
|  |  | WT-2.2. 5GS support for AI/ML-based services (SA2, Rel-18 WID 980019) |  | 0.4 | 0.3 |  | 0.6 |  | 0 | 0.2 | 0.2 | 0 | 0.1 | 0.1
|  |  | WT-2.3. Support for AI/ML services at application enablement layer (SA6, Rel-18 WID 970036), |  | 0.4 | 0.3 |  | 0.5 |  | 0 | 0.2 | 0 | 0.1 | 0.1 | 0.1
|  |  | WT-3. Study the management aspects (LCM CM and PM) of AI/ML functionalities defined by 3GPP SA5 WG, including WT-3.1. MDA (Management Data Analytics) phase 3 (SA5) |  | 0.4 | 0.3 |  | 0.5 |  | 0 | 0 | 0.2 | 0.1 | 0.1 | 0.1 | [5 empty] | No | SA1 | No
|  |  | WT-4. Study the AI/ML management and operation capabilities to support different types of AI/ML technologies as needed to support the AI/ML in 5GS, such as Federated Learning, Reinforcement Learning, Online and Offline training, Distributed Learning, and Generative AI. |  | 1 | 1 |  | 1.8 |  | 0 | 0.3 | 0.3 | 0.4 | 0.4 | 0.4 | [5 empty] | No | SA2 | No
|  |  | WT-5. Study the sustainability aspect of AI/ML, including WT-5.1 Evaluation of energy consumption/efficiency impacts associated with AI/ML solutions for all operational phases (training, emulation, deployment, inference). |  | 0.5 | 0.5 |  | 0.85 |  | 0 | 0.25 | 0 | 0.2 | 0.2 | 0.2 | [5 empty] | Maybe | Maybe | Maybe
|  |  | WT-6. Further study the trustworthiness aspects related to the AI/ML functionalities in 5GS, including WT-6.1 Concept of trustworthiness for AI/ML in the context of OAM, |  | 0.25 | 0.25 |  | 0.45 |  | 0 | 0 | 0.15 | 0.1 | 0.1 | 0.1 | [5 empty] | Maybe | Maybe | Maybe
|  |  | WT-6.2 Data (e.g., measurements, events) to support calculation of trustworthiness indicators. |  | 0.25 | 0.25 |  | 0.3 |  | 0 | 0 | 0.1 | 0 | 0.1 | 0.1 | [5 empty] | Maybe | Maybe | Maybe | [5 empty] | SID mentions 0.5 TU for WT-6 (Study) and 0.5 TU for WT-6 (Normative). Split here equally between WT-6.1 and WT-6.2.
2 | MDA | FS_eMDAS_Ph3 | Study on Management Data Analytics (MDA) – Phase 3 | 8.5 | 4 | 4.5 | 8.5 | 4.3 | 4.2 | 0 | 1.3 | 1.4 | 1.6 | 0.8 | 1 | 0.8 | 0.8 | 0.8 |  |  | Yes | Yes | No | SP-231726 | Primary Rapporteur: Brendan T Hassett (Huawei), brendan.t.hassett@huawei.com | 28.866 | Sept. 2024 | 1020019
|  |  | WT-1 Energy efficiency analytics, Note: The work on this aspect will be in collaboration with SA5 5GEE work on any new enabling data requirements e.g., new relevant performance measurements and/or new KPIs will be developed under the scope of 5GEE work. |  | 0.4 | 0.5 |  | 0.6 | 0.5 | 0 | 0.4 | 0 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  |  | Yes, RAN3 | Yes, SA1, SA2 | No
|  |  | WT-2 End-to-End performance analytics including Edge computing domain, |  | 0.5 | 0.5 |  | 0.4 | 0.5 | 0 | 0 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  |  | No | Yes, SA1, SA2 | No
|  |  | WT-3 Data correlation analytics including, but not limited to supporting and facilitating e.g., ML model training operational tasks, |  | 0.5 | 0.5 |  | 0.7 | 0.6 | 0 | 0.3 | 0.2 | 0.2 | 0.1 | 0.2 | 0.1 | 0.1 | 0.1 |  |  | No | Yes, SA2 | No
|  |  | WT-4 ATSSS performance analytics, |  | 0.4 | 0.5 |  | 0.4 | 0.5 | 0 | 0 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  |  | No | Yes, SA1, SA2 | No
|  |  | WT-5 Non-3GPP access performance analytics, |  | 0.4 | 0.5 |  | 0.2 | 0 | 0 | 0 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | No | Yes, SA2 | No
|  |  | WT-6 UE throughput analytics, |  | 0.4 | 0.5 |  | 0.4 | 0.5 | 0 | 0 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  |  | Yes, RAN2, RAN3 | No | No
|  |  | WT-7 Fault management related analytics and alarm prediction, |  | 0.5 | 0.5 |  | 0.7 | 0.6 | 0 | 0.3 | 0.2 | 0.2 | 0.1 | 0.2 | 0.1 | 0.1 | 0.1 |  |  | No | No | No
|  |  | WT-8 Software Upgrade Validation: Using MDAS predictions to validate the software upgrade for a future point of time, Note: Relation with CICD needs to be studied, as appropriate. |  | 0.5 | 0.5 |  | 0.7 | 0.5 | 0 | 0.3 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  |  | No | No | No
|  |  | WT-9 Control plane congestion analytics |  | 0.4 | 0.5 |  | 0.2 | 0.5 |  |  |  | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
3 | IDM | FS_IDMS_MN_Ph3 | Study on intent driven management services for mobile network phase 3 | 8 | 3.5 | 4.5 | 8 | 4.5 | 3.5 | 0.5 | 1.25 | 1 | 0.75 | 1 | 0.5 | [5 empty] | No | No | No | SP-231737 | Primary Rapporteur: Ruiyue Xu (Huawei), xuruiyue@huawei.com Secondary Rapporteur: Mark Scott (Ericsson), mark.scott@ericsson.com | 28.914 | Sept. 2024 | 1020008
|  |  | WT-1 Continuation of Rel-18 intent driven management service topics enhancement: WT-1.1 Intent driven management for user experience assurance WT-1.2 Enablers for Intent Fulfilment, including Intent-driven Closed Loop control, Intent-driven SON orchestration and Intent-driven for MDA. |  | 0.25 | 1 |  | 0.25 | 1 | 0 | 0 | 0.25 | 0 | 0 | 0 | [5 empty] | No | No | No
|  |  | WT-2 New scenarios for intent driven management for mobile network, including but not limited to: WT-2.1 Intent driven management for Uncrewed Aerial Vehicle (UAV)). WT-2.2 Intent driven management for 5G radio network traffic assurance. |  | 1 | 1 |  | 1.25 | 0.75 | 0.25 | 0.5 | 0.25 | 0 | 0.25 | 0.25 | [5 empty] | No | No | No
|  |  | WT-3 New requirements for additional intent driven management functionalities. WT-3.1 Intent negotiation functionalities, including WT-3.1.1 Management capability to enable MnS producer to ask the MnS consumer to decide which out of many possible outcomes is preferred from the MnS consumer’s perspective. WT-3.1.2 Management capability to enable MnS consumer to verify or check the feasibility if proposed intent expectation is possible for an MnS producer. WT-3.1.3 Management capability to enable MnS consumer to explore the best value that can be achieved from an specific intent expectation or target. WT-3.2 Intent handling state management, the management system (including MnS consumer and MnS producer) needs to know the state of an intent instance to pursue the intent lifecycle management WT-3.3 Implicit intent report subscription, the intent report subscription action is triggered by intent creation request automatically. This functionality is to support MnS consumer who expresses the intent can obtain the fulfilment report by default. |  | 1 | 1 |  | 1.25 | 0.75 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | [5 empty] | No | No | No
|  |  | WT-4 Study how Intent Utility Function can be used to allow Intent driven MnS consumer to improve priority handling by assigning relative preferences to Expectations. Study whether utility may impact existing use cases. |  | 0.5 | 0.5 |  | 0.75 | 0.25 | 0 | 0 | 0.25 | 0.25 | 0.25 | 0.25 | [5 empty] | No | No | No
|  |  | WT-5 Intent driven approach for network slicing delivering and assurance. |  | 0.25 | 1 |  | 0.5 | 0.75 | 0 | 0.25 | 0 | 0 | 0.25 | 0 | [5 empty] | No | No | No
|  |  | Note: WT-6 depends on the outcome of TR 28.836 (FS_ NETSLICE_IDMS) WT-6 Investigate the scenario and possibility to further use natural language to express the intent. |  | 0.5 | 0 |  | 0.5 | 0 | 0 | 0.25 | 0 | 0.25 | 0 | 0 | [5 empty] | No | No | No
4 | CCL | FS_CCLM | Study on closed control loop management | 8 | 5 | 3 | 9.43 | 6.43 | 3 | 0.5 | 1.6 | 1.25 | 1.12 | 0.98 | 0.98 | 0.98 | 0.49 |  |  |  | No | No | No | SP-231735 | Primary Rapporteur: Deepanshu Gautam (Samsung), deepanshu.g@samsung.com Secondary Rapporteur: Stephen Mwanje (Nokia), stephen.mwanje@nokia.com | 28.867 | Sept. 2024 | 1020009
|  |  | WT-1: Dynamic CCL creation: The CCL for communication service assurance (including network slice and network slice subnet) can be created by the management system implicitly based on some network events including but not limited to performance degradation, threshold crossing, slice Intent creation. |  | 0.75 | 0.5 |  | 0.94 |  | 0.25 | 0.25 | 0 | 0.16 | 0.14 | 0.14 | 0.14 | 0.07 |  |  |  | NO | NO | NO
|  |  | WT-2: Multi-vendor CCL management: The CCL for communication service assurance can be disintegrated into multiple parts each coming from different vendor implying the standardized interaction between them. It is to be studied whether there would be any advantages and/or constraints for the use of multi-vendor CCL. This may also include determining which SA5 defined management services can support individual steps of a CCL. |  | 0.75 | 0.5 |  | 0.94 |  | 0 | 0.25 | 0.25 | 0.16 | 0.14 | 0.14 | 0.14 | 0.07 |  |  |  | NO | NO | NO
|  |  | WT-3: Conflict Detection and Resolution: CCL related conflicts (including Initiation Conflict and Execution Conflicts) should be identified, mitigated or solved. |  | 1 | 0.5 |  | 1.48 |  | 0 | 0.3 | 0.3 | 0.32 | 0.28 | 0.28 | 0.14 | 0.07 |  |  |  | NO | NO | NO
|  |  | WT-4: CCL scope: The Rel-16 COSLA and Rel-17 eCOSLA defined the CCL only used for communication service assurance scenarios (including network slice and network slice subnet). It is to be studied if the CCL scope can be extended to cover other scenarios including but not limited to RAN UE throughput optimization, fault management, network coverage optimization. |  | 0.25 | 0.25 |  | 0.42 |  | 0 | 0 | 0.2 | 0.08 | 0.07 | 0.07 | 0.14 | 0.07 |  |  |  | NO | NO | NO
|  |  | WT-5: Management Coordination: Study the relation between closed loops and other management features (e.g. SON functions, MDA, Intent) with the objective to harmonize, as appropriate. |  | 1 | 0.5 |  | 1.04 |  | 0 | 0.3 | 0.3 | 0.16 | 0.14 | 0.14 | 0.14 | 0.07 |  |  |  | NO | NO | NO
|  |  | WT-6: Monitoring: Study the advanced monitoring functionalities that provide real-time insights into the performance and outcomes of CCLs. |  | 0.5 | 0.25 |  | 0.47 |  | 0 | 0.25 | 0 | 0.08 | 0.07 | 0.07 | 0.14 | 0.07 |  |  |  | NO | NO | NO
|  |  | WT-7: Other Enhancements: Study other probable measures (e.g CCL feedback, historical learning) to enhance the capabilities of a CCL for better and efficient operations. The study will be done considering the work done with ETSI ZSM, as appropriate. |  | 0.75 | 0.5 |  | 1.14 |  | 0.25 | 0.25 | 0.2 | 0.16 | 0.14 | 0.14 | 0.14 | 0.07 |  |  |  | NO | NO | NO
5 | NDT | FS_NDT | Study on management aspects of Network Digital Twin | 4 | 2 | 2 | 6 | 3 | 3 | 0.5 | 0.5 | 0.5 | 0.8 | 0.7 | 0.3 | [5 empty] | Yes | Yes | Yes | SP-231727 | Primary Rapporteur: Yushuang Hu (China Mobile), huyushuang@chinamobile.com | 28.915 | Sept. 2024 | 1020018
|  |  | WT-1 Investigate and define the terms related to Network Digital Twin in the 3GPP management system. |  | 0.5 | 0.5 |  | 0.8 | 0.8 | 0.3 | 0.2 | 0 | 0.2 | 0.1 | 0.1 | [5 empty] | No | No | Yes
|  |  | WT-2 Study scenarios and requirements for the use of NDT, e.g., for verification of the network operations. Scenarios may include RAN optimization and service assurance. |  | 1.5 | 1.5 |  | 2.2 | 2.2 | 0.2 | 0.3 | 0.5 | 0.6 | 0.6 | 0.2 | [5 empty] | Yes | Yes | Yes
6 | CMO | FS_Cloud_OAM | Study on Cloud Aspects of Management and Orchestration | 5 | 3 | 2 | 5.6 | 3.6 | 2 | 0.2 | 1 | 0.8 | 0.8 | 0.8 | 0 | [5 empty] | No | No | Yes | SP-231781 | Primary Rapporteur: Bahar Sadeghi (Microsoft), bahar.sadeghi@microsoft.com Secondary Rapporteur: Guangjing Cao (CMCC), caoguangjing@chinamobile.com | 28.869 | Sept. 2024 | 1020010
|  |  | WT-1: Analysethe use cases which utilize the VNF generic OAM functions (specified in ETSI) and their potential impacts when applied to the 3GPP management system and study whether and how to incorporate the VNF generic OAM functions into the 3GPP management system, i.e., the requirements and the potential solutions. |  | 1 | 0.75 |  | 1.3 |  | 0 | 0.4 | 0.3 | 0.3 | 0.3 | 0 | [5 empty] | No | No | ETSI
|  |  | WT-2: Study the use cases that utilize the newly developed industry solutions for management of cloud native network functions which leverage industry standards not limited to ETSI NFV MANO; study the potential impact of supporting such use cases on the 3GPP management system, i.e., the potential requirements and solutions. Note: WT-2 includes studying the terminology to determine the appropriate term and definition for cloud native network functions for use in the 3GPP management system. |  | 1.5 | 1 |  | 1.6 |  | 0.2 | 0.4 | 0.4 | 0.3 | 0.3 | 0 | [5 empty] | No | No | No
|  |  | WT-3: Study the use cases, potential requirements and possible solutions for 3GPP management system to support different cloud deployment scenarios, such as public-cloud, private-cloud, hybrid-cloud and multi-cloud deployment scenarios. |  | 0.5 | 0.25 |  | 0.7 |  | 0 | 0.2 | 0.1 | 0.2 | 0.2 | 0 | [5 empty] | No | No | No
7 | MSEC | FS_SECM | Study on Enablers for Security Monitoring | 2 | 1 | 1 | 1 | 1 | 0 | SA5#153: 0; SA5#154: 0.25; SA5#155: 0.5; SA5#156: 0.25 |  | Maybe | Yes | No | SP-231736 | Primary Rapporteur: Clifton Fernandes (Nokia), clifton.fernandes@nokia.com | 28.87 | Sept. 2024 | 1020016
|  |  | WT-1 - collection, management and correlation of security alarms, Specific scope is • WT-1.1 Filtering of security alarms • WT-1.2 Alarm reporting • WT-1.3 Retention policies of security alarms The above data could be possibly collected from radio and core NFs, MnFs and UEs. Note: The events/usecases which can lead to security risks/threats and the related data that needs to be exposed need to be primarily defined by SA3. There could be cases where OAM related security risks/threats may be defined by SA5. |  | 1 | 1 |  | 1 |  | SA5#153: 0; SA5#154: 0.25; SA5#155: 0.5; SA5#156: 0.25 |  | RAN(Maybe) | SA3(Yes) | No
8 | SBMA | FS_SBMA_Ph3 | Study on Service Based Management Architecture enhancement phase 3 | 7.5 | 3.5 | 4 | 9.5 | 5.5 | 4 | 0 | 1 | 1.35 | 1.15 | 1 | 1 | [5 empty] | No | No | No | SP-231725 | Primary Rapporteur: Kai Zhang (Huawei), kai.zhangkai@huawei.com Secondary Rapporteur: Jan Groenendijk (Ericsson), jan.groenendijk@ericsson.com | 28.871 | Sept. 2024 | 1020011
|  |  | WT-1 Further elaboration on usage guidance of model driven service based management services. Study how to enhance the SBMA definitions in TS 28.533 to clarify the model driven approach. |  | 0.5 | 0.5 |  | 0.6 |  | 0 | 0.1 | 0.2 | 0.2 | 0.1 | 0 | [5 empty] | No | No | No
|  |  | WT-2 Study restructuring TSs, including WT-2.1 Study restructuring the PM TSs, TS 32.401 and TS 28.550, as it is difficult to make good implementations due to that information is needed from many different TSs. WT-2.2 Study restructuring the CM TSs, TS 28.622, as it is difficult to make good implementations due to that information is needed from many different TSs |  | 0 | 0.5 |  | 0.4 |  | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | [5 empty] | No | No | No
|  |  | WT-3 Study aspects of alarm and notification including WT-3.1 Study whether a new 3GPP alarm type in Alarm definition if needed. WT-3.2 Study how to enhance reliability of notification transfer and how to document notification definitions. |  | 0.5 | 0.5 |  | 0.5 |  | 0 | 0.1 | 0.1 | 0.2 | 0.1 | 0 | [5 empty] | No | No | No
|  |  | WT-4 Study how to advertise the management capabilities supported by a MnS Producer. |  | 0.5 | 0.5 |  | 0.5 |  | 0 | 0.2 | 0.1 | 0.1 | 0.1 | 0 | [5 empty] | No | No | No
|  |  | WT-5 Study if and how to name a MnS supporting a specific set of capabilities. |  | 0.25 | 0.25 |  | 0.55 |  | 0 | 0.1 | 0.15 | 0 | 0.1 | 0.2 | [5 empty] | No | No | No
|  |  | WT-6 Study how to configure a MnF with the MnS producers to be consumed. |  | 0.25 | 0.25 |  | 0.55 |  | 0 | 0.1 | 0.15 | 0 | 0.1 | 0.2 | [5 empty] | No | No | No
|  |  | WT-7 Study where generic mechanisms (e.g. for data node selection or triggering action) can be applied to SA5 defined functions. |  | 0.5 | 0.5 |  | 0.6 |  | 0 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | [5 empty] | No | No | No
|  |  | WT-8 Study how to clarify the usage of MnsAgent. |  | 0.25 | 0.25 |  | 0.55 |  | 0 | 0 | 0.15 | 0.1 | 0.1 | 0.2 | [5 empty] | No | No | No
|  |  | WT-9 Study the introduction of common data type definitions. |  | 0.25 | 0.25 |  | 0.55 |  | 0 | 0 | 0.1 | 0.15 | 0.1 | 0.2 | [5 empty] | No | No | No
|  |  | WT-10 Study operations aspects including WT-10.1 Study how to use OpenAPI when the interface needs to support many, a priori unknown resource schemas e.g. North Bound Interface of a management system. WT-10.2 Study how to allow operations which might take longer than http timeout with progress information. WT-10.3 Study needs for transactional behavior. Client should be able to request atomic behavior of operations fully succeed or not at all. |  | 0.5 | 0.5 |  | 0.7 |  | 0 | 0.1 | 0.2 | 0.2 | 0.1 | 0.1 | [5 empty] | No | No | No
9 | PTM | FS_PlanM | Study on Management of planned configurations | 8 | 4 | 4 | 8 | 4 | 4 | 0 | 1.3 | 1.3 | 1.4 | 1 | 1 | [5 empty] | No | No | No | SP-231721 | Primary Rapporteur: Olaf Pollakowski (Nokia), olaf.pollakowski@nokia.com Secondary Rapporteur: Balazs Lengyel (Ericsson), balazs.lengyel@ericsson.com | 28.872 | Sept. 2024 | 1020033
|  |  | WT-1 methods for creating planned configurations. |  | 1 | 1 |  | 1 |  | 0 | 0.3 | 0.3 | 0.4 | 0.25 | 0.25 | [5 empty] | No | No | No
|  |  | WT-2 methods for updating planned configurations. |  | 1 | 1 |  | 1 |  | 0 | 0.3 | 0.4 | 0.3 | 0.25 | 0.25 | [5 empty] | No | No | No
|  |  | WT-3 methods for validating the planned configurations. |  | 1 | 1 |  | 1 |  | 0 | 0.4 | 0.3 | 0.3 | 0.25 | 0.25 | [5 empty] | No | No | No
|  |  | WT-4 methods for activating the planned configurations. |  | 1 | 1 |  | 1 |  | 0 | 0.3 | 0.3 | 0.4 | 0.25 | 0.25 | [5 empty] | No | No | No
10 | MADCOL | MADCOL_Ph2 | Data management phase 2 | 5 | 0 | 5 | 5 | 0 | 5 | 0 | 0.5 | 0.5 | 0.5 | 0.7 | 0.7 | [5 empty] | No | No | No | SP-231746 | Primary Rapporteur: Sivaramakrishnan Swaminathan (Nokia), sivaramakrishnan.swaminathan@nokia.com | 28.622, 28.623 | Jun. 2025 | 1020025
|  |  | WT-1.1 specify methods to discover historical management data |  | 0 | 1 |  |  |  | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | [5 empty] | No | No | No
|  |  | WT-1.2 specify enhancements to existing methods for requesting the collection of management data to allow also for requesting historical management data. |  | 0 | 1 |  |  |  | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | [5 empty] | No | No | No
|  |  | WT-1.3 specify enhancements to existing methods for reporting (newly) collected management data to allow also for reporting of historical management data. |  | 0 | 1 |  |  |  | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | [5 empty] | No | No | No
|  |  | WT-2 specify the reporting format for "ManagementDataCollection". |  | 0 | 1 |  |  |  | 0 | 0.1 | 0.1 | 0.1 | 0.2 | 0.2 | [5 empty] | No | No | No
|  |  | WT-3 specify methods to manage external management data. |  | 0 | 1 |  |  |  | 0 | 0.1 | 0.1 | 0.1 | 0.2 | 0.2 | [5 empty] | No | No | No
11 | SREP | FS_Data_SREP | Study on data management regarding subscriptions and reporting | 4 | 2 | 2 | 4 | 2 | 2 | SA5#153: 0; SA5#154: 0.6; SA5#155: 0.6; SA5#156: 0.8 |  | Maybe | Maybe | No | SP-231732 | Primary Rapporteur: Robert Petersen (Ericsson), robert.petersen@ericsson.com | 28.873 | Sept. 2024 | 1020012
|  |  | WT-1 Study how the load on the NFs and/or 3GPP mgmt. system can be decreased by extracting some of the required functionality to be deployed outside the NFs implementing management capabilities defined in SA5. |  | 1 | 1 |  | 1 |  | SA5#153: 0; SA5#154: 0.3; SA5#155: 0.3; SA5#156: 0.4 |  | Maybe | Maybe | No
|  |  | WT-2 Study how to solve to get unique job identifiers for performance measurement, Trace/MDT and QoE subscriptions/requests within a PLMN from different consumers. Propose potential requirements, use cases and solutions for this issue. |  | 1 | 1 |  | 1 |  | SA5#153: 0; SA5#154: 0.3; SA5#155: 0.3; SA5#156: 0.4 |  | Maybe | Maybe | No
12 | PM | PM_KPI_5G_Ph4 | 5G performance measurements and KPIs phase 4 | 3.5 | 0 | 3.5 | 3.5 | 0 | 3.5 | 0 | 0.5 | 0.4 | 0.5 | 0.4 | 0.4 | [5 empty] | Maybe | Maybe | No | SP-231747 | Primary Rapporteur: XiuMin Chen (China Telecom), chenxiumin@chinatelecom.cn Secondary Rapporteur: Xie Baoguo (ZTE), xie.baoguo@zte.com.cn | 28.552, 32.425, 28.554, 28.532, 28.550, 28.abc | Jun. 2025 | 1020026
|  |  | WT-1: To define new 5G performance measurements and KPIs for the following features, including: WT-1.1 Mobility Enhancements: Layer 1/2 triggered mobility (LTM); WT-1.2 Architecture Enhancements for XR (Extended Reality) and media service; WT-1.3 Mobile Terminated-Small Data Transmission; WT-1.4 Enhancements of NR Multicast and Broadcast Services; WT-1.5 Access Traffic Steering, Switch and Splitting support in the 5G system architecture Phase 3. NOTE: New performance measurements may be added/updated to support other related network new features based on the progress of other groups such as SA2. |  | 0 | 1.5 |  |  |  | 0 | 0.1 | 0.2 | 0.2 | 0.1 | 0.15 | [5 empty] | Maybe | Maybe | No
|  |  | WT-2: To define and enhance the 5G performance measurements and KPIs that are still missing for the features that have been implemented in Rel-18. |  | 0 | 0.75 |  |  |  | 0 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | [5 empty] | Maybe | Maybe | No
|  |  | WT-3: To define and enhance the UE level measurements to support data analytics and AI/ML related features in 5GS. |  | 0 | 0.75 |  |  |  | 0 | 0.1 | 0 | 0.1 | 0.1 | 0.1 | [5 empty] | Maybe | Maybe | No
|  |  | WT-4: To enhance the current PM streaming framework to have multiple measured objects in a stream and address requirements towards PM/KPI from other working groups. |  | 0 | 0.5 |  |  |  | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.05 | [5 empty] | Maybe | Maybe | No
13 | AdNRM | AdNRM_Ph3 | 5G Advanced NRM features phase 3 | 4.5 | 0 | 4.5 | 4.5 | 0 | 4.5 | 0 | 0.3 | 0.5 | 0.8 | 0.7 | 0.8 | [5 empty] | Yes | Yes | Maybe | SP-231745 | Primary Rapporteur: Sean Sun (Nokia), sean.sun@nokia-sbell.com Secondary Rapporteur: Shi Xiaoli (Huawei), (shixiaoli@huawei.com) | 28.540, 28.541, 28.622, 28.623 | Jun. 2025 | 1020027
|  |  | WT-1: Enhancement for 5GC NRM to support 5GC features (including but not limited to 5G_eLCS_Ph3, ranging based services). |  | 0 | 1.2 |  |  |  | 0 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | [5 empty] | Maybe | Yes | No
|  |  | WT-2: Enhancement for NR NRM to support NR features (note: to be updated based on RAN Rel19 progress). |  | 0 | 1 |  |  |  | 0 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | [5 empty] | Yes | Maybe | No
|  |  | WT-3: Enhancement for NRM fragment related to misalignment with NG.116. |  | 0 | 0.3 |  |  |  | 0 | 0.1 | 0 | 0 | 0 | 0.1 | [5 empty] | Maybe | Maybe | Maybe
|  |  | WT-4: Generic NRM enhancement. |  | 0 | 0.5 |  |  |  | 0 | 0 | 0.1 | 0.1 | 0.1 | 0 | [5 empty] | No | No | No
|  |  | WT-5: Stage 3 enhancement. |  | 0 | 0.5 |  |  |  | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | [5 empty] | No | No | No
|  |  | WT-6: Enhancement for edge NRM to support new EDGEAPP features defined in Rel-19. |  | 0 | 1 |  |  |  | 0 | 0 | 0.1 | 0.2 | 0.1 | 0.2
14 | TMQ | TraceQoE_OAM | Subscriber and Equipment Trace and QoE collection management | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | [5 empty] | Maybe | Maybe | No | SP-231748 | Primary Rapporteur: Zu Qiang (Ericsson), zu.qiang@ericsson.com | 32.421, 32.422, 32.423, 28.404, 28.405, 28.406, 28.622, 28.623 | Jun. 2025 | 1020028
|  |  | WT-1 Specify use cases and requirements. |  | 0 | 0.2 |  |  |  | 0 | 0.1 | 0.1 | 0 | 0 | 0 | [5 empty] | Maybe | Maybe | No
|  |  | WT-2 Specify overall function descriptions. |  | 0 | 0.5 |  |  |  | 0 | 0 | 0 | 0.1 | 0.1 | 0 | [5 empty] | Maybe | Maybe | No
|  |  | WT-3 Specify updated management requests. For all WTs: This is to be done for the already specified Rel-18 RAN MRO measurements: • Random Access (RA) Report • Successful Handover Report (SHR) • Successful PSCell Change Report (SPR) • Mobility History Information (MHI) Report • Xn message UE History Information (UHI) New Rel-19 topics from normative work from RAN3 and/or SA2. Also the RAN QoE work in Rel-18 that does not yet have any management support is included: • QoE measurement collection for application sessions delivered via MBS broadcast or multicast. • QMC support in RRC_IDLE and RRC_INACTIVE. |  | 0 | 0.3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.1 | [5 empty] | Maybe | Maybe | No
15 | NTNM | FS_ NTN_OAM_Ph2 | Study on Management Aspects of NTN Phase 2 | 5 | 3 | 2 | 5.5 | 3.5 | 2 | SA5#153: 0; SA5#154: 1; SA5#155: 1; SA5#156: 1; SA5#157: 0.5 |  | Yes | Yes | No | SP-231733 | Primary Rapporteur: MingRui Sun (China Unicom), sunmr19@chinaunicom.cn Secondary Rapporteur: Min Shu (CATT), shumin@catt.cn | 28.874 | Sept. 2024 | 1020013
|  |  | WT-1: Management capabilities to support new network architecture or functions for satellite regenerative payloads, considering different types of satellite constellations (both GSO and NGSO). |  | 1 | 1 |  | 1.1 |  | SA5#153: 0; SA5#154: 0.3; SA5#155: 0.4; SA5#156: 0.3; SA5#157: 0.1 |  | Yes (Partial with RAN2/RAN3) | Yes (Partial with SA2) | No
|  |  | WT-2: Management requirement, usecase and solution to support Store and Forward (S&F) satellite operation and UE-Satellite-UE communication. |  | 0.5 | 0.25 |  | 0.6 |  | SA5#153: 0; SA5#154: 0.3; SA5#155: 0.1; SA5#156: 0.1; SA5#157: 0.1 |  | Maybe | Yes (SA2) | No
|  |  | WT-3: Requirements and potential solutions to support end to end management (including RAN domain and CN domain) in NTN scenarios, such as coordinate with non-3GPP part (e.g. Satellite Control System, Transport System) to provide the NTN specific requirements. |  | 0.75 | 0.5 |  | 0.85 |  | SA5#153: 0; SA5#154: 0.2; SA5#155: 0.25; SA5#156: 0.3; SA5#157: 0.1 |  | Maybe | Maybe | No
|  |  | WT-4: Management enhancement for NTN-TN and NTN-NTN mobility coordination and better service continuity. NOTE: This study depends on the progress in 3GPP RAN WGs and SA2 WG and may require cooperation with them. |  | 0.75 | 0.25 |  | 0.95 |  | SA5#153: 0; SA5#154: 0.2; SA5#155: 0.25; SA5#156: 0.3; SA5#157: 0.2 |  | Yes (RAN2/RAN3) | Maybe | No
16 | IABM | FS_NR_mobile_IAB_OAM | Study on management of IAB nodes | 5 | 2 | 3 | 4.6 | 1.6 | 3 | SA5#153: 0; SA5#154: 0.5; SA5#155: 0.5; SA5#156: 0.4; SA5#157: 0.2 |  | Maybe | Maybe | No | SP-231729 | Primary Rapporteur: JunFeng Wang (Ericsson), junfeng.a.wang@ericsson.com | 28.875 | Sept. 2024 | 1020014
|  |  | WT-1 Identify the use cases and scenarios in which how IAB node connects to OAM system. |  | 0.5 | 0.5 |  | 0.4 |  | SA5#153: 0; SA5#154: 0.3; SA5#155: 0.1; SA5#156: 0; SA5#157: 0 |  | No | No | No
|  |  | WT-2 Investigate the potential enhancement to Plug and Connect NE to OAM system. |  | 0.5 | 0.5 |  | 0.4 |  | SA5#153: 0; SA5#154: 0.2; SA5#155: 0.2; SA5#156: 0; SA5#157: 0 |  | Maybe | Maybe | No
|  |  | WT-3 Identify the potential requirements and solutions to support the continuity of OAM connectivity during IAB node mobility and MBSR roaming over PLMNs. |  | 0.5 | 1 |  | 0.2 |  | SA5#153: 0; SA5#154: 0; SA5#155: 0.1; SA5#156: 0.1; SA5#157: 0 |  | Yes | Maybe | No
|  |  | WT-4 Investigate the potential impact to CM, PM, and FM, and identify the potential requirements and solutions to support IAB FCAP management. |  | 0.5 | 1 |  | 0.6 |  | SA5#153: 0; SA5#154: 0; SA5#155: 0.1; SA5#156: 0.3; SA5#157: 0.2 |  | Maybe | Maybe | No
17 | RedcapM | FS_NR_RedCap_OAM | Study on management aspects of RedCap feature | 5 | 2.5 | 2.5 | 5.5 | 3 | 2.5 | SA5#153: 0; SA5#154: 0.8; SA5#155: 0.8; SA5#156: 0.9; SA5#157: 0.5 |  | Yes | Yes | No | SP-231734 | Primary Rapporteur: Zhen Xing (China Unicom), xingz12@chinaunicom.cn Secondary Rapporteur: Shoufeng Wang (Asiainfo), wangsf11@asiainfo.com | 28.876 | Sept. 2024 | 1020017
|  |  | WT-1 Study potential requirements related to management of RedCap based features in RAN network WT-1.1 Enhancement on management of RedCap related initial BWP; WT-1.2 Enhancement on management of eDRX for RedCap; WT-1.3 Potential management enhancements related to other WGs; |  | 1 | 1 |  | 1.1 |  | SA5#153: 0; SA5#154: 0.4; SA5#155: 0.3; SA5#156: 0.3; SA5#157: 0.1 |  | Yes | Yes | No
|  |  | WT- 2 Study new performance measurements and new key performance indicators to evaluated performance of RedCap WT-2.1 Investigate the metrics for resource load of RedCap network; WT-2.2 Investigate new measurements or KPIs for Inactive UEs; |  | 0.5 | 0.5 |  | 0.6 |  | SA5#153: 0; SA5#154: 0.3; SA5#155: 0.1; SA5#156: 0.1; SA5#157: 0.1 |  | Yes | Yes | No
|  |  | WT- 3 Study the estimation method for RedCap energy consumption of network and the energy efficiency of RedCap. |  | 0.5 | 0.5 |  | 0.7 |  | SA5#153: 0; SA5#154: 0.1; SA5#155: 0.3; SA5#156: 0.1; SA5#157: 0.2 |  | Yes | Yes | No
|  |  | WT- 4 Study what information about RedCap can be exposed between CSP and CSC, according to different RedCap use cases and different deployment scenarios. |  | 0.5 | 0.5 |  | 0.6 |  | SA5#153: 0; SA5#154: 0; SA5#155: 0.1; SA5#156: 0.4; SA5#157: 0.1 |  | Yes | Yes | No
18 | NWDAFM | FS_NWDAF_OAM_Ph2 | Study on Enhancement of Management Aspects related to NWDAF Phase 2 | 3.5 | 1.5 | 2 | 3.5 | 1.5 | 2 | 0 | 0.6 | 0.4 | 0.5 | 0 | 0.6 | [5 empty] | No | No | No | SP-231724 | Primary Rapporteur: Song Zhao (China Telecom), zhaosong1@chinatelecom.cn | 28.877 | Sept. 2024 | 1020020
|  |  | WT-1 Investigate the potential CM enhancements for NWDAF to support the new features introduced in Rel-18, including accuracy checking capability, Analytics Exposure in Roaming Case and Federated Learning. |  | 1 | 1 |  | 1 |  | 0 | 0.4 | 0.2 | 0.4 | 0 | 0.3 | [5 empty] | No | No | No
|  |  | WT-2 Study how to evaluate the efficiency of the network data collection of NWDAF, data volume related to the data related services provided by NWDAF and the existed measurement about the number of NWDAF services invoked. |  | 0.5 | 1 |  | 0.5 |  | 0 | 0.2 | 0.2 | 0.1 | 0 | 0.3 | [5 empty] | No | No | No
19 | NSM | FS_NetShare_OAM_Ph3 | Study on Management of Network Sharing Phase3 | 4 | 2 | 2 | 4.6 | 2.6 | 2 | 0 | 0.8 | 0.6 | 0.6 | 0.4 | 0.2 | [5 empty] | No | No | No | SP-231731 | Primary Rapporteur: ZhaoNing Wang (China Unicom), wangzn18@chinaunicom.cn | 28.878 | Sept. 2024 | 1020015
|  |  | WT-1 Trace job and collection requirements for POPs. |  | 1 | 1 |  | 1.3 |  | 0 | 0.8 | 0.2 | 0.1 | 0.1 | 0.1 | [5 empty] | No | No | No
|  |  | WT-2 Study issues related to Rel-18, such as: WT-2.1 Study enhancements and scenarios for SBMA to support MOCN WT-2.2 Study scenarios related to access rights on CRUD operation of MOCN management data |  | 0.5 | 0.5 |  | 0.5 |  | SA5#155: 0.3; SA5#156: 0.1; SA5#157: 0.1; SA5#158: 0 |  | no | no | no
|  |  | WT-3 Investigate potential enhancements for Indirect Network Sharing scenarios. |  | 0.5 | 0.5 |  | 0.8 |  | SA5#155: 0.1; SA5#156: 0.4; SA5#157: 0.2; SA5#158: 0.1 |  | no | Maybe(SA1 and SA2) | no
20 | EE | FS_Energy_OAM_Ph3 | Study on energy efficiency and energy saving aspects of 5G networks and services | 8 | 5 | 3 | 8 | 5 | 3 | 0.4 | 1 | 1.3 | 1 | 0.8 | 0.5 | [5 empty] | Yes | Yes | Yes | SP-231723 | Primary Rapporteur: Jean-Michel Cornily (Huawei), jean.michel.cornily@huawei.com Secondary Rapporteur: Ashutosh Kaushik (Samsung), ashutosh19.k@samsung.com | 28.88 | Sept. 2024 | 1020021
|  |  | WT-1: Left-over SA5 topics from Rel-18 WT-1.1 Study new or enhanced Energy Consumption (EC) and Energy Efficiency (EE) KPIs and measurements, e.g. for new types of network slices, RAN sharing, etc. WT-1.2 Consideration of containerized VNFs, study enhancements to virtualized NF EC KPIs, including containerized VNF/VNFCs, and possible impacts to metrics collected from NFV MANO so as to be able to estimate their energy consumption based on e.g. their virtual CPU usage, virtual memory usage, etc. WT-1.3 Study new use cases, requirements and solutions for energy efficiency and energy saving, applying to NG-RAN and/or 5GC and/or network slicing, (including but not limited to intent based, analytics based and AI/ML assisted energy saving) WT-1.4 Study deployment scenarios involving multiple actors, e.g. in case of passive RAN sharing, active RAN sharing, MNO VNFs hosted on private cloud or public cloud, etc. |  | 0.5 | 0.5 |  | 0.9 |  | 0.1 | 0.1 | 0.1 | 0.3 | 0.2 | 0.1 | [5 empty] | No | No | No
|  |  | WT-2: New Rel-19 topics from other SA WGs WT-2.1 Consideration of energy consumption measurement/estimation at various granularities WT-2.2 Study whether and how mapping measured or estimated energy consumption measurements on to carbon emissions is possible. Study the estimation of carbon emissions efficiency and how to achieve carbon emissions saving in the 5G system. Additionally, whether and how renewable energy consumption information can be obtained will be studied WT-2.3 Study the support of different energy states of network elements and network functions. SA5 may have to provide OAM support NOTE: the exact scope of WoP#2 may have to be adjusted depending on ongoing Rel-19 SA1 work item (EnergyServ) and SA2 study item (FS_CNEES) outcomes. |  | 2 | 1 |  | 2 |  | 0.2 | 0.5 | 0.5 | 0.4 | 0.3 | 0.1 | [5 empty] | No | SA1, SA2 | No
|  |  | WT-3: OAM support to new Rel-19 RAN energy saving features WT-3.1 Study OAM support for requirements of RAN WGs related work as suitable and whether new performance measurements and/or new KPIs and/or new configuration parameters are needed to support energy saving features specified by RAN TSG/WGs NOTE: whether new performance measurements and/or KPIs and/or configuration parameters will be needed is unknown yet, since RAN TSG has not yet approved any Rel-19 SI or WI related to energy efficiency or energy saving. |  | 1 | 0.5 |  | 0.8 |  | 0 | 0.1 | 0.4 | 0.1 | 0.1 | 0.1 | [5 empty] | RAN1, RAN2, RAN3 | No | No
|  |  | WT-4: Coordination with other SDOs / fora to build comprehensive and consistent solutions for EE WT-4.1 Continue the existing collaboration with ETSI TC EE 02 on a unified architecture for the control and monitoring of PEE (Power, Energy, Environmental) parameters of ICT equipment in RAN sites WT-4.2 Potentially start collaborating with ETSI EE EEPS / ITU-T SG5 on multi-dimensional network energy efficiency metrics (including e.g. QoE, coverage, etc.) WT-4.3 Continue considering recommendations from NGMN GFN project WT-4.4 Continue exchanging information with ITU-T study groups on our respective outcomes WT-4.5 Potential collaboration with other SDOs, fora, etc. |  | 1 | 0.5 |  | 0.7 |  | 0 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | [5 empty] | No | No | ETSI EE, ETSI NFV, NGMN, ITU-T, …
|  |  | WT-5: Other WT-5.1 Continue maintaining SA5 comprehensive view of 3GPP work on energy efficiency and energy saving started in Rel-18 WT-5.2 This study on EE aspects of 5G networks and services may also have to monitor other study and/or work items in SA5 or in other WGs where some EE aspects are addressed, and propose harmonized solutions to them if deemed relevant. |  | 0.5 | 0.5 |  | 0.6 |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | [5 empty] | RAN1, RAN2, RAN3 | All SA WGs | No
21 | Mexpo | FS_MExpo | Study on Enhanced OAM for management exposure to external consumers | 6 | 4.5 | 1.5 | 5.8 | 4.3 | 1.5 | 0.25 | 1.25 | 1.5 | 0.65 | 0.5 | 0.15 | [5 empty] | No | Yes | Yes | SP-231728 | Primary Rapporteur: Scott Probasco (Nokia), scott.probasco@nokia.com | 28.879 | Sept. 2024 | 1020022
|  |  | WT-1 Exposure of management services to external consumers WT-1.1 Identify generic requirements for exposure of SA5 management services to external consumers, irrespective of the vertical industry. WT-1.2 Identify 1) potential mechanisms to discover management service producers and their respective capabilities while leveraging as much as possible the existing solutions and extending where necessary. Compare existing solutions (e.g., CAPIF, EGMF, MnS Registry and/or MSAC) that could be leveraged. 2) procedures for exposure of management services based on CAPIF, EGMF, MnS Registry, MSAC or a combination thereof. Some of the identified gaps for use of CAPIF in SA5 are listed in S5-236381 clause 4.1.2. WT-1.3 Identify potential requirements that would be provided to the access control (MSAC) work item. WT-1.4 Study whether and how SA5 defined exposure mechanisms fit within the GSMA Open Gateway framework. This framework includes OPG, CAMARA and TM Forum, as declared at https://www.gsma.com/futurenetworks/wp-content/uploads/2023/05/The-Ecosystem-for-Open-Gateway-NaaS-API-development.pdf . |  | 1.5 | 0.5 |  | 2.2 |  | 0.15 | 0.45 | 0.45 | 0.5 | 0.5 | 0.15 | [5 empty] | No | SA6 | OPG, CAMARA, TM Forum
|  |  | WT-2 management exposure WT-2.1 Study whether and how the requirements of communication services can be captured with <<ServiceProfile>> (datatype) WT-2.2 Study the definition of a new service management information model (focused on service requirements, and in scope of CSP), separated from the NRM fragment (focused on network constructions, and in scope of NOP). This new model would give the NOP the flexibility to decide which solution (e.g., with either network slicing, or DNN provisioning, or SNPN, …) is most appropriate to fulfil the requirements of a given communication service. WT-2.3 Study modelling solutions that provide alternative means to fulfil ServiceProfile other than via network slicing. Examples of these means include DNN provisioning and SNPN provisioning. WT-2.4 clarify the role of communication service (TS 28.530) in 3GPP management system, and the relationship with PDU session definition in 3GPP 5G system architecture (23.501) |  | 1.5 | 0.5 |  | 1.1 |  | 0.05 | 0.45 | 0.5 | 0.1 | 0 | 0 | [5 empty] | No | No | OPG
|  |  | WT-3 Exposing network slice management capabilities in network sharing scenarios: WT-3.1 identify network slicing management aspects in network sharing scenarios beyond RAN sharing, e.g. backhaul sharing. These scenarios are motivated with the increasing tendency of telco operators to offload the ownership and management of access infrastructures on 3rd parties. WT-3.2 study the impact of these aspects in the provisioning (28.531) and the models (Slice NRM fragment and the information elements of a potential new management information model). For this work, NSaaS and NSSaaS description reported 28.811 will be considered into account. |  | 1.5 | 0.5 |  | 1 |  | 0.05 | 0.35 | 0.55 | 0.05 | 0 | 0 | [5 empty] | No | No | No
|  | Total TUs for Rel-19 SIDs/WIDs |  | 113.6 | 52.7 | 60.9 | 121.63 | 62.03 | 59.6 | 2.35 | 17.6 | 17.25 | 16.82 | 12.38 | 9.53
|  |  | Total TUs left for Rel-19 WIDs/SIDs | 94
|  |  | Gap between Total TUs left and planned | 10.4 |  |  | 2.37
CH
1 | SATCH | FS_5GSAT_Ph3_CH | New SID on charging aspects of satellite access Phase 3 | 6 | 3 | 3 | [17 empty] | S5‑241830
|  |  | WT1: Possible business scenarios | 2 | 1 | 1 | [14 empty] | No | Maybe | No
|  |  | WT2: Possible charging scenarios and potential charging requirements based on business scenarios | 2 | 1 | 1 | [14 empty] | No | Yes | No
|  |  | WT3: Identify the potential charging solutions. | 2 | 1 | 1 | [14 empty] | No | Yes | No
2 | CAPCH | FS_CAPIF_Ph2_CH | New SID on Charging Aspects of CAPIF | 12 | 6 | 6 | [17 empty] | S5‑241832
|  |  | WT-1: Identify charging scenarios and requirements for supporting CAPIF | 4 | 2 | 2 | [14 empty] | No | No | No
|  |  | WT-2: Identify NEF functionalities which can implement CAPIF functionalities for charging scenarios | 4 | 2 | 2 | [14 empty] | No | No | No
|  |  | WT-3: Study the potential charging solutions in order to support CAPIF | 4 | 2 | 2 | [14 empty] | No | No | No
3 | RTCCH | FS_NG_RTC_Ph2_CH | New SID on Charging aspects of next generation real time communication services phase 2 | 8 | 5 | 3 | [17 empty] | S5‑241835
|  |  | WT-1: Identify charging scenarios and potential charging requirements to support the following aspects of IMS network capabilities exposure, standalone IMS data channel, avatar communication, services over IMS data channel as a part of 3GPP PS Data Off Exempt Services, and IMS data channel applications download | 3 | 2 | 1 | [14 empty] | No | Yes | No
|  |  | WT-2: Investigate the potential solutions to support the above charging scenarios and charging requirements | 5 | 3 | 2 | [14 empty] | No | Yes | No
4 | CHSEG | CHFSeg | New WID on CHF Segmentation | 4 | 0 | 4 | [17 empty] | S5‑241826
|  |  | WT-1: CHF Selection by NF Consumers Information | 1 | 0 | 1 | [14 empty] | No | No | No
|  |  | WT-2: CHF Selection based on SUPI or CHF Group ID | 1 | 0 | 1 | [14 empty] | No | Maybe | No
|  |  | WT-3: CHF Selection by a Tenant or Application | 1 | 0 | 1 | [14 empty] | No | Maybe | No
|  |  | WT-4: CHF Discovery by Charging Domains | 1 | 0 | 1 | [14 empty] | No | No | No
5 | RAGCH | Ranging_SL_CH | New WID on Charging Aspects of Ranging and Sidelink Positioning | 3 | 0 | 3 | [17 empty] | S5‑241827
6 |  |  | WT-1: Support of architecture for converged charging for Ranging and Sidelink Positioning | 0.5 | 0 | 0.5 | [14 empty] | No | No | No
7 |  |  | WT-2: Support of converged charging for UE positioning assisted by Sidelink Positioning and involving 5GC | 2 | 0 | 2 | [14 empty] | No | No | No
8 |  |  | WT-3: Support of converged charging for Ranging/SL Positioning service exposure | 0.5 | 0 | 0.5 | [14 empty] | No | No | No
9 | [20 empty] | No | Yes | No
10 | [20 empty] | No | Yes | No
6 | NSCH | NetShare_CH | Charging enhancement for indirect network sharing | 1 | 0 | 1 | [17 empty] | S5-243011
|  |  | WT-1: adding description of interconnect charging for indirect network sharing | 0 | 0 | 1
7 | UASCH | FS_UAS_CH | New SID on Charging aspects of Uncrewed Aerial Systems | 8 | 5 | 3 | [17 empty] | S5-242994
|  |  | WT-1: Identify charging scenarios and requirements for supporting UAS | 3 | 2 | 1
|  |  | WT-2: Evaluate the potential solutions to support the above charging scenarios and charging requirements | 5 | 3 | 2
8 | EESCH | EnergySys_CH | New WID on Charging Aspects for Energy Efficiency of 5G | 6 | 0 | 6 | [17 empty] | S5-243008
|  |  | WT-1: specify the charging principles, charging requirement and message flow. | 3 | 0 | 3
|  |  | WT-2: specify the corresponding enhancements to charging information, open API and CDR ASN.1 | 3 | 0 | 3
|  | Total TUs for Rel-19 SIDs/WIDs |  | 48 | 19 | 29

## SA#155 Stats update
90 | Bonus Cconsumed in minutes (SA5#155) | Bonus TU (SA5#155) | time consumed in minutes (SA5#155) | TU consumed in TU（#155） | Planned TU (#155) | time consumed in minutes (SA5#154) | TU consumed in TU（#154） | Planned TU (#154) | TU consumed in TU（#153） | Planned TU（#153） | total TU | TU leftover
1/2/3/4/5.1/5.2/5.3/5.4 - 26 (88m)
6.1 OAM Plenary - 37 (60m)
6.2 new WID - 2 (6m) | [5 empty] | 15 | 0.16667
6.3 Pre-Rel-18 CRs - 130 (150m)
6.4 Rel-18/Rel-19 CRs - 135 (372m)
6.19.1 FS_AIML_MGT_Ph2 - 29 (116m) | 90 | 1 | 85 | 0.95 | 0.95 | 150 | 1.6667 | 1.45 | 0 | 0 | 8.1 | 5.7
6.19.2 FS_eMDAS_Ph3 - 15(60m) | 30 | 0.33333 | 126 | 1.4 | 1.4 | 55 | 0.61111 | 1.3 | 0 | 0 | 8.5 | 5.8
6.19.3 FS_IDMS_MN_Ph3 - 19 (76m) | 150 | 1.6667 | 90 | 1 | 1 | 76 | 0.84444 | 1.25 | 0.5 | 0.5 | 8 | 5.25
6.19.4 FS_CCLM - 19 (76m) | 90 | 1 | 112 | 1.25 | 1.25 | 76 | 0.84444 | 1.6 | 0.3 | 0.5 | 8 | 4.65
6.19.5 FS_NDT - 14 (56m) | 90 | 1 | 45 | 0.5 | 0.5 | 60 | 0.66667 | 0.5 | 0.3 | 0.5 | 4 | 2.5
6.19.6 FS_Cloud_OAM - 25(100m) | 150 | 1.6667 | 72 | 0.8 | 0.8 | 80 | 0.88889 | 1 | 0.3 | 0.2 | 5 | 3
6.19.7 FS_SECM -2 (8m) |  |  | 0 | 0 | 0.5 | 0 | 0 | 0.25 | 0 | 0 | 2 | 1.25
6.19.8 FS_SBMA_Ph3 - 6 (24m) |  |  | 100 | 1.1111 | 1.35 | 30 | 0.33333 | 1 | 0 | 0 | 7.5 | 5.15
6.19.9 FS_PlanM - 5(20m) |  |  | 45 | 0.5 | 1.3 | 20 | 0.22222 | 1.3 | 0 | 0 | 8 | 5.4
6.19.10 MADCOL_ph2 - 9(36m) |  |  | 30 | 0.33333 | 0.5 | 40 | 0.44444 | 0.5 | 0 | 0 | 5 | 4
6.19.11 FS_Data_SREP - 5(20m) |  |  | 27 | 0.3 | 0.6 | 12 | 0.13333 | 0.6 | 0 | 0 | 4 | 2.8
6.19.12 PM_KPI_5G_Ph4 - 18(72m) |  |  | 30 | 0.33333 | 0.4 | 50 | 0.55556 | 0.5 | 0 | 0 | 3.5 | 2.6
6.19.13 AdNRM_ph3 - 8 (32m) |  |  | 25 | 0.27778 | 0.4 | 28 | 0.31111 | 0.3 | 0 | 0 | 2 | 1.3
6.19.14 TraceQoE_OAM - 6(24m) |  |  | 10 | 0.11111 | 0.1 | 10 | 0.11111 | 0.1 | 0 | 0 | 1 | 0.8
6.19.15 FS_ NTN_OAM_Ph2 - 13(52m) |  |  | 50 | 0.55556 | 1 | 40 | 0.44444 | 1 | 0 | 0 | 5 | 3
6.19.16 FS_NR_mobile_IAB_OAM - 7(28m) |  |  | 8 | 0.088889 | 0.5 | 15 | 0.16667 | 0.5 | 0 | 0 | 5 | 4
6.19.17 FS_NR_RedCap_OAM - 6(24m) |  |  | 30 | 0.33333 | 0.8 | 10 | 0.11111 | 0.8 | 0 | 0 | 5 | 3.4
6.19.18 FS_NWDAF_OAM_Ph2 - 8(32m) |  |  | 20 | 0.22222 | 0.4 | 20 | 0.22222 | 0.6 | 0 | 0 | 3.5 | 2.5
6.19.19 FS_NetShare_OAM_Ph3 - 5(20m) |  |  | 5 | 0.055556 | 0.6 | 10 | 0.11111 | 0.8 | 0 | 0 | 4 | 2.6
6.19.20 FS_Energy_OAM_Ph3 -16(64m) |  | 1 | 117 | 1.3 | 1.3 | 90 | 1 | 1 | 0.15 | 0.4 | 8 | 5.3
6.19.21 FS_MExpo - 13(52m) | 90 | 1 | 135 | 1.5 | 1.5 | 10 | 0.11111 | 1.25 | 0.1 | 0.25 | 6 | 3
total |  | 8.6667 |  | 12.9222 | 17.15 |  | 9.8 | 17.6 | 1.65 | 2.35 | 111.1 | 74
total TU consumed | [10 empty] | 37.1
(planned 2 TU) 0.35 TU spent on Rel-19 procedure discussion 1.IDMS(45m): submitted 12/treated 4 2.CCL(30m):submitted 6/treated 4 3.NDT(30m):submitted 13/treated 10 4. CMO(30m) submitted 5/treated 3 6 EE(15m) submitted 7/treated 6 7.Expo(10m):submitted 3/treated 3

## History TU tdocs information
Summary of change
SA5#153 | S5-240006 | S5-241078
SA5#154 | S5-241120 | S5-241853 | Add #154 TU consumption info
SA5#155 | S5-242320 | S5-243215 | 1. Separate TU plan and TU consumption statistics, latest TU plan is kept in page "SA5 work plan post", TU consumption statistics is updated after every meeting in "Stats update" page. 2. Add CH TU plan information according to agreed WI/SIs. 3. Update IDM plan according to rapp offline request 4. Update adNRM WTs as agreed in S5-242034, add TU plan for WT-6. 5. Update NSM WTs as agreed in S5-242035, add TU plan for WT-2 and WT-3. 6. Add #155 TU consumption.
1. update according to SA5#155 agreement on revised WIDs/SIDs and new CH topics. 2. Add adjusted TU plan columns mark the normative work cells in Orange.