## Slide 1: SA6#63 Work Plan Review
Atle Monrad (InterDigital)
SA6 Chair

## Slide 2: Overview: Rel-19 Studies (1/2)
Study Item | WI Code | SID Approved | SA6#62 | SA6#63 | Target Completion | Remarks
Study on enhanced application layer support for location services | FS_eLSAPP | SA#100 (06/2023) | 100% |  | SA#105 (09/2024) | Study completed
Study on Service aspects for supporting the eMMTel service | FS_eMMTelAPP | SA#100 (06/2023) | 80% | % | SA#105 (09/2024) | 
Study on application layer support for AI/ML services | FS_AIMLAPP | SA#101 (09/2023) | 100% |  | SA#105 (09/2024) | Study completed.
Study on application enablement for Localized Mobile Metaverse Services | FS_Metaverse_App | SA#102 (12/2023) | 100% |  | SA#105 (09/2024) | Study completed
Study on Application enabler for XR Services | FS_XRApp | SA#102 (12/2023) | 90% | % | SA#105 (09/2024) | 
Study on application enablement for Satellite access enabled 5G Services | FS_5GSAT_Ph3_App | SA#102 (12/2023) | 100% |  | SA#105 (09/2024) | Study completed
Study on CAPIF Phase 3 | FS_CAPIF_Ph3 | SA#102 (12/2023) | 90% | % | SA#105 (09/2024) | 
Study on MC services support on IOPS mode of operation | FS_Generic_IOPS | SA#104 (6/2024) | 40% | % | SA#106 (12/2024) | 

## Slide 3: Overview: Rel-19 Studies (2/2)
Study Item | WI Code | SID Approved | SA6#62 | SA6#63 | Target Completion | Remarks
Study on SEAL enhancements | FS_SEAL_Ph4 | SA#105 (09/2024) | - | % | SA#107 (03/2025) | 

## Slide 4: Overview: Rel-19 Work-Items (1/3)
Work Item | WI Code | WID Approved | SA6#62 | SA6#63 | Target Completion | Remarks
Enhanced Mission Critical Architecture | enhMC | SA#100 (06/2023) | 75% | % | SA#106 (12/2024) | 
Sharing of administrative configuration between interconnected MC service systems | MCShAC | SA#100 (06/2023) | 100% |  | SA#106 (12/2024) | WI completed
Railways specific Enhancements to Mission Critical Services Phase 5 | FRMCS_Ph5 | SA#100 (06/2023) | 70% | % | SA#106 (12/2024) | 
Application Architecture for MSGin5G Service Phase 3 | 5GMARCH_Ph3 | SA#100 (06/2023) | 50% | % | SA#106 (12/2024) | 
MC services support on IOPS mode of operation | FS_Generic_IOPS | SA#105 (9/2024) | - | % | SA#106 (12/2024) | 

## Slide 5: Overview: Rel-19 Work-Items (2/3)
Work Item | WI Code | WID Approved | SA6#62 | SA6#63 | Target Completion | Remarks
Architecture for enabling Edge Applications Phase 3 | EDGEAPP_Ph3 | SA#101 (09/2023) | 85% | % | SA#106 (12/2024) | 
Application Architecture for UAS applications Phase 3 | UASAPP_Ph3 | SA#101 (09/2023) | 75% | % | SA#106 (12/2024) | 
Guidelines for CAPIF Usage | CAPIF_EXT | SA#101 (09/2023) | 90% | % | SA#105 (09/2024) | 
SEAL DD (Data Delivery) Phase 2 | SEALDD_Ph2 | SA#101 (09/2023) | 80% | % | SA#106 (12/2024) | 
Enhanced application layer support for location services | eLSAPP | SA#104 (06/2024) | 30% | % | SA#106 (12/2024) | 
Technical Enhancements and Improvements for Release 19 | TEI19 | NA | N/A | N/A |  | 

## Slide 6: Overview: Rel-19 Work-Items (3/3)
Study Item | WI Code | SID Approved | SA6#61 | SA6#62 | Target Completion | Remarks
Application enablement aspects for MMTel | MMTel_App | SA#104 (06/2024) | 10% | % | SA#106 (12/2024) | 
Application enablement for AI/ML services | AIML_App | SA#104 (06/2024) | 40% | % | SA#106 (12/2024) | 
Application enablement for mobile metaverse services | Metaverse_App | SA#104 (06/2024) | 25% | % | SA#106 (12/2024) | 
Application enablement for XRM Services Phase 2 | XRM_Ph2_App | SA#104 (06/2024) | 15% | % | SA#106 (12/2024) | 
Application enablement for satellite access Phase 3 | 5GSAT_Ph3_App | SA#104 (06/2024) | 5% | % | SA#106 (12/2024) | 
Common API Framework (CAPIF) Phase 3 | CAPIF_Ph3 | SA#105 (09/2024) | - | % | SA#106 (12/2024) | 

## Slide 7: Conference calls and other items
Rapporteurs to make the draft TRs/TSs available Thursday October 24th 23:00 UTC
All documents must be uploaded before End-of-meeting
Pre-SA6#64 conference calls (Dates are TBD) – Maximum 2 hours/call and 1 hour/topic
  Potential Topics
    ???
  Date Exclusions
    ?

## Slide 8: SA6 meeting schedule
Meeting | Date | Location
2024 |  | 
SA6#63 | 14 – 18 October 2024 | Hyderabad, India
SA6#64 | 18 – 22 November 2024 | Orlando, USA
2025 |  | 
SA6#65 | 17 – 21 Feb 2025 | Greece, Athens
SA6#66 | 7 – 11 April 2025 | Gothenburg, Sweden
SA6#67 | 19 – 23 May 2025 | Japan, Location TBC
SA6#68 | 25 – 29 August 2025 | Gothenburg, Sweden
SA6#69 | 13 – 17 October 2025 | China, Location TBC
SA6#70 | 17 – 21 November 2025 | USA, Location TBC
2026 calendar is in progress and planned completed at SA#104. SA6 is currently scheduled for 6 f2f-meetings

## Slide 9: Thank You!