3GPP TSG-RAN WG4 Meeting #113	R4-2418880
Orlando, US, 18th – 22nd November, 2024

Agenda item:	7.12.3.2

Source:	CAICT

Title:	Framework and time plan for Rel-19 MIMO OTA performance requirements development (Nov 2024)

Document for:	Approval

1	Introduction

This contribution provides a framework and time plan for Rel-19 MIMO OTA performance requirements development, based on the WID [1], the workplan [2], the recent agreements in WF [3], Rel-17 and Rel-18 MIMO OTA lab alignment outcomes [4, 5], and the Rel-18 approved framework [6].

This contribution can be revised according to discussion outcomes of this meeting.

2	Discussion

At the last meeting, the framework for Rel-19 MIMO OTA performance requirements in has been discussed which is basically stable in the WF [3]. There are still a few of issues need further discussions [3]:

Issue 2-1-1: Target bands for Rel-19 MIMO OTA requirements Agreements: - Take the bands listed in the WID (n3, n8, n77, n79) as baseline, check if there is a need to further prioritize the bands and/or introduce new bands. - Keep a reasonable workload with 4 bands in Rel-19 MIMO OTA performance requirements work. Issue 2-1-2: 4x4 requirement or 2x2 requirement for band n3 Agreements: - RAN4 should make the decision on defining which MIMO OTA requirement for band n3 at RAN4#113 (Nov. 2024). - Option 1: 4x4 MIMO OTA requirement - Option 2: 2x2 MIMO OTA requirement - Encourage OEMs to provide the information on the proportion of 4Rx UEs in band n3.

In the WID, bands n3, n5, n7, n8, n20, n38, n77, n79 are the target bands for 1Tx Handheld UEs TRP and TRS requirements. It is reasonable to consider the same target bands for specifying FR1 MIMO OTA requirements in Rel-19. The MIMO OTA requirement for band n5 has been specified in Rel-18, so bands n7, n20, n38 can be considered as new target bands for specifying MIMO OTA requirement in Rel-19. Besides, there is no need to perform extra channel model validations for these bands within the Rel-17/18 aligned labs, because n7/38 share the same validation frequency with n41, and n20 shares the same validation frequency with n5/8.

Observation 1: In the WID, bands n7, n20, n38 are listed as target bands for 1Tx Handheld UEs TRP and TRS requirements. For MIMO OTA, there is no need to perform extra channel model validations for these bands within the Rel-17/18 aligned labs.

Regarding band n79, as stated in GSA Snapshot: Spectrum Positions Used for Mobile Services (Jun. 2024) [7], the market is at an early stage. GSA 5G Market Snapshot (Sep. 2024) [8] shows spectrum band support in 5G networks (Fig. 1), it can be seen that 5G network deployment for band n79 is also at an early stage.

Fig. 1.  Spectrum band support in 5G networks. Quoted from GSA 5G Market Snapshot (Sep. 2024) [8].

Observation 2: 5G market and network deployment for band n79 are at an early stage. It is not a relatively urgent demand to specify MIMO OTA requirement for band n79 during Rel-19.

To facilitate the discussion on how to select the target bands for FR1 OTA requirements in Rel-19, we also collected the number of 5G device models that support theses bands from GSA database. Fig. 1 shows the number of models (including all form factors) that support different NR bands, quoted from the GSA 5G Device Ecosystem Report (Sep. 2024) [9].

Fig. 2.  Announced 5G spectrum support, number of models by band, for bands supported by 500 devices or more (data not available for all devices). Quoted from GSA 5G Device Ecosystem Report (Sep. 2024) [9].

For the Phone form factor, the number of models that support n79, n7, n38, and n20 are listed in Table 1, based on GSA database (last updated: 6th November 2024).

Table 1. Number of models with Phone form factor for different bands (Source: GSA GAMBoD database)

| Band | n79 | n7 | n38 | n20 |
| --- | --- | --- | --- | --- |
| Number of models (Phone form factor) | 431 | 634 | 709 | 549 |

Observation 3:  Based on GSA database, the number of 5G device models that support n79, n7, n38, and n20 are as below:

| Band | n79 | n7 | n38 | n20 |
| --- | --- | --- | --- | --- |
| Number of models including all form factors (Sep. 2024) | 1,039 | 1,257 | 1,206 | 1,094 |
| Number of models with Phone form factor (Nov. 2024) | 431 | 634 | 709 | 549 |

Consider the readiness of 5G network and the number of 5G smartphone models for different bands, we propose to deprioritize band n79 in Rel-19 MIMO OTA requirements work, and select a subset (1 or 2 bands) from n7, n38, and n20 as new target bands.

Proposal 1: Deprioritize band n79 in Rel-19 MIMO OTA requirements work. Select a subset (1 or 2 bands) from n7, n38, and n20 as new target bands for Rel-19 MIMO OTA performance requirements, based on Operators’ demands and the number of device models support each band (provided in Observation 3).

Regarding the MIMO OTA requirements for band n3, we received some feedback from OEMs that a certain proportion of UEs has supported 4Rx capability. Although it is not a mandatory requirement by 3GPP, an enhanced capability and a higher throughput are always what UEs and networks pursue. Based on this, we believe the 4-layer MIMO OTA requirement would be more beneficial and future-proof to the industry.

Observation 4: Currently, a certain proportion of UEs has supported 4Rx capability. Considering an enhanced capability and a higher throughput are what UEs and networks pursue, the 4-layer MIMO OTA requirement would be more beneficial and future-proof to the industry.

Besides, 2x2 MIMO OTA testing and 4x4 MIMO OTA testing require different channel models (CDL-C UMi vs. CDL-C UMa), that is, different channel model validations are required before performing 2x2 vs. 4x4 MIMO OTA testing for band n3. To save time and test efforts, it would be better to make a decision first, and then start the channel model validation and the follow-up measurement campaign for band n3.

Observation 5: Different channel model validations (CDL-C UMi vs. CDL-C UMa) are required before performing 2x2 vs. 4x4 MIMO OTA testing. It would be better to make a decision first, and then start the channel model validation and the follow-up measurement campaign for band n3.

Proposal 2: Specify 4x4 MIMO OTA requirement for band n3 in Rel-19.

Based on the above Proposals, we updated the framework in Section 3.

3	Framework for Rel-19 MIMO OTA performance requirements development (for approval)

3.1 Overall work flow

The overall work flow of Rel-19 MIMO OTA performance requirements development for bands <1GHz (n8/[n20]) and bands >1GHz (n3/n77/[n7]/[n38]) are illustrated in Figs. 1 (a) and (b), respectively. The requirements will be specified based on the Rel-17 static MPAC test method.

(a) for bands <1GHz (n8/[n20])                           (b) for bands >1GHz (n3/n77/[n7]/[n38])

Fig. 1.  Work flow of Rel-19 MIMO OTA performance requirements development

In general, Rel-19 MIMO OTA performance requirements will be derived based on a measurement data pool of commercial devices per band. To establish valid and trustable measurement data pools for defining FR1 MIMO OTA performance requirements, the following activities are required.

  - For bands <1GHz (n8/[n20])

    - Channel Model Validation: Companies shall complete channel model validation before submitting measurement results, validation results should be submitted to RAN4 for review. Working procedures of the channel model validation are provided in Section 3.2.1.

      - Note: Labs that submitted channel model validation results for band n8/[n20] in Rel-18 (as captured in TR 38.761) do not need to submit the results again.

    - Measurement Campaign: Collect measurement data from Rel-18 aligned labs (Apple, CAICT, CMCC&BUPT, MediaTek, OPPP, Xiaomi) for defining FR1 MIMO OTA requirements for bands < 1GHz. Working procedures of the measurement campaign are provided in Section 3.2.2.

  - For bands >1GHz (n3/n77/[n7]/[n38])

    - Channel Model Validation: Companies shall complete channel model validation before submitting measurement results, validation results should be submitted to RAN4 for review. Working procedures of the channel model validation are provided in Section 3.2.1.

      - Note: Rel-17 aligned labs do not need to submit channel model validation results for band n77/[n7]/[n38].

    - Measurement Campaign: Collect measurement data from Rel-17 aligned labs (Apple, CAICT, CMCC&BUPT, Huawei, MediaTek, Xiaomi) for defining FR1 MIMO OTA requirements for bands > 1GHz. Working procedures of the measurement campaign are provided in Section 3.2.2.

Detailed working procedures for Rel-19 MIMO OTA performance requirements development are described in Section 3.2.

3.2 Detailed working procedures

3.2.1 Channel Model Validation

- The purpose of Channel Model Validation is to ensure that the channel models are correctly implemented and hence capable of generating the propagation environment, as described by the model, within the test zone of the MPAC system.

- The channel model validation measurements shall be performed as described in Annex C.3 of TS 38.151, including:

  - Power Delay Profile (PDP)

  - Doppler/Temporal correlation

  - Spatial correlation

  - Cross-polarization

  - Power validation

- Test band: n3, n8; Test frequency: as specified in Tables C.3.1-1 and C.3.1-2 of TS 38.151

- Channel model: as specified in Annex C.1 of TS 38.151

  - For band n8: FR1 UMi CDL-C (2x2 MIMO)

  - For band n3: FR1 UMa CDL-C (4x4 MIMO)

- Pass/fail limits: as defined in Annex C.4 of TS 38.151

3.2.2 Measurement Campaign

- The purpose of Measurement Campaign is to collect measurement results of commercial devices from permitted labs for specifying FR1 MIMO OTA performance requirements.

- Test Methodology: the static FR1 MIMO OTA test method based on Multi-Probe Anechoic Chamber (MPAC) test system. Test plan: 3GPP TS 38.151.

- Test cases for Rel-19 FR1 MIMO OTA Measurement Campaign:

  - Test bands: n3, n8, n77, and a subset (1 or 2 bands) from n7/n20/n38

  - MIMO layer:

    - For band n8, [n20]: 2x2 MIMO (with FR1 UMi CDL-C channel model)

    - For bands n77, n3, [n7], [n38]: 4x4 MIMO (with FR1 UMa CDL-C channel model)

  - Use scenario: Free space

  - Operation mode: SA (first stage)

  - Power class: PC3 (first stage)

- Commercial device (Smartphone) selection criteria for FR1 MIMO OTA Measurement Campaign:

  - DUT capability: supporting all the bands listed in the WID is preferred, but devices supporting only a subset of the above bands can equally be used in the measurement campaign for such supported bands

  - DUT variety: the selection of commercial devices should cover various of devices in the market. The following selection criteria can also be considered:

    - Year of production: 2021-2025

    - Brand variety

    - Price range (to cover different price ranges, including High/Mid/Low-end products)

    - Popularity

    - Number of bands supported

  - For band n3, UEs equipped with 4 Rx antenna ports shall be selected for the Measurement Campaign. Labs can try to identify 4Rx or 2Rx UEs in any methods listed below:

    - Method 1: If a UE can be connected to BS simulator with 4x4 MIMO, the UE can be confirmed as a 4Rx UE

    - Method 2: Obtain the MIMO layer information from BS simulator, e.g., check the IE maxNumberMIMO-LayersPDSCH

    - Method 3: Directly collect the information from OEMs.

    - Other methods are not precluded

- Commercial devices provision:

  - Test labs can prepare and collect commercial devices by themselves based on the above selection criteria.

  - Any 3GPP member can work with the selected test labs to provide devices

    - A test lab shall measure only one UE model in case different samples are provided

    - Same UE model supporting different sets of bands can be measured. For this case, the UE model should be marked as different model, e.g., model A-1, model A-2. (guidance on how to manage this case are provided in the spreadsheet in R4-2321191)

    - For band n3, make sure the devices are 4Rx UEs

    - The 3GPP member providing the DUTs should contact one of the selected labs to check their availability to receive the DUTs and define together the related provisioning aspects. Any issue should be reported to the rapporteur in a timely manner to discuss for an alternative solution

- Measurement results submission:

  - RAN4 Secretary will cover the role of the trusted and neutral third party for the whole procedure

  - UE information disclosure: labs use the spreadsheet in R4-2321191 to submit the device information. The UE information should NOT BE CORRELATED with the order in the measurement data submitted by the same lab for the respective list of devices in c, i.e., the UE mode order in the list should be randomly disrupted.

  - Labs use the worksheet template in [TBD, use Rel-18 template R4-2403019 as starting point] to submit the measurement results for Rel-19 3GPP FR1 MIMO OTA performance data pool. Do NOT apply any systematic offset to the measurement results.

  - The measurement results should be submitted to RAN4 by anonymous approach (the UE model should not be disclosed):

    - The minimum number of submitted devices from each lab is 3, the maximum number is 15. Meanwhile, labs are encouraged to provide as much data as possible within 15

    - Volunteer labs provide the device information sheet ONLY to the RAN4 Secretary and the sheet used to submit measurement results to 3GPP RAN4

  - RAN4 Secretary ONLY publishes to 3GPP RAN4 the following summary of statistical information after anonymizing the sensitive UE information data, i.e., UE model name and vendor name:

    - Total number of devices

    - Total number of models

    - Total number of devices vendors

    - Percentage of devices per vendor

    - Percentage of devices per Power Class

    - Percentage of devices per each supported band

    - Percentage of devices per year of production

    - Percentage of the devices that are certified by at least one of certification bodies as following: PTCRB, GCF, NAL/CTA (Chinese Network Access Licensed Test), FCC, CE

      - Once the device gets the above certification, for RAN4 discussion that means the device is not a prototype

- Percentage of the devices that are certified for each certification body (for information only)

3.2.3 Specifying Performance Requirements

- Only measurement data from the aligned labs with channel model validation completed will be considered for specifying requirements, as described in Section 3.1.

- Thresholds for specifying FR1 MIMO OTA performance requirement:

  - Minimum amount of data per band: 15

  - Minimum amount of UE models per band: 12

- Method of requirements derivation: per-band Data driven approach

- The value at [85%] percentile of the CDF curve can be selected as the starting point for requirement discussion

- Performance part of the work will proceed in a contribution-driven manner.

3.3 Time plan

1. Finalize the working procedures and time plan for Rel-19 MIMO OTA requirements development at RAN4 #113 (Nov 2024).

2. Measurement Campaign for bands n77/n8/[n7]/[n20]/[n38] can start at an early stage with the Rel-17/Rel-18 aligned labs that completed channel model validations for these bands.

3. Labs should submit channel model validation results for bands n3/n8 by formal T-docs no later than RAN4 #114-bis (Apr 2025) to participate in the Measurement Campaign at the corresponding bands. Earlier submission is encouraged.

4. To properly plan the Measurement Campaign, the following actions are requested no later than RAN4#115 (May 2025):

  - The rapporteur checks with the volunteer labs the amount of DUTs (minimum 3, maximum 15) they expect to be able to measure AND how many DUTs they can accommodate from 3GPP members

  - The 3GPP members providing devices for the measurement campaign (if any) check how many samples they intend to provide (in terms of maximum number)

  - Planning of the measurement campaign could be reviewed based on the above points

5. The 3GPP members (if any) should provide the devices to volunteer labs no later than RAN4#116 (Aug 2025).

6. Labs should submit measurement results of commercial devices by formal T-docs no later than RAN4#117 (Nov 2025), also submit the devices information to RAN4 Secretary.

7. Conclude FR1 MIMO OTA performance requirements no later than RAN4#118 (Feb 2026).

Proposal 3: Approve the updated framework in Section 3 of this contribution for Rel-19 MIMO OTA performance requirements development. Further refinement is not precluded.

4	Conclusion

Observation 1: In the WID, bands n7, n20, n38 are listed as target bands for 1Tx Handheld UEs TRP and TRS requirements. For MIMO OTA, there is no need to perform extra channel model validations for these bands within the Rel-17/18 aligned labs.

Observation 2: 5G market and network deployment for band n79 are at an early stage. It is not a relatively urgent demand to specify MIMO OTA requirement for band n79 during Rel-19.

Observation 3:  Based on GSA database, the number of 5G device models that support n79, n7, n38, and n20 are as below:

| Band | n79 | n7 | n38 | n20 |
| --- | --- | --- | --- | --- |
| Number of models including all form factors (Sep. 2024) | 1,039 | 1,257 | 1,206 | 1,094 |
| Number of models with Phone form factor (Nov. 2024) | 431 | 634 | 709 | 549 |

Proposal 1: Deprioritize band n79 in Rel-19 MIMO OTA requirements work. Select a subset (1 or 2 bands) from n7, n38, and n20 as new target bands for Rel-19 MIMO OTA performance requirements, based on Operators’ demands and the number of device models support each band (provided in Observation 3).

Observation 4: Currently, a certain proportion of UEs has supported 4Rx capability. Considering an enhanced capability and a higher throughput are what UEs and networks pursue, the 4-layer MIMO OTA requirement would be more beneficial and future-proof to the industry.

Observation 5: Different channel model validations (CDL-C UMi vs. CDL-C UMa) are required before performing 2x2 vs. 4x4 MIMO OTA testing. It would be better to make a decision first, and then start the channel model validation and the follow-up measurement campaign for band n3.

Proposal 2: Specify 4x4 MIMO OTA requirement for band n3 in Rel-19.

Proposal 3: Approve the updated framework in Section 3 of this contribution for Rel-19 MIMO OTA performance requirements development. Further refinement is not precluded.

References

- RP-241623, Revised WID: WI on FR1 TRP (Total Radiated Power), TRS (Total Radiated Sensitivity) and MIMO OTA (Over the Air) testing enhancement Phase 3, vivo, CAICT, 3GPP RAN#104, Jun. 2024.

- R4-2412056, Updated Workplan of Rel-19 FR1 OTA WI, vivo, CAICT, 3GPP RAN#112, Aug. 2024.

- R4-2416579, WF for [112bis][324] MIMO_OTA_Ph3, CAICT, 3GPP RAN#112bis, Oct. 2024.

- R4-2214360, WF on NR MIMO OTA (Rel-17), CAICT, vivo, 3GPP RAN4#104-e, Aug. 2022.

- R4-2406083, Way Forward for [110bis][337] NR_MIMO_OTA_enh, CAICT, 3GPP RAN4#110-bis, Apr. 2024.

- R4-2405468, Updated Framework and time plan for FR1 MIMO OTA performance requirements development (Apr 2024), CAICT, 3GPP RAN4#110-bis, Apr. 2024.

- GSA Snapshot: Spectrum Positions Used for Mobile Services (Jun. 2024)

- GSA 5G Market Snapshot (Sep. 2024)

- GSA 5G Device Ecosystem Report (Sep. 2024)