3GPP TSG RAN WG4 Meeting #113	 								                 R4-2419663

Orlando , USA, November 18th – 22nd, 2024

Title:	Work plan for WID: introduction of IoT-NTN TDD mode

Source:	Iridium

For:	Information

Agenda Item:	7.28

Release:	Release-19

WI:	Introduction of IoT-NTN TDD mode

# Introduction

In this contribution, a work plan for New WID on introduction of IoT-NTN TDD mode [1] is proposed for RAN 1, 2, and 4.

# WID Objective

The work item aims to specify enhancements for NB-IoT NTN to enable NTN operation with a NB-IoT TDD mode leveraging commonalities with half-duplex NB-IoT FDD NTN, by defining a new NB-IoT TDD mode for NTN based on minimum necessary changes to the NB-IoT NTN FDD frame structure and procedures for the NB-IoT operation in the targeted unpaired MSS allocated band (TN deployment is not expected in this band). The feature is not intended to be applicable to existing 3GPP bands.

The study and work objectives assume the following:

- LEO @600 km and @1200 km orbit respectively, with set-1 satellite parameters as reference scenarios (See 3GPP TR 36.763)

- Target the 1616-1626.5 MHz MSS allocated band

- Standalone deployment with anchor and non-anchor carriers (i.e. operating in carrier(s) used only for NB-IoT)

- Operate with Earth fixed Tracking area, with either Earth fixed cells or Earth moving cells for NGSO

- The new NB-IoT NTN TDD mode allows configuring the usage of radio resources in the targeted MSS allocated band with a periodic subset of the UL and DL subframes in N radio frames. The periodic pattern should consist of non-overlapping set of usable contiguous UL subframes and set of usable contiguous DL subframes, and guard periods, which is periodic every N radio frames, with N=9 as baseline. No blind detection is assumed at the UE side. The value of N and the configuration of the periodic pattern are fixed per band.

This work item includes the following objectives:

- Study the impact due to the periodic pattern, at least on UE downlink synchronization and other aspects (if identified) [RAN1, RAN4]

  - Checkpoint in RAN#106 for the completion of the study phase. RAN1 start from Oct’24. RAN4 start from Nov’24

- Specify a new NB-IoT TDD NTN mode based on minimum necessary changes to the NB-IoT NTN FDD frame structure and procedures, based on the outcome of the study, including:

  - Definition, configuration (if needed) and signaling (if needed) of the periodic pattern including confirming the value of N, and associated UE procedures [RAN1, RAN2]

  - Other necessary impacts on higher layers [RAN2]

  - RRM and RF core requirements [RAN4]

- Specify a new NB-IoT TDD operating NTN band for the MSS allocation spanning 1616-1626.5 MHz for DL and UL, based on the outcome of the study, to be used as example band for this WI [RAN4].

  - Specify band numbering

  - Specify SAN and UE RF characteristics

  - Specify DL and UL channelization.

  - Specify channel bandwidth as 200 kHz

  - Note1: No NTN-NTN coexistence study needed.

  - Note2: Leverage existing work as much as possible for TN-NTN coexistence of adjacent bands

Note3: Reuse the existing RAN4 requirements as much as possible (no intention to have any relaxation of the RF emissions requirements)

# Work Plan

The Work Plan for RAN1, 2, and 4 is provided in Table 1:

Table 1: RAN1, 2, and 4 Work Plan

| Quarter | Meeting # | TU | Work plan |
| --- | --- | --- | --- |
| RAN#105 (Sep. 2024) | RAN1#118bis | 0.5 | - Agree on assumptions and parameters to be used in the evaluation of TDD periodic pattern, by considering N=9 as a baseline - Define the evaluation methodology and relevant metrics for evaluations - Evaluate the impact due to the periodic pattern, particularly on UE downlink synchronization - Commence the work from Oct’24 and aim to complete the study phase by RAN#106 checkpoint |
|  | RAN2#127bis |  |  |
|  | RAN4#112bis |  |  |
|  | RAN1#119 | 0.5 | - Continue to evaluate the impact due to the periodic pattern, particularly on UE downlink synchronization - Confirm the value of N and TDD pattern parameters - Conclude the evaluation and assessments |
|  | RAN2#128 | 0 | - Work Plan submission for Information. |
|  | RAN4#113 | 0 | - Begin discussions starting from Nov’24 and target completion by the RAN#106 checkpoint. Start specifying a new NB-IoT TDD operating NTN band for the MSS allocation spanning 1616-1626.5 MHz for DL and UL. This includes detailing: - Band numbering & band definition (including EARFCN, raster etc.), DL and UL channelization, and specifying a channel bandwidth of 200 kHz (180 kHz occupied bandwidth) - Start discussion on SAN & UE RF requirements that can be re-used from previously defined S/L band. Address RRM and RF core requirements associated with the new NB-IoT TDD NTN mode Discuss requirements stemming from introduction of TDD mode for NB-IoT NTN and potential impact of the periodic pattern to RRM: offset-subframes, DL-UL gap |
| RAN#106 (Dec. 2024) | RAN1#120 | 0.5 | - Based on the study outcome, discuss potential solutions - Identify potential specification impacts - Define the TDD pattern parameters |
|  | RAN2#129 | 0.5 | - Start discussion on TDD support for NB IoT NTN - Identify potential impacts on higher layers - Start the definition and configuration of signalling of the periodic pattern, and associated UE procedures. |
|  | RAN4#114 | 0.5+0.25 | - Decide on RF, discuss on RRM requirements that can be re-used from previously defined S/L band. Start preparing Draft CRs for the requirements that can be reused - Conclude on requirements stemming from introduction of TDD mode for NB-IoT NTN and potential impact of the periodic pattern: offset-subframes, DL-UL gap - Start discussion on demodulation performance and specific configuration related to the new TDD pattern |
| RAN#107 (Mar. 2025) | RAN1#120bis | 0.5 | - Discuss remaining aspects on the TDD support in NB IoT NTN - Discuss (if needed) related RRC parameters and send LS to RAN2 - Discuss Draft CRs |
|  | RAN2#129bis | 0.5 | - Further discuss and down-select solutions to support TDD for NB IoT NTN - Conclude on potential impacts on higher layers - Complete the definition and configuration of signaling of the periodic pattern, and associated UE procedures |
|  | RAN4#114bis | 0.5+0.25 | - Finish draft CRs for RF part - Continue discussion on demodulation performance requirements, draft CRs for SAN conformance testing (as required). - Draft CR for RRM part |
|  | RAN1#121 | 0.5 | - Conclude on the solutions for the TDD support in NB IoT NTN - Further discuss (if needed) related RRC parameters and send LS to RAN2 - Finalize RAN1 CRs |
|  | RAN2#130 | 0.5 | - Conclude support of TDD mode in NB IoT NTN - Discuss stage-2 design of TDD support in NB IoT NTN - Discuss RAN2 CRs |
|  | RAN4#115 | 0.5+0.25 | - Finish CR for RRM part - Start drafting demodulation performance CRs |
| RAN#108 (Jun. 2025) | RAN1#122 |  |  |
|  | RAN2#131 | 0.5 | - Finalize stage-2 design on support of TDD in NB IoT NTN - Finalize RAN2 CRs - Conclude on the remaining aspects, if any |
|  | RAN4#116 | 0.5+0.25 | - Conclude on demodulation performance CR |
| RAN#109 (Sep. 2025) | RAN1#123 |  |  |
|  | RAN2#132 |  |  |
|  | RAN4#117 | 0.25 | - Finish demodulation performance CR |
| RAN#110 (Dec. 2025) | RAN1#123bis |  |  |
|  | RAN2#132bis |  |  |
|  | RAN4#117bis | 0.25 |  |
|  | RAN1#124 |  |  |
|  | RAN2#133 |  |  |
|  | RAN4#118 | 0.25 |  |

# References

- RP-242415 	New WID on introduction of IoT-NTN TDD mode, 3GPP TSG RAN Meeting #105,  Melbourne, Australia, September 9-12, 2024