## Cover sheet
3GPP TSG RAN WG5#105 | [8 empty] | R5-246459
<Orlando, United States, 18th Nov 2024 - 22nd Nov 2024>
Agenda Item: | 7.4.2
Source: | China Unicom
Title: | WP on UE Conformance - High power UE (power class 2) for NR FR1 FDD single band
Work item code: | HPUE_NR_FR1_FDD_R18 -UEConTest
Release: | Rel-18
Document for: | Information
RAN5 WP template v2.0
1. Introduction
Increasing the transmit power of UE has significant benefits on extending uplink coverage area and improving the experience of cell edge users. In Rel-17，several study/work items related to HPUE for FDD band have been standardized in RAN4. However，operators have increasing deployment demand on HPUE requirement for increasing NR bands which are still missing in R17 HPUE WIs in RAN4. At RP#98 meeting, RAN4 introduced an R18 basket WI for HPUE PC2 on NR FR1 FDD single bands as a continuation of R17 work, and this WI is estimated to be complete in Dec, 2023. At least 1 PC2 FDD band such as n8 will be completed at the RP#100 meeting in June 2023. To fulfil the urgent demand of the market, it is proposed to introduce an associated RAN5 work item to enable UE conformance test for NR PC2 UE on FDD bands in Rel-18.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed configurations (Note 1) | Number of new configurations | Comments
Overall completion |  | 31% (+16%) | 2 (+1) | 10
Completion Compensation |  | -
| Note 1: | Only test cases / configurations completed for all applicable WP areas and sub-areas are counted. For completed test cases / configurations per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed configurations | Number of new configurations | Comments
SA Option 2 (SA NR) (FR1) |  | 30.6% (+16.2%) | 2 (+1) | 10
FR1 |  | 30.6% (+16.2%) | 2 (+1) | 10
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS:Area Scope | TS/Area | Completion | Number of new completed PC2 configurations | Number of new PC2 configurations | FR1
[5 empty] | Completion | Number of new completed test cases / configurations | Number of new test cases / configurations
NR HPUE (PC2) configurations
HPUE (PC2) NR FR1 FDD single band
HPUE (PC2) NR FR1 FDD single band | PC2 NR FR1 FDD single band | 27% (+17%) | 2 (+1) | 10 | 27% (+17%) | 2 (+1) | 10
5 References
[1]RP-232774 | Revised WID on UE Conformance - High power UE (power class 2) for NR FR1 FDD single band
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP on UE Conformance - High power UE (power class 2) for NR FR1 FDD single band | [12 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | Relative weight of effort vs TS contribution | [8 empty] | End of workplan columns. Note! Do not remove this column.
WI code |  | HPUE_NR_FR1_FDD_R18 -UEConTest | [14 empty] | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 5 | 5
WP Scope: |  | The purpose of present document is to provide a workplan for the RAN5 work item UE Conformance - High power UE (power class 2) for NR FR1 FDD single band comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID). | [14 empty] | 38.508-1: Test frequencies | 38.508-2: UE capabilities | 38.521-1: Common Clause | 38.521-1: Tx test cases | 38.521-1: Rx test cases | 38.522: Test case applicability | 38.533: RRM test cases / 38:.522 Test case applicability | 38.903: MU and TT | 38.905: Test point analysis
WP Resp: |  | Yu Shi, China Unicom |  |  | shiyu19@chinaunicom.cn | [7 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | N/A |  |  | N/A
WP Item ID | Is new configuration or test case? | TS/Area | Configuration / Test case clause | UL configuration(s) / Test case title | Type of change | Interested Operator | Company | Status | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1
30.6% (+16.2%)
14
10
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row. | [15 empty] | CALCULATED CELLS | TS STATUS INPUT
HPUE (PC2) NR FR1 FDD single band
1 | Y | PC2 NR FR1 FDD single band | n2 |  | New PC2 Config | Verizon | Verizon | Ongoing | RAN5#106 (Feb-25) | 38.521-1: R5-247734 |  | 1 | 16.7% (+16.7%) | 16.7% (+16.7%) |  | 16.67% | 0% | 0% | 100% | 50% | 0% | 0% |  |  | 0%
2 |  | PC2 NR FR1 FDD single band | n5 |  | New PC2 Config | China Unicom | China Unicom |  | TBD |  | Stoped for PC2 in release 18. Continue in release 19. | 0
3 | Y | PC2 NR FR1 FDD single band | n7 |  | New PC2 Config | TIM | ZTE | Completed | RAN5#105 (Nov-24) | 38.521-1: R5-247398 R5-247400 R5-247399 38.508-2: 247397 38.905: 247401 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 100%
4 | Y | PC2 NR FR1 FDD single band | n8 |  | New PC2 Config | China Unicom | China Unicom | Completed | RAN5#103 (May-24) | 38.521-1: R5-240279 R5-240281 R5-243205 (AMPR) R5-243631( AMPR) 38.508-2: R5-241259 38.905: R5-243613 |  | 1 | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 100%
5 | Y | PC2 NR FR1 FDD single band | n13 |  | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
6 | Y | PC2 NR FR1 FDD single band | n14 |  | New PC2 Config | AT&T | China Unicom | Ongoing | RAN5#106 (Feb-25) | 38.521-1: R5-247245 38.508-2: R5-247246 |  | 1 | 36.7% (+36.7%) | 36.7% (+36.7%) |  | 36.67% | 100% | 100% | 100% | 50% | 0% | 100% |  |  | 0%
7 | Y | PC2 NR FR1 FDD single band | n25 |  | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
8 |  | PC2 NR FR1 FDD single band | n26 |  | New PC2 Config |  |  |  | TBD |  | Stoped for PC2 in release 18. Continue in release 19. | 0
9 |  | PC2 NR FR1 FDD single band | n28 |  | New PC2 Config | CMCC |  |  | TBD |  | Stoped for PC2 in release 18. Continue in release 19. | 0
10 | Y | PC2 NR FR1 FDD single band | n66 |  | New PC2 Config | Verizon | Verizon | Ongoing | RAN5#106 (Feb-25) | 38.521-1: R5-247734 |  | 1 | 16.7% (+16.7%) | 16.7% (+16.7%) |  | 16.67% | 0% | 0% | 100% | 50% | 0% | 0% |  |  | 0%
11 | Y | PC2 NR FR1 FDD single band | n70 |  | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
12 | Y | PC2 NR FR1 FDD single band | n71 |  | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
13 | Y | PC2 NR FR1 FDD single band | n85 |  | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
Note on S1: The TS's weight number is used to set the reletive weights between TS contributions used in the overall calculation of completeness of teh WP item. Setting it to 0 for a WP item means that it will not be included at all in the calculation.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new configuration or a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on M6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.
Note on Q12: Rapporteur guideline to assign applicable sub-areas for a WP item (columns S to X) To Set applicable sub-area(s) for a WP item do: - Copy the formula/cell content from one of the other non-empty cells under the "WP item status vs Area" section (columns S to X). To Clear applicable sub-area(s) for a WP item do: - Select the cell for teh WP item for the sub-area and press <Delete>-botton (clear content of the cell).