## Cover sheet
3GPP TSG-RAN5 Meeting #105 | [10 empty] | R5-246938
Orlando, United States, Nov 18-22, 2024
Agenda Item: | 7.5.2
Source: | Huawei, Hisilicon
Title: | WP UE Conformance - Network energy savings for NR
Work item code: | Netw_Energy_NR-UEConTest
Release: | Rel-18
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The objective of UE Conformance - Network energy savings for NR is to define the UE conformance requirements corresponding to WID on Network energy savings for NR, analyse the test case impact, applicability, test environment, and update the relevant conformance specifications for Rel-18. At the RAN#103 meeting in March 2024 the Rel-18 RAN5 work item for UE Conformance - Network energy savings for NR was approved [1]. The purpose of present document is to provide a workplan for the RAN5 work item on the conformance test cases for the core requirement introduced by the core work item. The workplan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 54% (+30%) | 8 (+4) | 17
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 61.3% (+33.6%) | 8 (+4) | 15
FR1 |  | 76.9% (+40.1%) | 8 (+4) | 13
FR2 |  | 20% (+15%) | 0 | 1
FR1 + FR2 |  | 20% (+15%) | 0 | 1
NSA Option 3 (EN-DC) |  | 16.6% (+11.6%) | 0 | 2
FR1 |  | 16.6% (+11.6%) | 0 | 2
FR2
FR1 + FR2
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [8 empty] | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 | [5 empty] | FR1 |  |  | FR2 |  |  | FR1 + FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1
Common ICS | 38.508-2 | 80% (+30%) |  |  | 80% (+30%)
NR RF/RRM
RRM test cases | 38.533 | 57.1% (+46.6%) | 3 (+3) | 9 | 77.3% (+59.7%) | 3 (+3) | 5 | 24.4% (+24.4%) | 0 | 1 | 24.4% (+24.4%) | 0 | 1 | 19.2% (+19.2%) | 0 | 2
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 24.1% (+24.1%) |  |  | 30% (+30%) |  |  | 20% (+20%) |  |  | 20% (+20%) |  |  | 0%
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 18.9% (+18.9%) |  |  | 30% (+30%) |  |  | 0% |  |  | 0% |  |  | 0%
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 82.5% (+32.5%) | 5 (+1) | 8 | 82.5% (+32.5%) | 5 (+1) | 8
Applicability Protocol test cases | 38.523-2 | 90% (+20%) |  |  | 90% (+20%)
Test suites (TTCN) | 38.523-3
5 References
[1] RP-240291 | New WID on UE Conformance - Network energy savings for NR
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP UE Conformance - Network energy savings for NR | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | [5 empty] | End of workplan columns. Note! Do not remove this column.
WI code |  | Netw_Energy_NR-UEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item UE Conformance Test Aspects for Network energy savings for NR comprising the necessary new clauses/test cases and updates to existing clauses/test cases. | [13 empty] | vs Area
WP Resp: |  | Yaping Zhang |  |  | zhangyaping13@huawei.com | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) |  |  | NSA Option 3 (EN-DC)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) |  | FR1 | FR2 | FR1 + FR2 | FR1 | FR2 | FR1 + FR2
[15 empty] | 76.9% (+40.1%) | 20% (+15%) | 20% (+15%) | 16.6% (+11.6%)
[15 empty] | 24 (+3) | 5 | 5 | 6 | 0 | 0
[15 empty] | 16.5 (+0.9) | 3.1 | 3.1 | 4.1 | 0 | 0
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
1 |  | 38.508-1 | 4.6.3 | Radio resource control information elements | Adding the default message configuration for features about network energy savings | Huawei, TF160 | RAN5#107 (May-25) | R5-245630 R5-246400 |  | TBD | 70% (+20%) | 70% (+20%) |  |  | 70%
TS 38.508-2: Common ICS
2 |  | 38.508-2 | A.4.3.2 | Physical Layer Baseline Implementation Capabilities | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. | Huawei, Nokia | RAN5#107 (May-25) | R5-245975 R5-247236 R5-246924 |  | 0.3 | 80% (+30%) | 80% (+30%) |  |  | 80%
NR RF/RRM
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
3 |  | 38.522 | 4.2 | RRM conformance test cases | Add test case applicability statements for the new test cases introduced in 38.533. | Huawei, Ericsson | TBD | R5-247479 R5-246930 |  | 0.5 | 17.5% (+17.5%) | 23.3% (+23.3%) | 0% |  | 30% | 20% | 20% | 0%
TS 38.533: RRM test cases
|  | 38.533 | 4.5.3 | SCell activation and deactivation delay | Sub-clause header |  |  |  |  | 0
4 | Y | 38.533 | 4.5.3.11 | EN-DC FR1 TRS-based SCell Activation of SSB-less SCell in FR1 collocated inter-band in non-DRX | SSB-less SCell activation | Huawei | TBD |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
5 | Y | 38.533 | 4.5.3.12 | EN-DC FR1 Inter-band SSB-less Scell activation using A-TRS in non-DRX | SSB-less SCell activation | Nokia | TBD | R5-247984 |  | 1 | 50% (+50%) |  | 50% (+50%) |  |  |  |  | 50%
|  | 38.533 | 6.3.3 | Conditional handover | Sub-clause header |  |  |  |  | 0
6 |  | 38.533 | 6.3.3.0.1 | Minimum conformance requirements for NR FR1 intra-frequency conditional handover | Adding minimum requirements for NES-based CHO | Huawei | RAN5#105 (Nov-24) | R5-246925 |  | 0.2 | 100% (+100%) | 100% (+100%) |  |  | 100%
7 |  | 38.533 | 6.3.3.0.2 | Minimum conformance requirements for NR FR1 inter-frequency conditional handover | Adding minimum requirements for NES-based CHO | Huawei | RAN5#105 (Nov-24) | R5-246925 |  | 0.2 | 100% (+100%) | 100% (+100%) |  |  | 100%
8 | Y | 38.533 | 6.3.3.6 | NR SA FR1 Intra-frequency NES triggering conditional handover | NES-based CHO | Huawei | RAN5#105 (Nov-24) | R5-247836 |  | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
9 | Y | 38.533 | 6.3.3.7 | NR SA FR1-FR1 Inter-frequency NES-based Inter-frequency conditional handover | NES-based CHO | Huawei | RAN5#105 (Nov-24) | R5-247920 |  | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
|  | 38.533 | 6.5.3 | SCell activation and deactivation delay | Sub-clause header |  |  |  |  | 0
10 | Y | 38.533 | 6.5.3.15 | NR SA FR1 TRS based SCell Activation of SSB-less SCell in inter-band CA in non-DRX | SSB-less SCell activation | Nokia | RAN5#108 (Aug-25) | R5-244565 R5-246990 |  | 1 | 60% (+10%) | 60% (+10%) |  |  | 60%
11 | Y | 38.533 | 6.5.3.16 | NR SA FR1 Inter-band SSB-less SCell Activation based on A-TRS in non-DRX | SSB-less SCell activation | Nokia | RAN5#108 (Aug-25) | R5-245880 R5-247807 |  | 1 | 60% (+10%) | 60% (+10%) |  |  | 60%
|  | 38.533 | 6.6.1 | Intra-frequency measurements | Sub-clause header |  |  |  |  | 0
|  | 38.533 | 6.6.1.2 | NR SA FR1 event-triggered reporting without gap in DRX | Update the test applicability to allow skipping legacy CHO test when NES-based CHO is executed. | Huawei | RAN5#105 (Nov-24) | R5-246929 |  | 0.5 | 100% (+100%) | 100% (+100%) |  |  | 100%
12 | Y | 38.533 | 6.6.1.13 | NR SA FR1 event triggered reporting tests without gap in DRX under Cell DTX | Cell DTX | Huawei | RAN5#105 (Nov-24) | R5-247921 |  | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
|  | 38.533 | 7.3.3 | Conditional handover | Sub-clause header |  |  |  |  | 0
13 | Y | 38.533 | 7.3.3.3 | NR SA FR2 intra-frequency NES triggering conditional handover | NES-based CHO | Ericsson | RAN5#106 (Feb-25) | R5-247808 |  | 1 | 30% (+30%) | 30% (+30%) |  |  |  | 30%
14 | Y | 38.533 | 7.3.3.4 | NR SA FR2-FR1 inter-frequency NES triggering conditional handover | NES-based CHO | Ericsson | RAN5#106 (Feb-25) | R5-247472 |  | 1 | 30% (+30%) | 30% (+30%) |  |  |  |  | 30%
15 |  | 38.533 | Annex A | RRM test configurations | RRM test configurations Adding reference Cell DTX configurations |  | TBD |  |  | 0.1 | 0% | 0% |  |  | 0%
16 |  | 38.533 | Annex E | Cell configuration mapping | Define cell configuration mapping | Huawei, Ericsson | TBD | R5-247473 |  | 0.3 | 15% (+15%) | 20% (+20%) | 0% |  | 0% | 30% | 30% | 0%
17 |  | 38.533 | Annex F | Measurement uncertainties and test tolerances | Define measurement uncertainties and test tolerances |  | TBD |  |  | 0.3 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
18 |  | 38.903 | 8 | Grouping of test cases defined in TS 38.533 | TT analysis for RRM Test cases | Huawei, Ericsson, Nokia | RAN5#105 (Nov-24) | R5-246931 R5-246932 R5-246933 |  | 1 | 7.5% (+7.5%) | 10% (+10%) | 0% |  | 30% | 0% | 0% | 0%
Idle Mode
19 |  | 38.523-1 | 6.1.2 | NG-RAN Only Cell Selection |  |  | RAN5#108 (Aug-25) |  |  | 0
20 | Y | 38.523-1 | 6.1.2.28 | Cell selection / NES mode | Verify that legacy UEs can't camp on the cells that adopt NES techniques. TP 1: Verify that NES UE can follow the legacy barring when barring bit in SIB is absent. TP 2: Verify that NES UE can follow the NES barring bit in SIB. | Huawei | RAN5#108 (Aug-25) | R5-247624 |  | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
Layer 2
|  | 38.523-1 | 7.1.1.14 | Network Energy Saving | New sub-clause header |  | RAN5#108 (Aug-25) |  |  | 0
|  | 38.523-1 | 7.1.1.14.1 | Cell DTX/DRX adaptations | New sub-clause header |  | RAN5#108 (Aug-25) |  |  | 0
21 | Y | 38.523-1 | 7.1.1.14.1.1 | Cell DTX operation / Correct handling of DL assignment / (De)activation by RRC configuration | TP 1: Verify that UEs do not monitor PDCCH when cell DTX operation is activated by RRC configuration and the Serving Cell is not in the cell DTX Active Period TP 2: Verify that UEs monitor PDCCH when cell DTX operation is deactivated by RRC configuration and the Serving Cell is not in the cell DTX Active Period | Huawei | RAN5#108 (Aug-25) | R5-245631 R5-247622 |  | 1 | 100% | 100% |  |  | 100%
22 | Y | 38.523-1 | 7.1.1.14.1.2 | Cell DTX operation / Correct handling of DL assignment / (De)activation by DCI format 2_9 | TP 1: Verify that UEs do not monitor PDCCH when cell DTX operation is activated by DCI 2_9 indication and the Serving Cell is not in the cell DTX Active Period TP 2: Verify that UEs monitor PDCCH when cell DTX operation is deactivated by DCI 2_9 indication and the Serving Cell is not in the cell DTX Active Period | Huawei | RAN5#108 (Aug-25) | R5-245632 R5-247622 |  | 1 | 100% | 100% |  |  | 100%
23 | Y | 38.523-1 | 7.1.1.14.1.3 | Cell DRX operation / Correct handling of UL grant / (De)activation by RRC configuration | TP 1: Verify that UEs do not monitor PDCCH when cell DRX operation is activated by RRC configuration and the Serving Cell is not in the cell DRX Active Period TP 2: Verify that UEs monitor PDCCH when cell DRX operation is deactivated by RRC configuration and the Serving Cell is not in the cell DRX Active Period | Huawei | RAN5#108 (Aug-25) | R5-245633 R5-247623 |  | 1 | 100% | 100% |  |  | 100%
24 | Y | 38.523-1 | 7.1.1.14.1.4 | Cell DRX operation / Correct handling of UL grant / (De)activation by DCI format 2_9 | TP 1: Verify that UEs do not monitor PDCCH when cell DRX operation is activated by DCI 2_9 indication and the Serving Cell is not in the cell DRX Active Period TP 2: Verify that UEs monitor PDCCH when cell DRX operation is deactivated by DCI 2_9 indication and the Serving Cell is not in the cell DRX Active Period | Huawei | RAN5#108 (Aug-25) | R5-245634 R5-247623 |  | 1 | 100% | 100% |  |  | 100%
25 |  | 38.523-1 | 7.1.1.14.2 | NES spatial and power domain adaptations | New sub-clause header |  | RAN5#108 (Aug-25) |  |  | 0
26 | Y | 38.523-1 | 7.1.1.14.2.1 | NES spatial domain Type 1 adaptation / Periodic CSI reporting | Verify that UEs should perform periodic CSI reporting for each CSI report subconfiguration defined for NES spatial domain Type 1 adaptation | Nokia | RAN5#108 (Aug-25) | R5-247626 |  | 1 | 80% (+80%) | 80% (+80%) |  |  | 80%
27 | Y | 38.523-1 | 7.1.1.14.2.2 | NES spatial domain Type 2 adaptation / Aperiodic CSI reporting | Verify that UEs should perform aperiodic CSI reporting for each CSI report subconfiguration defined for NES spatial domain Type 2 adaptation | Huawei | RAN5#108 (Aug-25) |  |  | 1 | 0% | 0% |  |  | 0%
28 | Y | 38.523-1 | 7.1.1.14.2.3 | NES power domain adaptation / Semi-periodic CSI reporting on PUCCH | Verify that UEs should perform semi-periodic CSI reporting on PUCCH for each CSI report subconfiguration defined for NES power domain adaptation | Nokia | RAN5#108 (Aug-25) | R5-247627 |  | 1 | 80% (+80%) | 80% (+80%) |  |  | 80%
TS 38.523-2: Applicability for Protocol test cases
29 |  | 38.523-2 | 4 | Recommended Test Case Applicability | Add test case applicability statements for the new test cases introduced in 38.523-1 | Huawei, Nokia | RAN5#108 (Aug-25) | R5-245635 R5-247625 R5-247628 |  | 0.1 | 90% (+20%) | 90% (+20%) |  |  | 90%
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
|  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.