## Cover sheet
3GPP TSG-RAN5 Meeting #105 | [7 empty] | R5-247089
Orlando, United States, 18th - 22nd November 2024
Agenda Item: | 7.5.2
Source: | Ericsson, FirstNet, Element, Samsung
Title: | WP Protocol enhancements for Mission Critical Services (MCPTT, MCVideo, MCData) for Rel-17
Work item code: | MCProtoc17_enh3MCPTT_eMCData3_MCOver5GS-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
The objective of this work item is to provide UE conformance test specifications for the Rel-17 core requirements for MCPTT, MCVideo and MCData. The RAT for this Work Item is both LTE and 5G NR. A new series of specifications (3GPP TS 37.579-x), under 3GPP TS 37-series (Multiple radio access technology aspects series), containing Mission Critical Services UE test cases for both LTE and 5G NR RATs in the same specification will be created. (UID: 1050128)
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 16% (+16%) | 0 | 24 (+24)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
LTE (Mission Critical Services) |  | 16.2% (+16.2%) | 0 | 24 (+24)
Mission Critical Services |  | 16.2% (+16.2%) | 0 | 24 (+24)
NR |  | 16.4% (+16.4%) | 0 | 24 (+24)
Mission Critical Services |  | 16.4% (+16.4%) | 0 | 24 (+24)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | LTE |  |  |  | NR
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | Mission Critical Services |  |  |  | Mission Critical Services
[5 empty] | Completion | Number of new completed test cases | Number of new test cases |  | Completion | Number of new completed test cases | Number of new test cases
Mission Critical Services
MC Common test environment | 37.579-1 | 8.3% (+8.3%) |  |  | 8.3% (+8.3%) |  |  |  | 8.3% (+8.3%)
MCPTT UE test cases | 37.579-2 | 16.7% (+16.7%) | 0 | 3 (+3) | 16.7% (+16.7%) | 0 | 3 (+3) |  | 16.7% (+16.7%) | 0 | 3 (+3)
MC Server Application test cases | 37.579-3
Applicability and ICS MC test cases | 37.579-4 | 47.6% (+47.6%) |  |  | 47.6% (+47.6%) |  |  |  | 47.6% (+47.6%)
MC Test suite (TTCN) | 37.579-5 | 50% (+50%) |  |  | 50% (+50%) |  |  |  | 50% (+50%)
MC Video UE test cases | 37.579-6 | 7.4% (+7.4%) | 0 | 11 (+11) | 7.1% (+7.1%) | 0 | 11 (+11) |  | 7.7% (+7.7%) | 0 | 11 (+11)
MC Data UE test cases | 37.579-7 | 6.7% (+6.7%) | 0 | 10 (+10) | 6.7% (+6.7%) | 0 | 10 (+10) |  | 6.7% (+6.7%) | 0 | 10 (+10)
5 References
[1] RP-241755 | New WID on UE Conformance - Protocol enhancements for Mission Critical Services (MCPTT, MCVideo, MCData) for Rel-17
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance - Protocol enhancements for Mission Critical Services (MCPTT, MCVideo, MCData) for Rel-17 | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | MCProtoc17_enh3MCPTT_eMCData3_MCOver5GS-UEConTest
WP Scope: |  | Rel-17 Mission Critical Services Conformance test aspects
WP Resp: |  | Calle Hagenfeldt |  |  | calle.hagenfeldt@ericsson.com | [5 empty] | WP item completion |  |  |  | LTE | NR
TS Resp: |  | Calle Hagenfeldt |  |  | calle.hagenfeldt@ericsson.com
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | LTE | NR |  | Mission Critical Services | Mission Critical Services
[15 empty] | 16.2% (+16.2%) | 16.4% (+16.4%)
[15 empty] | 52 (+52) | 51 (+51)
[15 empty] | 51.1 (+51.1) | 50.1 (+50.1)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
Mission Critical Services
TS 37.579-1: MC Common test environment
|  | 37.579-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 37.579-1 |  | Import contents of TS 36.579-1 |  | Ericsson | RAN5#105 (Nov-24) | R5-247090 |  | 1 | 100% (+100%) | 100% (+100%) | 100% (+100%) |  | 100% | 100%
2 |  | 37.579-1 |  | Update for NR |  | Ericsson | RAN5#106 (Feb-25) |  |  | 1
TBD |  | 37.579-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 37.579-1 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
3 |  | 37.579-1 | 5.5.3.1 | SDP Message | Add new parameters for Rel-17 |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
4 |  | 37.579-1 | 5.5.3.2 | MCS Info Lists | Add new parameters for Rel-17 |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
5 |  | 37.579-1 | 5.5.3.3 | Resource-lists | Add new parameters for Rel-17 |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
6 |  | 37.579-1 | 5.5.3.4 | Location-info | Add new parameters for Rel-17 |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
7 |  | 37.579-1 | 5.5.3.5 | PIDF | Add new parameters for Rel-17 |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
8 |  | 37.579-1 | 5.5.8.3 | MCPTT User Profile | Add new parameters for Rel-17 |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
9 |  | 37.579-1 | 5.5.8.11 | MCData User Profile | Add new parameters for Rel-17 |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
10 |  | 37.579-1 | 5.5.8.12 | MCData Service Configuration | Add new parameters for Rel-17 |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
11 |  | 37.579-1 | TBD |  | Add 5GS QoS model | Ericsson | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
|  | 37.579-1 | TBD |  | Add 5GS default messages | Ericsson | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
12 |  | 37.579-1 | TBD |  | Add 5GS preamble | Ericsson | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
TS 37.579-2: MCPTT UE test cases
|  | 37.579-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
13 |  | 37.579-2 |  | Import contents of TS 36.579-2 |  | Ericsson | RAN5#105 (Nov-24) | R5-247091 |  | 1 | 100% (+100%) | 100% (+100%) | 100% (+100%) |  | 100% | 100%
14 |  | 37.579-2 |  | Update for NR |  | Ericsson | RAN5#106 (Feb-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
15 |  | 37.579-2 |  | Clean-up of floor queued cancel related procedures | See Tdoc C1-213628 |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
TBD |  | 37.579-2 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 37.579-2 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
16 | Y | 37.579-2 | 5.11 | Configuration / Rules based affiliation status change / Group defined rules | 24.379 clause 9.2.1.7.3 | Ericsson | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
17 | Y | 37.579-2 | TBD | An authorized user to request clearing the entire queue instead of specifying the list of users to be cleared | See Tdoc C1-213614 (And extisting TCs 6.1.1.1 and 6.1.1.2) | Ericsson | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
18 | Y | 37.579-2 | 6.1.1.22 | On-network / On-demand Pre-arranged Group Call / Preconfigured Group Use Only | 24.379 clause 10.1.1.2.1 (See Tdoc C1-205347) A group can be configured for use only as a preconfigured group. Calls and alerts on such a group are not allowed. | Ericsson | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
TS 37.579-4: Applicability and ICS MC test cases
19 |  | 37.579-4 |  | Import contents of TS 36.579-4 |  | FirstNet | RAN5#105 (Nov-24) | R5-247092 |  | 1 | 100% (+100%) | 100% (+100%) | 100% (+100%) |  | 100% | 100%
20 |  | 37.579-4 |  | Update for NR |  | FirstNet | RAN5#106 (Feb-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
TBD |  | 37.579-4 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0.1
21 |  | 37.579-4 | 4 | Recommended Test Case Applicability | Add test case applicability statements for the new test cases introduced in 37.579-x. |  | RAN5#109 (Nov-25) |  |  | 0.1 | 0% | 0% | 0% |  | 0% | 0%
TS 37.579-5: MC Test suite (TTCN)
|  | 37.579-5 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
22 |  | 37.579-5 |  | Import contents of TS 36.579-5 |  | TF160 | RAN5#105 (Nov-24) | R5-246402 |  | 1 | 100% (+100%) | 100% (+100%) | 100% (+100%) |  | 100% | 100%
23 |  | 37.579-5 |  | Addition of NR/5GC RAT support |  | TF160 | RAN5#106 (Feb-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
TS 37.579-6: MC Video UE test cases
|  | 37.579-6 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
24 |  | 37.579-6 |  | Import contents of TS 36.579-6 |  | Ericsson | RAN5#105 (Nov-24) | R5-247093 |  | 1 | 100% (+100%) | 100% (+100%) | 100% (+100%) |  | 100% | 100%
25 |  | 37.579-6 |  | Update for NR |  | Ericsson | RAN5#106 (Feb-25) |  |  | 1 | 0% | 0% |  |  | 0%
TBD |  | 37.579-6 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 37.579-6 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD |  | 37.579-6 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
26 | Y | 37.579-6 | 5.5 | Configuration / Download CSK | 24.281 clause 7.2.5 | Ericsson | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
27 | Y | 37.579-6 | 5.6 | Configuration / Functional Alias / Functional alias status determination / Activate functional alias / Deactivate functional alias | 24.281 clauses 20.2.1.2, 20.2.1.3 | Ericsson | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
28 | Y | 37.579-6 | 5.7 | Configuration / Functional Alias / Location based functional alias status change | 24.281 clauses 20.2.1.4 | Ericsson | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
29 | Y | 37.579-6 | 5.8 | Configuration / Rules based affiliation status change | 24.281 clauses 8.2.1.2 | Ericsson | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
30 | Y | 37.579-6 | 6.3.3 | On-network / Emergency Alert / Group geographic area | 24.281 clause 11.2.1.4 | FirstNet | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
31 | Y | 37.579-6 | 6.3.4 | On-network / Emergency Alert / Emergency alert area | 24.281 clause 11.2.1.5 |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
32 | Y | 37.579-6 | 6.1.1.22 | On-network / On-demand Pre-arranged Group Call / Preconfigured Group Use Only | 24.281 clause 9.2.1.2.1 |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
33 |  | 37.579-6 | 6.10 | Regroup using a preconfigured group | New sub-clause header |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
34 | Y | 37.579-6 | 6.10.1 | On-network / Regroup using a preconfigured group / Requesting a group regroup using a preconfigured group / Removing a regroup using preconfigured group / Client Originated (CO) | 24.281 clause 21.2.1.1, 21.2.1.2 | FirstNet | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
35 | Y | 37.579-6 | 6.10.2 | On-network / Regroup using a preconfigured group / Receiving a notification of creation of a regroup using preconfigured group / Receiving notification of removal of a regroup using preconfigured group / Client Terminated (CT) | 24.281 clause 21.2.1.3, 21.2.1.4 | FirstNet | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
36 | Y | 37.579-6 | 6.10.3 | On-network / Regroup using a preconfigured group / Requesting a user regroup using a preconfigured group / Removing a regroup using preconfigured group / Client Originated (CO) | 24.281 clause 21.3.1.1, 21.3.1.2, 21.2.1.2 | Element | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
37 | Y | 37.579-6 | 6.10.4 | On-network / Regroup using a preconfigured group / Creating a user regroup using preconfigured group / Removing a user regroup using preconfigured group / Client Terminated (CT) | 24.281 clause 21.3.1.3, 21.2.1.2, 21.3.1.4, 21.2.1.4 | Element | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
TS 37.579-7: MC Data UE test cases
|  | 37.579-7 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
38 |  | 37.579-7 |  | Import contents of TS 36.579-6 |  | Ericsson | RAN5#105 (Nov-24) | R5-247094 |  | 1 | 100% (+100%) | 100% (+100%) | 100% (+100%) |  | 100% | 100%
39 |  | 37.579-7 |  | Update for NR |  | Ericsson | RAN5#106 (Feb-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
TBD |  | 37.579-7 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 37.579-7 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD |  | 37.579-7 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
40 | Y | 37.579-7 | 6.1.23 | On-network / Short Data Service (SDS) / SDS Session / Group SDS Session / Pre-established session / Preconfigured Group Use Only | 24.282 clause 9.2.3.2.3 | Samsung | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
41 | Y | 37.579-7 | 6.1.23 | On-network / File Distribution (FD) / FD Using HTTP / Group Standalone FD / Preconfigured Group Use Only | 24.282 clause 10.2.4.2.1 |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
42 | Y | 37.579-7 | 6.1.24 | On-network / File Distribution (FD) / FD Using Media Plane / Group Standalone FD / Preconfigured Group Use Only | 24.282 clause 10.2.5.2.3 |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
43 | Y | 37.579-7 | 6.4.3 | On-network / Emergency Alert / Group Geographic Area | 24.282 clause 16.2.1.4 | Element | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
44 | Y | 37.579-7 | 6.4.4 | On-network / Emergency Alert / Emergency Alert Area | 24.282 clause 16.2.1.5 |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
51 |  | 37.579-7 | 6.7.1 | On-network / IP Connectivity / Client Originated (CO) | Update the test case to Rel-17 core requirements | Ericsson | RAN5#109 (Nov-25) |  | Outcome of discussion paper in R5-246421 | 1 | 0% | 0% | 0% |  | 0% | 0%
52 |  | 37.579-7 | 6.7.2 | On-network / IP Connectivity / Client Terminated (CT) | Update the test case to Rel-17 core requirements | Ericsson | RAN5#109 (Nov-25) |  | Outcome of discussion paper in R5-246421 | 1 | 0% | 0% | 0% |  | 0% | 0%
45 | Y | 37.579-7 | 6.8.5 | On-network / MCData Message Store / Notification Channel / Create / Open / Update / Delete | 24.282 clause 21.2.19, 21.2.20. 21.2.21, 21.2.22 |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
46 |  | 37.579-7 | 6.9 | Regroup using a preconfigured group | New sub-clause header |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
47 | Y | 37.579-7 | 6.9.1 | On-network / Regroup using a preconfigured group / Requesting a group regroup using a preconfigured group / Removing a regroup using preconfigured group / Client Originated (CO) | 24.281 clause 23.2.1.1, 23.2.1.2 | Samsung | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
48 | Y | 37.579-7 | 6.9.2 | On-network / Regroup using a preconfigured group / Receiving a notification of creation of a regroup using preconfigured group / Receiving notification of removal of a regroup using preconfigured group / Client Terminated (CT) | 24.281 clause 23.2.1.3, 23.2.1.4 | Samsung | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
49 | Y | 37.579-7 | 6.9.3 | On-network / Regroup using a preconfigured group / Requesting a user regroup using a preconfigured group / Removing a regroup using preconfigured group / Client Originated (CO) | 24.281 clause 23.3.1.1, 23.3.1.2, 23.2.1.2 | Element | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
50 | Y | 37.579-7 | 6.9.4 | On-network / Regroup using a preconfigured group / Creating a user regroup using preconfigured group / Removing a user regroup using preconfigured group / Client Terminated (CT) | 24.281 clause 23.3.1.3, 23.2.1.2, 23.3.1.4, 23.2.1.4 | Element | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.