## Cover sheet
3GPP TSG-RAN5 Meeting #105 | [8 empty] | R5-247139
Orlando, USA, Nov 18 - 22, 2024
Agenda Item: | 7.4.2
Source: | Qualcomm
Title: | WP UE Conformance Test Aspects - Solutions for NR to support non-terrestrial networks (NTN)
Work item code: | NR_NTN_solutions_plus_CT-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0
1. Introduction
<Description of work item and its scope>
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 86% (+4%) | 19 | 111 (+23)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR1) |  | 85.8% (+3.8%) | 52 | 111 (+23)
FR1 |  | 85.8% (+3.8%) | 52 | 111 (+23)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 100% |  |  | 100%
Common ICS | 38.508-2 | 90% (-0%) |  |  | 90%
UE specific testing functions | 38.509 | 100% |  |  | 100%
Conducted RF Transmitter Test cases | 38.521-5 | 100% | 0 | 33 | 100% | 33 | 33
Protocol Test Cases | 38.523-1 | 98.2% | 19 | 22 | 98.2% | 19 | 22
RRM Test cases | 38.533 | 77.5% (+35%) | 0 | 56 (+23)
5 References
[1] RP-221299 | New WID on UE Conformance - Further enhancement on NR demodulation performance
[2] R5-231336 | WP UE Conformance Test Aspects - Solutions for NR to support non-terrestrial networks (NTN)
[3] R5-232846 | WP UE Conformance Test Aspects - Solutions for NR to support non-terrestrial networks (NTN)
[4] R5-234268 | WP UE Conformance Test Aspects - Solutions for NR to support non-terrestrial networks (NTN)
[5] R5-237269 | WP UE Conformance Test Aspects - Solutions for NR to support non-terrestrial networks (NTN)
[6] R5-241134 | WP UE Conformance Test Aspects - Solutions for NR to support non-terrestrial networks (NTN)
[7] R5-243426 | WP UE Conformance Test Aspects - Solutions for NR to support non-terrestrial networks (NTN)
[8] R5-245288 | WP UE Conformance Test Aspects - Solutions for NR to support non-terrestrial networks (NTN)
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance- Solutions for NR to support non-terrestrial networks (NTN) | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_NTN_solutions_plus_CT-UEConTest
WP Scope: |  | This part of the work plan covers all applicable test cases for Solutions for NR to support non-terrestrial networks (NTN) Work item
WP Resp: |  | Vijay Balasubramanian |  |  | vijayb@qti.qualcomm.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | Vijay Balasubramanian |  |  | vijayb@qti.qualcomm.com
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1
85.8% (+3.8%)
169 (+4)
267.2 (+126)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
1 |  | 38.508-1 | 4, 6 | Introduction of General and RF Demod Test Environment for Rel17 NTN solutions |  | Google, Qualcomm, Keysight, R&S, ZTE |  | R5-227480, R5-230882, R5-230884, R5-225352, R5-225353, R5-225354, R5-225355, R5-233434, R5-233435, R5-233436, R5-232693, R5-233369, R5-232520, R5-235336, R5-235951, R5-237863, R5-242007, R5-242016, R5-242017, R5-243286, R5-246631 |  | 1 | 100% | 100% |  | 100%
TS 38.508-2: Common ICS
2 |  | 38.508-2 | TBD | Introduction of common implementation conformance statements for Rel-17 NTN solutions |  | Qualcomm, CAICT, ZTE |  | R5-226551 R5-237611 R5-237611 R5-241909 R5-241270 R5-243287 R5-243398 |  | 1 | 90% | 90% |  | 90%
TS 38.509: UE specific testing functions
62 |  | 38.509 | TBD |  |  | Qualcomm |  |  | No change needed | 1 | 100% | 100% |  | 100%
TS 38.521-5: Conducted RF Transmitter Test cases
3 |  | 38.521-5 | 2,3,4 | General |  | Qualcomm | RAN5#97 (Nov-22) | R5-226639 R5-226640 R5-241810 R5-241149 R5-245073 R5-247800 |  | 0.2 | 100% | 100% |  | 100%
4 |  | 38.521-5 | 5 | Operating bands and channel arrangement |  | Qualcomm | RAN5#97 (Nov-22) | R5-226641 |  | 0.2 | 100% | 100% |  | 100%
5 |  | 38.521-5 | 5.1 | General |  | Qualcomm, ZTE | RAN5#97 (Nov-22) | R5-226641 R5-243288 |  | 0.2 | 100% | 100% |  | 100%
6 |  | 38.521-5 | 5.2 | Operating bands |  | Qualcomm | RAN5#97 (Nov-22) | R5-226641 R5-240840 |  | 0.2 | 100% | 100% |  | 100%
7 |  | 38.521-5 | 5.3 | UE Channel Bandwidth |  | Qualcomm, ZTE | RAN5#97 (Nov-22) | R5-226641 |  | 0.2 | 100% | 100% |  | 100%
8 |  | 38.521-5 | 5.4 | Channel arrangment |  | Qualcomm | RAN5#97 (Nov-22) | R5-226641 |  | 0.2 | 100% | 100% |  | 100%
9 |  | 38.521-5 | 6 | Conducted Transmitter characteristics |  | Google | RAN5#97 (Nov-22) | R5-227885 |  | 0.2 | 100% | 100% |  | 100%
10 |  | 38.521-5 | 6.1 | General |  | Google, Keysight | RAN5#97 (Nov-22) | R5-227885 R5-235456 R5-237864 |  | 20 | 100% | 100% |  | 100%
11 |  | 38.521-5 | 6.2 | Transmitter Power |  | Google | RAN5#97 (Nov-22) | R5-227885 |  | 0.2 | 100% | 100% |  | 100%
12 | Y | 38.521-5 | 6.2.1 | UE maximum output power |  | Google, Keysight | RAN5#97 (Nov-22) | R5-227885, R5-231854 R5-235186 R5-240854 R5-243676 |  | 1 | 100% | 100% |  | 100%
13 | Y | 38.521-5 | 6.2.2 | UE maximum output power reduction |  | Google, ZTE, Keysight | RAN5#97 (Nov-22) | R5-227886. R5-231854 R5-235186 R5-240841 R5-242508 |  | 1 | 100% | 100% |  | 100%
14 | Y | 38.521-5 | 6.2.3 | UE additional maximum output power reduction |  | Google, ZTE, Keysight | RAN5#98 (Feb-23) | R5-233569 R5-234627 R5-235186 R5-241805 R5-243677 R5-243289 |  | 1 | 100% | 100% |  | 100%
15 | Y | 38.521-5 | 6.2.4 | Configured transmitted power |  | Google, Keysight | RAN5#97 (Nov-22) | R5-232519 R5-234628 R5-235186 R5-242510 |  | 1 | 100% | 100% |  | 100%
16 |  | 38.521-5 | 6.3 | Output power dynamics
17 | Y | 38.521-5 | 6.3.1 | Minimum output power |  | Keysight | RAN5#98 (Feb-23) | R5-231738 R5-235824 R5-235186 R5-241396 |  | 1 | 100% | 100% |  | 100%
18 | Y | 38.521-5 | 6.3.2 | Transmit off power |  | Keysight | RAN5#98 (Feb-23) | R5-231739 R5-235824 R5-235186 R5-240843 R5-241397 |  | 1 | 100% | 100% |  | 100%
19 | Y | 38.521-5 | 6.3.3 | Transmit on/off time mask |  | Apple | RAN5#98 (Feb-23) | R5-231367 R5-233571 R5-235186 R5-235679 R5-241806 R5-241440 R5-243681 |  | 1 | 100% | 100% |  | 100%
20 | Y | 38.521-5 | 6.3.4 | Power control |  | Qualcomm |  | R5-243679 R5-245098 |  | 1 | 100% | 100% |  | 100%
21 |  | 38.521-5 | 6.4 | Transmit signal quality
22 |  | 38.521-5 | 6.4.1 | Frequency error |  | Qualcomm
22 | Y | 38.521-5 | 6.4.1_1 | Frequency error with GSO ephemeris |  | Qualcomm, R&S |  | R5-237875 R5-242013 R5-241808 |  | 1 | 100% | 100% |  | 100%
22 | Y | 38.521-5 | 6.4.1_2 | Frequency error with NGSO ephemeris |  | Qualcomm, R&S |  | R5-237875 R5-242013 R5-241808 |  | 1 | 100% | 100% |  | 100%
23 |  | 38.521-5 | 6.4.2 | Transmit modulation quality |  | Keysight
23 | Y | 38.521-5 | 6.4.2.1 | Error Vector Magnitude |  | Keysight |  | R5-242501 |  | 1 | 100% | 100% |  | 100%
23 | Y | 38.521-5 | 6.4.2.1A | Error Vector Magnitude including symbols with transient period |  | Keysight |  | R5-243896 |  | 1 | 100% | 100% |  | 100%
23 | Y | 38.521-5 | 6.4.2.2 | Carrier leakage |  | Keysight |  | R5-243673 |  | 1 | 100% | 100% |  | 100%
23 | Y | 38.521-5 | 6.4.2.3 | In-band emissions |  | Keysight |  | R5-243674 |  | 1 | 100% | 100% |  | 100%
23 | Y | 38.521-5 | 6.4.2.4 | EVM equalizer spectrum flatness |  | Keysight |  | R5-243675 |  | 1 | 100% | 100% |  | 100%
23 | Y | 38.521-5 | 6.4.2.5 | EVM equalizer spectrum flatness for Pi/2 BPSK |  | Keysight |  | R5-242506 |  | 1 | 100% | 100% |  | 100%
24 |  | 38.521-5 | 6.5 | Output RF spectrum emissions
25 | Y | 38.521-5 | 6.5.1 | Occupied Bandwidth |  | Keysight |  | R5-242500 |  | 1 | 100% | 100% |  | 100%
26 | Y | 38.521-5 | 6.5.2 | Out of band emissions | [5 empty] | 0
27 |  | 38.521-5 | 6.5.2.1 | General | [5 empty] | 0.2
28 | Y | 38.521-5 | 6.5.2.2 | Spectrum emission mask |  | Apple |  | R5-231368 R5-233572 R5-235186 R5-235683 R5-240846 R5-241441 R5-243814 |  | 1 | 100% | 100% |  | 100%
29 | Y | 38.521-5 | 6.5.2.4 | Adjacent channel leakage ratio |  | Apple |  | R5-231369 R5-233573 R5-235186 R5-235681 R5-240846 R5-241442 R5-243417 |  | 1 | 100% | 100% |  | 100%
30 |  | 38.521-5 | 6.5.3 | Spurious emission |  | Qualcomm
31 | Y | 38.521-5 | 6.5.3.1 | General spurious emission |  | Qualcomm |  | R5-230877 R5-233158 R5-235186 R5-241807 R5-242009 |  | 1 | 100% | 100% |  | 100%
32 | Y | 38.521-5 | 6.5.3.2 | Spurious emissions for UE co-existence |  | Qualcomm |  | R5-230879 R5-235827 R5-235186 R5-241807 R5-242010 |  | 1 | 100% | 100% |  | 100%
33 | Y | 38.521-5 | 6.5.3.3 | Additional spurious emissions |  | Qualcomm, ZTE |  | R5-237690 R5-242008 R5-242947 R5-243290 R5-246434 |  | 1 | 100% | 100% |  | 100%
34 | Y | 38.521-5 | 6.5.4 | Transmit intermodulation |  | Qualcomm |  | R5-235826 R5-235186 R5-242011 |  | 1 | 100% | 100% |  | 100%
TS 38.521-5: Conducted RF Receiver Test cases
35 |  | 38.521-5 | 7.1 | General |  | Qualcomm, Keysight | RAN5#97 (Nov-22) | R5-230878 R5-235456 R5-237864 |  | 12 | 100% | 100% |  | 100%
36 |  | 38.521-5 | 7.2 | Diversity Characteristics |  | Qualcomm | RAN5#97 (Nov-22) |  |  | 0
37 |  | 38.521-5 | 7.3 | Reference sensitivity |  | Qualcomm | RAN5#97 (Nov-22) | R5-230878 | [5 empty] | 100%
38 |  | 38.521-5 | 7.3.1 | General |  | Qualcomm | RAN5#97 (Nov-22) | R5-230878 |  | 0.2 | 100% | 100% |  | 100%
39 | Y | 38.521-5 | 7.3.2 | Reference sensitivity power level |  | Qualcomm |  | R5-230878 R5-235866 R5-235186 R5-237876 R5-241877 R5-242012 R5-244933 |  | 1 | 100% | 100% |  | 100%
40 | Y | 38.521-5 | 7.4 | Maximum input level |  | Keysight | RAN5#98 (Feb-23) | R5-232346 R5-235825 R5-235186 R5-240850 R5-241398 |  | 1 | 100% | 100% |  | 100%
41 | Y | 38.521-5 | 7.5 | Adjacent channel selectivity |  | CAICT | RAN5#98 (Feb-23) | R5-233567 R5-235186 R5-237874 R5-240851 |  | 1 | 100% | 100% |  | 100%
42 |  | 38.521-5 | 7.6 | Blocking characteristics |  | CAICT
43 |  | 38.521-5 | 7.6.1 | General |  | Apple
44 | Y | 38.521-5 | 7.6.2 | In-band blocking |  | Apple |  | R5-240852 R5-245856 |  | 1 | 100% | 100% |  | 100%
45 | Y | 38.521-5 | 7.6.3 | Out-of-band blocking |  | Apple |  | R5-231383 R5-235186 R5-240852 R5-245858 |  | 1 | 100% | 100% |  | 100%
45 | Y | 38.521-5 | 7.6.4 | Narrow band blocing |  | Apple |  | R5-245857 |  | 1 | 100% | 100% |  | 100%
46 | Y | 38.521-5 | 7.7 | Spurious response |  | CAICT |  | R5-237834 |  | 1 | 100% | 100% |  | 100%
47 |  | 38.521-5 | 7.8 | Intermodulation characteristics
65 |  | 38.521-5 | 7.8.1 | General |  | CAICT |  | R5-237835 |  | 0.1 | 100% | 100% |  | 100%
66 | Y | 38.521-5 | 7.8.2 | Wideband intermodulation |  | CAICT |  | R5-237835 |  | 1 | 100% | 100% |  | 100%
48 | Y | 38.521-5 | 7.9 | Spurious emissions |  | CAICT |  | R5-231740 R5-232372 R5-235186 R5-237836 |  | 1 | 100% | 100% |  | 100%
TS 38.521-5: Demodulation Performance Test Cases
49 |  | 38.521-5 | 8 | General |  | Qualcomm | RAN5#97 (Nov-22)
50 |  | 38.521-5 | 8.1 | General |  | Keysight | RAN5#97 (Nov-22) | R5-235456 R5-237864
51 |  | 38.521-5 | 8.1.1 | Relationship between minimum requirements and test requirements |  | Qualcomm | RAN5#97 (Nov-22) | R5-231741 |  | 0.2 | 100% | 100% |  | 100%
52 |  | 38.521-5 | 8.1.2 | Applicability of minimum requirements |  | Qualcomm | RAN5#97 (Nov-22) | R5-231741 |  | 0.2 | 100% | 100% |  | 100%
53 |  | 38.521-5 | 8.1.3 | Conducted requirements |  | Qualcomm | RAN5#97 (Nov-22) | R5-231741 |  | 0.2 | 100% | 100% |  | 100%
54 |  | 38.521-5 | 8.2 | Demodulation performance requirements |  | Qualcomm | RAN5#97 (Nov-22)
55 |  | 38.521-5 | 8.2.1 | General |  | Qualcomm | RAN5#97 (Nov-22)
56 |  | 38.521-5 | 8.2.1.2 | PDSCH demodulation requirements |  | Qualcomm | RAN5#97 (Nov-22) | R5-231742 |  | 0.2 | 100% | 100% |  | 100%
57 |  | 38.521-5 | 8.2.1.2.1 | 1RX requirements
58 |  | 38.521-5 | 8.2.1.2.2 | 2RX requirements |  | Qualcomm | RAN5#97 (Nov-22) | R5-231742
61 | Y | 38.521-5 | 8.2.1.2.2.1.1_1 | 2Rx FDD FR1 PDSCH Mapping Type A for Satellite Access |  | Qualcomm |  | R5-233570 R5-236291 R5-237877 R5-241148 R5-243899 R5-245854 R5-247785 R5-247787 |  | 1 | 100% | 100% |  | 100%
TS 38.521-5: Annex
59 |  | 38.521-5 | A | Measurement channels |  | CAICT, ZTE |  | R5-233568 R5-237864 R5-240853 R5-242018 |  | 0.2 | 100% | 100% |  | 100%
59 |  | 38.521-5 | B | Propagation conditions |  | CAICT |  | R5-233568 R5-236147 |  | 0.2 | 100% | 100% |  | 100%
59 |  | 38.521-5 | C.3 | Connection (Conducted) |  | Qualcomm | RAN5#97 (Nov-22) | R5-231741 |  | 0.2 | 100% | 100% |  | 100%
59 |  | 38.521-5 | D | Characteristics of Interfering signal |  | CAICT |  | R5-236148 |  | 0.2 | 100% | 100% |  | 100%
59 |  | 38.521-5 | F | Acceptable uncertainty of Test System |  | Keysight, Qualcomm, CAICT |  | R5-235824 R5-236149 R5-236150 R5-242012 R5-243678 |  | 0.2 | 100% | 100% |  | 100%
|  | 38.521-5 | G | Minimum test time |  | Qualcomm |  |  |  | 0.5
59 |  | 38.521-5 | H | Statistical Testing |  | CAICT |  | R5-236151 |  | 0.2 | 100% | 100% |  | 100%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
|  | 38.903 | 8 | Test toleance analysis for satellite access test cases in TS 38.533 |  | Qualcomm, Keysight |  | R5-247835 R5-247883 R5-247884 |  | 1 | 10% (+10%) | 10% (+10%) |  | 10%
TS 38.905: Derivation of test points for radio transmission and reception test cases
63 |  | 38.905 | 4.4 | Test point analysis for satellite access test cases in TS 38.521-5 |  | Google, Qualcomm, Apple, Keysight |  | R5-234630 R5-235858 R5-235680 R5-235682 R5-235684 R5-242014 R5-243448 |  | 1 | 90% | 90% |  | 90%
TS 38.522: Applicability for RF Transmitter and Receiver Test cases
60 |  | 38.522 | 4.1, 4.2 | Add test case applicability statements for the new test cases introduced in 38.521-5 |  | CAICT, Qualcomm, Apple, Keysight, R&S, Bureau Veritas |  | R5-241910 R5-242512 R5-243292 R5-243394 R5-243440 R5-245371 R5-245371 R5-246063 R5-246322 R5-247150 R5-247829 |  | 1 | 90% | 90% |  | 90%
TS 38.533: RRM Test cases
|  | 38.533 |  | Placeholder | [5 empty] | 100 | 100% | 100% |  | 100%
|  | 38.533 | 3.3 | Abreviations |  | Qualcomm |  | R5-234647 |  | 0.1 | 100% | 100% |  | 100%
|  | 38.533 | 14 | NR standalone tests for Satellite access |  | Qualcomm |  | R5-234646 |  | 0
|  | 38.533 | 14.0 | General |  | Qualcomm |  | R5-234646 R5-241265 R5-243363 R5-245245 |  | 0.1 | 100% | 100% |  | 100%
|  | 38.533 | 14.1 | RRC_IDLE state mobility |  | Qualcomm |  | R5-234646 |  | 0
| Y | 38.533 | 14.1.1 | NR SA FR1 Cell reselection for Satellite Access |  | Qualcomm |  | R5-246825 | Editor's Note: - MU and TT analysis is incomplete - Message contents are FFS - Several test parameters and configuration are still in brackets | 1 | 50% (+50%) | 50% (+50%) |  | 50%
| Y | 38.533 | 14.1.2 | NR SA FR1 Cell reselection for UE configured with enhanced requirements for Satellite Access | Required to be tested for UE supporting both TN and NTN | Qualcomm |  | R5-241268 | Editor's Note: - MU and TT analysis is incomplete - Message contents are FFS - Call setup and test procedure needs to be updated - Applicability needs to be updated - Exceptionts to connection diagram may need to be updated - Several sections are in brackets - Several test parameters and configuration are still in brackets - Annex E and F need to be updated | 1 | 30% | 30% |  | 30%
| Y | 38.533 | 14.1.3 | NR SA FR1 Time based measurement initiation cell reselection for Satellite Access | Required to be tested for UE supporting both TN and NTN | Qualcomm |  | R5-241268 | Editor's Note: - MU and TT analysis is incomplete - Message contents are FFS - Call setup and test procedure needs to be updated - Applicability needs to be updated - Exceptions to connection diagram may need to be updated - Several sections are in brackets - Several test parameters and configuration are still in brackets - Annex E and F need to be updated | 1 | 30% | 30% |  | 30%
| Y | 38.533 | 14.1.4 | NR SA FR1 Location-based measurement initiation cell reselection for Satellite Access | Required to be tested for UE supporting both TN and NTN | Qualcomm |  | R5-241268 | Editor's Note: - MU and TT analysis is incomplete - Message contents are FFS - Call setup and test procedure needs to be updated - Applicability needs to be updated - Exceptions to connection diagram may need to be updated - Several sections are in brackets - Several test parameters and configuration are still in brackets - Annex E and F need to be updated | 1 | 30% | 30% |  | 30%
| Y | 38.533 | 14.1.5 | NR SA FR1-FR1 Cell reselection for Satellite Access |  | Qualcomm |  | R5-246825 | Editor's Note: - MU and TT analysis is incomplete - Message contents are FFS - Several test parameters and configuration are still in brackets | 1 | 50% (+50%) | 50% (+50%) |  | 50%
| Y | 38.533 | 14.1.6 | NR SA FR1-FR1 Cell reselection for UE configured with enhanced requirements for Satellite Access |  | Qualcomm |  | R5-246826 | Editor's Note: - MU and TT analysis is incomplete - Message contents are FFS - Several test parameters and configuration are still in brackets | 1 | 50% (+50%) | 50% (+50%) |  | 50%
| Y | 38.533 | 14.1.7 | NR SA FR1-FR1 Time based measurement initiation cell reselection for Satellite Access | Required to be tested for UE supporting both TN and NTN | Qualcomm |  | R5-243361 | Editor’s Note: - MU and TT analysis is incomplete - Message contents are FFS - Call setup and test procedure needs to be updated - Several test parameters and configuration are still in brackets - Annex E and F need to be updated | 1 | 55% | 55% |  | 55%
| Y | 38.533 | 14.1.8 | NR SA FR1-FR1 Location-based measurement initiation cell reselection for Satellite Access | Required to be tested for UE supporting both TN and NTN | Qualcomm |  | R5-243361 | Editor’s Note: - MU and TT analysis is incomplete - Message contents are FFS - Call setup and test procedure needs to be updated - Several test parameters and configuration are still in brackets - Annex E and F need to be updated | 1 | 55% | 55% |  | 55%
| Y | 38.533 | 14.1.9 | NR SA FR1-FR1 Cell reselection for UE fulfilling low mobility relaxed measurement criterion for Satellite Access | Required to be tested for UE supporting both TN and NTN | Qualcomm |  | R5-246827 | Editor’s Note: - MU and TT analysis is incomplete - Message contents are FFS - Test procedure may need to be updated | 1 | 50% (+50%) | 50% (+50%) |  | 50%
| Y | 38.533 | 14.1.10 | NR SA FR1-FR1 Cell reselection for UE fulfilling not-at-cell edge relaxed measurement criterion for Satellite Access |  | Qualcomm |  | R5-246827 | Editor’s Note: - MU and TT analysis is incomplete - Message contents are FFS - Test procedure may need to be updated | 1 | 50% (+50%) | 50% (+50%) |  | 50%
|  | 38.533 | 14.2 | RRC_CONNECTED state mobility |  | Qualcomm |  | R5-234646 |  | 0
|  | 38.533 | 14.2.1 | Handover for SAN |  | Qualcomm |  | R5-241267 |  | 0
| Y | 38.533 | 14.2.1.1 | NR SA FR1 Handover for Satellite Access | [5 empty] | 1 | 0% | 0% |  | 0%
| Y | 38.533 | 14.2.1.2 | NR SA FR1-FR1 Handover for Satellite Access | [5 empty] | 1 | 0% | 0% |  | 0%
| Y | 38.533 | 14.2.1.3 | NR SA FR1 Time-based Conditional Handover for Satellite Access | Required to be tested for UE supporting both TN and NTN | Qualcomm |  | R5-241267 | Editor's Note: - MU and TT analysis is incomplete - Message contents are FFS - Call setup and test procedure needs to be updated - Applicability may need to be updated - Exceptionts to connection diagram may need to be updated - Several sections are in brackets - Several test parameters and configuration are still in brackets - Annex E and F need to be updated | 1 | 30% | 30% |  | 30%
| Y | 38.533 | 14.2.1.4 | NR SA FR1-FR1 Time-based Conditional Handover for Satellite Access | Required to be tested for UE supporting both TN and NTN | Qualcomm |  | R5-241267 | Editor's Note: - MU and TT analysis is incomplete - Message contents are FFS - Call setup and test procedure needs to be updated - Applicability may need to be updated - Exceptionts to connection diagram may need to be updated - Several sections are in brackets - Several test parameters and configuration are still in brackets - Annex E and F need to be updated | 1 | 30% | 30% |  | 30%
| Y | 38.533 | 14.2.1.5 | NR SA FR1 Distance-based Conditional Handover for Satellite Access | Required to be tested for UE supporting both TN and NTN | Qualcomm |  | R5-243360 | Editor's Note: - MU and TT analysis is incomplete - Message contents are FFS - Call setup and test procedure needs to be updated - Several test parameters and configuration are still in brackets - Annex E and F need to be updated | 1 | 55% | 55% |  | 55%
| Y | 38.533 | 14.2.1.6 | NR SA FR1-FR1 Distance-based Conditional Handover for Satellite Access | Required to be tested for UE supporting both TN and NTN | Qualcomm |  | R5-243360 | Editor's Note: - MU and TT analysis is incomplete - Message contents are FFS - Call setup and test procedure needs to be updated - Several test parameters and configuration are still in brackets - Annex E and F need to be updated | 1 | 55% | 55% |  | 55%
|  | 38.533 | 14.2.2 | RRC Connection Mobility Control |  | Qualcomm |  | R5-245345 |  | 0
|  | 38.533 | 14.2.2.1 | RRC Re-establishment for SAN |  | Qualcomm |  | R5-245345 |  | 0
|  | 38.533 | 14.2.2.1.1 | NR SA FR1 RRC Re-establishment for Satellite Access |  | Qualcomm |  | R5-245345 | Editor's Note: - MU and TT analysis is incomplete - Message contents may need to be updated - Applicability may need to be updated - Several test parameters and configuration are still TBD or need to be recalculated - Re-establishment delay calculation needs to be aligned with legacy tests | 1 | 50% | 50% |  | 50%
|  | 38.533 | 14.2.2.1.2 | NR SA FR1-FR1 RRC Re-establishment for Satellite Access |  | Qualcomm |  | R5-245345 | Editor's Note: - MU and TT analysis is incomplete - Message contents may need to be updated - Applicability may need to be updated - Several test parameters and configuration are still TBD or need to be recalculated - Re-establishment delay calculation needs to be aligned with legacy tests | 1 | 50% | 50% |  | 50%
|  | 38.533 | 14.2.2.2 | Random Access for SAN | [5 empty] | 0
| Y | 38.533 | 14.2.2.2.1 | NR SA FR1 4-step contention based random access for Satellite Access | [5 empty] | 1 | 0% | 0% |  | 0%
| Y | 38.533 | 14.2.2.2.2 | NR SA FR1 4-step non-contention based random access for Satellite Access | [5 empty] | 1 | 0% | 0% |  | 0%
|  | 38.533 | 14.2.2.3 | RRC Connection Release with Redirection for SAN | [5 empty] | 0
| Y | 38.533 | 14.2.2.3.1 | NR SA FR1-FR1 RRC connection release with redirection for Satellite Access | [5 empty] | 1 | 0% | 0% |  | 0%
|  | 38.533 | 14.3 | Timing for Satellite Access |  | Qualcomm |  | R5-241266 |  | 0
|  | 38.533 | 14.3.1 | UE Transmit Timing for SAN |  | Qualcomm |  | R5-241266 |  | 0
| Y | 38.533 | 14.3.1.1 | NR SA FR1 UE transmit timing accuracy for Satellite Access | Required to be tested for UE supporting both TN and NTN | Qualcomm |  | R5-241266 | Editor's Note: - MU and TT analysis is incomplete - Message contents are FFS - Call setup and test procedure needs to be updated - Applicability may need to be updated - Exceptions to connection diagram may need to be updated - Several sections are in brackets - Several test parameters and configuration are still in brackets - Whether GNSS is used and its config is FFS | 1 | 30% | 30% |  | 30%
|  | 38.533 | 14.3.2 | Timing Advance for SAN |  | Qualcomm |  | R5-243359 |  | 0
| Y | 38.533 | 14.3.2.1 | NR SA FR1 Timing advance adjustment accuracy for Satellite Access |  | Qualcomm |  | R5-243359 | Editor's Note: - MU and TT analysis is incomplete - Message contents are FFS | 1 | 70% | 70% |  | 70%
|  | 38.533 | 14.4 | Signalling Characteristics for Satellite Access |  | Qualcomm |  | R5-245344 |  | 0
|  | 38.533 | 14.4.1 | Radio Link Monitoring for SAN |  | Qualcomm |  | R5-245344 |  | 0
|  | 38.533 | 14.4.1.1 | NR SA FR1 Radio Link Monitoring Out-of-sync for PCell configured with SSB-based RLM RS in non-DRX mode for Satellite Access |  | Qualcomm |  | R5-245344 R5-246822 | Editor's Note: This test is incomplete in the following aspects: - MU and TT analysis is incomplete - Message contents may need to be updated | 1 | 75% (+25%) | 75% (+25%) |  | 75%
|  | 38.533 | 14.4.1.2 | NR SA FR1 Radio Link Monitoring In-sync for PCell configured with SSB-based RLM RS in non-DRX mode for Satellite Access |  | Qualcomm |  | R5-245344 R5-246822 | Editor's Note: This test is incomplete in the following aspects: - MU and TT analysis is incomplete - Message contents may need to be updated | 1 | 75% (+25%) | 75% (+25%) |  | 75%
|  | 38.533 | 14.4.1.3 | NR SA FR1 Radio Link Monitoring Out-of-sync for PCell configured with SSB-based RLM RS in DRX mode for Satellite Access |  | Qualcomm |  | R5-245344 R5-246822 | Editor's Note: This test is incomplete in the following aspects: - MU and TT analysis is incomplete - Message contents may need to be updated | 1 | 75% (+25%) | 75% (+25%) |  | 75%
|  | 38.533 | 14.4.1.4 | NR SA FR1 Radio Link Monitoring In-sync for PCell configured with SSB-based RLM RS in DRX mode for Satellite Access |  | Qualcomm |  | R5-245344 R5-246822 | Editor's Note: This test is incomplete in the following aspects: - MU and TT analysis is incomplete - Message contents may need to be updated | 1 | 75% (+25%) | 75% (+25%) |  | 75%
|  | 38.533 | 14.4.1.5 | NR SA FR1 Radio Link Monitoring Out-of-sync for PCell configured with CSI-RS-based RLM RS in non-DRX mode for Satellite Access |  | Qualcomm |  | R5-245344 R5-246822 | Editor's Note: This test is incomplete in the following aspects: - MU and TT analysis is incomplete - Message contents may need to be updated | 1 | 75% (+25%) | 75% (+25%) |  | 75%
|  | 38.533 | 14.4.1.6 | NR SA FR1 Radio Link Monitoring In-sync for PCell configured with CSI-RS-based RLM RS in non-DRX mode for Satellite Access |  | Qualcomm |  | R5-245344 R5-246822 | Editor's Note: This test is incomplete in the following aspects: - MU and TT analysis is incomplete - Message contents may need to be updated | 1 | 75% (+25%) | 75% (+25%) |  | 75%
|  | 38.533 | 14.4.1.7 | NR SA FR1 Radio Link Monitoring Out-of-sync for PCell configured with CSI-RS-based RLM RS in DRX mode for Satellite Access |  | Qualcomm |  | R5-245344 R5-246822 | Editor's Note: This test is incomplete in the following aspects: - MU and TT analysis is incomplete - Message contents may need to be updated | 1 | 75% (+25%) | 75% (+25%) |  | 75%
|  | 38.533 | 14.4.1.8 | NR SA FR1 Radio Link Monitoring In-sync for PCell configured with CSI-RS-based RLM RS in DRX mode for Satellite Access |  | Qualcomm |  | R5-245344 R5-246822 | Editor's Note: This test is incomplete in the following aspects: - MU and TT analysis is incomplete - Message contents may need to be updated | 1 | 75% (+25%) | 75% (+25%) |  | 75%
|  | 38.533 | 14.4.2 | Beam Failure Detection and Link recovery procedures for SAN | [5 empty] | 0
| Y | 38.533 | 14.4.2.1 | NR SA FR1 Beam Failure Detection and Link Recovery Test for PCell configured with SSB-based BFD and LR in non-DRX mode for Satellite Access |  | Keysight |  | R5-247879 | Editor’s note: This test tolerance analysis is incomplete. The following aspects are missing: - The accuracy requirement for L1-RSRP are in [ ] in TS 38.133 and not yet finalised - The results of the TT analysis are provisional until the corresponding uncertainty requirement values are agreed | 1 | 95% (+95%) | 95% (+95%) |  | 95%
| Y | 38.533 | 14.4.2.2 | NR SA FR1 Beam Failure Detection and Link Recovery Test for PCell configured with SSB-based BFD and LR in DRX mode for Satellite Access |  | Keysight |  | R5-247880 | Editor’s note: This test tolerance analysis is incomplete. The following aspects are missing: - The accuracy requirement for L1-RSRP are in [ ] in TS 38.133 and not yet finalised - The results of the TT analysis are provisional until the corresponding uncertainty requirement values are agreed | 1 | 95% (+95%) | 95% (+95%) |  | 95%
| Y | 38.533 | 14.4.2.3 | NR SA FR1 Beam Failure Detection and Link Recovery Test for PCell configured with CSI-RS-based BFD and LR in non-DRX mode for Satellite Access |  | Keysight |  | R5-247881 | Editor’s note: This test tolerance analysis is incomplete. The following aspects are missing: - The accuracy requirement for L1-RSRP are in [ ] in TS 38.133 and not yet finalised - The results of the TT analysis are provisional until the corresponding uncertainty requirement values are agreed | 1 | 95% (+95%) | 95% (+95%) |  | 95%
| Y | 38.533 | 14.4.2.4 | NR SA FR1 Beam Failure Detection and Link Recovery Test for PCell configured with CSI-RS-based BFD and LR in DRX mode for Satellite Access |  | Keysight |  | R5-247945 | Editor’s note: This test tolerance analysis is incomplete. The following aspects are missing: - The accuracy requirement for L1-RSRP are in [ ] in TS 38.133 and not yet finalised - The results of the TT analysis are provisional until the corresponding uncertainty requirement values are agreed | 1 | 95% (+95%) | 95% (+95%) |  | 95%
| Y | 38.533 | 14.4.2.5 | NR SA FR1 Beam Failure Detection and Link Recovery Test for SCell configured with CSI-RS-based BFD and SSB-based LR in non-DRX mode for Satellite Access | [5 empty] | 1 | 0% | 0% |  | 0%
| Y | 38.533 | 14.4.2.6 | NR SA FR1 Beam Failure Detection and Link Recovery Test for SCell configured with CSI-RS-based BFD and SSB-based LR in DRX mode for Satellite Access | [5 empty] | 1 | 0% | 0% |  | 0%
|  | 38.533 | 14.4.3 | Active BWP Switch for SAN | [5 empty] | 0
|  | 38.533 | 14.4.3.1 | DCI-based and Timer-based Active BWP Switch | [5 empty] | 0
| Y | 38.533 | 14.4.3.1.1 | NR SA FR1 DCI-based DL active BWP switch with non-DRX for Satellite Access | [5 empty] | 1 | 0% | 0% |  | 0%
|  | 38.533 | 14.4.3.2 | RRC-based Active BWP Switch | [5 empty] | 0
| Y | 38.533 | 14.4.3.2.1 | NR SA FR1 RRC-based DL active BWP switch with non-DRX for Satellite Access | [5 empty] | 1 | 0% | 0% |  | 0%
|  | 38.533 | 14.4.4 | UE specific CBW change for SAN | [5 empty] | 0
| Y | 38.533 | 14.4.4.1 | NR SA FR1 UE specific CBW change on PCell in non-DRX for Satellite Access | [5 empty] | 1 | 0% | 0% |  | 0%
|  | 38.533 | 14.4.5 | Pathloss reference signal switching delay for SAN | [5 empty] | 0
| Y | 38.533 | 14.4.5.1 | NR SA FR1 MAC-CE based pathloss reference signal switch delay for Satellite Access | [5 empty] | 1 | 0% | 0% |  | 0%
|  | 38.533 | 14.5 | Measurement procedure |  | Qualcomm |  | R5-234646 |  | 0
|  | 38.533 | 14.5.1 | Intra-frequency Measurements for SAN |  | Qualcomm |  | R5-234646 |  | 0
| Y | 38.533 | 14.5.1.1 | NR SA FR1 Event-triggered reporting tests without gap under non-DRX for NR satellite access | Required to be tested for UE supporting both TN and NTN | Qualcomm |  | R5-234646 R5-246824 | Editor's Note: - Message contents are FFS - Call setup and test procedure needs to be updated - Several test parameters and configuration are still in brackets | 1 | 85% (+45%) | 85% (+45%) |  | 85%
| Y | 38.533 | 14.5.1.2 | NR SA FR1 Event triggered reporting tests without gap under DRX for NR satellite access | Required to be tested for UE supporting both TN and NTN | Qualcomm |  | R5-234646 R5-246824 | Editor's Note: - Message contents are FFS - Call setup and test procedure needs to be updated - Several test parameters and configuration are still in brackets | 1 | 85% (+45%) | 85% (+45%) |  | 85%
| Y | 38.533 | 14.5.1.3 | NR SA FR1 event triggered reporting tests without gap under non-DRX with FDD PCell with SSB index reading for NR satellite access | Required to be tested for UE supporting both TN and NTN | Qualcomm |  | R5-234646 R5-246824 | Editor's Note: - Message contents are FFS - Call setup and test procedure needs to be updated - Several test parameters and configuration are still in brackets | 1 | 85% (+45%) | 85% (+45%) |  | 85%
| Y | 38.533 | 14.5.1.4 | NR SA FR1 Event-triggered reporting without SSB time index detection when DRX is not used with single gap for satellite access | Required to be tested for UE supporting both TN and NTN | Qualcomm |  | R5-237833 R5-246824 | Editor's Note: - Message contents are FFS - Call setup and test procedure needs to be updated - Several test parameters and configuration are still in brackets | 1 | 85% (+45%) | 85% (+45%) |  | 85%
| Y | 38.533 | 14.5.1.5 | NR SA FR1 Event-triggered reporting without SSB time index detection when DRX is used with two concurrent fully non-overlapped (FNO) gaps for satellite access | Required to be tested for UE supporting both TN and NTN | Qualcomm |  | R5-237833 R5-246824 | Editor's Note: - Message contents are FFS - Call setup and test procedure needs to be updated - Several test parameters and configuration are still in brackets | 1 | 85% (+45%) | 85% (+45%) |  | 85%
| Y | 38.533 | 14.5.1.6 | NR SA FR1 Event-triggered reporting with SSB time index detection when DRX is not used with two concurrent partial overlapping (PPO) gaps for satellite access | Required to be tested for UE supporting both TN and NTN | Qualcomm |  | R5-237833 R5-246824 | Editor's Note: - Message contents are FFS - Call setup and test procedure needs to be updated - Several test parameters and configuration are still in brackets | 1 | 85% (+45%) | 85% (+45%) |  | 85%
|  | 38.533 | 14.5.2 | Inter-frequency Measurements for SAN |  | Qualcomm |  | R5-237688 |  | 0
| Y | 38.533 | 14.5.2.1 | NR SA FR1-FR1 Event-triggered reporting without SSB time index detection when DRX is not used with single gap for satellite access | Required to be tested for UE supporting both TN and NTN | Qualcomm |  | R5-237688 | Editor's Note: - MU and TT analysis is incomplete - Message contents are FFS - Call setup and test procedure needs to be updated - Applicability needs to be updated - Exceptions to connection diagram may need to be updated - Several sections are in brackets - Several test parameters and configuration are still in brackets | 1 | 40% | 40% |  | 40%
| Y | 38.533 | 14.5.2.2 | NR SA FR1-FR1 Event-triggered reporting without SSB time index detection when DRX is used with single gap for satellite access | Required to be tested for UE supporting both TN and NTN | Qualcomm |  | R5-237688 | Editor's Note: - MU and TT analysis is incomplete - Message contents are FFS - Call setup and test procedure needs to be updated - Applicability needs to be updated - Exceptions to connection diagram may need to be updated - Several sections are in brackets - Several test parameters and configuration are still in brackets | 1 | 40% | 40% |  | 40%
| Y | 38.533 | 14.5.2.3 | NR SA FR1-FR1 Event-triggered reporting with SSB time index detection when DRX is not used with single gap for satellite access |  | Qualcomm |  | R5-237688 | Editor's Note: - MU and TT analysis is incomplete - Message contents are FFS - Call setup and test procedure needs to be updated - Applicability needs to be updated - Exceptions to connection diagram may need to be updated - Several sections are in brackets - Several test parameters and configuration are still in brackets | 1 | 40% | 40% |  | 40%
| Y | 38.533 | 14.5.2.4 | NR SA FR1-FR1 Event-triggered reporting without SSB time index detection when DRX is not used with two concurrent fully non-overlapped (FNO) gaps for satellite access |  | Qualcomm |  | R5-237689 | Editor's Note: - MU and TT analysis is incomplete - Message contents are FFS - Call setup and test procedure needs to be updated - Applicability needs to be updated - Exceptions to connection diagram may need to be updated - Several sections are in brackets - Several test parameters and configuration are still in brackets | 1 | 40% | 40% |  | 40%
| Y | 38.533 | 14.5.2.6 | NR SA FR1-FR1 Event-triggered reporting without SSB time index detection when DRX is not used with two concurrent partial overlapping (PPO) gaps for satellite access |  | Qualcomm |  | R5-237689 | Editor's Note: - MU and TT analysis is incomplete - Message contents are FFS - Call setup and test procedure needs to be updated - Applicability needs to be updated - Exceptions to connection diagram may need to be updated - Several sections are in brackets - Several test parameters and configuration are still in brackets - Test requirement is TBD in 38.133 | 1 | 40% | 40% |  | 40%
| Y | 38.533 | 14.5.2.7 | NR SA FR1-FR1 Event triggered reporting without gap under non-DRX for Satellite Access |  | R&S |  |  |  | 1 | 0% | 0% |  | 0%
| Y | 38.533 | 14.5.2.8 | NR SA FR1-FR1 Event triggered reporting without gap under DRX for Satellite Access |  | R&S |  |  |  | 1 | 0% | 0% |  | 0%
|  | 38.533 | 14.5.3 | L1-RSRP measurement for beam reporting for SAN |  | R&S
| Y | 38.533 | 14.5.3.1 | NR SA FR1 SSB based L1-RSRP measurement when DRX is not used for Satellite Access |  | R&S |  | R5-247284 | Editor’s note: This test case is incomplete in following aspects: - MU and TT analysis is incomplete. - Message contents may need to be updated. - Call setup and test procedure are FFS - Applicability needs to be updated. - Test requirements contain parameters in square brackets. | 1 | 20% (+20%) | 20% (+20%) |  | 20%
| Y | 38.533 | 14.5.3.2 | NR SA FR1 SSB based L1-RSRP measurement when DRX is used for Satellite Access |  | R&S |  | R5-247284 | Editor’s note: This test case is incomplete in following aspects: - MU and TT analysis is incomplete. - Message contents may need to be updated. - Call setup and test procedure are FFS - Applicability needs to be updated. - Test requirements contain parameters in square brackets. | 1 | 20% (+20%) | 20% (+20%) |  | 20%
| Y | 38.533 | 14.5.3.3 | NR SA FR1 CSI-RS based L1-RSRP measurement when DRX is not used for Satellite Access |  | R&S |  |  |  | 1 | 0% | 0% |  | 0%
| Y | 38.533 | 14.5.3.4 | NR SA FR1 CSI-RS based L1-RSRP measurement when DRX is used for Satellite Access |  | R&S |  |  |  | 1 | 0% | 0% |  | 0%
|  | 38.533 | 14.6 | Measurement Performance Requirements |  | R&S |  | R5-241269 |  | 0
|  | 38.533 | 14.6.1 | SS-RSRP for SAN |  | R&S |  | R5-245243 |  | 0
| Y | 38.533 | 14.6.1.1 | NR SA FR1 SS-RSRP measurement accuracy for Satellite Access |  | R&S |  | R5-245243 | Editor’s note: This test case is incomplete in following aspects: - MU and TT analysis is incomplete. - Message contents may need to be updated. - Call setup and test procedure may need to be updated. - Applicability needs to be updated. - Test requirements contain parameters in square brackets. | 1 | 30% | 30% |  | 30%
| Y | 38.533 | 14.6.1.2 | NR SA FR1-FR1 SS-RSRP measurement accuracy for Satellite Access |  | R&S |  | R5-245243 | Editor’s note: This test case is incomplete in following aspects: - MU and TT analysis is incomplete. - Message contents may need to be updated. - Call setup and test procedure may need to be updated. - Applicability needs to be updated. - Test requirements contain parameters in square brackets. | 1 | 30% | 30% |  | 30%
|  | 38.533 | 14.6.2 | SS-RSRQ for SAN |  | R&S |  | R5-245244 |  | 0
| Y | 38.533 | 14.6.2.1 | NR SA FR1 SS-RSRQ measurement accuracy for Satellite Access |  | R&S |  | R5-245244 | Editor’s note: This test case is incomplete in following aspects: - MU and TT analysis is incomplete. - Message contents may need to be updated. - Call setup and test procedure may need to be updated. - Applicability needs to be updated. - Test requirements contain parameters in square brackets. | 1 | 30% | 30% |  | 30%
| Y | 38.533 | 14.6.2.2 | NR SA FR1-FR1 SS-RSRQ measurement accuracy for Satellite Access |  | R&S |  | R5-245244 | Editor’s note: This test case is incomplete in following aspects: - MU and TT analysis is incomplete. - Message contents may need to be updated. - Call setup and test procedure may need to be updated. - Applicability needs to be updated. - Test requirements contain parameters in square brackets. | 1 | 30% | 30% |  | 30%
|  | 38.533 | 14.6.3 | SS-SINR for SAN |  | Qualcomm |  | R5-241269 |  | 0
| Y | 38.533 | 14.6.3.1 | NR SA FR1 SS-SINR measurement accuracy for Satellite Access | Required to be tested for UE supporting both TN and NTN | Qualcomm |  | R5-241269 | Editor's Note: - MU and TT analysis is incomplete - Message contents may need to be updated - Call setup and test procedure needs to be updated - Applicability may need to be updated - Exceptions to connection diagram may need to be updated - Several sections are in brackets - Several test parameters and configuration are still in brackets - Annex E and F need to be updated | 1 | 30% | 30% |  | 30%
| Y | 38.533 | 14.6.3.2 | NR SA FR1-FR1 SS-SINR measurement accuracy for Satellite Access | Required to be tested for UE supporting both TN and NTN | Qualcomm |  | R5-241269 | Editor's Note: - MU and TT analysis is incomplete - Message contents may need to be updated - Call setup and test procedure needs to be updated - Applicability may need to be updated - Exceptions to connection diagram may need to be updated - Several sections are in brackets - Several test parameters and configuration are still in brackets - Annex E and F need to be updated | 1 | 30% | 30% |  | 30%
|  | 38.533 | 14.6.4 | L1-RSRP measurement for beam reporting for SAN |  | Qualcomm |  | R5-243362 |  | 0
| Y | 38.533 | 14.6.4.1 | NR SA FR1 SSB based L1-RSRP measurement accuracy for Satellite Access | Required to be tested for UE supporting both TN and NTN | Qualcomm |  | R5-243362 | Editor's Note: - MU and TT analysis is incomplete - Message contents may need to be updated - Call setup and test procedure needs to be updated - Applicability may need to be updated - Several test parameters and configuration are still in brackets - Annex E and F need to be updated | 1 | 55% | 55% |  | 55%
| Y | 38.533 | 14.6.4.2 | NR SA FR1 CSI-RS based L1-RSRP measurement accuracy on resource set with repetition off for Satellite Access | Required to be tested for UE supporting both TN and NTN | Qualcomm |  | R5-243362 | Editor's Note: - MU and TT analysis is incomplete - Message contents may need to be updated - Call setup and test procedure needs to be updated - Applicability may need to be updated - Several test parameters and configuration are still in brackets - Annex E and F need to be updated | 1 | 55% | 55% |  | 55%
|  | 38.533 | Annex A | RRM test configurations; Satellite access configuration |  | Qualcomm, Keysight |  | R5-234647 R5-237865 |  | 1 | 100% | 100% |  | 100%
|  | 38.533 | Annex B | Conditions for RRM requirements applicability for operating bands; Satellite access, High level test procedure for SAN RRM tests |  | Qualcomm, Keysight |  | R5-234647 R5-237866 |  | 1 | 100% | 100% |  | 100%
|  | 38.533 | Annex E | Cell configuration mapping |  | Qualcomm |  | R5-245346 |  | 1 | 100% | 100% |  | 100%
|  | 38.533 | Annex F | Measurement uncertainties and test tolerances |  | Qualcomm, Keysight |  | R5-246823 R5-247882 |  | 1 | 25% (+25%) | 25% (+25%) |  | 25%
TS 38.523-1: Protocol test cases
Idle Mode
|  | 38.523-1 | 6.1 | [7 empty] | 0% | 0% |  | 0%
|  | 38.523-1 | 6.7.1 | NTN idle mode operations
| Y | 38.523-1 | 6.7.1.5 | NR NTN / Cell reselection, Sintrasearch, Snonintrasearch / location based measurements | (1) with { UE supporting location-based measurements in NR RRC_IDLE state on a cell which provides access by NR NTN } ensure that { when { Sintrasearch is non-zero in system information and distance between UE and the serving cell reference location referenceLocation is larger than distanceThresh } then { UE performs measurement and reselects the highest ranked cell upon Srxlev < Sintrasearch } } (2) with { UE supporting location-based measurements in NR RRC_IDLE state on a cell which provides access by NR NTN } ensure that { when { Snonintrasearch is non-zero in system information and distance between UE and the serving cell reference location referenceLocation is larger than distanceThresh } then { UE performs measurement and reselects the cell which belong to the equal priority frequency upon Srxlev < Snonintrasearch } } | Qualcomm | RAN5#103 (May-24) | R5-243562, R5-247591 | TS 38.304 clauses: 5.2.4.2, 5.3.1, 5.2.4.7.0, 5.2.4.9.0 | 1 | 100% | 100% |  | 100%
| Y | 38.523-1 | 6.7.1.6 | NR NTN / Cell reselection, Sintrasearch, Snonintrasearch / time based measurements | (1) with { UE supporting time-based measurements in NR RRC_IDLE state on a cell which provides access by NR NTN } ensure that { when { t-Service of the serving cell is present in SIB19 } then { UE performs measurement and reselects the highest ranked intra-frequency cell } } (2) with { UE supporting time-based measurements in NR RRC_IDLE state on a cell which provides access by NR NTN } ensure that { when { t-Service of the serving cell is present in SIB19 } then { UE performs measurement and reselects the highest ranked inter-frequency cell } } | Qualcomm | RAN5#103 (May-24) | R5-243563, R5-247591 | TS 38.304 clauses: 5.2.4.2, 5.3.1, 5.2.4.7.0, 5.2.4.9.0 | 1 | 100% | 100% |  | 100%
|  | 38.523-1 | 6.7.2 | NTN in RRC_INACTIVE state
| Y | 38.523-1 | 6.7.2.1 | NR NTN / Cell reselection, Sintrasearch, Snonintrasearch in RRC_Inactive state / location based measurements | (1) with { UE supporting location-based measurements in NR RRC_INACTIVE state on a cell which provides access by NR NTN } ensure that { when { Sintrasearch is non-zero in system information and distance between UE and the serving cell reference location referenceLocation is larger than distanceThresh } then { UE performs measurement and reselects the highest ranked cell upon Srxlev < Sintrasearch } } (2) with { UE supporting location-based measurements in NR RRC_INACTIVE state on a cell which provides access by NR NTN } ensure that { when { Snonintrasearch is non-zero in system information and distance between UE and the serving cell reference location referenceLocation is larger than distanceThresh } then { UE performs measurement and reselects the cell which belong to the equal priority frequency upon Srxlev < Snonintrasearch } } | Qualcomm | RAN5#104 (Aug-24) | R5-245118, R5-247591 | TS 38.304 clauses: 5.2.4.2, 5.3.1, 5.2.4.7.0, 5.2.4.9.0 | 1 | 100% | 100% |  | 100%
| Y | 38.523-1 | 6.7.2.2 | NR NTN / Cell reselection, Sintrasearch, Snonintrasearch in RRC_Inactive state / time based measurements | (1) with { UE supporting time-based measurements in NR RRC_INACTIVE state on a cell which provides access by NR NTN } ensure that { when { t-Service of the serving cell is present in SIB19 } then { UE performs measurement and reselects the highest ranked intra-frequency cell } } (2) with { UE supporting time-based measurements in NR RRC_INACTIVE state on a cell which provides access by NR NTN } ensure that { when { t-Service of the serving cell is present in SIB19 } then { UE performs measurement and reselects the highest ranked inter-frequency cell } } | Qualcomm | RAN5#104 (Aug-24) | R5-245121, R5-247591 | TS 38.304 clauses: 5.2.4.2, 5.3.1, 5.2.4.7.0, 5.2.4.9.0 | 1 | 100% | 100% |  | 100%
28 | Y | 38.523-1 | 6.7.1.1 | NR NTN / Cell Selection / GNSS location / NTN | (1) with { UE in 5GMM-DEREGISTERED/RRC-IDLE and UE finds a cell which provides access by NR NTN RAT } ensure that { when { UE has no valid GNSS position } then { UE shall not establish RRC connection to perform a Registration procedure } } (2) with { UE in 5GMM-DEREGISTERED/RRC-IDLE and UE finds a cell which provides access by NR NTN } ensure that { when { Cell broadcasts SIB19 and UE has a valid GNSS position } then { UE establishes RRC connection and successfully performs Registration procedure } | Qualcomm Huawei | RAN5#100 (Aug-23) | R5-235338 R5-237389 | TS38.306 clauses 16.14.1, 16.14.2.1 and 16.14.5, TS 38.331 clauses 5.2.2.3.1, 5.2.2.4.1, 5.2.2.4.21, 5.2.2.5 and 5.2.2.6. | 1 | 100% | 100% |  | 100%
29 | Y | 38.523-1 | 6.7.1.2 | NR NTN / Cell Selection / MultiTAC / NTN / trackingAreaList-r17 | (1) with { UE in NR RRC_IDLE and UE finds a suitable cell which provides access by NR NTN RAT } ensure that { when { SIB1 broadcast more than one TAC per PLMN } then { UE forwards the trackingAreaList to upper layers for mobility management procedure and reselects the cell} } | Qualcomm | RAN5#103 (May-24) | R5-235337, R5-243560, R5-247592 | TS38.306 clauses 5.2.2.4.1, and 5.2.2.4.2. | 1 | 100% | 100% |  | 100%
64 | Y | 38.523-1 | 6.7.1.3 | NR NTN / Cell Selection / Serving cell becomes non-suitable (CellBarredNTN) | (1) with { UE in NR RRC_IDLE state } ensure that { when { UE finds a suitable cell that provides access by NR NTN RAT and cellBarredNTN in SIB1 is not present } then { the UE considers the cell as barred and no camping on this cell can take place } (2) with { UE in NR RRC_IDLE state } ensure that { when { UE finds a suitable cell that provides access by NR NTN RAT and cellBarredNTN in SIB1 is “not barred” } then { the UE considers the cell suitable and camps on it } (3) with { UE in NR RRC_IDLE state } ensure that { when { UE finds a suitable cell that provides access by NR NTN RAT and cellBarredNTN in SIB1 changes to “barred” } then { the UE considers the cell as barred and no camping on this cell can take place } | Qualcomm | RAN5#101 (Nov-23) | R5-237432 | TS 38.304, clause 5.3.1 | 1 | 100% | 100% |  | 100%
| Y | 38.523-1 | 6.7.1.4 | NR -NTN / PLMN selection / Periodic reselection / MinimumPeriodicSearchTimer test case | with { UE configured with “MinimumPeriodicSearchTimer“ and camped on an VPLMN cell} ensure that { when {Cells of a higher priority PLMN available, the higher priority PLMN search timer T stored in the USIM } then { T shall be set to the MinimumPeriodicSearchTimer. After the first attempt to the higher priority PLMN cell is made, the UE shall not use a value for T that is less than the MinimumPeriodicSearchTimer. When the T expires the UE selects and camps on a cell of the highest priority PLMN and UE attempts a location registration on the selected cell and when successfully registered indicates the selected PLMN to the user } } | Qualcomm | RAN5#103 (May-24) | R5-241566 R5-245561 | 23.122 Cl 4.4.3.3.1 | 1 | 100% | 100% |  | 100%
MAC
17 |  | 38.523-1 | 7.1 | NR Layer 2 | [5 empty] | 0 | 0% | 0% |  | 0%
18 |  | 38.523-1 | 7.1.1 | MAC | [5 empty] | 0 | 0% | 0% |  | 0%
26 | Y | 38.523-1 | 7.1.1.5.6 | NR NTN / DRX operation / Short cycle not configured / HARQ RTT | (1) with { UE in RRC_CONNECTED state with long DRX cycle configured and the corresponding HARQ process is configured with HARQ feedback enabled } ensure that { when { HARQ-RTT-TimerDL-NTN expires in the PDCCH Occasion and the data in the soft buffer of the corresponding HARQ process was not successfully decoded } then { UE starts the drx-RetransmissionTimerDL for the corresponding HARQ process in the first symbol after the expiry of HARQ-RTT-TimerDL-NTN } } (2) with { UE in RRC_CONNECTED state with long DRX cycle configured and the corresponding HARQ process is configured as HARQModeA } ensure that { when { HARQ-RTT-TimerUL-NTN expires in the PDCCH Occasion } then { UE starts the drx-RetransmissionTimerUL for the corresponding HARQ process in the first symbol after the expiry of HARQ-RTT-TimerUL-NTN } } | Qualcomm | RAN5#103 (May-24) | R5-242769 R5-244667, R5-246622, R5-247595 | 38.321, clauses 5.7 | 1 | 100% | 100% |  | 100%
| Y | 38.523-1 | 7.1.1.5.10 | NR NTN / DRX operation / Short cycle not configured / Correct HARQ process handling / HARQ feedback disabled / HARQ modeB |  | Qualcomm | RAN5#104 (Aug-24) | R5-245562, R5-247596 |  | 1 | 100% | 100% |  | 100%
22 | Y | 38.523-1 | 7.1.1.10.4 | NR NTN / UE specific TA report / UE specific Koffset | (1) with { UE in RRC_IDLE state on a cell which provides access by NR NTN and ta-Report-r17 is configured with value enabled in SIB19 } ensure that { when { UE initiates the Random Access procedure } then { UE performs the Timing Advance reporting procedure } } (2) with { UE in RRC_IDLE state on a cell which provides access by NR NTN and ta-Report-r17 is not configured in SIB19 } ensure that { when { offsetThresholdTA-r17 is received in rrcSetup message } then { UE performs the Timing Advance reporting procedure } } | Qualcomm | RAN5#103 (May-24) | R5-242757 | TS 38.321, clauses 5.4.8, 6.1.3.56 and TS 38.331, clauses 5.3.3.3, 6.3.2 | 1 | 100% | 100% |  | 100%
RLC
| Y | 38.523-1 | 7.1.2.2.5a | NR NTN / UM RLC / t-Reassembly expiry / t-ReassemblyExt-r17 configured | (1) with { UE in RRC_CONNECTED state on a cell which provides access by NR NTN and using UM RLC } ensure that { when { t-ReassemblyExt-r17 is configured expires } then { UE updates RX_Next_Reassembly and discards all segments with SN < updated RX_Next_Reassembly considering the value signalled in t-ReassemblyExt-r17 and ignores t-Reassembly } } | Qualcomm | RAN5#102 (Feb-24) | R5-244421 | TS 38.322, clauses 5.2.2.2.1, 5.2.2.2.3, 5.2.2.2.4, 7.1 and TS 38.331, clause 6.3.2 | 1 | 100% | 100% |  | 100%
| Y | 38.523-1 | 7.1.2.3.9a | NR NTN / AM RLC / t-Reassembly expiry / t-ReassemblyExt-r17 configured | (1) with { UE in RRC_CONNECTED state on a cell which provides access by NR NTN and using AM RLC } ensure that { when { t-ReassemblyExt-r17 is configured expires } then { UE updates RX_Highest_Status to the SN of the first RLC SDU with SN >= RX_Next_Status_Trigger for which not all bytes have been received considering the value signalled in t-ReassemblyExt-r17 and ignores t-Reassembly } } | Qualcomm | RAN5#103 (May-24) | R5-243564 | TS 38.322, clauses 5.2.2.2.1, 5.2.2.2.3, 5.2.2.2.4, 7.1 and TS 38.331, clause 6.3.2 | 1 | 100% | 100% |  | 100%
PDCP
| Y | 38.523-1 | 7.1.3.5.1a | NR NTN / PDCP Discard / discardTimerExt2 configured | (1) with { UE in RRC_CONNECTED state on a cell which provides access by NR NTN } ensure that { when { discardTimerExt2 is configured } then { UE discards the PDCP SDU considering value signalled in discardTimerExt2 and ignores discardTimer } } | Qualcomm | RAN5#102 (Feb-24) | R5-241571 | TS 38.323, clause 5.3, 7.1, 6.3.5, 7.3 and TS 38.331, clause 6.3.2. | 1 | 100% | 100% |  | 100%
RRC
4 |  | 38.523-1 | 8.1 | NR RRC | Existing sub-clause header |  |  |  |  | 0 | 0% | 0% |  | 0%
|  |  | 8.1.3 | Measurement configuration control and reporting | [5 empty] | 0 | 0% | 0% |  | 0%
9 | Y | 38.523-1 | 8.1.3.1.26 | NR NTN / Measurement configuration control and reporting / Event D1 / Measurement of Neighbour NR cell | (1) with { UE in NR RRC_CONNECTED and measurement configured for event D1 with event based periodical reporting } ensure that { when { Entering condition for event D1 is satisfied } then { UE sends MeasurementReport message at regular intervals while entering condition for event D1 is satisfied } } (2) with { { UE in NR RRC_CONNECTED and measurement configured for event D1 with event based periodical reporting } ensure that { when { Leaving condition for event D1 is satisfied } then { UE stops sending MeasurementReport message } | Qualcomm | RAN5#102 (Feb-24) | R5-242134 | TS 38.331 5.5.4.15; 5.5.4.1 | 1 | 80% | 80% |  | 80%
|  | 38.523-1 | 8.1.4.4 | Conditional handover
30 | Y | 38.523-1 | 8.1.4.4.5 | NR NTN / Conditional handover / Success / CondEventA4 | (1) with { UE in NR RRC_CONNECTED state and supporting conditional handover and receiving an RRCReconfiguration message including ConditionalReconfiguration } ensure that { when { any CHO execution condition is not satisfied } then { UE maintains connection with source gNB and starts evaluating the CHO execution conditions for the candidate cell(s) } } (2) with { UE in NR RRC_CONNECTED state and supporting conditional handover and supporting event A4 based conditional handover } ensure that { when { UE receives an RRCReconfiguration message including ConditionalReconfiguration and condEvent A4 is configured as conditional handover trigger event } then { UE starts evaluating the CHO execution condition A4 and perform conditional handover to the neighbour cell triggered in conditional configuration execution } } | Qualcomm | RAN5#103 (May-24) | R5-243598 R5-245566, R5-247593 | TS 38.331 5.3.5.13.1; 5.3.5.13.4 | 1 | 100% | 100% |  | 100%
31 | Y | 38.523-1 | 8.1.4.4.6 | NR NTN / Conditional handover / Success / CondEventT1 | (1) with { UE in NR RRC_CONNECTED state and supporting time based conditional handover and receiving an RRCReconfiguration message including ConditionalReconfiguration } ensure that { when { any CHO execution condition is not satisfied } then { UE maintains connection with source gNB and starts evaluating the CHO execution conditions for the candidate cell(s) } } (2) with { UE in NR RRC_CONNECTED state and supporting conditional handover and supporting time based conditional handover } ensure that { when { UE receives an RRCReconfiguration message including ConditionalReconfiguration and condEvent T1 is configured as conditional handover trigger event } then { UE starts evaluating the CHO execution condition T1 and perform conditional handover to the neighbour cell triggered in conditional configuration execution } } (3) with { UE in NR RRC_CONNECTED state and supporting time based conditional handover } ensure that { when { UE perform conditional handover procedure successfully } then { UE releases stored CHO configurations } } | Qualcomm | RAN5#103 (May-24) | R5-243599 R5-244302, R5-247594 | TS 38.331 5.3.5.13.1; 5.3.5.13.4 | 1 | 90% | 90% |  | 90%
| Y | 38.523-1 | 8.1.4.4.7 | NR NTN / Conditional handover / Success / CondEventD1 | (1) with { UE in NR RRC_CONNECTED state and supporting location based conditional handover and receiving an RRCReconfiguration message including ConditionalReconfiguration } ensure that { when { conditional handover execution condition is not satisfied } then { UE maintains connection with source gNB and starts evaluating the CHO execution conditions for the candidate cell(s) } } (2) with { UE in NR RRC_CONNECTED state and supporting location based conditional handover } ensure that { when { UE receives an RRCReconfiguration message including ConditionalReconfiguration and condEvent D1 is configured as conditional handover trigger event } then { UE starts evaluating the conditional handover execution conditionand perform conditional handover to the neighbour cell triggered in conditional configuration execution } } (3) with { UE in NR RRC_CONNECTED state and supporting location based conditional handover } ensure that { when { UE perform conditional handover procedure successfully } then { UE releases stored CHO configurations } } | Qualcomm | RAN5#103 (May-24) | R5-243561 R5-244303 | TS 38.331 5.3.5.13.1; 5.3.5.13.4 | 1 | 90% | 90% |  | 90%
5 |  | 38.523-1 | 8.1.5 | RRC others | Existing sub-clause header |  |  |  |  | 0 | 0% | 0% |  | 0%
11 |  | 38.523-1 | 8.1.5.1 | UE capability transfer | Existing sub-clause header |  |  |  |  | 0 | 0% | 0% |  | 0%
6 |  | 38.523-1 | 8.1.5.x.x | [6 empty] | 0 | 0% | 0% |  | 0%
|  | 38.523-1 | 8.1.5.14 | NTN Other RRC Topics
7 | Y | 38.523-1 | 8.1.5.14.1 | NR NTN / SIB19 / T430 with the timer value set to ntn-UlSyncValidityDuration / T430 Expiry | (1) with { UE has acquired SIB19 and in RRC_CONNECTED state and starts timer T430 with ntn-UlSyncValidityDuration } ensure that { when { T430 expires in RRC_CONNECTED state } then { UE informs lower layers that the UL synchronization is lost and initiates the UL synchronization restoration procedure } } | Qualcomm | RAN5#103 (May-24) | R5-243559 |  | 1 | 100% | 100% |  | 100%
NAS
4 |  | 38.523-1 | 9.4 | Non-Terrestrial Network | (New) sub-clause header |  |  |  |  | 0 | 0% | 0% |  | 0%
5 |  | 38.523-1 | 9.4.1 | 5GS mobility management for Non-Terrestrial Network | (New) sub-clause header |  |  |  |  | 0 | 0% | 0% |  | 0%
11 | Y | 38.523-1 | 9.4.1.1 | NR NTN / GNSS position reporting / reject cause #78 "PLMN not allowed to operate at the present UE location" | (1) with { UE has sent an REGISTRATION REQUEST message } ensure that { when { UE receives an REGISTRATION REJECT message with the reject cause #78 set to "PLMN not allowed to operate at the present UE location" } then { UE sets the 5GS update status to 5U3 ROAMING NOT ALLOWED, UE deletes the 5G-GUTI, last visited registered TAI, TAI list and ngKSI, UE resets the registration attempt counter, UE enters the state 5GMM-DEREGISTERED.PLMN-SEARCH and perform a PLMN selection } } | Qualcomm | RAN5#103 (May-24) | R5-237387, R5-241567, R5-243556, R5-243560, R5-244411 | TS 23.122 clause 3.1, TS 24.501, clauses 4.23.2, 5.5.1.2.5, 5.4.5.3.2, 5.4.5.3.3, 5.1.3.2.2 | 1 | 100% | 100% |  | 100%
| Y | 38.523-1 | 9.4.1.2 | NR NTN / Mobility registration update / supported TACs not part of UE registration area | with { UE in NR RRC_IDLE and UE finds a suitable cell which provides access by NR NTN RAT } ensure that { when { SIB1 broadcast more than one TAC per PLMN } then { UE forwards the trackingAreaList to upper layers for mobility management procedure and reselects the cell} } | Qualcomm | RAN5#103 (May-24) | R5-241568, R5-243557, R5-243560 | 23.501 Cl 5.4.11.6 Similar to Refer to 22.2.13 | 1 | 100% | 100% |  | 100%
| Y | 38.523-1 | 9.4.1.3 | NR NTN / TAI(s) not allowed / forbidden TAI(s) in the Registration Accept message | with { UE in NR RRC_IDLE and UE finds a suitable cell which provides access by NR NTN RAT } ensure that{ When{the UE receive the broadcast TAI(s) from the NG-RAN} Then {The UE stores the TAI(s) in the appropriate Forbidden Area list and removes the TAI(s) from Registration Area if present.} } | Qualcomm | RAN5#103 (May-24) | R5-243558 | 23.501, Cl 5.4.11.8 | 1 | 100% | 100% |  | 100%
Session management
|  | 38.523-1 | 10.5 | NR NTN Session Management
Multi-layer and Services
|  | 38.523-1 | 11.9 | Multi-layer and Services
TS 38.523-2: Applicability for Protocol test cases
23 |  | 38.523-2 | 4.1, 4.2 | Add test case applicability statements for the new test cases introduced in 38.523-1 |  | Qualcomm | RAN5#102 (Feb-24) | R5-235339, R5-235419, R5-236584, R5-243565, R5-242766, R5-245563, R5-247597 |  | 0.1 | 40% | 40% |  | 40%
TS 38.523-3: Protocol test suites (TTCN)
24 |  | 38.523-3 | NA | Introduction of General and Signaling Test Environment for NR-NTN |  |  | RAN5#99 (May-23) | R5-242320, R5-244422 |  | 0 | 80% | 80% |  | 80%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.