## R5#103
3GPP TSG RAN WG5 (RAN5) Meeting #103 | [9 empty] | R5-242114 (Draft v1)
Fukuoka, Japan, 20 - 24 May 2024
WI Progress and Target Completion Date Review
Source: RAN5 Chair
To: RAN5
Purpose: For Endorsement
UIC | WI Name | Rel | Tdoc# | Pre TCD | pre % | post % | post TCD | change (mths) | Rapporteur | other comments
830083 | UE Conformance Test Aspects - Rel-16 NR CA and DC; and NR and LTE DC Configurations | Rel-16 | R5-243039 | 2024-06-01 | 52% | 52% | 2024-12-01 | +6 | CMCC
880069 | UE Conformance Test Aspects - 5G V2X with NR sidelink | Rel-16 | R5-243098 | 2024-06-01 | 65% | 68% | 2024-12-01 | +6 | Huawei | A.I. ref
900056 | UE Conformance - Rel-17 NR CA and DC; and NR and LTE DC Configurations | Rel-17 | R5-243196 | 2024-12-01 | 11% | 11% | 2024-12-01 |  | Huawei
911003 | UE Conformance Test Aspects - NR-based access to unlicensed spectrum | Rel-16 | R5-243425 | 2024-06-01 | 70% | 79% | 2024-12-01 | +6 | Qualcomm | +6 RP
930051 | UE Conformance - Power Class 2 for EN-DC with x LTE bands + y NR band(s) in DL and with 1 LTE band +1 TDD NR band in UL (either x= 2, 3, y=1 or x=1, 2, y=2) | Rel-17 | R5-242627 | 2024-06-01 | 6% | 6% | 2024-09-01 | +3 | Ericsson | A.I.
950062 | UE Conformance - Introduction of FR2 FWA (Fixed Wireless Access) UE with maximum TRP (Total Radiated Power) of 23dBm for band n257 and n258 | Rel-17 | R5-243192 | 2024-12-01 | 33% | 49% | 2024-12-01 |  | Huawei | RAN5#102
960072 | UE Conformance - NR small data transmissions in INACTIVE state | Rel-17 | R5-242554 | 2024-06-01 | 95% | 98% | 2024-12-01 | +6 | Qualcomm | A.I.
960074 | UE Conformance - Solutions for NR to support non-terrestrial networks (NTN) | Rel-17 | R5-243427 | 2024-06-01 | 70% | 78% | 2024-12-01 | +6 | Qualcomm | +6 RP
960075 | UE Conformance - Further enhancement on NR demodulation performance | Rel-17 | R5-242437 | 2024-06-01 | 82% | 93% | 2024-09-01 | +3 | China Telecom | A.I.
960076 | UE Conformance - Enhancement of Private Network Support for NG-RAN including CT aspects | Rel-17 | R5-242686 | 2024-06-01 | 63% | 96% | 2024-09-01 | +3 | China Telecom | +
960079 | UE Conformance - Further enhancements on MIMO for NR | Rel-17 | R5-242665 | 2024-06-01 | 67% | 92% | 2024-12-01 |  | Samsung | Nov. RP#104
960080 | UE Conformance - NR support for high speed train scenario in frequency range 2 | Rel-17 | R5-242667 | 2024-06-01 | 44% | 60% | 2024-12-01 |  | Samsung | Nov. RP#104
960083 | UE Conformance - NR Sidelink Relay | Rel-17 | R5-242840 | 2024-09-01 | 25% | 30% | 2024-09-01 |  | CATT
960084 | UE Conformance - NR Sidelink enhancement | Rel-17 | R5-242838 | 2024-09-01 | 5% | 5% | 2024-09-01 |  | CATT
960089 | UE Conformance Test Aspects - NR RRM enhancement | Rel-16 | R5-243262 | 2024-06-01 | 65% | 70% | 2024-12-01 |  | Apple | Dec-24
970072 | UE Conformance - NR QoE management and optimizations for diverse services | Rel-17 | R5-242404 | 2024-09-01 | 20% | 20% | 2024-09-01 |  | Ericsson | A.I.
970075 | UE Conformance - NR Positioning Enhancements | Rel-17 | R5-242238 | 2024-06-01 | 38% | 56% | 2024-12-01 | +6 | CATT
970077 | Conformance Test Aspects - Protocol enhancements for Mission Critical Services for Rel-16 (MCPTT, MCVideo, MCData) | Rel-16 | R5-243265 | 2024-09-01 | 67% | 82% | 2024-09-01 |  | NIST
981035 | UE Conformance - NR and MR-DC measurement gap enhancements | Rel-17 | R5-242190 | 2024-06-01 | 95% | 100% | 2024-06-01 |  | MediaTek
991033 | UE Conformance - Further Multi-RAT Dual-Connectivity enhancement | Rel-17 | R5-242848 | 2024-06-01 | 94% | 100% | 2024-06-01 |  | Huawei
991034 | UE Conformance - Support of Uncrewed Aerial Systems Connectivity, Identification, and Tracking | Rel-17 | R5-242553 | 2024-12-01 | 95% | 100% | 2024-12-01 |  | Qualcomm | A.I.
1000050 | UE Conformance - Additional NR bands for UL-MIMO in Rel-18 | Rel-18 | R5-243306 | 2024-12-01 | 49% | 49% | 2024-12-01 |  | China Unicom | A.I.
1000051 | UE Conformance - High power UE (power class 2) for NR FR1 FDD single band | Rel-18 | R5-243308 | 2024-12-01 | 12% | 12% | 2024-12-01 |  | China Unicom | 3GPP A.I.
1000052 | UE Conformance - IMS voice service support and network usability guarantee for UE’s E-UTRA capability disabled scenario in 5GS | Rel-17 | R5-242457 | 2024-06-01 | 74% | 100% | 2024-06-01 |  | China Telecom
1000053 | UE Conformance - High power UE (power class 1.5) for NR FR1 TDD single band | Rel-18 | R5-243063 | 2025-06-01 | 66% | 100% | 2025-06-01 |  | CMCC | -12?
1000054 | UE Conformance - Rel-18 High Power UE for NR CA and DC; and NR and LTE DC Configurations | Rel-18 | R5-242688 | 2025-06-01 | 40% | 55% | 2025-06-01 |  | China Telecom
1000055 | UE Conformance - IMS Data Channel | Rel-17 | R5-242747 | 2024-09-01 | 8% | 8% | 2024-09-01 |  | Huawei
1000056 | UE Conformance - UE Conformance - Rel-17 Power Class 2 UE for NR inter-band CA/DC with or without SUL configurations with x (6>=x>2) bands DL and y (y=1, 2) bands UL | Rel-17 | R5-243194 | 2025-06-01 | 9% | 9% | 2025-06-01 |  | Huawei | RAN5#102
1000057 | UE Conformance - Rel-18 NR CA and DC; and NR and LTE DC Configurations | Rel-18 | R5-243162 | 2025-06-01 | 5% | 5% | 2025-06-01 |  | Huawei
1000058 | UE Conformance - New Rel-18 NR licensed bands and extension of existing NR bands | Rel-18 | R5-243198 | 2025-06-01 | 5% | 12% | 2025-06-01 |  | Huawei
1000059 | UE Conformance - High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands in Rel-18 | Rel-18 | R5-242377 | 2024-06-01 | 18% | 26% | 2024-12-01 | +6 | Nokia | +month
1010050 | UE Conformance - Access Traffic Steering, Switch and Splitting support in the 5G system architecture; Phase 2 | Rel-17 | R5-242459 | 2024-09-01 | 36% | 100% | 2024-06-01 |  | China Telecom
1010051 | UE Conformance - Rel-17 LTE CA Configurations | Rel-17 | R5-242690 | 2024-12-01 | 30% | 50% | 2024-12-01 |  | China Telecom | RP
1020087 | UE Conformance - Air-to-ground network for NR | Rel-18 | R5-243034 | 2025-06-01 | 50% | 50% | 2025-06-01 |  | CMCC | Core part Perf part
1020088 | UE Conformance - 4Rx handheld UE for low NR bands (<1GHz) and/or 3Tx for NR inter-band UL Carrier Aggregation (CA) and EN-DC | Rel-18 | R5-242850 | 2025-06-01 | 7% | 26% | 2025-06-01 |  | Huawei
1030060 | UE Conformance - NR support for dedicated spectrum less than 5MHz for FR1 | Rel-18 | R5-242616 | 2025-12-01 |  | 22% | 2025-12-01 |  | Nokia
1030061 | UE Conformance - Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR | Rel-18 | R5-242455 | 2025-06-01 |  | 5% | 2025-06-01 |  | China Telecom
1030062 | UE Conformance - Enhanced support of reduced capability NR devices plus CT1 | Rel-18 | R5-243277 | 2025-12-01 |  | 5% | 2025-12-01 |  | China Unicom | A.I.
1030063 | UE Conformance - XR (eXtended Reality) enhancements for NR plus CT1 aspects | Rel-18 | R5-243180 | 2025-12-01 |  | 5% | 2025-12-01 |  | Nokia
1030064 | UE Conformance - Introduction of 900 MHz LTE band in the US | Rel-18 | R5-242383 | 2025-03-01 |  | 85% | 2025-03-01 |  | Nokia
1030065 | UE Conformance - NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 | Rel-18 | R5-243405 | 2025-03-01 |  | 5% | 2025-03-01 |  | Apple | A.I.
1030066 | UE Conformance - Further RF requirements enhancement for NR and EN-DC in frequency range 1 | Rel-18 | R5-243200 | 2025-06-01 |  | 5% | 2025-06-01 |  | Huawei
1030067 | UE Conformance - Network energy savings for NR | Rel-18 | R5-242852 | 2025-12-01 |  | 5% | 2025-12-01 |  | Huawei
1030068 | UE Conformance - Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18 | Rel-18 | R5-242854 | 2025-06-01 |  | 58% | 2025-06-01 |  | Huawei
1030069 | UE Conformance - Further NR coverage enhancements | Rel-18 | R5-242836 | 2025-12-01 |  | 5% | 2025-12-01 |  | China Telecom
1030070 | UE Conformance - Multi-carrier enhancements for NR | Rel-18 | R5-242843 | 2025-12-01 |  | 18% | 2025-12-01 |  | China Telecom
1030071 | UE Conformance - Enhanced NR support for high speed train scenario in frequency range 2 (FR2) | Rel-18 | R5-243082 | 2025-12-01 |  | 5% | 2025-12-01 |  | Samsung
1030072 | UE Conformance - NR MIMO evolution for downlink and uplink | Rel-18 | R5-243083 | 2025-12-01 |  | 5% | 2025-12-01 |  | Samsung
1030073 | UE Conformance - IoT (Internet of Things) NTN (non-terrestrial network) enhancements plus CT1 aspects | Rel-18 | R5-243054 | 2025-12-01 |  | 16% | 2025-12-01 |  | CMCC