## Slide 1
Puneet Jain
TSG SA Chair
SA Rel-20 5G-Advanced Content Definition Process

## Slide 2
Rel-20 (5G-Advanced)
  For 5G-Advanced: 18-month. Assuming no delay of Rel-19
    Stage-1 freeze : Jun 2025
    Stage-2 freeze : Jun 2026 (>=80%); Sep 2026 (100%)
    Stage-3 freeze : Mar 2027
    ASN.1/OpenAPI freeze: June 2027
Release 20: 5G-Advanced Timeline
2024
#103
Mar.
#111
Mar.
#107
Mar.
#104
Jun.
#108
Jun.
#112
Jun.
#105
Sep.
#109
Sep.
#102
Dec.
#106
Dec.
#110
Dec.
TSGs
SA1 5GA SID definition
100%
SA1 5GA Studies + Norm 80%
100%
St. 2 (SA2, SA6, …) 5GA St.+Norm 80%
Stage 3 5GA St + Norm
#113
Sep.
#114
Dec.
#115
Mar.
Jun
RAN1
RAN Completion (RAN2/3/4core)
#116
RAN4 C.def.
RAN4 Perf
RP Content def.
Rel-20 - 5GA part
2025
2026
2027
5GA ASN.1 & Open APIs
St.2 SID def. TBD
St.3 SID def. TBD
Workshop 5GA SA

## Slide 3: Rel-20 5G-Advaced Content Definition Process
TSG #107
TSG #108
TSG #109
TSG #110
TSG #111
TSG #112
TSG #113
TSG #114
TSG #115
TSG #116
TSG #117
TSG #118
TSG #105
2026
2027
Mar.
Sep.
Sep.
Sep.
Dec.
Dec.
Dec.
Mar.
Mar.
Jun.
Jun.
Jun.
Jun.
Stage-3 (CT & SA)
Stage-2 Study/Work Phase
Rel-20 5GA Content Approval
Rel-20 5GA
Workshop
TSG #106
Dec.
2025
Now
100%
SA1 Stage-1 80%
ASN.1 / Open API
Stage-1 Freeze
Selected Rel-20 SID/WID Approval
Rel-20 Final Package Approval
Stage-2 Freeze
Stage-3 Freeze
Rel-20 5GA complete
MED
Moderated Email Discussions
MED
WG starts working on Rel-20 SID/WID approved at SA#107
Rel-20 Scope Discussion / Guidance to WG
2024
ASN.1 / Open API
Stage-2 80% Complete

## Slide 4: SA Rel-20 5GA Content Definition steps
Discussion and Guidance for Rel-20 5GA Scope: The content proposals for Rel-20 5GA will be discussed during the SA Rel-20 5GA Workshop, and overall guidance will be provided to the SA WGs on Rel-20 5GA topics.
  This guidance will include a list of core and miscellaneous topics for Rel-20 5GA. The core topics have garnered significant interest based on numerous presentations, while the miscellaneous topics have been presented in a limited number of instances. The level of detail is yet to be determined.
  The WG's capacity including Max# of SID/WID and TU budget estimates will be taken into account.
Moderated Email Discussions: The Working Group may organize Moderated Email Discussions to develop SID/WID details corresponding to the Rel-20 5GA topics identified in the Core/Miscellaneous list. The focus will be on defining technical objectives, work tasks, and estimated budgets for each task. These discussions can occur in either Q1 or Q2 or both.
Approval of Selected Rel-20 5GA SID/WID: This marks the first step in the approval process for Rel-20 5GA content. The WG may submit the SID/WID to SA#107 for approval. Ideally, the Rel-20 5GA SID/WID for approval at this step should have no dependencies on RAN. SID/WID for approval should follow the guidance on Rapporteurship (see SP-230746). Part of WG capacity will be assigned during the first step approval process.
WG commences Rel-20 5GA SI/WI Work: After the approval of the SID/WID at SA#107, the Working Group can start working on the approved SID/WID during their Q2 meetings.
Final Approval of Rel-20 5GA Package: This represents the second and final step in the approval process for the Rel-20 5GA content definition. The WG can submit the Rel-20 5GA SID/WID to SA#108 for approval. SID/WID for approval should follow the guidance on Rapporteurship (see SP-230746). Further prioritization, if necessary, will be handled based on WG capacity.

## Slide 5: Thank You !
Puneet Jain
Chair of 3GPP SA
puneet.jain@intel.com
www.3gpp.org