## SA2#160AHE Jan
|  |  | Month | Aug, 23 | Oct, 23 | Nov, 23 | Jan, 24 | Feb, 24 | Apr, 24 | May, 24 | Aug, 24 | Oct, 24 | Nov, 24
|  |  | Meeting | #158 | #159 | #160 | E Ad hoc | #161 | #162 | #163 | #164 | #165 | #166
|  |  | TU total (for planning purposes) | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36
Pre-Rel-17 maintenance
Planned |  |  |  | 1 | 1 | 1 | 0 | bar: #161 to #166
Actual |  |  |  | 2 | 1 | 1.7
Rel-17 maintenance
Planned |  |  |  | 3 | 2 | 2 | 0 | bar: #161 to #166
Actual |  |  |  | 3 | 2 | 1.2
Rel-18 maintenance
Planned |  |  |  | 20 | 18 | 18 | 14 | 14 | 10 | 8 | 8 | 6 | 6
Actual |  |  |  | 22 | 22 | 20.6
Buffer (TEI19, overflow, other)
Planned |  |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
Actual |  |  |  | 0 | 1 | 6
Total of Maintenance + Buffer
Planned |  |  |  | 30 | 27 | 27 | 20 | 22 | 18 | 16 | 16 | 14 | 14
Actual |  |  |  | 27 | 26 | 29.5
Rel-19
Planned |  |  |  | 6 | 9 | 9 | 16 | 14 | 18 | 20 | 20 | 22 | 22
Actual |  |  |  | 9 | 10 | 5.25
Overall total
Planned |  |  |  | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36
Actual |  |  |  | 36 | 36 | 34.75
Rel-19 SID/WID detailed plan |  | TU estimates (from SID)
FS_5GSAT_Ph3_ARCH | Study TU's planned | 7 | 7 |  | 1 | 1 | 1.5 | #161: 1; #162: 1.5; #163: 1
Jean Yves Fine | Study TU's used |  | 2 |  | 1 | 1
Hucheng Wang | Normative TU's planned | 5.5 | 0
Normative TU's used
FS_NG_RTC_Ph2 | Study TU's planned | 6 | 6 |  | 1 | 1.5 | 1 | #161: 1; #162: 1; #163: 0.5
Yi Jiang | Study TU's used |  | 2.5 |  | 1 | 1.5
| Normative TU's planned | 5.5 | 0
Normative TU's used
FS_XRM Ph2 | Study TU's planned | 7 | 7 |  | 1 | 1 | 1 | #161: 1; #162: 1; #163: 2
Devaki Chandramouli | Study TU's used |  | 2 |  | 1 | 1
Curt Wong | Normative TU's planned | 6 | 0
Normative TU's used
FS_EnergySys | Study TU's planned | 6.5 | 6.5 |  | 1 | 1 | 1 | #161: 1.5; #162: 1; #163: 1
Junshin Park | Study TU's used |  | 2 |  | 1 | 1
Konstantinos Samdanis | Normative TU's planned | 6.5 | 0
Normative TU's used
FS_MPS4msg | Study TU's planned | 3 | 3 |  |  | 0.75 | 0.5 | #161: 1; #162: 0; #163: 0.75
Robert Streijl | Study TU's used |  | 0.75 |  |  | 0.75
| Normative TU's planned | 3 | 0
Normative TU's used
FS_VMR_Ph2 | Study TU's planned | 3 | 3 |  |  |  | 0.5 | #161: 0.5; #162: 1; #163: 1
Hong Cheng | Study TU's used |  | 0
Lars Nord | Normative TU's planned | 2.5 | 0
Normative TU's used
FS_5G_ProSe_Ph3 | Study TU's planned | 2 | 2 |  |  |  | 0.5 | #161: 0.5; #162: 0.5; #163: 0.5
Hugh Shieh | Study TU's used |  | 0
Nassima Toumi | Normative TU's planned | 1.5 | 0
Normative TU's used
FS_UIA_ARC | Study TU's planned | 5.25 | 5.25 |  |  |  | 0.5 | #161: 1.5; #162: 1.75; #163: 1.5
Mike Starsinic | Study TU's used |  | 0
| Normative TU's planned | 4.25 | 0
Normative TU's used
FS_eEDGE_5GC_ph3 | Study TU's planned | 4.5 | 4.5 |  |  |  | 0.5 | #161: 1.5; #162: 1.5; #163: 1
Changhong Shan | Study TU's used |  | 0
| Normative TU's planned | 3 | 0
Normative TU's used
FS_UAS_Ph3 | Study TU's planned | 3.5 | 3.5 |  |  |  | 0.5 | bar: #161 to #163
LaeYoung Kim | Study TU's used |  | 0
Shabnam Sultana | Normative TU's planned | 3 | 0
Normative TU's used
FS_ISAC_ARC | Study TU's planned | 0 | 0
| Study TU's used |  | 0
| Normative TU's planned | 0 | 0
Normative TU's used
FS_UPEAS_Ph2 | Study TU's planned | 2.25 | 2.25 |  |  |  | 0.25 | #161: 0.5; #162: 1; #163: 0.5
Jinguo Zhu | Study TU's used |  | 0
| Normative TU's planned | 2.25 | 0
Normative TU's used
FS_5G_Femto | Study TU's planned | 2 | 2.25 |  |  |  | 0.5 | #161: 0.5; #162: 0.5; #163: 0.75
Malla Reddy Sama | Study TU's used |  | 0
| Normative TU's planned | 3 | 0
Normative TU's used
FS_MASSS | Study TU's planned | 7.5 | 7.5 |  |  |  | 1.5 | #161: 2; #162: 2; #163: 2
Krizstian Kiss | Study TU's used |  | 0
Zhuoyi Chen | Normative TU's planned | 6 | 0
Normative TU's used
FS_AmbientIoT | Study TU's planned | 11.5 | 11.5 |  |  |  | 0.5 | 2 | 2 | 2 | 2 | 1.5 | 1.5
Runze Zhou | Study TU's used |  | 0
Fei Lu | Normative TU's planned | 0 | 0
Normative TU's used
FS_AIML_CN | Study TU's planned | 4 | 4 |  |  |  | 0.5 | #161: 1.5; #162: 1; #163: 1
Xiaobo Wu | Study TU's used |  | 0
Mehrdad Shariat | Normative TU's planned | 4 | 0
Normative TU's used
Total planned (overall plan) |  |  |  |  | 9 | 9 | 16 | 14 | 18 | 20 | 20 | 22 | 22
Total planned (sum of item plans) |  |  |  |  | 4 | 5.25 | 10.75 | 17 | 16.75 | 16.5 | 2 | 1.5 | 1.5
|  | Planned | Used
Total for Rel-19 Studies |  | 75 | 9.25 |  | 4 | 5.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total for Rel-19 Normative |  | 56 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total for Rel-19 SID/WID |  | 131 | 9.25 |  | 4 | 5.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## SA2#161 Feb
|  |  | Month | Aug, 23 | Oct, 23 | Nov, 23 | Jan, 24 | Feb, 24 | Apr, 24 | May, 24 | Aug, 24 | Oct, 24 | Nov, 24
|  |  | Meeting | #158 | #159 | #160 | E Ad hoc | #161 | #162 | #163 | #164 | #165 | #166
|  |  | TU total (for planning purposes) | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36
Pre-Rel-17 maintenance
Planned |  |  |  | 1 | 1 | 1 | 0 | bar: #161 to #166
Actual |  |  |  | 2 | 1 | 1.7 | N/A
Rel-17 maintenance
Planned |  |  |  | 3 | 2 | 2 | 0 | bar: #161 to #166
Actual |  |  |  | 3 | 2 | 1.2 | N/A
Rel-18 maintenance
Planned |  |  |  | 20 | 18 | 18 | 14 | 14 | 10 | 8 | 8 | 6 | 6
Actual |  |  |  | 22 | 22 | 20.6 | N/A
Buffer (TEI19, overflow, other)
Planned |  |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
Actual |  |  |  | 0 | 1 | 6 | N/A
Total of Maintenance + Buffer
Planned |  |  |  | 30 | 27 | 27 | 20 | 22 | 18 | 16 | 16 | 14 | 14
Actual |  |  |  | 27 | 26 | 29.5 | N/A
Rel-19
Planned |  |  |  | 6 | 9 | 9 | 16 | 14 | 18 | 20 | 20 | 22 | 22
Actual |  |  |  | 9 | 10 | 5.25 | 10.75
Overall total
Planned |  |  |  | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36
Actual |  |  |  | 36 | 36 | 34.75 | N/A
Rel-19 SID/WID detailed plan |  | TU estimates (from SID)
FS_5GSAT_Ph3_ARCH | Study TU's planned | 7 | 7 |  | 1 | 1 | 1.5 | #161: 1; #162: 1.5; #163: 1
Jean Yves Fine | Study TU's used |  | 3.5 |  | 1 | 1 | 1.5
Hucheng Wang | Normative TU's planned | 5.5 | 0
Normative TU's used
FS_NG_RTC_Ph2 | Study TU's planned | 6 | 6 |  | 1 | 1.5 | 1 | #161: 1; #162: 1; #163: 0.5
Yi Jiang | Study TU's used |  | 3.5 |  | 1 | 1.5 | 1
| Normative TU's planned | 5.5 | 0
Normative TU's used
FS_XRM Ph2 | Study TU's planned | 7 | 7 |  | 1 | 1 | 1 | #161: 1; #162: 1; #163: 2
Devaki Chandramouli | Study TU's used |  | 3 |  | 1 | 1 | 1
Curt Wong | Normative TU's planned | 6 | 0
Normative TU's used
FS_EnergySys | Study TU's planned | 6.5 | 6.5 |  | 1 | 1 | 1 | #161: 1.5; #162: 1; #163: 1
Junshin Park | Study TU's used |  | 3 |  | 1 | 1 | 1
Konstantinos Samdanis | Normative TU's planned | 6.5 | 0
Normative TU's used
FS_MPS4msg | Study TU's planned | 3 | 3 |  |  | 0.75 | 0.5 | #161: 1; #162: 0; #163: 0.75
Robert Streijl | Study TU's used |  | 1.25 |  |  | 0.75 | 0.5
| Normative TU's planned | 3 | 0
Normative TU's used
FS_VMR_Ph2 | Study TU's planned | 3 | 3 |  |  |  | 0.5 | #161: 0.5; #162: 1; #163: 1
Hong Cheng | Study TU's used |  | 0.5 |  |  |  | 0.5
Lars Nord | Normative TU's planned | 2.5 | 0
Normative TU's used
FS_5G_ProSe_Ph3 | Study TU's planned | 2 | 2 |  |  |  | 0.5 | #161: 0.5; #162: 0.5; #163: 0.5
Hugh Shieh | Study TU's used |  | 0.5 |  |  |  | 0.5
Nassima Toumi | Normative TU's planned | 1.5 | 0
Normative TU's used
FS_UIA_ARC | Study TU's planned | 5.25 | 5.25 |  |  |  | 0.5 | #161: 1.5; #162: 1.75; #163: 1.5
Mike Starsinic | Study TU's used |  | 0.5 |  |  |  | 0.5
| Normative TU's planned | 4.25 | 0
Normative TU's used
FS_eEDGE_5GC_ph3 | Study TU's planned | 4.5 | 4.5 |  |  |  | 0.5 | #161: 1.5; #162: 1.5; #163: 1
Changhong Shan | Study TU's used |  | 0.5 |  |  |  | 0.5
| Normative TU's planned | 3 | 0
Normative TU's used
FS_UAS_Ph3 | Study TU's planned | 3.5 | 3.5 |  |  |  | 0.5 | bar: #161 to #163
LaeYoung Kim | Study TU's used |  | 0.5 |  |  |  | 0.5
Shabnam Sultana | Normative TU's planned | 3 | 0
Normative TU's used
FS_ISAC_ARC | Study TU's planned | 0 | 0
| Study TU's used |  | 0
| Normative TU's planned | 0 | 0
Normative TU's used
FS_UPEAS_Ph2 | Study TU's planned | 2.25 | 2.25 |  |  |  | 0.25 | #161: 0.5; #162: 1; #163: 0.5
Jinguo Zhu | Study TU's used |  | 0.25 |  |  |  | 0.25
| Normative TU's planned | 2.25 | 0
Normative TU's used
FS_5G_Femto | Study TU's planned | 2 | 2.25 |  |  |  | 0.5 | #161: 0.5; #162: 0.5; #163: 0.75
Malla Reddy Sama | Study TU's used |  | 0.5 |  |  |  | 0.5
| Normative TU's planned | 3 | 0
Normative TU's used
FS_MASSS | Study TU's planned | 7.5 | 7.5 |  |  |  | 1.5 | #161: 2; #162: 2; #163: 2
Krizstian Kiss | Study TU's used |  | 1.5 |  |  |  | 1.5
Zhuoyi Chen | Normative TU's planned | 6 | 0
Normative TU's used
FS_AmbientIoT | Study TU's planned | 11.5 | 11.5 |  |  |  | 0.5 | 2 | 2 | 2 | 2 | 1.5 | 1.5
Runze Zhou | Study TU's used |  | 0.5 |  |  |  | 0.5
Fei Lu | Normative TU's planned | 0 | 0
Normative TU's used
FS_AIML_CN | Study TU's planned | 4 | 4 |  |  |  | 0.5 | #161: 1.5; #162: 1; #163: 1
Xiaobo Wu | Study TU's used |  | 0.5 |  |  |  | 0.5
Mehrdad Shariat | Normative TU's planned | 4 | 0
Normative TU's used
Total planned (overall plan) |  |  |  |  | 9 | 9 | 16 | 14 | 18 | 20 | 20 | 22 | 22
Total planned (sum of individual plans) |  |  |  |  | 4 | 5.25 | 10.75 | 17 | 16.75 | 16.5 | 2 | 1.5 | 1.5
|  | Planned | Used
Total for Rel-19 Studies |  | 75 | 20 |  | 4 | 5.25 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0
Total for Rel-19 Normative |  | 56 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total for Rel-19 SID/WID |  | 131 | 20 |  | 4 | 5.25 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0

## SA2#162 Apr
|  |  | Month | Aug, 23 | Oct, 23 | Nov, 23 | Jan, 24 | Feb, 24 | Apr, 24 | May, 24 | Aug, 24 | Oct, 24 | Nov, 24
|  |  | Meeting | #158 | #159 | #160 | E Ad hoc | #161 | #162 | #163 | #164 | #165 | #166
|  |  | TU total (for planning purposes) | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36
Pre-Rel-17 maintenance
Planned |  |  |  | 1 | 1 | 1 | 0 | bar: #161 to #166
Actual |  |  |  | 2 | 1 | 1.7 | N/A | bar: #161
Rel-17 maintenance
Planned |  |  |  | 3 | 2 | 2 | 0 | bar: #161 to #166
Actual |  |  |  | 3 | 2 | 1.2 | N/A | #161: 1.5
Rel-18 maintenance
Planned |  |  |  | 20 | 18 | 18 | 14 | 14 | 10 | 8 | 8 | 6 | 6
Actual |  |  |  | 22 | 22 | 20.6 | N/A | #161: 8.25
Buffer (Overflow, other)
Planned |  |  |  | 6 | 6 | 6 | 6 | 6 | 4 | 4 | 4 | 3 | 3
Actual |  |  |  | 0 | 1 | 6 | N/A | #161: 0
Total of Maintenance + Buffer
Planned |  |  |  | 30 | 27 | 27 | 20 | 22 | 16 | 14 | 14 | 11 | 11
Actual |  |  |  | 27 | 26 | 29.5 | N/A | #161: 10.75
Rel-19
Planned |  |  |  | 6 | 9 | 9 | 16 | 14 | 18 | 20 | 20 | 22 | 22
Actual |  |  |  | 9 | 10 | 5.25 | 10.75 | #161: 16
Rel-19 TEI
Planned | [7 empty] | 0 | 2 | 2 | 2 | 3 | 3
Actual | [7 empty] | #161: 6
Overall total
Planned |  |  |  | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36
Actual |  |  |  | 36 | 36 | 34.75 | N/A | #161: 32.75
Rel-19 SID/WID detailed plan |  | TU estimates (from SID)
FS_5GSAT_Ph3_ARCH | Study TU's planned | 7 | 7 |  | 1 | 1 | 1.5 | #161: 1; #162: 1.5; #163: 1
Jean Yves Fine | Study TU's used |  | 4.5 |  | 1 | 1 | 1.5 | bar: #161
Hucheng Wang | Normative TU's planned | 5.5 | 0
Normative TU's used
FS_NG_RTC_Ph2 | Study TU's planned | 6 | 6 |  | 1 | 1.5 | 1 | #161: 1; #162: 1; #163: 0.5
Yi Jiang | Study TU's used |  | 4.5 |  | 1 | 1.5 | 1 | bar: #161
| Normative TU's planned | 5.5 | 0
Normative TU's used
FS_XRM Ph2 | Study TU's planned | 7 | 7 |  | 1 | 1 | 1 | #161: 1; #162: 1; #163: 2
Devaki Chandramouli | Study TU's used |  | 3 |  | 1 | 1 | 1
Curt Wong | Normative TU's planned | 6 | 0
Normative TU's used
FS_EnergySys | Study TU's planned | 6.5 | 6.5 |  | 1 | 1 | 1 | #161: 1.5; #162: 1; #163: 1
Junshin Park | Study TU's used |  | 4.5 |  | 1 | 1 | 1 | #161: 1.5
Konstantinos Samdanis | Normative TU's planned | 6.5 | 0
Normative TU's used
FS_MPS4msg | Study TU's planned | 3 | 3.5 |  |  | 0.75 | 0.5 | #161: 1; #162: 0; #163: 1.25
Robert Streijl | Study TU's used |  | 2 |  |  | 0.75 | 0.5 | #161: 0.75
| Normative TU's planned | 3 | 0
Normative TU's used
FS_VMR_Ph2 | Study TU's planned | 3 | 3 |  |  |  | 0.5 | #161: 0.5; #162: 1; #163: 1
Hong Cheng | Study TU's used |  | 1 |  |  |  | 0.5 | #161: 0.5
Lars Nord | Normative TU's planned | 2.5 | 0
Normative TU's used
FS_5G_ProSe_Ph3 | Study TU's planned | 2 | 2 |  |  |  | 0.5 | #161: 0.5; #162: 0.5; #163: 0.5
Hugh Shieh | Study TU's used |  | 1 |  |  |  | 0.5 | #161: 0.5
Nassima Toumi | Normative TU's planned | 1.5 | 0
Normative TU's used
FS_UIA_ARC | Study TU's planned | 5.25 | 5.25 |  |  |  | 0.5 | #161: 1.5; #162: 1.75; #163: 1.5
Mike Starsinic | Study TU's used |  | 2 |  |  |  | 0.5 | #161: 1.5
| Normative TU's planned | 4.25 | 0
Normative TU's used
FS_eEDGE_5GC_ph3 | Study TU's planned | 4.5 | 4.5 |  |  |  | 0.5 | #161: 1.5; #162: 1.5; #163: 1
Changhong Shan | Study TU's used |  | 2 |  |  |  | 0.5 | #161: 1.5
| Normative TU's planned | 3 | 0
Normative TU's used
FS_UAS_Ph3 | Study TU's planned | 3.5 | 3.5 |  |  |  | 0.5 | bar: #161 to #163
LaeYoung Kim | Study TU's used |  | 1.5 |  |  |  | 0.5 | bar: #161
Shabnam Sultana | Normative TU's planned | 3 | 0
Normative TU's used
FS_ISAC_ARC | Study TU's planned | 0 | 0
| Study TU's used |  | 0
| Normative TU's planned | 0 | 0
Normative TU's used
FS_UPEAS_Ph2 | Study TU's planned | 2.25 | 2.25 |  |  |  | 0.25 | #161: 0.5; #162: 1; #163: 0.5
Jinguo Zhu | Study TU's used |  | 0.75 |  |  |  | 0.25 | #161: 0.5
Susana Sabater | Normative TU's planned | 2.25 | 0
Normative TU's used
FS_5G_Femto | Study TU's planned | 2 | 2.25 |  |  |  | 0.5 | #161: 0.5; #162: 0.5; #163: 0.75
Malla Reddy Sama | Study TU's used |  | 1.5 |  |  |  | 0.5 | bar: #161
| Normative TU's planned | 3 | 0
Normative TU's used
FS_MASSS | Study TU's planned | 7.5 | 7.5 |  |  |  | 1.5 | #161: 2; #162: 2; #163: 2
Krizstian Kiss | Study TU's used |  | 3.5 |  |  |  | 1.5 | #161: 2
Zhuoyi Chen | Normative TU's planned | 6 | 0
Normative TU's used
FS_AmbientIoT | Study TU's planned | 11.5 | 11.5 |  |  |  | 0.5 | 2 | 2 | 2 | 2 | 1.5 | 1.5
Runze Zhou | Study TU's used |  | 2.5 |  |  |  | 0.5 | #161: 2
Fei Lu | Normative TU's planned | 0 | 0
Normative TU's used
FS_AIML_CN | Study TU's planned | 4 | 4 |  |  |  | 0.5 | #161: 1.5; #162: 1; #163: 1
Xiaobo Wu | Study TU's used |  | 2 |  |  |  | 0.5 | #161: 1.5
Mehrdad Shariat | Normative TU's planned | 4 | 0
Normative TU's used
Total planned (from the original overall plan) |  |  |  |  | 9 | 9 | 16 | 14 | 18 | 20 | 20 | 22 | 22
Total planned (sum of individual plans) |  |  |  |  | 4 | 5.25 | 10.75 | 17 | 16.75 | 17 | 2 | 1.5 | 1.5
|  | Planned | Used
Total for Rel-19 Studies |  | 75 | 36.25 |  | 4 | 5.25 | 10.75 | 16.25 | 0 | 0 | 0 | 0 | 0
Total for Rel-19 Normative |  | 56 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total for Rel-19 SID/WID |  | 131 | 36.25 |  | 4 | 5.25 | 10.75 | 16.25 | 0 | 0 | 0 | 0 | 0
TEI19 items
TEI19_NetShare | Tianqi Xing | [6 empty] | #162: 0.5; #163: 0.5
TEI19_RVAS | Qian Chen | [6 empty] | #162: 0.5; #163: 0.5
TEI19_MINPA | Belen Pancorbo | [6 empty] | #162: 0.5; #163: 0.5
TEI19_DLPM | Richard Batorfi | [6 empty] | #166: 0.5
TEI19_VLANSUB | Stefan Rommer | [6 empty] | #165: 0.5
TEI19_IP-SP-EXP | Stefan Rommer | [6 empty] | #165: 0.5
TEI19_SLUPiR | Uri Baniel | [6 empty] | #164: 0.5
TEI19_TIME_SUB_EPS | Sebastian Speicher | [6 empty] | #164: 0.5
TEI19_OBGAD | Aihua Li | [6 empty] | #164: 0.5
TEI19_QME | Aihua Li | [6 empty] | #165: 0.5
TEI19_NFsel_by_tPLMN | Thomas Belling | [6 empty] | #164: 0.5
TEI19_HSBO | Hyesung Kim | [6 empty] | #165: 0.5; #166: 0.25
TEI19_MLR4RTR | Simon Cai | [6 empty] | #165: 0.5; #166: 0.5
TEI19_ProSe_NPN | Walter Dees | [6 empty] | #162: 0.5; #163: 0.5

## SA2#163 May
|  |  | Month | Aug, 23 | Oct, 23 | Nov, 23 | Jan, 24 | Feb, 24 | Apr, 24 | May, 24 | Aug, 24 | Oct, 24 | Nov, 24
|  |  | Meeting | #158 | #159 | #160 | E Ad hoc | #161 | #162 | #163 | #164 | #165 | #166
|  |  | TU total (for planning purposes) | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36
Pre-Rel-17 maintenance
Planned |  |  |  | 1 | 1 | 1 | 0 | bar: #161 to #166
Actual |  |  |  | 2 | 1 | 1.7 | N/A | bar: #161 to #162
Rel-17 maintenance
Planned |  |  |  | 3 | 2 | 2 | 0 | bar: #161 to #166
Actual |  |  |  | 3 | 2 | 1.2 | N/A | #161: 1.5; #162: 1
Rel-18 maintenance
Planned |  |  |  | 20 | 18 | 18 | 14 | 14 | 10 | 8 | 8 | 6 | 6
Actual |  |  |  | 22 | 22 | 20.6 | N/A | #161: 8.25; #162: 6
Buffer (Overflow, other)
Planned |  |  |  | 6 | 6 | 6 | 6 | 6 | 4 | 4 | 4 | 3 | 3
Actual |  |  |  | 0 | 1 | 6 | N/A | #161: 0; #162: 5
Total of Maintenance + Buffer
Planned |  |  |  | 30 | 27 | 27 | 20 | 22 | 16 | 14 | 14 | 11 | 11
Actual |  |  |  | 27 | 26 | 29.5 | N/A | #161: 10.75; #162: 13
Rel-19
Planned |  |  |  | 6 | 9 | 9 | 16 | 14 | 18 | 20 | 20 | 22 | 22
Actual |  |  |  | 9 | 10 | 5.25 | 10.75 | #161: 16; #162: 21.25
Rel-19 TEI
Planned | [7 empty] | 0 | 2 | 2 | 2 | 3 | 3
Actual | [7 empty] | #161: 6; #162: 2
Overall total
Planned |  |  |  | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36
Actual |  |  |  | 36 | 36 | 34.75 | N/A | #161: 32.75; #162: 36.25
Rel-19 SID/WID detailed plan |  | TU estimates (from SID)
FS_5GSAT_Ph3_ARCH | Study TU's planned | 7 | 7 |  | 1 | 1 | 1.5 | #161: 1; #162: 1.5; #163: 1
Jean Yves Fine | Study TU's used |  | 6 |  | 1 | 1 | 1.5 | #161: 1; #162: 1.5
Hucheng Wang | Normative TU's planned | 5.5 | 0
Normative TU's used
FS_NG_RTC_Ph2 | Study TU's planned | 6 | 6 |  | 1 | 1.5 | 1 | #161: 1; #162: 1; #163: 0.5
Yi Jiang | Study TU's used |  | 5.5 |  | 1 | 1.5 | 1 | bar: #161 to #162
| Normative TU's planned | 5.5 | 0
Normative TU's used
FS_XRM Ph2 | Study TU's planned | 7 | 7 |  | 1 | 1 | 1 | #161: 1; #162: 1; #163: 2
Devaki Chandramouli | Study TU's used |  | 4 |  | 1 | 1 | 1 | bar: #162
Curt Wong | Normative TU's planned | 6 | 0
Normative TU's used
FS_EnergySys | Study TU's planned | 6.5 | 6.5 |  | 1 | 1 | 1 | #161: 1.5; #162: 1; #163: 1
Junshin Park | Study TU's used |  | 5.5 |  | 1 | 1 | 1 | #161: 1.5; #162: 1
Konstantinos Samdanis | Normative TU's planned | 6.5 | 0
Normative TU's used
FS_MPS4msg | Study TU's planned | 3 | 3.5 |  |  | 0.75 | 0.5 | #161: 1; #162: 0; #163: 1.25
Robert Streijl | Study TU's used |  | 2 |  |  | 0.75 | 0.5 | #161: 0.75; #162: 0
| Normative TU's planned | 3 | 0
Normative TU's used
FS_VMR_Ph2 | Study TU's planned | 3 | 3 |  |  |  | 0.5 | #161: 0.5; #162: 1; #163: 1
Hong Cheng | Study TU's used |  | 2 |  |  |  | 0.5 | #161: 0.5; #162: 1
Lars Nord | Normative TU's planned | 2.5 | 0
Normative TU's used
FS_5G_ProSe_Ph3 | Study TU's planned | 2 | 2 |  |  |  | 0.5 | #161: 0.5; #162: 0.5; #163: 0.5
Hugh Shieh | Study TU's used |  | 1 |  |  |  | 0.5 | #161: 0.5
Nassima Toumi | Normative TU's planned | 1.5 | 0
Normative TU's used
FS_UIA_ARC | Study TU's planned | 5.25 | 5.25 |  |  |  | 0.5 | #161: 1.5; #162: 1.75; #163: 1.5
Mike Starsinic | Study TU's used |  | 3.75 |  |  |  | 0.5 | #161: 1.5; #162: 1.75
| Normative TU's planned | 4.25 | 0
Normative TU's used
FS_eEDGE_5GC_ph3 | Study TU's planned | 4.5 | 4.5 |  |  |  | 0.5 | #161: 1.5; #162: 1.5; #163: 1
Changhong Shan | Study TU's used |  | 3.5 |  |  |  | 0.5 | #161: 1.5; #162: 1.5
| Normative TU's planned | 3 | 0
Normative TU's used
FS_UAS_Ph3 | Study TU's planned | 3.5 | 3.5 |  |  |  | 0.5 | bar: #161 to #163
LaeYoung Kim | Study TU's used |  | 2.5 |  |  |  | 0.5 | bar: #161 to #162
Shabnam Sultana | Normative TU's planned | 3 | 0
Normative TU's used
FS_ISAC_ARC | Study TU's planned | 0 | 0
| Study TU's used |  | 0
| Normative TU's planned | 0 | 0
Normative TU's used
FS_UPEAS_Ph2 | Study TU's planned | 2.25 | 2.25 |  |  |  | 0.25 | #161: 0.5; #162: 1; #163: 0.5
Jinguo Zhu | Study TU's used |  | 1.75 |  |  |  | 0.25 | #161: 0.5; #162: 1
Susana Sabater | Normative TU's planned | 2.25 | 0
Normative TU's used
FS_5G_Femto | Study TU's planned | 2 | 2.25 |  |  |  | 0.5 | #161: 0.5; #162: 0.5; #163: 0.75
Malla Reddy Sama | Study TU's used |  | 2 |  |  |  | 0.5 | #161: 1; #162: 0.5
| Normative TU's planned | 3 | 0
Normative TU's used
FS_MASSS | Study TU's planned | 7.5 | 7.5 |  |  |  | 1.5 | #161: 2; #162: 2; #163: 2
Krizstian Kiss | Study TU's used |  | 5.5 |  |  |  | 1.5 | #161: 2; #162: 2
Zhuoyi Chen | Normative TU's planned | 6 | 0
Normative TU's used
FS_AmbientIoT | Study TU's planned | 11.5 | 11.5 |  |  |  | 0.5 | 2 | 2 | 2 | 2 | 1.5 | 1.5
Runze Zhou | Study TU's used |  | 4.5 |  |  |  | 0.5 | #161: 2; #162: 2
Fei Lu | Normative TU's planned | 0 | 0
Normative TU's used
FS_AIML_CN | Study TU's planned | 4 | 4 |  |  |  | 0.5 | #161: 1.5; #162: 1; #163: 1
Xiaobo Wu | Study TU's used |  | 3 |  |  |  | 0.5 | #161: 1.5; #162: 1
Mehrdad Shariat | Normative TU's planned | 4 | 0
Normative TU's used
Drafting sessions (Q1 - Q5) | [7 empty] | #162: 5
Drafting sessions (Q0) | [7 empty] | #162: 5
Total planned (from the original overall plan) |  |  |  |  | 9 | 9 | 16 | 14 | 18 | 20 | 20 | 22 | 22
Total planned (sum of individual plans) |  |  |  |  | 4 | 5.25 | 10.75 | 17 | 16.75 | 17 | 2 | 1.5 | 1.5
|  | Planned | Used
Total for Rel-19 Studies |  | 75 | 52.5 |  | 4 | 5.25 | 10.75 | 16.25 | 16.25 | 0 | 0 | 0 | 0
Total for Rel-19 Normative |  | 56 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total for Rel-19 SID/WID |  | 131 | 52.5 |  | 4 | 5.25 | 10.75 | 16.25 | 16.25 | 0 | 0 | 0 | 0
TEI19 items
TEI19_NetShare | Tianqi Xing | [6 empty] | #162: 0.5; #163: 0.25
TEI19_RVAS | Qian Chen | [6 empty] | #162: 0.5; #163: 0.25
TEI19_MINPA | Belen Pancorbo | [6 empty] | #162: 0.5; #163: 0.25
TEI19_DLPM | Richard Batorfi | [6 empty] | #165: 0.5
TEI19_VLANSUB | Stefan Rommer | [6 empty] | #165: 0.5
TEI19_IP-SP-EXP | Stefan Rommer | [6 empty] | #164: 0.5
TEI19_SLUPiR | Uri Baniel | [6 empty] | #163: 0.5
TEI19_TIME_SUB_EPS | Sebastian Speicher | [6 empty] | #164: 0.5
TEI19_OBGAD | Aihua Li | [6 empty] | #164: 0.5
TEI19_QME | Aihua Li | [6 empty] | #163: 0.5
TEI19_NFsel_by_tPLMN | Thomas Belling | [6 empty] | #163: 0.5
TEI19_HSBO | Hyesung Kim | [6 empty] | #165: 0.5; #166: 0.25
TEI19_MLR4RTR | Simon Cai | [6 empty] | #165: 0.5; #166: 0.5
TEI19_ProSe_NPN | Walter Dees | [6 empty] | #162: 0.5; #163: 0.25
Drafting sessions used | Total
FS_5GSAT_Ph3_ARCH | 1 | bar: #162
FS_NG_RTC_Ph2 | 0.75 | [6 empty] | #162: 0.75
FS_XRM Ph2 | 1.5 |  |  |  |  | 0.75 |  | #162: 0.75
FS_EnergySys | 0.75 | [6 empty] | #162: 0.75
FS_MPS4msg | 0
FS_VMR_Ph2 | 0
FS_5G_ProSe_Ph3 | 1 | bar: #162
FS_UIA_ARC | 0.75 | [6 empty] | #162: 0.75
FS_eEDGE_5GC_ph3 | 0.75 | [6 empty] | #162: 0.75
FS_UAS_Ph3 | 0
FS_UPEAS_Ph2 | 0
FS_5G_Femto | 0.75 | [6 empty] | #162: 0.75
FS_MASSS | 1.5 | [6 empty] | #161: 0.75; #162: 0.75
FS_AmbientIoT | 1 | bar: #162
FS_AIML_CN | 0.75 | [6 empty] | #161: 0.75

## SA2#164 August
S2-2408314
|  |  | Month | Aug, 23 | Oct, 23 | Nov, 23 | Jan, 24 | Feb, 24 | Apr, 24 | May, 24 | Aug, 24 | Oct, 24 | Nov, 24
|  |  | Meeting | #158 | #159 | #160 | E Ad hoc | #161 | #162 | #163 | #164 | #165 | #166
|  |  | TU total (for planning purposes) | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36
Pre-Rel-17 maintenance
Planned |  |  |  | 1 | 1 | 1 | 0 | bar: #161 to #166
Actual |  |  |  | 2 | 1 | 1.7 | N/A | #161: 1; #162: 1; #163: 0
Rel-17 maintenance
Planned |  |  |  | 3 | 2 | 2 | 0 | bar: #161 to #166
Actual |  |  |  | 3 | 2 | 1.2 | N/A | #161: 1.5; #162: 1; #163: 0.25
Rel-18 maintenance
Planned |  |  |  | 20 | 18 | 18 | 14 | 14 | 10 | 8 | 8 | 6 | 6
Actual |  |  |  | 22 | 22 | 20.6 | N/A | #161: 8.25; #162: 6; #163: 4.5
Buffer (Overflow, other)
Planned |  |  |  | 6 | 6 | 6 | 6 | 6 | 4 | 4 | 4 | 3 | 3
Actual |  |  |  | 0 | 1 | 6 | N/A | #161: 0; #162: 5; #163: 3
Total of Maintenance + Buffer
Planned |  |  |  | 30 | 27 | 27 | 20 | 22 | 16 | 14 | 14 | 11 | 11
Actual |  |  |  | 27 | 26 | 29.5 | N/A | #161: 10.75; #162: 13; #163: 7.25
Rel-19
Planned |  |  |  | 6 | 9 | 9 | 16 | 14 | 18 | 20 | 20 | 22 | 22
Actual |  |  |  | 9 | 10 | 5.25 | 10.75 | #161: 16; #162: 21.25; #163: 26.75
Rel-19 TEI
Planned | [7 empty] | 0 | 2 | 2 | 2 | 3 | 3
Actual | [7 empty] | #161: 6; #162: 2; #163: 2.5
Overall total
Planned |  |  |  | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36
Actual |  |  |  | 36 | 36 | 34.75 | N/A | #161: 32.75; #162: 36.25; #163: 36.5
Rel-19 SID/WID detailed plan |  | TU estimates (from SID)
FS_5GSAT_Ph3_ARCH | Study TU's planned | 7 | 7 |  | 1 | 1 | 1.5 | 1 | 1.5 | 1 | 0
Hucheng Wang | Study TU's used |  | 7 |  | 1 | 1 | 1.5 | #161: 1; #162: 1.5; #163: 1
Ramon Ferrus | Normative TU's planned | 5.5 | 1.5 |  |  |  |  | #164: 1.5
Normative TU's used
FS_NG_RTC_Ph2 | Study TU's planned | 6 | 6.5 |  | 1 | 1.5 | 1 | 1 | 1 | 0.5 | 0.5
Yi Jiang | Study TU's used |  | 6 |  | 1 | 1.5 | 1 | #161: 1; #162: 1; #163: 0.5
| Normative TU's planned | 5.5 | 1.5 |  |  |  |  | #164: 1.5
Normative TU's used
FS_XRM Ph2 | Study TU's planned | 7 | 7.5 |  | 1 | 1 | 1 | 1 | 1 | 2 | 0.5
Devaki Chandramouli | Study TU's used |  | 6 |  | 1 | 1 | 1 | #162: 1; #163: 2
Curt Wong | Normative TU's planned | 6 | 1.5 |  |  |  |  | #164: 1.5
Normative TU's used
FS_EnergySys | Study TU's planned | 6.5 | 8.5 |  | 1 | 1 | 1 | 1.5 | 1 | 1 | 2
Junshin Park | Study TU's used |  | 6.5 |  | 1 | 1 | 1 | #161: 1.5; #162: 1; #163: 1
Costas Samdanis | Normative TU's planned | 6.5 | 0 |  |  |  |  | #164: 0
Normative TU's used
FS_MPS4msg | Study TU's planned | 3 | 3.5 |  |  | 0.75 | 0.5 | 1 | 0 | 1.25 | 0
Robert Streijl | Study TU's used |  | 2.5 |  |  | 0.75 | 0.5 | #161: 0.75; #162: 0; #163: 0.5
| Normative TU's planned | 3 | 1 | bar: #164
Normative TU's used
FS_VMR_Ph2 | Study TU's planned | 3 | 3.25 |  |  |  | 0.5 | 0.5 | 1 | 1 | 0.25
Hong Cheng | Study TU's used |  | 3 |  |  |  | 0.5 | #161: 0.5; #162: 1; #163: 1
Lars Nord | Normative TU's planned | 2.5 | 0.75 |  |  |  |  | #164: 0.75
Normative TU's used
FS_5G_ProSe_Ph3 | Study TU's planned | 2 | 2.5 |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Hugh Shieh | Study TU's used |  | 1.5 |  |  |  | 0.5 | #161: 0.5; #163: 0.5
Nassima Toumi | Normative TU's planned | 1.5 | 0.5 |  |  |  |  | #164: 0.5
Normative TU's used
FS_UIA_ARC | Study TU's planned | 5.25 | 6.25 |  |  |  | 0.5 | 1.5 | 1.75 | 1.5 | 1
Mike Starsinic | Study TU's used |  | 5.25 |  |  |  | 0.5 | #161: 1.5; #162: 1.75; #163: 1.5
| Normative TU's planned | 4.25 | 0.5 |  |  |  |  | #164: 0.5
Normative TU's used
FS_eEDGE_5GC_ph3 | Study TU's planned | 4.5 | 4.75 |  |  |  | 0.5 | 1.5 | 1.5 | 1 | 0.25
Changhong Shan | Study TU's used |  | 4.5 |  |  |  | 0.5 | #161: 1.5; #162: 1.5; #163: 1
| Normative TU's planned | 3 | 0.75 |  |  |  |  | #164: 0.75
Normative TU's used
FS_UAS_Ph3 | Study TU's planned | 3.5 | 3.75 |  |  |  | 0.5 | 1 | 1 | 1 | 0.25
LaeYoung Kim | Study TU's used |  | 3.5 |  |  |  | 0.5 | bar: #161 to #163
Shabnam Sultana | Normative TU's planned | 3 | 0.75 |  |  |  |  | #164: 0.75
Normative TU's used
FS_ISAC_ARC | Study TU's planned | 0 | 0
| Study TU's used |  | 0
| Normative TU's planned | 0 | 0
Normative TU's used
FS_UPEAS_Ph2 | Study TU's planned | 2.25 | 2.25 |  |  |  | 0.25 | 0.5 | 1 | 0.5 | 0
Jinguo Zhu | Study TU's used |  | 2.75 |  |  |  | 0.25 | #161: 0.5; #162: 1; #163: 1
Susana Sabater | Normative TU's planned | 2.25 | 1 | bar: #164
Normative TU's used
FS_5G_Femto | Study TU's planned | 2 | 2.5 |  |  |  | 0.5 | 0.5 | 0.5 | 0.75 | 0.25
Malla Reddy Sama | Study TU's used |  | 2.75 |  |  |  | 0.5 | #161: 1; #162: 0.5; #163: 0.75
| Normative TU's planned | 3 | 0.75 |  |  |  |  | #164: 0.75
Normative TU's used
FS_MASSS | Study TU's planned | 7.5 | 9 |  |  |  | 1.5 | 2 | 2 | 2 | 1.5
Krizstian Kiss | Study TU's used |  | 7.5 |  |  |  | 1.5 | #161: 2; #162: 2; #163: 2
Zhuoyi Chen | Normative TU's planned | 6 | 0.5 |  |  |  |  | #164: 0.5
Normative TU's used
FS_AmbientIoT | Study TU's planned | 11.5 | 11.5 |  |  |  | 0.5 | 2 | 2 | 2 | 2 | 1.5 | 1.5
Runze Zhou | Study TU's used |  | 6.5 |  |  |  | 0.5 | #161: 2; #162: 2; #163: 2
Fei Lu | Normative TU's planned | 0 | 0 |  |  |  |  | #164: 0
Normative TU's used
FS_AIML_CN | Study TU's planned | 4 | 4 |  |  |  | 0.5 | 1.5 | 1 | 1 | 0
Xiaobo Wu | Study TU's used |  | 4 |  |  |  | 0.5 | #161: 1.5; #162: 1; #163: 1
Mehrdad Shariat | Normative TU's planned | 4 | 1 | bar: #164
Normative TU's used
Drafting sessions (Q1 - Q5) | [7 empty] | #162: 5; #163: 10
Drafting sessions (Q0) | [7 empty] | #162: 5; #163: 2.25
Total planned (from the original overall plan) |  |  |  |  | 9 | 9 | 16 | 14 | 18 | 20 | 20 | 22 | 22
Total planned study (sum of individual plans) |  |  |  |  | 4 | 5.25 | 10.75 | 17 | 16.75 | 17 | 9 | 1.5 | 1.5
Total planned normative (sum of individual plans) | [7 empty] | #164: 12; #165: 0; #166: 0
|  | Planned | Used
Total for Rel-19 Studies |  | 75 | 69.25 |  | 4 | 5.25 | 10.75 | 16.25 | 16.25 | 16.75 | 0 | 0 | 0
Total for Rel-19 Normative |  | 56 | 12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0
Total for Rel-19 SID/WID |  | 131 | 81.25 |  | 4 | 5.25 | 10.75 | 16.25 | 16.25 | 16.75 | 12 | 0 | 0
TEI19 items
| 8.75 | [7 empty] | 2 | 2.5 | 1.5 | 2 | 0.75
TEI19_NetShare | Tianqi Xing | [6 empty] | #162: 0.5; #163: 0.25
TEI19_RVAS | Qian Chen | [6 empty] | #162: 0.5; #163: 0.25
TEI19_MINPA | Belen Pancorbo | [6 empty] | #162: 0.5; #163: 0.25
TEI19_DLPM | Richard Batorfi | [6 empty] | #165: 0.5
TEI19_VLANSUB | Stefan Rommer | [6 empty] | #165: 0.5
TEI19_IP-SP-EXP | Stefan Rommer | [6 empty] | #164: 0.5
TEI19_SLUPiR | Uri Baniel | [6 empty] | #163: 0.5
TEI19_TIME_SUB_EPS | Sebastian Speicher | [6 empty] | #164: 0.5
TEI19_OBGAD | Aihua Li | [6 empty] | #164: 0.5
TEI19_QME | Aihua Li | [6 empty] | #163: 0.5
TEI19_NFsel_by_tPLMN | Thomas Belling | [6 empty] | #163: 0.5
TEI19_HSBO | Hyesung Kim | [6 empty] | #165: 0.5; #166: 0.25
TEI19_MLR4RTR | Simon Cai | [6 empty] | #165: 0.5; #166: 0.5
TEI19_ProSe_NPN | Walter Dees | [6 empty] | #162: 0.5; #163: 0.25
Drafting sessions used | Total
FS_5GSAT_Ph3_ARCH | 1.75 | [6 empty] | #162: 1; #163: 0.75
FS_NG_RTC_Ph2 | 1.75 | [6 empty] | #162: 0.75; #163: 1
FS_XRM Ph2 | 2.5 |  |  |  |  | 0.75 |  | #162: 0.75; #163: 1
FS_EnergySys | 1.75 | [6 empty] | #162: 0.75; #163: 1
FS_MPS4msg | 0
FS_VMR_Ph2 | 1 | bar: #163
FS_5G_ProSe_Ph3 | 2 | bar: #162 to #163
FS_UIA_ARC | 1.75 | [6 empty] | #162: 0.75; #163: 1
FS_eEDGE_5GC_ph3 | 1.75 | [6 empty] | #162: 0.75; #163: 1
FS_UAS_Ph3 | 1 | bar: #163
FS_UPEAS_Ph2 | 0.75 | [6 empty] | #163: 0.75
FS_5G_Femto | 1.5 | [6 empty] | #162: 0.75; #163: 0.75
FS_MASSS | 2.5 | [6 empty] | #161: 0.75; #162: 0.75; #163: 1
FS_AmbientIoT | 1 | bar: #162
FS_AIML_CN | 1.75 | [6 empty] | #161: 0.75; #163: 1

## SA2#165 October
S2-2410465
|  |  | Month | Aug, 23 | Oct, 23 | Nov, 23 | Jan, 24 | Feb, 24 | Apr, 24 | May, 24 | Aug, 24 | Oct, 24 | Nov, 24
|  |  | Meeting | #158 | #159 | #160 | E Ad hoc | #161 | #162 | #163 | #164 | #165 | #166
|  |  | TU total (for planning purposes) | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36
Pre-Rel-17 maintenance
Planned |  |  |  | 1 | 1 | 1 | 0 | bar: #161 to #166
Actual |  |  |  | 2 | 1 | 1.7 | N/A | 1 | 1 | 0 | 1
Rel-17 maintenance
Planned |  |  |  | 3 | 2 | 2 | 0 | bar: #161 to #166
Actual |  |  |  | 3 | 2 | 1.2 | N/A | 1.5 | 1 | 0.25 | 3
Rel-18 maintenance
Planned |  |  |  | 20 | 18 | 18 | 14 | 14 | 10 | 8 | 8 | 6 | 6
Actual |  |  |  | 22 | 22 | 20.6 | N/A | 8.25 | 6 | 4.5 | 6
Buffer (Overflow, other)
Planned |  |  |  | 6 | 6 | 6 | 6 | 6 | 4 | 4 | 4 | 3 | 3
Actual |  |  |  | 0 | 1 | 6 | N/A | 0 | 5 | 3 | 4
Total of Maintenance + Buffer
Planned |  |  |  | 30 | 27 | 27 | 20 | 22 | 16 | 14 | 14 | 11 | 11
Actual |  |  |  | 27 | 26 | 29.5 | N/A | 10.75 | 13 | 7.75 | 14
Rel-19
Planned |  |  |  | 6 | 9 | 9 | 16 | 14 | 18 | 20 | 20 | 22 | 22
Actual (not including drafting) |  |  |  | 9 | 10 | 5.25 | 10.75 | 16 | 16.25 | 16.75 | 8.5
Rel-19 TEI
Planned | [7 empty] | 0 | 2 | 2 | 2 | 3 | 3
Actual | [7 empty] | 6 | 2 | 2.5 | 1.5
Overall total
Planned |  |  |  | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36
Actual |  |  |  | 36 | 36 | 34.75 | N/A | 32.75 | 31.25 | 27 | 24
Rel-19 SID/WID detailed plan |  | TU estimates (from SID)
FS_5GSAT_Ph3_ARCH | Study TU's planned | 7 | 7 |  | 1 | 1 | 1.5 | 1 | 1.5 | 1 | 0 | 0 | 0
Hucheng Wang | Study TU's used |  | 7 |  | 1 | 1 | 1.5 | #161: 1; #162: 1.5; #163: 1
Ramon Ferrus | Normative TU's planned | 5.5 | 5.5 |  |  |  |  | #164: 1.5; #165: 2; #166: 2
| Normative TU's used |  | 1.5 |  |  |  |  | #164: 1.5
FS_NG_RTC_Ph2 | Study TU's planned | 6 | 6.5 |  | 1 | 1.5 | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0
Yi Jiang | Study TU's used |  | 6 |  | 1 | 1.5 | 1 | #161: 1; #162: 1; #163: 0.5
| Normative TU's planned | 5.5 | 4.5 |  |  |  |  | #164: 1.5; #165: 1.5; #166: 1.5
| Normative TU's used |  | 2 |  |  |  |  | #164: 2
FS_XRM_Ph2 | Study TU's planned | 7 | 7.5 |  | 1 | 1 | 1 | 1 | 1 | 2 | 0.5 | 0 | 0
Georgios Gkellas | Study TU's used |  | 6.5 |  | 1 | 1 | 1 | #162: 1; #163: 2; #164: 0.5
Curt Wong | Normative TU's planned | 6 | 5.5 |  |  |  |  | #164: 1.5; #165: 2; #166: 2
| Normative TU's used |  | 1.5 |  |  |  |  | #164: 1.5
FS_EnergySys | Study TU's planned | 6.5 | 8.5 |  | 1 | 1 | 1 | 1.5 | 1 | 1 | 2 | 0 | 0
Junshin Park | Study TU's used |  | 8.5 |  | 1 | 1 | 1 | 1.5 | 1 | 1 | 2
Costas Samdanis | Normative TU's planned | 6.5 | 4 |  |  |  |  | #164: 0; #165: 2; #166: 2
| Normative TU's used |  | 0 |  |  |  |  | #164: 0
FS_MPS4msg | Study TU's planned | 3 | 3.5 |  |  | 0.75 | 0.5 | 1 | 0 | 1.25 | 0 | 0 | 0
Robert Streijl | Study TU's used |  | 2.5 |  |  | 0.75 | 0.5 | 0.75 | 0 | 0.5 | 0
| Normative TU's planned | 3 | 2 |  |  |  |  | #164: 1; #165: 0; #166: 1
| Normative TU's used |  | 1 | bar: #164
FS_VMR_Ph2 | Study TU's planned | 3 | 3.25 |  |  |  | 0.5 | 0.5 | 1 | 1 | 0.25 | 0 | 0
Hong Cheng | Study TU's used |  | 3.25 |  |  |  | 0.5 | 0.5 | 1 | 1 | 0.25
Lars Nord | Normative TU's planned | 2.5 | 2.75 |  |  |  |  | #164: 0.75; #165: 1; #166: 1
| Normative TU's used |  | 0.75 |  |  |  |  | #164: 0.75
FS_5G_ProSe_Ph3 | Study TU's planned | 2 | 2.5 |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0
Nassima Toumi | Study TU's used |  | 2 |  |  |  | 0.5 | #161: 0.5; #163: 0.5; #164: 0.5
| Normative TU's planned | 1.5 | 1.5 |  |  |  |  | #164: 0.5; #165: 0; #166: 1
| Normative TU's used |  | 0.5 |  |  |  |  | #164: 0.5
FS_UIA_ARC | Study TU's planned | 5.25 | 6.25 |  |  |  | 0.5 | 1.5 | 1.75 | 1.5 | 1 | 0 | 0
Mike Starsinic | Study TU's used |  | 6.25 |  |  |  | 0.5 | 1.5 | 1.75 | 1.5 | 1
| Normative TU's planned | 4.25 | 1.5 |  |  |  |  | #164: 0.5; #165: 0.5; #166: 0.5
| Normative TU's used |  | 0.5 |  |  |  |  | #164: 0.5
FS_eEDGE_5GC_ph3 | Study TU's planned | 4.5 | 4.75 |  |  |  | 0.5 | 1.5 | 1.5 | 1 | 0.25 | 0 | 0
Changhong Shan | Study TU's used |  | 4.75 |  |  |  | 0.5 | 1.5 | 1.5 | 1 | 0.25
| Normative TU's planned | 3 | 2.75 |  |  |  |  | #164: 0.75; #165: 1; #166: 1
| Normative TU's used |  | 0.75 |  |  |  |  | #164: 0.75
FS_UAS_Ph3 | Study TU's planned | 3.5 | 3.75 |  |  |  | 0.5 | 1 | 1 | 1 | 0.25 | 0 | 0
LaeYoung Kim | Study TU's used |  | 3.75 |  |  |  | 0.5 | 1 | 1 | 1 | 0.25
Shabnam Sultana | Normative TU's planned | 3 | 2.75 |  |  |  |  | #164: 0.75; #165: 1; #166: 1
| Normative TU's used |  | 0.75 |  |  |  |  | #164: 0.75
FS_ISAC_ARC | Study TU's planned | 0 | 0
| Study TU's used |  | 0
| Normative TU's planned | 0 | 0
| Normative TU's used |  | 0
FS_UPEAS_Ph2 | Study TU's planned | 2.25 | 2.25 |  |  |  | 0.25 | 0.5 | 1 | 0.5 | 0 | 0 | 0
Jinguo Zhu | Study TU's used |  | 2.75 |  |  |  | 0.25 | 0.5 | 1 | 1 | 0
Susana Sabater | Normative TU's planned | 2.25 | 2.25 |  |  |  |  | #164: 1; #165: 0.75; #166: 0.5
| Normative TU's used |  | 1 | bar: #164
FS_5G_Femto | Study TU's planned | 2 | 2.5 |  |  |  | 0.5 | 0.5 | 0.5 | 0.75 | 0.25 | 0 | 0
Malla Reddy Sama | Study TU's used |  | 3 |  |  |  | 0.5 | 1 | 0.5 | 0.75 | 0.25
| Normative TU's planned | 3 | 2.75 |  |  |  |  | #164: 0.75; #165: 1; #166: 1
| Normative TU's used |  | 0.75 |  |  |  |  | #164: 0.75
FS_MASSS | Study TU's planned | 7.5 | 9 |  |  |  | 1.5 | 2 | 2 | 2 | 1.5 | 0 | 0
Krizstian Kiss | Study TU's used |  | 9 |  |  |  | 1.5 | 2 | 2 | 2 | 1.5
Zhuoyi Chen | Normative TU's planned | 6 | 2.5 |  |  |  |  | #164: 0.5; #165: 1; #166: 1
| Normative TU's used |  | 0.5 |  |  |  |  | #164: 0.5
FS_AmbientIoT | Study TU's planned | 11.5 | 11.5 |  |  |  | 0.5 | 2 | 2 | 2 | 2 | 1.5 | 1.5
Runze Zhou | Study TU's used |  | 8.5 |  |  |  | 0.5 | 2 | 2 | 2 | 2
Fei Lu | Normative TU's planned | 0 | 0 |  |  |  |  | #164: 0; #165: 0; #166: 0
| Normative TU's used |  | 0
FS_AIML_CN | Study TU's planned | 4 | 4 |  |  |  | 0.5 | 1.5 | 1 | 1 | 0 | 0 | 0
Xiaobo Wu | Study TU's used |  | 4 |  |  |  | 0.5 | 1.5 | 1 | 1 | 0
Mehrdad Shariat | Normative TU's planned | 4 | 4 |  |  |  |  | #164: 1; #165: 1.5; #166: 1.5
| Normative TU's used |  | 1 | bar: #164
Drafting sessions (Q1 - Q5) | [7 empty] | #162: 5; #163: 10; #164: 0
Drafting sessions (Q0) | [7 empty] | #162: 5; #163: 2.25; #164: 5.25
Total planned (from the original overall plan) |  |  | 150 |  | 9 | 9 | 16 | 14 | 18 | 20 | 20 | 22 | 22
Total planned study (sum of individual plans) |  |  | 82.75 |  | 4 | 5.25 | 10.75 | 17 | 16.75 | 17 | 9 | 1.5 | 1.5
Total planned normative (sum of individual plans) |  |  | 44.25 |  |  |  |  | #164: 12; #165: 15.25; #166: 17
|  | Planned | Used
Total for Rel-19 Studies |  | 75 | 77.75 |  | 4 | 5.25 | 10.75 | 16.25 | 16.25 | 16.75 | 8.5 | 0 | 0
Total for Rel-19 Normative |  | 56 | 12.5 |  |  |  |  | #164: 12.5
Total for Rel-19 SID/WID |  | 131 | 90.25 |  | 4 | 5.25 | 10.75 | 16.25 | 16.25 | 16.75 | 21 | 0 | 0
TEI19 items
| 8.75 | [7 empty] | 2 | 2.5 | 1.5 | 2 | 0.75
TEI19_NetShare | Tianqi Xing | [6 empty] | #162: 0.5; #163: 0.25
TEI19_RVAS | Qian Chen | [6 empty] | #162: 0.5; #163: 0.25
TEI19_MINPA | Belen Pancorbo | [6 empty] | #162: 0.5; #163: 0.25
TEI19_DLPM | Richard Batorfi | [6 empty] | #165: 0.5
TEI19_VLANSUB | Stefan Rommer | [6 empty] | #165: 0.5
TEI19_IP-SP-EXP | Stefan Rommer | [6 empty] | #164: 0.5
TEI19_SLUPiR | Uri Baniel | [6 empty] | #163: 0.5
TEI19_TIME_SUB_EPS | Sebastian Speicher | [6 empty] | #164: 0.5
TEI19_OBGAD | Aihua Li | [6 empty] | #164: 0.5
TEI19_QME | Aihua Li | [6 empty] | #163: 0.5
TEI19_NFsel_by_tPLMN | Thomas Belling | [6 empty] | #163: 0.5
TEI19_HSBO | Hyesung Kim | [6 empty] | #165: 0.5; #166: 0.25
TEI19_MLR4RTR | Simon Cai | [6 empty] | #165: 0.5; #166: 0.5
TEI19_ProSe_NPN | Walter Dees | [6 empty] | #162: 0.5; #163: 0.25
Drafting sessions used | Total
FS_5GSAT_Ph3_ARCH | 1.75 | [6 empty] | #162: 1; #163: 0.75
FS_NG_RTC_Ph2 | 1.75 | [6 empty] | #162: 0.75; #163: 1
FS_XRM Ph2 | 3.25 |  |  |  |  | 0.75 |  | #162: 0.75; #163: 1; #164: 0.75
FS_EnergySys | 2.5 | [6 empty] | #162: 0.75; #163: 1; #164: 0.75
FS_MPS4msg | 0
FS_VMR_Ph2 | 1 | bar: #163
FS_5G_ProSe_Ph3 | 2 | bar: #162 to #163
FS_UIA_ARC | 1.75 | [6 empty] | #162: 0.75; #163: 1
FS_eEDGE_5GC_ph3 | 2.5 | [6 empty] | #162: 0.75; #163: 1; #164: 0.75
FS_UAS_Ph3 | 1.75 | [6 empty] | #163: 1; #164: 0.75
FS_UPEAS_Ph2 | 0.75 | [6 empty] | #163: 0.75
FS_5G_Femto | 1.5 | [6 empty] | #162: 0.75; #163: 0.75
FS_MASSS | 3.25 | [6 empty] | 0.75 | 0.75 | 1 | 0.75
FS_AmbientIoT | 1.75 | [6 empty] | #162: 1; #164: 0.75
FS_AIML_CN | 2.5 | [6 empty] | #161: 0.75; #163: 1; #164: 0.75
| 28 |  |  |  |  | 0.75 | 0 | 1.5 | 8.25 | 12.25 | 5.25 | 0 | 0

## SA2#166 November
S2-2412754
|  |  | Month | Aug, 23 | Oct, 23 | Nov, 23 | Jan, 24 | Feb, 24 | Apr, 24 | May, 24 | Aug, 24 | Oct, 24 | Nov, 24
|  |  | Meeting | #158 | #159 | #160 | E Ad hoc | #161 | #162 | #163 | #164 | #165 | #166
|  |  | TU total (for planning purposes) | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36
Pre-Rel-17 maintenance
Planned |  |  |  | 1 | 1 | 1 | 0 | bar: #161 to #166
Actual |  |  |  | 2 | 1 | 1.7 | N/A | 1 | 1 | 0 | 1 | 1
Rel-17 maintenance
Planned |  |  |  | 3 | 2 | 2 | 0 | bar: #161 to #166
Actual |  |  |  | 3 | 2 | 1.2 | N/A | 1.5 | 1 | 0.25 | 3 | 1
Rel-18 maintenance
Planned |  |  |  | 20 | 18 | 18 | 14 | 14 | 10 | 8 | 8 | 6 | 6
Actual |  |  |  | 22 | 22 | 20.6 | N/A | 8.25 | 6 | 4.5 | 6 | 6
Buffer (Overflow, other)
Planned |  |  |  | 6 | 6 | 6 | 6 | 6 | 4 | 4 | 4 | 3 | 3
Actual |  |  |  | 0 | 1 | 6 | N/A | 0 | 5 | 3 | 4 | 5
Total of Maintenance + Buffer
Planned |  |  |  | 30 | 27 | 27 | 20 | 22 | 16 | 14 | 14 | 11 | 11
Actual |  |  |  | 27 | 26 | 29.5 | N/A | 10.75 | 13 | 7.75 | 14 | 13
Rel-19
Planned |  |  |  | 6 | 9 | 9 | 16 | 14 | 18 | 20 | 20 | 22 | 22
Actual (not including drafting) |  |  |  | 9 | 10 | 5.25 | 10.75 | 16 | 16.75 | 16.75 | 21 | 17.75
Rel-19 TEI
Planned | [7 empty] | 0 | 2 | 2 | 2 | 3 | 3
Actual | [7 empty] | 6 | 2 | 2.5 | 1.5 | 2.5
Overall total
Planned |  |  |  | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36
Actual |  |  |  | 36 | 36 | 34.75 | N/A | 32.75 | 31.75 | 27 | 36.5 | 33.25
Rel-19 SID/WID detailed plan |  | TU estimates (from SID)
FS_5GSAT_Ph3_ARCH | Study TU's planned | 7 | 7 |  | 1 | 1 | 1.5 | 1 | 1.5 | 1 | 0 | 0 | 0
Hucheng Wang | Study TU's used |  | 7 |  | 1 | 1 | 1.5 | 1 | 1.5 | 1 | 0 | 0 | 0
Ramon Ferrus | Normative TU's planned | 5.5 | 5.5 |  |  |  |  | #164: 1.5; #165: 2; #166: 2
| Normative TU's used |  | 3.25 |  |  |  |  | #164: 1.5; #165: 1.75
FS_NG_RTC_Ph2 | Study TU's planned | 6 | 6.5 |  | 1 | 1.5 | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0
Yi Jiang | Study TU's used |  | 6 |  | 1 | 1.5 | 1 | 1 | 1 | 0.5 | 0 | 0 | 0
| Normative TU's planned | 5.5 | 5 |  |  |  |  | #164: 1.5; #165: 1.5; #166: 2
| Normative TU's used |  | 3.5 |  |  |  |  | #164: 2; #165: 1.5
FS_XRM_Ph2/XRM_Ph2 | Study TU's planned | 7 | 7.5 |  | 1 | 1 | 1 | 1 | 1 | 2 | 0.5 | 0 | 0
Georgios Gkellas | Study TU's used |  | 6.5 |  | 1 | 1 | 1 |  | 1 | 2 | 0.5 | 0 | 0
Curt Wong | Normative TU's planned | 6 | 5.5 |  |  |  |  | #164: 1.5; #165: 2; #166: 2
| Normative TU's used |  | 3.5 |  |  |  |  | #164: 1.5; #165: 2
FS_EnergySys/EnergySys | Study TU's planned | 6.5 | 8.5 |  | 1 | 1 | 1 | 1.5 | 1 | 1 | 2 | 0 | 0
Junshin Park | Study TU's used |  | 8.5 |  | 1 | 1 | 1 | 1.5 | 1 | 1 | 2 | 0 | 0
Costas Samdanis | Normative TU's planned | 6.5 | 4 |  |  |  |  | #164: 0; #165: 2; #166: 2
| Normative TU's used |  | 2 |  |  |  |  | #164: 0; #165: 2
FS_MPS4msg/MPS4msg | Study TU's planned | 3 | 3.5 |  |  | 0.75 | 0.5 | 1 | 0 | 1.25 | 0 | 0 | 0
Robert Streijl | Study TU's used |  | 2.5 |  |  | 0.75 | 0.5 | 0.75 | 0 | 0.5 | 0 | 0 | 0
| Normative TU's planned | 3 | 2 |  |  |  |  | #164: 1; #165: 0; #166: 1
| Normative TU's used |  | 1 |  |  |  |  | #164: 1; #165: 0
FS_VMR_Ph2/VMR_Ph2 | Study TU's planned | 3 | 3.25 |  |  |  | 0.5 | 0.5 | 1 | 1 | 0.25 | 0 | 0
Hong Cheng | Study TU's used |  | 3.25 |  |  |  | 0.5 | 0.5 | 1 | 1 | 0.25 | 0 | 0
Lars Nord | Normative TU's planned | 2.5 | 2.75 |  |  |  |  | #164: 0.75; #165: 1; #166: 1
| Normative TU's used |  | 1.75 |  |  |  |  | #164: 0.75; #165: 1
FS_5G_ProSe_Ph3/5G_ProSe_Ph3 | Study TU's planned | 2 | 2.5 |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0
Nassima Toumi | Study TU's used |  | 2.25 |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.25 | 0 | 0
| Normative TU's planned | 1.5 | 1.5 |  |  |  |  | #164: 0.5; #165: 0; #166: 1
| Normative TU's used |  | 0.75 |  |  |  |  | #164: 0.75; #165: 0
FS_UIA_ARC/UIA_ARC | Study TU's planned | 5.25 | 6.25 |  |  |  | 0.5 | 1.5 | 1.75 | 1.5 | 1 | 0 | 0
Mike Starsinic | Study TU's used |  | 6.25 |  |  |  | 0.5 | 1.5 | 1.75 | 1.5 | 1 | 0 | 0
| Normative TU's planned | 4.25 | 1.5 |  |  |  |  | #164: 0.5; #165: 0.5; #166: 0.5
| Normative TU's used |  | 1.5 |  |  |  |  | #164: 0.5; #165: 1
FS_eEDGE_5GC_ph3/eEDGE_5GC_ph3 | Study TU's planned | 4.5 | 4.75 |  |  |  | 0.5 | 1.5 | 1.5 | 1 | 0.25 | 0 | 0
Changhong Shan | Study TU's used |  | 4.75 |  |  |  | 0.5 | 1.5 | 1.5 | 1 | 0.25 | 0 | 0
| Normative TU's planned | 3 | 2.75 |  |  |  |  | #164: 0.75; #165: 1; #166: 1
| Normative TU's used |  | 1.75 |  |  |  |  | #164: 0.75; #165: 1
FS_UAS_Ph3/UAS_Ph3 | Study TU's planned | 3.5 | 3.75 |  |  |  | 0.5 | 1 | 1 | 1 | 0.25 | 0 | 0
LaeYoung Kim | Study TU's used |  | 3.75 |  |  |  | 0.5 | 1 | 1 | 1 | 0.25 | 0 | 0
Shabnam Sultana | Normative TU's planned | 3 | 2.75 |  |  |  |  | #164: 0.75; #165: 1; #166: 1
| Normative TU's used |  | 1.75 |  |  |  |  | #164: 0.75; #165: 1
FS_ISAC_ARC | Study TU's planned | 0 | 0
| Study TU's used |  | 0
| Normative TU's planned | 0 | 0
| Normative TU's used |  | 0
FS_UPEAS_Ph2/UPEAS_Ph2 | Study TU's planned | 2.25 | 2.25 |  |  |  | 0.25 | 0.5 | 1 | 0.5 | 0 | 0 | 0
Jinguo Zhu | Study TU's used |  | 2.75 |  |  |  | 0.25 | 0.5 | 1 | 1 | 0 | 0 | 0
Susana Sabater | Normative TU's planned | 2.25 | 2.25 |  |  |  |  | #164: 1; #165: 0.75; #166: 0.5
| Normative TU's used |  | 2 | bar: #164 to #165
FS_5G_Femto/5G_Femto | Study TU's planned | 2 | 2.5 |  |  |  | 0.5 | 0.5 | 0.5 | 0.75 | 0.25 | 0 | 0
Malla Reddy Sama | Study TU's used |  | 3 |  |  |  | 0.5 | 1 | 0.5 | 0.75 | 0.25 | 0 | 0
| Normative TU's planned | 3 | 2.75 |  |  |  |  | #164: 0.75; #165: 1; #166: 1
| Normative TU's used |  | 1.75 |  |  |  |  | #164: 0.75; #165: 1
FS_MASSS/MASSS | Study TU's planned | 7.5 | 9 |  |  |  | 1.5 | 2 | 2 | 2 | 1.5 | 0 | 0
Krizstian Kiss | Study TU's used |  | 9 |  |  |  | 1.5 | 2 | 2 | 2 | 1.5 | 0 | 0
Zhuoyi Chen | Normative TU's planned | 6 | 2.5 |  |  |  |  | #164: 0.5; #165: 1; #166: 1
| Normative TU's used |  | 1.5 |  |  |  |  | #164: 0.5; #165: 1
FS_AmbientIoT | Study TU's planned | 11.5 | 11.5 |  |  |  | 0.5 | 2 | 2 | 2 | 2 | 1.5 | 1.5
Runze Zhou | Study TU's used |  | 10.5 |  |  |  | 0.5 | 2 | 2 | 2 | 2 | 2
Fei Lu | Normative TU's planned | 0 | 0 |  |  |  |  | #164: 0; #165: 0; #166: 0
| Normative TU's used |  | 0 |  |  |  |  | #164: 0; #165: 0; #166: 0
FS_AIML_CN/AIML_CN | Study TU's planned | 4 | 4 |  |  |  | 0.5 | 1.5 | 1 | 1 | 0 | 0 | 0
Xiaobo Wu | Study TU's used |  | 4 |  |  |  | 0.5 | 1.5 | 1 | 1 | 0 | 0 | 0
Mehrdad Shariat | Normative TU's planned | 4 | 4 |  |  |  |  | #164: 1; #165: 1.5; #166: 1.5
| Normative TU's used |  | 2.5 |  |  |  |  | #164: 1; #165: 1.5
Drafting sessions (Q1 - Q5) | [8 empty] | 5 | 10 | 0 | 0
Drafting sessions (Q0) | [8 empty] | 5 | 2.25 | 5.25 | 4.5
Total planned (from the original overall plan) |  |  | 150 |  | 9 | 9 | 16 | 14 | 18 | 20 | 20 | 22 | 22
Total planned study (sum of individual plans) |  |  | 82.75 |  | 4 | 5.25 | 10.75 | 17 | 16.75 | 17 | 9 | 1.5 | 1.5
Total planned normative (sum of individual plans) |  |  | 44.75 |  |  |  |  | #164: 12; #165: 15.25; #166: 17.5
|  | Planned | Used
Total for Rel-19 Studies |  | 75 | 80 |  | 4 | 5.25 | 10.75 | 16.25 | 16.75 | 16.75 | 8.25 | 2 | 0
Total for Rel-19 Normative |  | 56 | 28.5 |  |  |  |  | #164: 12.75; #165: 15.75
Total for Rel-19 SID/WID |  | 131 | 108.5 |  | 4 | 5.25 | 10.75 | 16.25 | 16.75 | 16.75 | 21 | 17.75 | 0
TEI19 items
| 8.75 | [7 empty] | 2 | 2.5 | 1.5 | 2 | 0.75
TEI19_NetShare | Tianqi Xing | [6 empty] | #162: 0.5; #163: 0.25
TEI19_RVAS | Qian Chen | [6 empty] | #162: 0.5; #163: 0.25
TEI19_MINPA | Belen Pancorbo | [6 empty] | #162: 0.5; #163: 0.25
TEI19_DLPM | Richard Batorfi | [6 empty] | #165: 0.5
TEI19_VLANSUB | Stefan Rommer | [6 empty] | #165: 0.5
TEI19_IP-SP-EXP | Stefan Rommer | [6 empty] | #164: 0.5
TEI19_SLUPiR | Uri Baniel | [6 empty] | #163: 0.5
TEI19_TIME_SUB_EPS | Sebastian Speicher | [6 empty] | #164: 0.5
TEI19_OBGAD | Aihua Li | [6 empty] | #164: 0.5
TEI19_QME | Aihua Li | [6 empty] | #163: 0.5
TEI19_NFsel_by_tPLMN | Thomas Belling | [6 empty] | #163: 0.5
TEI19_HSBO | Hyesung Kim | [6 empty] | #165: 0.5; #166: 0.25
TEI19_MLR4RTR | Simon Cai | [6 empty] | #165: 0.5; #166: 0.5
TEI19_ProSe_NPN | Walter Dees | [6 empty] | #162: 0.5; #163: 0.25
Drafting sessions used | Total
FS_5GSAT_Ph3_ARCH | 1.75 | [6 empty] | #162: 1; #163: 0.75
FS_NG_RTC_Ph2 | 2.5 | [6 empty] | #162: 0.75; #163: 1; #165: 0.75
FS_XRM Ph2 | 4 |  |  |  |  | 0.75 |  |  | 0.75 | 1 | 0.75 | 0.75
FS_EnergySys | 3.25 | [7 empty] | 0.75 | 1 | 0.75 | 0.75
FS_MPS4msg | 0
FS_VMR_Ph2 | 1 | bar: #163
FS_5G_ProSe_Ph3 | 2 | bar: #162 to #163
FS_UIA_ARC | 1.75 | [6 empty] | #162: 0.75; #163: 1
FS_eEDGE_5GC_ph3 | 3.25 | [7 empty] | 0.75 | 1 | 0.75 | 0.75
FS_UAS_Ph3 | 1.75 | [6 empty] | #163: 1; #164: 0.75
FS_UPEAS_Ph2 | 0.75 | [6 empty] | #163: 0.75
FS_5G_Femto | 1.5 | [6 empty] | #162: 0.75; #163: 0.75
FS_MASSS | 3.25 | [6 empty] | 0.75 | 0.75 | 1 | 0.75
FS_AmbientIoT | 2.5 | [6 empty] | #162: 1; #164: 0.75; #165: 0.75
FS_AIML_CN | 3.25 | [6 empty] | 0.75 |  | 1 | 0.75 | 0.75
| 32.5 |  |  |  |  | 0.75 | 0 | 1.5 | 8.25 | 12.25 | 5.25 | 4.5 | 0