Source:	Editor

Title:	IVAS BASOP Verification (IVAS-10)

Version:	0.1.0

Agenda Item:	7.5

# Scope

This document outlines the planning, tools and results for the conversion of the IVAS floating point code in TS 26.258 to the BASOP version to become part of TS 26.251.

Additional information on the codec development project can be found in the other IVAS permanent documents, for which the latest versions can be found at:

https://www.3gpp.org/ftp/tsg_sa/WG4_CODEC/IVAS_Permanent_Documents.

# Introduction

The conversion of the IVAS floating point code to BASOP code is being done by Ittiam, under a contract issued by ETSI. The organization of this conversion is outlined in [1], which is also attached to the contract. Upon delivery of the code to ETSI, SA4 is expected to verify that the delivery meets the FL-to-FX requirements specified in [1]. The verification relies on objective measurement to cover a large set of operating points within a limited time but needs to be complemented with subjective listening tests. A more detailed time plan was provided in [2], now included in this document.

# Key factors / requirements for IVAS FL-to-FX conversion

## BASOPS

- Usage of BASOPs in IVAS FX code

- STL2023 BASOPs are used in IVAS FX code (64-bit and shorter).

- The EVS part of IVAS FX is reused from the “alternative” 64-bit FX EVS implementation (TS 26.452).

- Overflow and Carry flag used inside the BASOPs and written to global variables shall be avoided. In case Overflow or Carry would be required, new dedicated operators that expose those flags without the use of global variables shall be used.

To reflect this and potential other necessary improvements, some operators may need an update; this update will be provided by Audio SWG to Ittiam in time.

- Contribution to ITU-T on modified BASOPs will be desirable.

## Complexity

- Complexity (WMOPS) ratio between IVAS FX and IVAS FL should be no worse than the complexity ratio between EVS FX and EVS FL; the goal is that the design constraints are met with the FX code.

- Memory savings: always use the smallest data type (and respective BASOPs) as far as possible, in a reasonable balance with complexity.

## FX coding practices

- 3GPP Forge will be used as the platform of FX development, similarly to the development of FL code in Public Collaboration.

- Inclusion of 3rd party code or open-source code is not allowed; inclusion of code from generative  AI tools is not allowed.

- Structure of FL code shall be preserved to the maximum extent to allow comparison between FL and FX code and easier maintainability of the two code bases. This includes the best preservation of function prototypes and comments in the code; file names shall remain unchanged. In addition, all variables converted to FX shall be marked with precision information (integer, fractional) in Q-notation; precision changes should be documented; the goal is that the original functions could be used interchangeably during development; function names of converted functions shall avoid symbol clashes during the development; the objective is to ultimately have maximum similarity to the FL code and eventually all variables and function names also in FX shall be unified to their FL counterpart.

- Interoperability between FX and FL codes shall be guaranteed; for example, valid FL bitstreams shall be decodable by the FX-decoder, related to certain quality requirements (no drop).

- Making test vectors available for conversion is responsibility of Audio SWG.

# Time plan

Table 1: Verification time plan in table format. SA4 milestones in italics, verification milestones in bold.

| Date | Milestone |
| --- | --- |
| 31st August 2024 | - D1: Delivery of IVAS fixed-point Decoder and Renderer by Ittiam to SA4, fulfilling the FL-to-FX requirements |
| 1st September - 15th October | - Pre-testing phase D1: Decoder and Renderer - Testing starts in parallel on all formats. There may be "inter-format impact" from resolved issues. Fixes with wide impact need to be integrated for further testing. - Pre-testing may entail both objective and subjective testing, on a need basis. Objective testing may filter out critical cases to listen to. |
| Audio SWG telco (Sept. 13) | - Review progress of the fixed-point code conversion |
| 30th September 2024 | - D2: Delivery of IVAS fixed-point Encoder by Ittiam to SA4, fulfilling the FL-to-FX requirements, covering the following operation modes: - Mono (EVS) - ISM (core coder) - Stereo - MCT |
| 1st October - 13th January | - Pre-testing phase D2 Encoder for Mono, ISM, Stereo and MCT |
| Audio SWG telco (Oct. 18) | - Review progress of the fixed-point code conversion |
| 15th October – 12th November | - Subjective test phase of Decoder and renderer - Code freeze Decoder and renderer |
| 31st October 2024 | - D3: Delivery of IVAS fixed-point Encoder by Ittiam to SA4, fulfilling the FL-to-FX requirements, covering the following operation modes: - MASA - SBA - Parametric modes |
| Audio SWG telco (Nov. 4) | - Review progress of the fixed-point code conversion |
| 1st November - 13th January | - Pre-testing phase D3: encoder for MASA, SBA and Parametric modes |
| 12th November | - SA4#130 submission deadline, test report for Decoder and Renderer uploaded |
| SA4#130 (18th – 22nd November 2024) | - Verification and Agreement by SA4 on Delivery by Ittiam of IVAS fixed-point Decoder and Renderer, fulfilling FL-to-FX requirements |
| 30th November 2024 | - D4: Delivery of complete IVAS fixed-point Encoder v1 by Ittiam to SA4, targeting fulfilment the FL-to-FX requirements, including the following operation modes: - Combined formats |
| 1st December - 31th January, 2025 | - Pre-testing phase D4: Encoder v1 for Combined formats and remaining functionality |
| Audio SWG telco (Mar 14 2025) | - Verification by TSG SA WG 4 (SA4) on Encoder v2 (with potential additional bugfixes) |
| TSG SA#106 (10th – 12th December 2024) | - Approval by TSG SA (SA#106) of Delivery of IVAS fixed-point Decoder and Renderer, fulfilling FL-to-FX requirements, based on agreement in SA4 |
| January 31st, 2025 | - Delivery of the Encoder v2, targeting fulfilment of FL-to-FX requirements, as basis for subjective verification |
| 31st January 2025 - 11th February 2025 | - Subjective test phase D2-D4: Encoder v2 |
| Audio SWG Telco (Mar 14 2025) | - Verification by TSG SA WG 4 (SA4) on Encoder v2 (with potential additional bugfixes) |
| 31st March 2025 | - Delivery of the Encoder v3 (addressing most severe issues identified by the verification) |
| 13th May 2025 | - SA4#132 submission deadline, test report for Encoder uploaded |
| SA4#132 (19th – 23rd May 2025) | - Verification and Agreement by SA4 on Delivery by Ittiam of IVAS fixed-point Encoder, fulfilling FL-to-FX requirements |
| TSG SA#108 (10th – 13th June 2025) | - Approval by TSG SA (SA#108) of Delivery of IVAS fixed-point Encoder, fulfilling FL-to-FX requirements, based on agreement in SA4 |
| June 30th 2025 | - Delivery of Maintenance (further corrections and optimizations) to IVAS fixed-point Encoder/Decoder/Renderer |
| SA4#133-e, 21st -25th July, 2025 | - Agreement by TSG SA WG 4 (SA4) on Delivery of Maintenance (further corrections and optimizations) to IVAS fixed-point Encoder/Decoder/Renderer |
| TSG SA#109, 16th – 19th September, 2025 | - Approval on Delivery of Maintenance (further corrections and optimizations) to IVAS fixed-point Encoder/Decoder/Renderer |

# References

- SA4aA240038, Organization of IVAS Characterization Phase rev 1, https://www.3gpp.org/ftp/TSG_SA/WG4_CODEC/3GPP_SA4_AHOC_MTGs/SA4_Audio/Docs/SA4aA240038.zip

- S4aA240056, On the status of the IVAS BASOP conversion, https://www.3gpp.org/ftp/TSG_SA/WG4_CODEC/3GPP_SA4_AHOC_MTGs/SA4_Audio/Docs/S4aA240056.zip

# Revision history

| Date | Meeting | Subject/Comment | Old | New |
| --- | --- | --- | --- | --- |
| 2024-11-18 | SA4#130 | Initial version including requirements from SA4aA240038 and time plan from S4aA240056. | N/A | 0.0.1 |
| 2024-11-19 | SA4#130 | Included IVAS BASOP Decoder and Renderer from S4-242054 as Annex A. | 0.0.1 | 0.1.0 |
| 2024-11-21 | SA4#130 | Updated time plan based on S4-24xxxx | 0.1.0 | 0.1.1 |

Verification of Decoder and Renderer

The report on the verification of the IVAS BASOP Decoder and Renderer can be found in the electronic attachment “IVAS-10 Annex A Verification_of_IVAS_BASOP_decoder_and_renderer.docx”

Erik Norvell – Ericsson LM