Source:		Funding and Finance Group Chairman

Title:		Report from the Funding and Finance Group (FFG)

Agenda item:	8.1

| Decision | X |
| --- | --- |
| Discussion |  |
| Information |  |

Document for:

# 1	Introduction

The 3GPP Funding and Finance Group held its first meeting in Dusseldorf, Germany, from 19-20 June 2000.  The following representatives were present:

Phil Davidson	ETSI (Chair)

Keiji Yoshino	TTC

Yukio Yoshimura	ARIB

Yutaka Maeda	ARIB

Asok Chatterjee	T1 (reporting)

Myung G. Jang	TTA

Adrian Scrase	MCC

# 2	Agenda and documentation

The approved Agenda [3GPP FFG#1(00)01] and other meeting documentation is available under the OP area of the 3GPP web site.

# 3	Next meetings

FFG#2	Evening of Monday July 17, 2000 (especially to meet with CWTS prior to the OP meeting).

FFG#3	October 17-18, 2000, North America (with T1P1)

FFG#4	January 17-18 2001, Japan.

# 4	Terms of reference

The following Terms of Reference were agreed by the OP representatives.

The 3GPP Funding and Finance Group performs the following tasks:

- To progress all funding, finance and audit matters referred to the group by the 3GPP Organizational Partners and Project Coordination Group;

- To act solely through the Organizational Partners to facilitate their financial management of 3GPP;

- Specifically to offer guidance to the Mobile Competence Centre on expenditure issues, to carry out periodic auditing of expenditure, provide audit reports to the Organizational Partners, to check funding requests from the Technical Specification Groups and offer advice to the 3GPP Organizational Partners and Project Coordination Group.

It is recommended that the OP meeting approve these Terms of Reference.

Rec FFG1/1:	Terms of Reference for FFG to be approved by the Organizational Partners.

# 5	Open Invitation

There is an open invitation to visit MCC (Adrian Scrase) whenever FFG members are in the Sophia Antipolis area, to examine the records keeping and accounting practices.  As a matter of principle, MCC will supply any level of detailed information as requested by the OPs.

# 6	Working Methods

A good overview of finances will be provided at each meeting of the Group, such as expenditure to-date, projections for the end of the year, etc. Between meetings, MCC will provide as much information as requested by the Group members.

# 7	Financial Report (year 2000)

## 7.1	Expenditure

A Financial Report for year 2000 was received [3GPP FFG#1(00)02].

The expenditure figures provided by Mr Scrase were accepted.  For ‘Overhead’ expenses (other than PC/Laptops), there is at present no mechanism for actually tracking the ‘actual’ costs.  These are too deeply embedded in ETSI expenses.  Some improvement is required in this area.  There is a good  tracking of the major expenditures.

An extra 55 Keuro may be required for PCs/Laptops to be taken from Contingency fund for a year end figure of 100 kEuro.

There is a new PCG request for funding for of an authentication algorithm:  All Partners have agreed to the activity.  During pre-meeting discussions all SDOs except ARIB and TTC supported taking the funding from Contingency fund.

Rec FFG1/2:	It was agreed at the present meeting that work should start as soon as practicable on the preparation of a 3G Authentication Algorithm.

Rec FFG1/3:	Funding for this task will be taken from the Contingency

Rec FFG1/4:	The previously agreed upon principle of special funding mechanism involving ARIB/TTC for ‘Specific Tasks’ related expenses will be respected. [ARIB and TTC are considered as a single SDO for the purposes of ‘Task Specific’ expenses.

## 7.2	Income

TTA has paid 50% of their dues on June 13. The remaining 50% will be paid in August.

ARIB has sent 100% of their dues on June 14.

TTC’s situation was not clear but is now 100% received.

T1 will pay its full dues latest by the 1st week of July.

ETSI has already pent more than its ‘due’.

The situation of CWTS is not clear.

Action FFG1/1:	The meeting report, and funding situation etc. will be put in the OP area of the 3GPP Web site.

## 7.3	CWTS Custodianship

CWTS has requested custodianship of the ciphering algorithm. All other (4) SDOs [T1, ETSI, TTA, TTC/ARIB – TTC and ARIB are considered as a single SDO for this ‘task specific’ purpose] are custodians. The 344.7 Keuros for ciphering algorithm was paid by these 4 SDOs. CWTS has asked  how much it would cost if they were to sign the distribution agreement and become a custodian of this algorithm.

Rec FFG1/5:	FFG believes that there may be revenues to be made by CWTS, through administrative charges levied on the recipients.  CWTS should pay the same amount as other SDOs.  The amount (344.7 Keuros) should be divided into 5 parts, CWTS should pay that 1/5th amount.  The extra payments already made by the 4 SDOs for this purpose should be carried forward towards the accounts of these SDOs for the next year.

## 7.4	Asset register

Asset Register: The register of assets (the only assets that are uniquely 3GPP specific are the the PCs and Laptops) will be maintained by MCC, and presented to each meeting of the Committee – for visbiliity.  Other assets like servers, furniture are co-owned by 3GPP with ETSI, and are difficult to track at this point in time.

# 8	Finance for year 2001

A first draft Budget proposal was presented [3GPP FFG#1(00)03]

Overhead expenses in 2000 within the 3GPP budget are approximately 14% of the staff salary.  The proposal is to make overhead allocation to be 25% of the staff salary for 2001, in line with the actual historic cost figures of ETSI.  This is a more realistic figure so far as ETSI practices are concerned.  As of now there is only one item for ‘specific task’ expenditure in 2000: 312 kEuro for TTCN.

Rec FFG1/6:	Financing of 3GPP should reflect the true costs. Accounts for 2001 must be uditable.  Contingency should be 10% of costs.

Action FFG1/2:	Mr Scrase to bring in actual line by line numbers for overhead costs to explain as to why 25% is a realistic figure.  All OPs are invited to share similar information (i.e. business norm for overhead as a percentage of staff salary) with Mr Scrase over the next couple of weeks, if possible.  This will help the discussions to further refine the 2001 budget at the OP meeting in Beijing.  Furthermore, we need to track the actual salary/overhead ratio for 2000. Based on that actual figure, the actual contribution dues from the OPs for 2001 may have to be adjusted sometime during the year 2001.

# 9	Funding Mechanism for 2001

TTA will continue to provide one expert for 2001.

Probably ARIB expert will continue for 2001. To be confirmed.

Need to confirm the situation regarding expert from GSM Association.

Rec FFG1/7:	The existing mechanism and principle for funding (i.e. the 50-50 split,  ‘specific task funding’, etc.) should be retained for 2001.

Rec FFG1/8:	CWTS should take the full reponsibility of an OP’s financial obligations starting with the year 2001.

Rec FFG1/9:	GERAN should be 20% of the expenses, [after one expert from GSM Association, ½ an expert supporting ‘New SMG 9’, are taken out]. The remainder is the support  expenses for the current 4 TSGs. The GERAN expenses will be supported by the participating OPs only.  As of now we know that ETSI and T1 will participate in GERAN, and ARIB and TTC have indicated that they will not. It is HIGHLY RECOMMENDED that CWTS and TTA indicate their interests regarding participation in GERAN as soon as possible so that the budgets for 2001 can be finalized.