Source:	MCC

Title:	Status Report for Q2

Agenda item:	3

| Document for: Decision |  |
| --- | --- |
| Discussion | X |
| Information |  |

This report provides detailed information on 3GPP income and expenditure for H1 2006, and is based on figures available at 1 Sept 2006.

Table of Contents

1	Year 2006 MCC Expenditure	3

1.1	MCC Staff Expenditure (Officers and Assistants)	3

1.1.1	Additional Staff	3

1.2	MCC Contracted Support Experts Expenditure	4

1.2.1	MCC Contracted Support Experts Expenditure including non remunerated experts	4

1.2.2	MCC Contracted Support Experts Expenditure excluding non remunerated experts	6

1.2.3	MCC Contracted Experts Expenditure Detailed Breakdown by Activity	8

1.3	MCC Travel and Subsistence	16

2	Year 2006 Expenditure for 3GPP Task Forces	17

2.1	MCC Task Force 160 - 3GPP ATSs and PIXIT for UE R99	17

2.2	MCC Task Force 272 -  Test GERAN / UTRAN	19

3	Contingency	20

4	Year 2006 Partner Contributions	20

4.1	ARIB (24 Members)	20

4.2	CCSA (9 Members)	20

4.3	ETSI (205 Members)	20

4.4	ATIS (19 Members)	21

4.5	TTA (11 Members)	21

4.6	TTC (7 Members)	21

4.7	Total income expected from Partners	21

5	Invoices and credit notes issued 2006	21

6	Payments received in year 2006 from 3GPP Partners	22

# 1	Year 2006 MCC Expenditure

## MCC Staff Expenditure (Officers and Assistants)

This budget line is for those permanently employed ETSI Secretariat Staff within the Mobile Competence Centre.  There have been a number of changes in the staff complement which, during 2006, is now 4 Support Officers, 4 Assistants, and 0,5 Area Manager as follows:

John MEREDITH, Maurice POPE, Adrian ZOICAS, Gaby LENHARDT, Susanna KOOISTRA, Florence THOMAS, Emmanuelle WURFFEL, Loubna ALIAT and Adrian SCRASE (0,5).

Due to staff changes made during 2006, expenditure for H1 is lower than was originally planned. It is predicted that the year will close well within the prescribed budget.

### 1.1.1	Additional Staff

The additional budget line is included to cover the full time employment of Shicheng Hu for the management of TTCN development within MCC.  (Shicheng Hu is part of another ETSI Secretariat Team but currently works full time on MCC matters).  A budget of 150kEUR has been set for this item which will be sufficient for the year.

## 1.2	MCC Contracted Support Experts Expenditure

### MCC Contracted Support Experts Expenditure including non remunerated experts

The table and chart given below show the expenditure incurred for MCC Support Experts, including the value of those experts which are provided on a non-remunerated basis.  In each case, the number of days worked by each expert can be seen and the total value of that work given.  The slight overspend during H1 will be corrected when contractors take their vacation (for which they are not remunerated).

| MCC | Jan. | Feb. | March | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Total days | Total kEUR |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| C. Arzelier | 18,00 | 18,00 | 26,50 | 19,50 | 22,50 | 25,00 |  |  |  |  |  |  | 129,50 |  |
| S. Baev | 16,00 | 23,00 | 24,00 | 17,00 | 23,00 | 24,00 |  |  |  |  |  |  | 127,00 |  |
| A. Brekalo | 20,00 | 23,00 | 21,00 | 14,00 | 18,00 | 2,00 |  |  |  |  |  |  | 98,00 |  |
| J. Caldenhoven | 18,00 | 23,00 | 23,00 | 10,00 | 24,00 | 18,50 |  |  |  |  |  |  | 116,50 |  |
| M. Clayton | 21,00 | 26,00 | 22,50 | 21,00 | 5,00 | 13,00 |  |  |  |  |  |  | 108,50 |  |
| C. Gutierrez | 15,00 | 15,00 | 24,00 | 16,00 | 23,00 | 18,50 |  |  |  |  |  |  | 111,50 |  |
| S. Han | 22,00 | 19,50 | 22,50 | 16,00 | 19,00 | 21,00 |  |  |  |  |  |  | 120,00 |  |
| Y. Ishii | 19,00 | 15,00 | 20,00 | 14,00 | 13,00 | 20,00 |  |  |  |  |  |  | 101,00 |  |
| K. Kymalainen | 17,00 | 23,00 | 19,00 | 14,00 | 21,00 | 19,00 |  |  |  |  |  |  | 113,00 |  |
| A. Sultan | 10,00 | 13,00 | 14,50 | 5,00 | 8,00 | 11,00 |  |  |  |  |  |  | 61,50 |  |
| G. Thomasen | 21,00 | 15,00 | 24,00 | 24,00 | 21,00 | 23,00 |  |  |  |  |  |  | 128,00 |  |
| P. Usaï | 20,00 | 20,00 | 23,00 | 18,00 | 16,00 | 22,00 |  |  |  |  |  |  | 119,00 |  |
| Total | 217,00 | 233,50 | 264,00 | 188,50 | 213,50 | 217,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 1333,50 | 800,10 |

This chart includes the equivalent monetary value of the experts provided by ARIB and TTA

### MCC Contracted Support Experts Expenditure excluding non remunerated experts

The table and chart given below show the expenditure incurred for MCC Support Experts, excluding the value of those experts which are provided on a non-remunerated basis.  In each case, the number of days worked by each expert can be seen.

| MCC | Jan. | Feb. | March | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Total days | Total kEUR |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| C. Arzelier | 18,00 | 18,00 | 26,50 | 19,50 | 22,50 | 25,00 |  |  |  |  |  |  | 129,50 |  |
| S. Baev | 16,00 | 23,00 | 24,00 | 17,00 | 23,00 | 24,00 |  |  |  |  |  |  | 127,00 |  |
| A. Brekalo | 20,00 | 23,00 | 21,00 | 14,00 | 18,00 | 2,00 |  |  |  |  |  |  | 98,00 |  |
| J. Caldenhoven | 18,00 | 23,00 | 23,00 | 10,00 | 24,00 | 18,50 |  |  |  |  |  |  | 116,50 |  |
| M. Clayton | 21,00 | 26,00 | 22,50 | 21,00 | 5,00 | 13,00 |  |  |  |  |  |  | 108,50 |  |
| C. Gutierrez | 15,00 | 15,00 | 24,00 | 16,00 | 23,00 | 18,50 |  |  |  |  |  |  | 111,50 |  |
| K. Kymalainen | 17,00 | 23,00 | 19,00 | 14,00 | 21,00 | 19,00 |  |  |  |  |  |  | 113,00 |  |
| A. Sultan | 10,00 | 13,00 | 14,50 | 5,00 | 8,00 | 11,00 |  |  |  |  |  |  | 61,50 |  |
| G. Thomasen | 21,00 | 15,00 | 24,00 | 24,00 | 21,00 | 23,00 |  |  |  |  |  |  | 128,00 |  |
| P. Usaï | 20,00 | 20,00 | 23,00 | 18,00 | 16,00 | 22,00 |  |  |  |  |  |  | 119,00 |  |
| Total | 176,00 | 199,00 | 221,50 | 158,50 | 181,50 | 176,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 1112,50 | 667,50 |

This chart excludes the equivalent monetary value of the experts provided by ARIB and TTA

### 1.2.3	MCC Contracted Experts Expenditure Detailed Breakdown by Activity

#### 1.2.3.1	3GPP Including Non Remunerated Experts

This budget line shows the expenditure incurred by MCC experts in support of 3GPP TSGs, including non remunerated experts.  In previous years, the cost of supporting TSG GERAN had been separated out but this is no longer necessary due to the simplification of the Funding Formula.

| MCC | Jan. | Feb. | March | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Total days | Total kEUR |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| C. Arzelier | 18,00 | 18,00 | 26,50 | 19,50 | 22,50 | 25,00 |  |  |  |  |  |  | 129,50 |  |
| S. Baev | 16,00 | 23,00 | 24,00 | 17,00 | 23,00 | 24,00 |  |  |  |  |  |  | 127,00 |  |
| A. Brekalo | 20,00 | 23,00 | 21,00 | 14,00 | 18,00 | 2,00 |  |  |  |  |  |  | 98,00 |  |
| J. Caldenhoven | 18,00 | 23,00 | 23,00 | 10,00 | 24,00 | 18,50 |  |  |  |  |  |  | 116,50 |  |
| M. Clayton | 21,00 | 26,00 | 22,50 | 21,00 | 5,00 | 13,00 |  |  |  |  |  |  | 108,50 |  |
| C. Gutierrez | 5,00 | 11,00 | 22,50 | 12,00 | 18,00 | 15,50 |  |  |  |  |  |  | 84,00 |  |
| S. Han | 22,00 | 19,50 | 22,50 | 16,00 | 19,00 | 21,00 |  |  |  |  |  |  | 120,00 |  |
| Y. Ishii | 19,00 | 15,00 | 20,00 | 14,00 | 13,00 | 20,00 |  |  |  |  |  |  | 101,00 |  |
| K. Kymalainen | 17,00 | 23,00 | 19,00 | 14,00 | 21,00 | 19,00 |  |  |  |  |  |  | 113,00 |  |
| A. Sultan | 10,00 | 13,00 | 14,50 | 5,00 | 8,00 | 11,00 |  |  |  |  |  |  | 61,50 |  |
| G. Thomasen | 21,00 | 15,00 | 24,00 | 24,00 | 21,00 | 23,00 |  |  |  |  |  |  | 128,00 |  |
| P. Usaï | 20,00 | 20,00 | 23,00 | 18,00 | 16,00 | 22,00 |  |  |  |  |  |  | 119,00 |  |
| Total | 207,00 | 229,50 | 262,50 | 184,50 | 208,50 | 214,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 1306,00 | 783,60 |

This chart shows the use of Contractor resources for the support of 3GPP TSGs and includes non remunerated experts

#### 3GPP Excluding Non Remunerated Experts

This budget line shows the expenditure incurred by MCC experts in support of 3GPP TSGs, excluding non remunerated experts.

| MCC | Jan. | Feb. | March | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Total days | Total kEUR |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| C. Arzelier | 18,00 | 18,00 | 26,50 | 19,50 | 22,50 | 25,00 |  |  |  |  |  |  | 129,50 |  |
| S. Baev | 16,00 | 23,00 | 24,00 | 17,00 | 23,00 | 24,00 |  |  |  |  |  |  | 127,00 |  |
| A. Brekalo | 20,00 | 23,00 | 21,00 | 14,00 | 18,00 | 2,00 |  |  |  |  |  |  | 98,00 |  |
| J. Caldenhoven | 18,00 | 23,00 | 23,00 | 10,00 | 24,00 | 18,50 |  |  |  |  |  |  | 116,50 |  |
| M. Clayton | 21,00 | 26,00 | 22,50 | 21,00 | 5,00 | 13,00 |  |  |  |  |  |  | 108,50 |  |
| C. Gutierrez | 5,00 | 11,00 | 22,50 | 12,00 | 18,00 | 15,50 |  |  |  |  |  |  | 84,00 |  |
| K. Kymalainen | 17,00 | 23,00 | 19,00 | 14,00 | 21,00 | 19,00 |  |  |  |  |  |  | 113,00 |  |
| A. Sultan | 10,00 | 13,00 | 14,50 | 5,00 | 8,00 | 11,00 |  |  |  |  |  |  | 61,50 |  |
| G. Thomasen | 21,00 | 15,00 | 24,00 | 24,00 | 21,00 | 23,00 |  |  |  |  |  |  | 128,00 |  |
| P. Usaï | 20,00 | 20,00 | 23,00 | 18,00 | 16,00 | 22,00 |  |  |  |  |  |  | 119,00 |  |
| Total | 166,00 | 195,00 | 220,00 | 154,50 | 176,50 | 173,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 1085,00 | 651,00 |

This chart shows the use of Contractor resources for the support of 3GPP TSGs and excludes non remunerated experts

#### 1.2.3.3	ETSI TC MSG

This budget line shows the expenditure incurred in support of the ETSI Mobile Standards Group activity which is closely aligned with the work of 3GPP.  The activity is 100% funded by ETSI so it is necessary to accurately track the true cost such that it may be deducted from the 3GPP accounts.  The overspend is inconsequential for 3GPP since it will only impact on the ETSI accounts.

| MCC | Jan. | Feb. | March | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Total days | Total kEUR |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| C. Arzelier |  |  |  |  |  |  |  |  |  |  |  |  | 0,00 |  |
| S. Baev |  |  |  |  |  |  |  |  |  |  |  |  | 0,00 |  |
| J. Caldenhoven |  |  |  |  |  |  |  |  |  |  |  |  | 0,00 |  |
| M. Clayton |  |  |  |  |  |  |  |  |  |  |  |  | 0,00 |  |
| C. Gutierrez | 5,00 | 4,00 | 1,50 | 0,50 | 5,00 | 3,00 |  |  |  |  |  |  | 19,00 |  |
| S. Han |  |  |  |  |  |  |  |  |  |  |  |  | 0,00 |  |
| Y. Ishii |  |  |  |  |  |  |  |  |  |  |  |  | 0,00 |  |
| A. Jurisic |  |  |  |  |  |  |  |  |  |  |  |  | 0,00 |  |
| K. Kymalainen |  |  |  |  |  |  |  |  |  |  |  |  | 0,00 |  |
| A. Sultan |  |  |  |  |  |  |  |  |  |  |  |  | 0,00 |  |
| G. Thomasen |  |  |  |  |  |  |  |  |  |  |  |  | 0,00 |  |
| P. Usaï |  |  |  |  |  |  |  |  |  |  |  |  | 0,00 |  |
| Total | 5,00 | 4,00 | 1,50 | 0,50 | 5,00 | 3,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 19,00 | 11,40 |

#### 1.2.3.4	ETSI RT

This budget line shows the expenditure incurred in support of the ETSI Railway Telecommunications activity which performs the adaptation of 3GPP’s work for deployment in high speed trains.  The activity is 100% funded by ETSI so it is necessary to accurately track the true cost such that it may be deducted from the 3GPP accounts.

| MCC | Jan. | Feb. | March | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Total days | Total kEUR |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| C. Arzelier |  |  |  |  |  |  |  |  |  |  |  |  | 0,00 |  |
| S. Baev |  |  |  |  |  |  |  |  |  |  |  |  | 0,00 |  |
| J. Caldenhoven |  |  |  |  |  |  |  |  |  |  |  |  | 0,00 |  |
| M. Clayton |  |  |  |  |  |  |  |  |  |  |  |  | 0,00 |  |
| C. Gutierrez | 5,00 | 0,00 | 0,00 | 3,50 | 0,00 | 0,00 |  |  |  |  |  |  | 8,50 |  |
| S. Han |  |  |  |  |  |  |  |  |  |  |  |  | 0,00 |  |
| Y. Ishii |  |  |  |  |  |  |  |  |  |  |  |  | 0,00 |  |
| A. Jurisic |  |  |  |  |  |  |  |  |  |  |  |  | 0,00 |  |
| K. Kymalainen |  |  |  |  |  |  |  |  |  |  |  |  | 0,00 |  |
| A. Sultan |  |  |  |  |  |  |  |  |  |  |  |  | 0,00 |  |
| G. Thomasen |  |  |  |  |  |  |  |  |  |  |  |  | 0,00 |  |
| P. Usaï |  |  |  |  |  |  |  |  |  |  |  |  | 0,00 |  |
| Total | 5,00 | 0,00 | 0,00 | 3,50 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 8,50 | 5,10 |

## MCC Travel and Subsistence

The cost of travel and subsistence incurred by MCC is given in the chart below.  It is expected that the year will close within the prescribed budget.

# 2	Year 2006 Expenditure for 3GPP Task Forces

## MCC Task Force 160 - 3GPP ATSs and PIXIT for UE R99

This Task is the ongoing activity for the development of TTCN for 3G terminals.

The budget for this activity in 2006 is comprised of the following elements:

754 000 EUR – 2006 3GPP funding allocation

39 000 EUR – GCF funding allocation (invoice dated 15.06.06, not paid yet)

Total 2006 budget is therefore = 793 000 EUR.

The table given below shows the expenditure incurred during H1:

PAID EXPERTS

| STF 160 | Jan. | Feb. | March | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Total days | Total kEUR |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| W. Baloch | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 12,00 |  |  |  |  |  |  | 12,00 |  |
| V. Bardaux | 15,00 | 16,00 | 18,00 | 8,00 | 17,00 | 12,00 |  |  |  |  |  |  | 86,00 |  |
| X. Chen | 0,00 | 0,00 | 0,00 | 7,00 | 0,00 | 3,00 |  |  |  |  |  |  | 10,00 |  |
| O. Genoud | 4,00 | 0,00 | 11,00 | 2,00 | 8,00 | 0,00 |  |  |  |  |  |  | 25,00 |  |
| H. Griffiths | 7,00 | 6,00 | 6,00 | 4,00 | 9,00 | 7,00 |  |  |  |  |  |  | 39,00 |  |
| M. Abdul | 17,00 | 0,00 | 0,00 | 9,00 | 23,00 | 22,00 |  |  |  |  |  |  | 71,00 |  |
| L. Salmeron | 0,00 | 8,00 | 6,00 | 12,00 | 9,00 | 5,00 |  |  |  |  |  |  | 40,00 |  |
| T. Wacker | 4,50 | 10,00 | 5,50 | 2,50 | 7,50 | 3,00 |  |  |  |  |  |  | 33,00 |  |
| N. Wang | 0,00 | 0,00 | 3,00 | 3,00 | 3,00 | 3,00 |  |  |  |  |  |  | 12,00 |  |
| E. Weber | 1,00 | 6,00 | 4,50 | 5,00 | 7,00 | 2,00 |  |  |  |  |  |  | 25,50 |  |
| H. Zhang | 0,00 | 0,00 | 0,00 | 7,00 | 0,00 | 3,00 |  |  |  |  |  |  | 10,00 |  |
| J. Zhao | 0,00 | 0,00 | 0,00 | 7,00 | 0,00 | 3,00 |  |  |  |  |  |  | 10,00 |  |
| H. Zischler | 16,00 | 13,00 | 12,00 | 10,00 | 15,00 | 12,00 |  |  |  |  |  |  | 78,00 |  |
| Total | 64,50 | 59,00 | 66,00 | 76,50 | 98,50 | 87,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 451,50 | 270,90 |

In addition, the following voluntary resources have been pledged for this task:

10 man months – TDIA contribution

4,3 man months – R&S contribution

4 man months – Qualcomm contribution

1 man months – Testing Technologies

1 man months – Motorola

5 man months – Anritsu

The total 2006 voluntary resources therefore = 25,3 man months

The table given below shows the total value of the voluntary resources used for the development of TTCN:

VOLUNTARY EXPERTS

| STF 160 | Jan. | Feb. | March | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Total days | Total kEUR |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| X. Chen | 0,00 | 0,00 | 5,00 | 7,00 | 11,00 | 15,00 |  |  |  |  |  |  | 38,00 |  |
| M. Abdul | 0,00 | 0,00 | 10,00 | 11,00 | 0,00 | 0,00 |  |  |  |  |  |  | 21,00 |  |
| Thiruvathirai | 8,00 | 1,00 | 0,00 | 0,25 | 2,75 | 5,75 |  |  |  |  |  |  | 17,75 |  |
| L. Salmeron | 2,00 | 5,00 | 17,00 | 8,00 | 13,00 | 9,00 |  |  |  |  |  |  | 54,00 |  |
| W. Seka | 0,00 | 0,00 | 10,00 | 11,25 | 18,00 | 19,00 |  |  |  |  |  |  | 58,25 |  |
| N. Wang | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 |  |  |  |  |  |  | 0,00 |  |
| H. Zhang | 0,00 | 0,00 | 5,00 | 13,00 | 8,00 | 15,00 |  |  |  |  |  |  | 41,00 |  |
| Y. Zhang | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 |  |  |  |  |  |  | 0,00 |  |
| J. Zhao | 0,00 | 0,00 | 5,00 | 13,00 | 11,00 | 18,00 |  |  |  |  |  |  | 47,00 |  |
| Total | 10,00 | 6,00 | 52,00 | 63,50 | 63,75 | 81,75 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 277,00 | 166,20 |

## MCC Task Force 272 -  Test GERAN / UTRAN

This Task is for the development of TTCN for GERAN to UTRAN handover.

39 000 EUR has been allocated for this activity in 2006 and the table below shows how the expenditure incurred:

| STF 272 | Jan. | Feb. | March | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Total days | Total kEUR |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| H. Griffiths | 7,50 | 6,00 | 5,50 | 5,00 | 9,00 | 7,00 |  |  |  |  |  |  | 40,00 |  |
| Total | 7,50 | 6,00 | 5,50 | 5,00 | 9,00 | 7,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 40,00 | 24,00 |

# Contingency

| Contingency | Contingency Allocated |
| --- | --- |
| 200 | None |

# 4	Year 2006 Partner Contributions

The following tables give the contributions expected from the Organizational Partners in year 2006.  These tables do not take into account the credit notes that were issued in respect of the year 2005 surplus.

## 4.1	ARIB (24 Members)

| Budget category | ###### Amount (k€) |
| --- | --- |
| Equal division of Support budget | 189 |
| Proportional division of Support budget | 396 |
| Total | 585 |
| Deduction for provision of human resources | 136,20 |
| Amount due | 448,80 |

## 4.2	CCSA (9 Members)

| Budget category | ###### Amount (k€) |
| --- | --- |
| Equal division of Support budget | 189 |
| Proportional division of Support budget | 148 |
| Amount due | 337,00 |

## 4.3	ETSI (205 Members)

| Budget category | ###### Amount (k€) |
| --- | --- |
| Equal division of Support budget | 189 |
| Proportional division of Support budget | 3381 |
| Amount due | 3570,00 |

## 4.4	ATIS (19 Members)

| Budget category | ###### Amount (k€) |
| --- | --- |
| Equal division of Support budget | 189 |
| Proportional division of Support budget | 313 |
| Amount due | 502,00 |

## 4.5	TTA (11 Members)

| Budget category | ###### Amount (k€) |
| --- | --- |
| Equal division of Support budget | 189 |
| Proportional division of Support budget | 181 |
| Total | 370 |
| Deduction for provision of human resources | 136,20 |
| Amount due | 233,80 |

## 4.6	TTC (7 Members)

| Budget category | ###### Amount (k€) |
| --- | --- |
| Equal division of Support budget | 189 |
| Proportional division of Support budget | 115 |
| Amount due | 304,00 |

## 4.7	Total income expected from Partners

Total Financial Payment from Partners = 		5396,6 kEUR

Value of voluntary resources from Partners = 	   	272,4 kEUR

Total = 				  5669  kEUR

# 5	Invoices and credit notes issued 2006

The following credit notes and invoices were addressed to 3GPP Partners for 2005.

ARIB (Japan)

| 2005 CREDIT NOTE | dated 18/05/2006 | 70 370 EUR |
| --- | --- | --- |
| 2006 INVOICE | dated 18/05/2006 | 448 800 EUR |
| AMOUNT DUE | dated 18/05/2006 | 378 430 EUR |

CCSA (China)

| 2005 CREDIT NOTE | dated 18/05/2006 | 35 530 EUR |
| --- | --- | --- |
| 2006 INVOICE | dated 18/05/2006 | 337 000 EUR |
| AMOUNT DUE | dated 18/05/2006 | 301 470 EUR |

ETSI (France)

| 2005 CREDIT NOTE | dated 18/05/2006 | 437 190 EUR |
| --- | --- | --- |
| 2006 INVOICE | dated 18/05/2006 | 3 570 000 EUR |
| AMOUNT DUE |  | 3 132 810 EUR |

ATIS (United States)

| 2005 CREDIT NOTE | dated 18/05/2006 | 55 160 EUR |
| --- | --- | --- |
| 2006 INVOICE | dated 18/05/2006 | 502 000 EUR |
| AMOUNT DUE | dated 18/05/2006 | 446 840 EUR |

TTA (Korea)

| 2005 CREDIT NOTE | dated 18/05/2006 | 35 530EUR |
| --- | --- | --- |
| 2006 INVOICE | dated 18/05/2006 | 233 800 EUR |
| AMOUNT DUE | dated 18/05/2006 | 198 270 EUR |

TTC (Japan)

| 2005 CREDIT NOTE | dated 18/05/2006 | 37 620 EUR |
| --- | --- | --- |
| 2006 INVOICE | dated 18/05/2006 | 304 000 EUR |
| AMOUNT DUE | dated 18/05/2006 | 266 380 EUR |

TOTAL PAYMENTS DUE = 4 724 200 EUR

# 6	Payments received in year 2006 from 3GPP Partners

The following payments have been received from 3GPP Organizational Partners during year 2005.

ARIB (Japan)

Amount due	378 430 EUR

Amount Paid	378 430 EUR		21.06.06

CCSA (China)

Amount due	301 470 EUR

Amount Paid	301 470 EUR		16.08.06

ETSI (France)

Amount due	3 132 810 EUR

Amount Paid	3 132 810 EUR		18.05.06

ATIS (USA)

Amount due	446 840 EUR

Amount Paid	446 840 EUR		21.06.06

TTA (Korea)

Amount due	198 270 EUR

Amount Paid	198 270 EUR		08.06.06

TTC (Japan)

Amount due	266 380 EUR

Amount Paid	266 380 EUR		01.09.06

TOTAL PAYMENTS RECEIVED FROM ORGANIZATIONAL PARTNERS = 4 724 200 EUR

Additional contributions:

GCF

Amount due	  39 000 EUR		unpaid as of 31.08.06 – Invoice sent on 15.06.2006