Source:		Funding and Finance Group

Title:		Year 2009 Financial Status and calculation of Year End Surplus

Agenda item:	3.2

| Decision | X |
| --- | --- |
| Discussion |  |
| Information |  |

Document for:

# 1	Introduction

Document FFG#27(10)02 provides a detailed description of the income and expenditure for MCC in year 2009.  This present document uses that detailed description to calculate an income and expenditure summary relevant to 3GPP to determine the surplus to be returned to the Organizational Partners.

# Year 2009 income and expenditure by budget heading

## 2.1	Income 2009

The payments received from the Partners during 2009 are tabulated below.  In order to calculate the surplus to be returned to each Partner it is necessary to find the proportional value of the payments and these too are shown in the table.

| Source 2009 | Partner Payments |  |
| --- | --- | --- |
| ARIB | 515 | 9,13% |
| ATIS | 502 | 8,90% |
| CCSA | 332 | 5,88% |
| ETSI | 3655 | 64,78% |
| TTA | 345 | 6,12% |
| TTC | 293 | 5,19% |
| Total | 5642 | 100% |

(all figures in kEUR)

## 2.2	Expenditure

The following table shows the 2009 3GPP budget allocation and expenditure relating to each budget line within MCC.

It can be seen that total expenditure was 5380,98 kEUR against an income of 5642 kEUR.  There is therefore a surplus of 261,02 kEUR to be returned to the Partners.

| Resource description 2009 | ###### 3GPP ###### Budget (OP#21(09)07) | ###### 3GPP Expenditure | ###### Year end situation |
| --- | --- | --- | --- |
| MCC Staff (Note 1) | 1375,00 | 1 415,44 | -40,44 |
| Additional MCC Testing Staff | 150,00 | 157,76 | -7,76 |
| Promotional and Marketing materials | 75,00 | 60,10 | +14,90 |
| MCC Contractor Support to 3GPP (inc non-remunerated expert) (Note 2) | 913,00 | 807,60 | +105,40 |
| Additional IT support | 24,00 | 30,00 | -6,00 |
| MCC Travel and Subsistence | 580,00 | 530,00 | +50,00 |
| Specific Task 160 (Note 3) | 1040,00 | 1037,10 | +2,90 |
| Overheads (Note 4) | 1385,00 | 1332,98 | +52,02 |
| Contingency | 100,00 | 10,00 | +90,00 |
| Totals (kEUR) | 5642 | 5380,98 | 261,02 |

Note 1	Total MCC Staff (1466,904 kEUR) – TC SCP Support (51,469 kEUR)

Note 2:	3GPP Paid Contractors (671,40) + value of non-remunerated expert (136,20)

Note 3:	Excludes voluntary effort of 905,75 days (with a value of 543,45 kEUR)

Note 4:	Overheads calculated as follows:

| MCC staff costs in support of 3GPP | 1 415,44 |
| --- | --- |
| Additional testing staff | 157,76 |
| 3GPP contractors for MCC support | 807,60 |
| 3GPP contractors for Specific Task 160 | 1 037,10 |
| TOTAL Workforce | 3 417,90 |
| Overhead: 39%*Workforce expenditure (figure based on ETSI overhead calculation) | 1 332,98 |

# 3	Year 2009 surplus to be returned to 3GPP Partners

The following table summarises the manner in which the surplus funds from year 2009 are to be returned to 3GPP Partners:

| Partner | Proportion | 2009 Surplus to be returned |
| --- | --- | --- |
| ARIB | 9,13% | 23,83 |
| ATIS | 8,90% | 23,23 |
| CCSA | 5,88% | 15,35 |
| ETSI | 64,78% | 169,09 |
| TTA | 6,12% | 15,97 |
| TTC | 5,19% | 13,55 |
| Sub Total | 100% | 261,02 |

All figures in kEUR

# 4	3GPP Income and Expenditure Summary for year 2009

All figures in kEUR

| INCOME |  | EXPENDITURE |  |
| --- | --- | --- | --- |
| Monetary payments received from 3GPP Partners for project support (including contingency). Note 1 | 5505,80 | MCC costs relating to 3GPP support. Note 3 | 4343,88 |
| Expert resources provided by 3GPP Partners in lieu of monetary payment. Note 2 | 136,20 | MCC costs relating to 3GPP specific tasks Note 4 | 1037,10 |
| TOTAL INCOME | 5642 | TOTAL EXPENDITURE | 5381 |

2009 year end situation = 261 kEUR

Surplus to be returned to Partners = 261 kEUR

Note 1	Partners payments, excluding the value of non-remunerated expert

Note 2	Value of non-remunerated expert from TTA

Note 3	Costs of staff, travel, paid contractors, non-remunerated expert and overheads for 3GPP support

Note 4	Contractor cost for Task 160 (TTCN for 3G terminals)