## Slide 1: Summary of 2021 H1 Income and Expenditure
Source
3GPP Funding and Finance Group
OP#46(21)05

## Slide 2: Contents
Manpower (MCC staff)
Manpower (MCC Seconded Experts)
Manpower (IT support staff)
Manpower (TTCN testing support staff)
Manpower (TTCN STF 160 contractors)
Manpower (TTCN STF 160P, 160G & 160V contractors)
Travel and subsistence
Promotion and marketing materials
Training
Overheads
Contingency
Income from Partners
Conclusions

## Slide 3
Manpower (MCC staff)
During H1 2021 one MCC staff member resigned. A replacement was recruited but at higher cost due to competence and experience.
All meeting have taken place virtually during this period. Those virtual meetings have taken place over more days that the equivalent face-to-face meetings. This has led to the full holiday entitlement not having been taken by all staff. A provision has been set aside to cover this potential cost.
Taking the above into account, expenditure at the end of H1 2021 under the MCC staff budget line was approximately 1201 kEUR out of an annual budget of 2150 kEUR.
It is predicted that by the year end the expenditure under this budget line will be approximately 2290 kEUR. This will represent an overspend of approximately 140 kEUR.

## Slide 4
Manpower (MCC Seconded Experts)
CCSA, TTA and TSDSI have each provided a seconded expert (in-lieu of payment ) that has worked full time within MCC during H1 2021. This is expected to continue for the remainder of 2021.
They each have a value of 136,2 kEUR which has been deducted from the invoices issued to those Partners.
It is therefore not expected that this budget line will result in any overspend or underspend at the year end.

## Slide 5: Manpower (IT support staff)
The pandemic situation had a widespread impact on 3GPP during H1 2021. No physical meetings were held during this period hence no onsite IT support was required.
Taking the above into account, expenditure at the end of H1 2021 under the IT support staff budget line was 0 kEur out of an annual budget of 137 kEUR. The situation is expected to be the same by the year end as a return to face-to-face meetings is not foreseen until 2022.

## Slide 6
Manpower (TTCN testing support staff)
One full-time TTCN support expert is provided to manage the development of TTCN within 3GPP.
The cost of that expert at the end of H1 2021 was 73,2 kEUR out of an annual budget of 139 kEUR.
The year-end forecast is 143 kEUR, with an overspend of approximately 4kEUR (resulting from seniority increase).

## Slide 7
Manpower (TTCN STF 160 contractors)
By the end of H1 2021, 257 kEUR of contracts have been established for STF160 out of the annual budget of 754 kEUR. Further allocations will take place by the end of September.
The year-end prediction is that expenditure for this service will close within budget (with the possibility of a slight underspend).

## Slide 8
Manpower (TTCN STF 160P, 160G and 160Q contractors)
By the end of H1 2021:
156 kEUR has been allocated for TTCN development funded by PTCRB/CTIA
156 kEUR has been allocated for TTCN development funded by GCF
26 kEUR has been allocated for TTCN development funded by Qualcomm
The year-end prediction is that these funds will be exhausted by the year end.

## Slide 9: Travel and subsistence
The pandemic situation has led to the cancellation of all face-to-face meetings during H1 2021.
Due to the reimbursement of travel and flight reservations, expenditure at the end of H1 2021 under the travel and subsistence budget line was -271 EUR (-0,271 kEUR) out of an annual budget of 525 kEUR.
It is assumed that there will be no further physical meetings held for the remainder of 2021 and therefore no further expenditure under this budget line. It is also assumed that no tickets will be forward purchased during Q4 2021 for use in 2022. It is therefore predicted that the full amount of this budget line will be underspent by the year end.

## Slide 10: Promotion and marketing materials
The expenditure on promotion and marketing materials at the end of H1 2021 amounted to 14,3 kEUR from an annual budget of 60 kEUR. As of today, expenses are committed for 35,6 kEUR.
It is predicted that year end expenditure will be within the prescribed budget.

## Slide 11: Training
The expenditure on training at the end of H1 2021 amounted to approximately 1,8 kEUR from an annual budget of 20 kEUR.
It is predicted that training expenditure will be within budget at the year end (as training sessions have already been scheduled for Q3/Q4 2021).

## Slide 12: Overheads
The expenditure at the end of H1 2021 amounted to 677 kEUR from an annual budget of 1346 kEUR
It is predicted that by the year end expenditure will be approximately 1402 kEUR, representing an overspending of approximately 56 kEUR.
This prediction is made on the assumption that overheads for the year amount to 39% of manpower expenditure. However, an early calculation indicates that, due to the considerable change in working behaviour, overheads for 2021 may reduce to 36% of manpower expenditure. This fact will be verified by the year end and taken into account when calculating the amount to be returned to each Partner.

## Slide 13: Contingency
A contingency of 150 kEUR had been set aside for 2021.
During H1 2021 the expenditure of this budget line was 1,217 kEUR (expert’s immigration and work permit fees).
It is predicted that by the year end expenditure will be approximately 2 kEUR and that approximately 148 kEUR will remain in contingency.

## Slide 14
3GPP Income from Partners
Invoices issued and payment received by September 2021
Partner | Amount invoiced (kEUR) | Amount paid (kEUR)
ARIB | 265,467 | 265,467
CCSA | 649,701 | 649,701
ETSI | 2435,644 | 2435,644
ATIS | 410,324 | 410,324
TTA | 111,704 | 111,704
TTC | 173,340 | 173,340
TSDSI | 91,795 | 0
TOTAL | 4137,975 | 

## Slide 15: Year end prediction
Budget Line | Mid year actuals (kEUR) | Predicted year end situation (kEUR)
Manpower (MCC staff) | 1201 | +140
Manpower (Seconded Experts) | 204 | 0
Manpower (IT support staff) | 0 | -137
Manpower (TTCN testing support staff) | 73 | +4
Manpower (STF160 TTCN support contractors) | 257 | 0
Travel and subsistence | 0 | -525
Promotion and marketing materials | 14 | 0
Training | 2 | 0
Overheads | 677 | +56
Contingency | 1 | -148
Overall Year end Prediction | 2429 | -610
RED = Overspend
BLUE = Underspend

## Slide 16
Conclusions
On the expenditure side, the unforeseen pandemic has led to significant underspending as physical meetings have all but ceased and the associated travel cancelled.
On the income side, most Partner payments have been received. All payments are expected to be received by the year end.
It is not possible to predict precisely what will happen during the remainder of 2021, but at this stage it is expected that there will be an overall budget surplus in the order of 610 kEUR.