## Slide 1: Summary of 2023 H1 Income and Expenditure
Source
3GPP Funding and Finance Group
OP#50(23)05

## Slide 2: Contents
Personnel (MCC staff)
Personnel (MCC Seconded Experts)
Personnel (IT support staff)
Personnel (TTCN testing support staff)
Personnel (TTCN STF 160 contractors)
Personnel (TTCN STF 160P, 160G & 160V contractors)
Travel and subsistence
Promotion and marketing materials
Training
Overheads
Contingency
Income from Partners
Conclusions

## Slide 3
Personnel (MCC staff)
At the end of H1 2023 ETSI’s former CTO, Adrian Scrase went on retirement and the MCC Director, Issam Toufik has been appointed as the new CTO. No other changes to be reported.
At the end of H1 2023, approximately 1,399 kEUR had been spent from the MCC staff budget out of an annual budget of 2,374 kEUR, which had been underestimated due to an error in the calculation of the former CTO costs for H1 2023.
It is predicted that, by the year end, the expenditure under this budget line will be approximately 2,430 kEUR. This will represent an overspend of approximately 56 kEUR.

## Slide 4
Personnel (MCC Seconded Experts)
CCSA, TTA and TSDSI have each provided a seconded expert (in-lieu of payment ) that has worked full time within MCC during H1 2023. This is expected to continue for the remainder of 2023.
They each have a value of 136,2 kEUR which has been deducted from the invoices issued to those Partners.
It is therefore not expected that this budget line will result in any overspend or underspend at the year end.

## Slide 5: Personnel (IT support staff)
All F2F meeting occurrences where more than 100 delegates are expected to be present are now supported by dedicated IT personnel for the full duration of the meeting.
It includes the provision of online-access for remote attendees.
At the end of H1 2023 IT support had been provided for the following meetings:
- February: working groups in Athens (RAN, SA, CT)
- March: plenary meetings in Rotterdam
- May: working groups in Berlin (SA), Bratislava (CT), Incheon (RAN)
- June: plenary meetings in Taipei
The expenditure at the end of H1 2023 under the IT support staff budget line was 46,2 kEUR out of an annual budget of 51 kEUR.
The following H2 2023 face-to-face meetings are planned to be supported:
- August: working groups in Gothenburg (CT and SA), and Toulouse (RAN)
- September: plenary meetings in Bangalore
- October: working groups in Xiamen (-- > 6 hotels, 4 people required)
- November: working groups in Chicago
- December: plenaries in Edinburgh.
Taking the above into account, it is predicted that expenditure under the IT support budget by the year-end will be approximately 108,6 kEUR, which will represent an overspend of 57,6 kEUR.

## Slide 6
Personnel (TTCN testing support staff)
One full-time TTCN support expert is provided to manage the development of TTCN within 3GPP.
The cost of that expert at the end of H1 2023 was 98,5 kEUR out of an annual budget of 150 kEUR.
The year-end forecast is 160 kEUR, with an overspend of approximately 10 kEUR, resulting from salary related increases and bonuses.

## Slide 7
Personnel (TTCN STF 160 contractors)
By the end of H1 2023, 450 kEUR of contracts have been established for STF160 out of the annual budget of 754 kEUR. Further allocations will take place by the end of September.
The year-end prediction is that expenditure for this service will be underspent by 100 kEUR. This amount will be further confirmed when the next allocation will be closed.

## Slide 8
Personnel (TTCN STF 160P, 160G and 160Q contractors)
At the end of H1 2023:
156 kEUR has been allocated for TTCN development funded by PTCRB/CTIA
156 kEUR has been allocated for TTCN development funded by GCF
26 kEUR has been allocated for TTCN development funded by Qualcomm
It is predicted that these funds will be exhausted by the year end.

## Slide 9: Travel and subsistence
Travel have resumed at normal pace during H1 2023 and an increase of the cost for air travel and accommodation has been noticed .
The travel costs amounted to 203,7 kEUR out of a budget of 400 kEUR.
By the end of the year, it is predicted that travel costs will be equal to the budget of 400 kEUR.

## Slide 10: Promotion and marketing materials
The expenditure on promotion and marketing materials at the end of H1 2023 was 9,2 kEUR from an annual budget of 60 kEUR.
It is predicted that, by the end of the year, expenditure will be approximately 50 kEUR which will represent an underspend of 10 kEUR.

## Slide 11: Training
No trainings were delivered in H1 2023, but three training sessions are planned in H2.
It is therefore predicted that the training budget of 20 kEUR will be underspend by 5 KEUR by the end of the year.

## Slide 12: Overheads
The expenditure at the end of H1 2023 amounted to 751,3 kEUR from an annual budget of 1,438 kEUR
It is predicted that, by the year end, expenditure will be approximately 1,425 kEUR, representing an underspending of approximately 13 kEUR.
This prediction is made on the assumption that the overhead rate of 39% is applied which needs to be confirmed by the ETSI auditors.
It should be noted that the overhead rate may be impacted by the rapidly increasing rate of inflation, a fact that will be reassessed by the ETSI auditors at the year end.

## Slide 13: Contingency
A contingency of 150 kEUR had been set aside for 2023.
During H1 2023, the expenditure of this budget line was 15,4 kEUR (expert’s immigration, work permit fees and exchange rates costs).
It is predicted that by the year end, expenditure will be 20 kEUR and that approximately 130 kEUR will remain in contingency.

## Slide 14
3GPP Income from Partners
Invoices issued and payment received by September 2023
Partners | Amount invoiced (kEUR) | Amount paid (kEUR)
ARIB | 323 513 | 323 513
CCSA | 942 304 | Not paid yet
ETSI | 2 642 592 | 2 642 592
ATIS | 493 930 | 493 930
TTA | 170 527 | 170 527
TTC | 224 562 | 224 562
TSDSI | 324 158 | Not paid yet
TOTAL | 5 121 586 | 3 855 124

## Slide 15: Year end prediction
Budget Line | Mid year actuals (kEUR) | Predicted year end situation (kEUR)
Personnel (MCC staff) | 1 399 | + 56
Personnel (Seconded Experts) | 204,3 | 0
Personnel (IT support staff) | 46,2 | +58
Personnel (TTCN testing support staff) | 98,5 | +10
Personnel (STF160 TTCN support contractors) | 225 | - 100
Travel and subsistence | 203,7 | 0
Promotion and marketing materials | 9,2 | -10
Training | 0 | -5
Overheads | 751,3 | -14
Contingency | 15,4 | -130
Overall Year end Prediction | 2 952,6 | -135
RED = Overspend
BLUE = Underspend

## Slide 16
Conclusions
On the expenditure side, the error in the budget for the staff salaries in 2023 and the IT support required which is more than expected due to the multiplication of meeting venues and the support needed for remote access, will lead to an overspend of these two budget lines.
The other budget items are more in control compared to the original budget.
On the income side, two significant Partner payments are still pending. All payments are expected to be received by the year end.
Some budget items still need some fine tuning for the remainder of 2023, but at this stage it is expected that there will be an overall budget surplus in the order of 135 kEUR.