## Slide 1
3GPP F2F return
Overall plan from 4Q/2022 onwards Outcome from DM#6
21st September 2022
OPf220051

## Slide 2: Planning for November/2022 WGs
Decision from DM#5
  November WG meetings confirmed to be co-hosted by EF3 and NAF3 in Toulouse
    The potential budget gap of 155KEUR is confirmed to be jointly funded by EF3 and NAF3
    Invitations to be sent out within a week
  2-way remote access confirmed for all WGs’ main session and official break-out sessions
    Remote access for offline sessions will be arranged on a best-effort basis
      WG chairs and MCC will discuss and announce the details well in-advance of the meeting
Update from DM#6
  MCC provided a detailed update on the remote access setup for the different WGs and their break-out sessions. Plans are proceeding well.
  There was a confirmation from Toulouse council that they will fund the budget gap of 155KEUR – excellent news!

## Slide 3: Overall Planning for 2023
Proposed 2023 plan – overall considerations
  Goal is for 4 F2F WG meetings and 2 F2F TSGs. All other meetings planned as Electronic.
  CCSA to provide feedback on the most workable F2F meeting spacing (and location) from the perspective of pandemic-related hardship
    Option A: Feb, May, Aug, Nov as F2F WG meetings. 1 Electronic WG meeting each in Q2 and Q4. Option B: April, May, Oct, Nov as F2F WG meetings. 1 Electronic WG meeting each in Q1 and Q3. Option C: April, May, Aug, Nov as F2F WG meetings. 1 Electronic WG meeting each in Q1 and Q4.
    F2F TSGs: March, September. Other TSGs planned as Electronic.
  It is decided to pursue Option A
  In case travel hardship eases, then 1 additional WG meeting (October) and 1 additional TSG meeting (December) in 2H/2023 can potentially be converted to F2F

## Slide 4: Detailed Planning for 2023
Proposed 2023 meeting plan (confirmed, pending)
  February WGs: F2F in Europe – Athens (RAN), TBD (SA/CT), invitation latest by end of October
  March TSGs: F2F in Europe (Rotterdam)
  April WGs: Electronic
  May WGs: F2F in Asia (RAN in Korea, SA/CT in Europe (check Singapore option latest by end of November)
  June TSGs: Electronic
  August WGs: F2F in Europe
  September TSGs: F2F in Europe/India [location TBD latest by end of November]
  October WGs: Electronic
  November WGs: F2F in NA (probably US, invitation latest 9 months ahead, preferably earlier)
  December TSGs: Electronic / India [TBC, next check end of November 2022]

## Slide 5: Next steps for F2F_DM
F2F_DM#7 to be held F2F on 16th November 11:30-14h UTC in Toulouse
  Remote participation will also be supported

## Slide 6
Thank You!