## Slide 1
3GPP F2F return
Overall plan from 4Q/2022 onwards Outcome from DM#5
29th August 2022
OPf220053

## Slide 2: Proposed planning for November/2022 WGs
Agreements from DM#3bis
  November WG meetings confirmed to be hosted by NAF3 in Canada. This has been overridden by DM#4 and DM#5
  TSG chairs to work on best practices for 2-way remote access
  If pandemic-related travel hardship does not fundamentally and substantially degrade, OPs will not veto the November meeting to go ahead F2F
  Strongly encourage F2F participation, 2-way remote access primarily meant for folks under severe pandemic-related hardship
Decision from DM#4
  Re-locate November WG meetings to Europe EF3 to seek suitable location(s), and provide information by 29th August
Decision from DM#5
  November WG meetings confirmed to be hosted by EF3 in Toulouse
    The potential budget gap of 155KEUR is confirmed to be jointly funded by EF3 and NAF3
    Invitations to be sent out within a week
  2-way remote access confirmed for all WGs’ main session and official break-out sessions
    Remote access for offline sessions will be arranged on a best-effort basis
      WG chairs and MCC will discuss and announce the details well in-advance of the meeting

## Slide 3: Overall Planning for 2023
Proposed 2023 plan – overall considerations
  Goal is for 4 F2F WG meetings and 2 F2F TSGs. All other meetings planned as Electronic.
  CCSA to provide feedback on the most workable F2F meeting spacing (and location) from the perspective of pandemic-related hardship
    Option A: Feb, May, Aug, Nov as F2F WG meetings. 1 Electronic WG meeting each in Q2 and Q4. Option B: April, May, Oct, Nov as F2F WG meetings. 1 Electronic WG meeting each in Q1 and Q3. Option C: April, May, Aug, Nov as F2F WG meetings. 1 Electronic WG meeting each in Q1 and Q4.
    F2F TSGs: March, September. Other TSGs planned as Electronic.
  It is decided to pursue Option A
  In case travel hardship eases, then 1 additional WG meeting (October) and 1 additional TSG meeting (December) in 2H/2023 can potentially be converted to F2F

## Slide 4: Detailed Planning for 2023
Proposed 2023 meeting plan (confirmed, pending)
  February WGs: F2F in Europe – Athens (RAN), TBD (SA/CT)
  March TSGs: F2F in Europe (Rotterdam)
  April WGs: Electronic
  May WGs: F2F in Asia (RAN in Korea, SA/CT in Europe (check Singapore option latest by end of November)
  June TSGs: Electronic
  August WGs: F2F in Europe
  September TSGs: F2F in Europe/India [location TBD latest by end of November]
  October WGs: Electronic
  November WGs: F2F in NA
  December TSGs: Electronic / India [TBC, next check end of November 2022]

## Slide 5: Next steps for F2F_DM
F2F_DM#5bis on 2024 meeting hosting distribution to be held 21/Sept 13-14h UTC
F2F_DM#6 to be held face-to-face during the November WG meetings in Toulouse, exact date&time TBD
  Review 2023 plan and confirm pending issues where possible
  Distribution of hosts for 2024 meeting calendar

## Slide 6
Thank You!