## Slide 1
3GPP F2F return
Overall plan
F2F DM interim meeting – 28/Jan/2022
HOSTING_F2F_CC#002_SynchUp OPf220002
28 January 2022, Conference Call

## Slide 2: Overall plan
Based on the current covid-related travel and quarantine policies it is proposed to target the following general plan for 2022:
  All 3GPP meetings until end of May are to be held as E-meetings
  TSG#96 in June to be held F2F in Budapest/HU
  All July WG meetings to be held as E-meetings
  RAN WGs in August to be held F2F in Toulouse/FR
  SA and CT WGs in August to be held F2F in Gothenburg/Sweden
    Some smaller groups are hosted in Malaga/SP, Wroclaw/PL, Bath/UK
  TSG#97 in September to be held as E-meeting (originally NA)
  All WG meetings in October to be held as E-meetings (originally India and China)
  All WG meetings in November to be held F2F
  TSG#98 in December: proposal to hold this as F2F meeting in Seville/SP
In case return-quarantine restrictions entirely disappear, moving even more meetings to F2F in 2022 can be considered
  A minimum of 6 months lead time is needed for the host to find location, sign contract, etc…
Confirm target plan now
Tentative for now,
confirm target plan on 2nd March

## Slide 3: Detailed considerations
Review the status of June and August meetings – see separate contributions
November WG planning (14-18/Nov)
  Planned to be hosted in North America
  ATIS to seek a suitable location (considering the impact on delegates of all Covid-19 rules and visa issues) and present information for F2F_DM#2 (2nd/March)
  F2F_DM#2 to confirm, or re-consider November WG meeting location if suitable North American location is not identified
    Re-confirm North America, or move the location to Europe
December TSG planning (12-16/Dec)
  EF3 has signed contract (from earlier postponement) for Seville/SP
  Unreasonable hardship if return-quarantine is still in place: X-mas quarantine!
  Re-check status at F2F_DM#2 (2nd/March)

## Slide 4: F2F Decision Meeting plan
F2F DM interim sync up 28th January (Friday) 13-15h UTC
  Re-confirm/update plans for F2F meetings.
[MHSG#27: 7th February (Monday) 13-15h UTC
  Update F2F resumption study on key criteria to cover Omicron policies]
F2F_DM#2: 2nd March (Wednesday) 13-15h UTC
  Confirm target plan for Sept-Dec/2022
  Make formal decision on June TSGs
  Review planning status (August, Nov meetings)
F2F_DM#3: 10th May (Tuesday) 13-15h UTC
  Formal decision on August WGs, formal decision on September TSGs
F2F_DM#4: 16 August (Tuesday) 13-15h UTC
  Formal decision on November WGs and December TSGs

## Slide 5
Thank You!