## Slide 1
3GPP F2F return
Overall plan from 4Q/2022 onwards Input for discussion and decision to DM#4
16th August 2022
OPf220040

## Slide 2: Proposed planning for November/2022 WGs
Agreements from DM#3bis
  November WGs confirmed as F2F, and to be hosted in Canada
  TSG chairs to work on best practices for 2-way remote access
  If pandemic-related travel hardship does not fundamentally and substantially degrade, OPs will not veto the November meeting to go ahead F2F
  Strongly encourage F2F participation, 2-way remote access primarily meant for folks under severe pandemic-related hardship
Proposal for DM#4
  In case meeting invite cannot be distributed in time for expected length of the visa process, explore alternative location for November F2F meetings in Europe

## Slide 3: Overall Planning for 2023
Proposed 2023 plan – overall considerations
  Goal is for 4 F2F WG meetings and 2 F2F TSGs. All other meetings planned as Electronic.
  CCSA to provide feedback on the most workable F2F meeting spacing (and location) from the perspective of pandemic-related hardship
    Option A: Feb, May, Aug, Nov as F2F WG meetings. 1 Electronic WG meeting each in Q2 and Q4. Option B: April, May, Oct, Nov as F2F WG meetings. 1 Electronic WG meeting each in Q1 and Q3. Option C: April, May, Aug, Nov as F2F WG meetings. 1 Electronic WG meeting each in Q1 and Q4.
    F2F TSGs: March, September. Other TSGs planned as Electronic.
  Based on CCSA feedback it is proposed to pursue Option C
  In case travel hardship eases, then 1 additional WG meeting and 1 additional TSG meeting in 2H/2023 can potentially be converted to F2F

## Slide 4: Detailed Planning for 2023
Proposed 2023 meeting plan
  February WGs: Electronic
  March TSGs: F2F in Europe
  April WGs: F2F in [Europe?]
  May WGs: F2F in Asia (RAN in Korea, SA/CT in [TBD])
  June TSGs: Electronic
  August WGs: F2F in Europe
  September TSGs: F2F in [Europe?]
  October WGs: Electronic
  November WGs: F2F in [NA]
  December TSGs: [Electronic]

## Slide 5: Next steps for F2F_DM
Summary from F2F_DM#4 on 16/August
  [November/2022 meeting conclusion]
  [2023 meeting planning outcome]
Actions for F2F_DM
  [Follow up F2F_DM#4bis on 29/August to undertake final confirmation for November WG meetings and potential other items]

## Slide 6
Thank You!