## Cover sheet
3GPP TSG RAN WG5#94-e | [8 empty] | R5-220772
<Electronic meeting, 21st Feb - 4th Mar, 2022>
Agenda Item: | 7.4.2
Source: | China Unicom
Title: | WP on ENDC_UE_PC2_R17_NR_TDD-UEConTest for RAN5#94e
Work item code: | ENDC_UE_PC2_R17_NR_TDD-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The HPUE (PC2) for EN-DC with 1 LTE band and 1 NR TDD band have significant benefits for increasing UE transmission power and improving EN-DC network UL coverage. In R16, RAN4 have already finished 2 work items on High power UE (power class 2) for EN-DC combos, one WI is for HPUE ENDC with 1 LTE FDD band + 1 NR TDD band, another is for HPUE ENDC with 1 LTE TDD band + 1 NR TDD band. Since there are only a few HPUE ENDC configurations are included in these two R16 WIs, RAN4 have approved a R17 basket WI ENDC_UE_PC2_R17_NR_TDD at Sep 2020 to meet operators’ deployment demand of increasing PC2 ENDC combinations. It is proposed to introduce an associated RAN5 work item to enable UE conformance testing for High power (power class 2) EN-DC with 1 LTE band + 1 NR TDD band UEs in time.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed configurations (Note 1) | Number of new configurations | Comments
Overall completion |  | 17% (+1%) | 2 | 26
Completion Compensation |  | -
| Note 1: | Only test cases / configurations completed for all applicable WP areas and sub-areas are counted. For completed test cases / configurations per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed configurations | Number of new configurations | Comments
NSA Option 3 (EN-DC) (FR1) |  | 17.4% (+5%) | 2 | 26
FR1 |  | 17.4% (+5%) | 2 | 26
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | NSA Option 3 (EN-DC)
TS:Area Scope | TS/Area | Completion | Number of new completed PC2 configurations | Number of new PC2 configurations | FR1
[5 empty] | Completion | Number of new completed test cases / configurations | Number of new test cases / configurations
EN-DC HPUE (PC2) configurations
EN-DC FR1 PC2 (2 bands)
EN-DC FR1 Inter-band (two bands) | PC2 EN-DC (two bands) | 13% (+5.3%) | 2 | 26 | 13% (+5.3%) | 2 | 26
5 References
[1] RP-211420 | Revised WID on UE conformance - ENDC_UE_PC2_R17_NR_TDD for RAN#92e
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP on UE conformance - ENDC_UE_PC2_R17_NR_TDD | [12 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | Relative weight of effort vs TS contribution | [8 empty] | End of workplan columns. Note! Do not remove this column.
WI code |  | ENDC_UE_PC2_R17_NR_TDD-UEConTest | [14 empty] | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 5 | 5
WP Scope: |  | The purpose of present document is to provide a workplan for the RAN5 work item High power UE (power class 2) for EN-DC (1 LTE FDD band + 1 NR TDD band) comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID). | [14 empty] | 38.508-1: Test frequencies | 38.508-2: UE capabilities | 38.521-x: Common Clause | 38.521-x: Tx test cases / 38.522: Test case applicability | 38.521-x: Rx test cases / 38.522 Test case applicability | 38.521-4: RF perfromance test cases / 38.522: Test case applicability | 38.533: RRM test cases / 38:.522 Test case applicability | 38.903: MU and TT | 38.905: Test point analysis
WP Resp: |  | Yu Shi, China Unicom |  |  | shiyu19@chinaunicom.cn | [7 empty] | WP item completion |  |  | NSA Option 3 (EN-DC)
TS Resp: |  | N/A |  |  | N/A
WP Item ID | Is new configuration or test case? | TS/Area | Configuration / Test case clause | UL configuration(s) / Test case title | Type of change | Interested Operator | Company | Status | Target | TDOC(s) | Comments | Weight | Overall | NSA Option 3 (EN-DC) |  | FR1
17.4% (+5%)
27
26
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row. | [15 empty] | CALCULATED CELLS | TS STATUS INPUT
38.101-3: HPUE (PC2) EN-DC Inter-band (two bands)
1 | Y | PC2 EN-DC (two bands) | DC_1A_n78A | DC_1A_n78A | New PC2 Config | China Unicom | China Unicom | Completed | RAN5#91-e (May-21) | 38.508-2： R5-213258 38.521-3： R5-214030(cl 7.3B), R5-221892 |  | 1 | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
2 | Y | PC2 EN-DC (two bands) | DC_1A_n78C | DC_1A_n78A | New PC2 Config | China Unicom | China Unicom | Completed | RAN5#92 (Aug-21) | 38.508-2： R5-215982 |  | 1 | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
3 | Y | PC2 EN-DC (two bands) | DC_2A_n41A | DC_2A_n41A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4 | Y | PC2 EN-DC (two bands) | DC_2A_n77a | DC_2A_n77A | New PC2 Config | Verizon | Verizon Qualcomm Ericsson | Ongoing | RAN5#95 (May-22) | 38.521-3: R5-221337 |  | 1 | 14.3% (+14.3%) | 14.3% (+14.3%) |  | 14.29% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0%
5 | Y | PC2 EN-DC (two bands) | DC_2A-2A_n77A | DC_2A_n77A | New PC2 Config | Verizon |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6 | Y | PC2 EN-DC (two bands) | DC_5A_n77A | DC_5A_n77A | New PC2 Config | Verizon | Verizon Qualcomm Ericsson | Ongoing | RAN5#95 (May-22) | 38.521-3: R5-221337 |  | 1 | 14.3% (+14.3%) | 14.3% (+14.3%) |  | 14.29% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0%
7 | Y | PC2 EN-DC (two bands) | DC_5A_n78A | DC_5A_n78A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8 | Y | PC2 EN-DC (two bands) | DC_7A_n78A | DC_7A_n78A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
9 | Y | PC2 EN-DC (two bands) | DC_8A_n78A | DC_8A_n78A | New PC2 Config | China Unicom | China Unicom | Ongoing | RAN5#95 (May-22) | 38508-2: R5-220776 38521-3: R5-221892 |  | 1 | 81% (+81%) | 81% (+81%) |  | 80.95% | 0% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100%
10 | Y | PC2 EN-DC (two bands) | DC_12A_n77A | DC_12A_n77A | New PC2 Config | AT&T |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
11 | Y | PC2 EN-DC (two bands) | DC_13A_n77A | DC_13A_n77A | New PC2 Config | Verizon | Verizon Qualcomm Ericsson | Ongoing | RAN5#95 (May-22) | 38.521-3: R5-221337 |  | 1 | 14.3% (+14.3%) | 14.3% (+14.3%) |  | 14.29% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0%
12 | Y | PC2 EN-DC (two bands) | DC_14A_n77A | DC_14A_n77A | New PC2 Config | AT&T |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
13 | Y | PC2 EN-DC (two bands) | DC_30A_n77A | DC_30A_n77A | New PC2 Config | AT&T |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
14 | Y | PC2 EN-DC (two bands) | DC_66A_n41A | DC_66A_n41A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
15 | Y | PC2 EN-DC (two bands) | DC_66A_n77A | DC_66A_n77A | New PC2 Config | Verizon | Verizon Qualcomm Ericsson | Ongoing | RAN5#95 (May-22) | 38.521-3: R5-221337 |  | 1 | 14.3% (+14.3%) | 14.3% (+14.3%) |  | 14.29% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0%
16 | Y | PC2 EN-DC (two bands) | DC_66A-66A_n77A | DC_66A_n77A | New PC2 Config | Verizon |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
17 | Y | PC2 EN-DC (two bands) | DC_66A-66A-66A_n77A | DC_66A_n77A | New PC2 Config | Verizon |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
18 | Y | PC2 EN-DC (two bands) | DC_48A_n77A | DC_48A_n77A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
19 | Y | PC2 EN-DC (two bands) | DC_48C_n77A | DC_48A_n77A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
20 | Y | PC2 EN-DC (two bands) | DC_48C_N77C | DC_48A_n77A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
21 | Y | PC2 EN-DC (two bands) | DC_48A_N77C | DC_48A_n77A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
22 | Y | PC2 EN-DC (two bands) | DC_48D_n77A | DC_48A_n77A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
23 | Y | PC2 EN-DC (two bands) | DC_48D_N77C | DC_48A_n77A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
24 | Y | PC2 EN-DC (two bands) | DC_48C_n77C | DC_48A_n77A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
25 | Y | PC2 EN-DC (two bands) | DC_48E_n77A | DC_48A_n77A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
26 | Y | PC2 EN-DC (two bands) | DC_28A_n78A | DC_28A_n78A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Note on S1: The TS's weight number is used to set the reletive weights between TS contributions used in the overall calculation of completeness of teh WP item. Setting it to 0 for a WP item means that it will not be included at all in the calculation.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new configuration or a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on M6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.
Note on Q12: Rapporteur guideline to assign applicable sub-areas for a WP item (columns S to X) To Set applicable sub-area(s) for a WP item do: - Copy the formula/cell content from one of the other non-empty cells under the "WP item status vs Area" section (columns S to X). To Clear applicable sub-area(s) for a WP item do: - Select the cell for teh WP item for the sub-area and press <Delete>-botton (clear content of the cell).