## Slide 1: On 3GPP Timeline
MediaTek Inc.
3GPP TSG RAN#98e RP-223245
December 12th – 16th, 2023 Agenda Items 6.1, 15

## Slide 2: Proposal
Rel-18 Timeline
Current Timeline
  Stage 2 Mar 2023 (#99)
  Stage 3 PHY Sep 2023 (#101)
  Stage 3 Other Dec 2023 (#102)
  ASN.1, APIs etc. Mar 2024 (#103)
  Perf. Jun 2024 (#104)
Observation 1
  R18 planning was done with the above Timeline and associated TUs
  At this plenary, Rel-18 effort continues with
    Misc. SI>WI conversions
    Misc. WI scope discussions
    Misc. new R18 proposals
  It is important to continue these discussions following the same Timeline assumptions as above
  The main issue at this TSG#98e is Stage 2 (SA)
Proposal 1
  RAN#98e to keep RAN Rel-18 timeline unchanged
[1/2]
Rel-19 Planning
Observation 2
  Rel-19 Package in Sep 2023 is overall not realistic
  Cross TSG alignment from the outset is important
Proposal 2
  RAN and SA Packages approval in TSG#102 / Dec 2023
  RAN and SA WS in Q2 2023
  R19 Schedule to be discussed in TSG#99/100
  NOTE: the above of course requires SA decision and cross TSG coord.

## Slide 3: Proposal
[2/2]
2023 |  |  |  | 2024 | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2
#99 | #100 | #101 | #102 | #103 | #104
R18 Current |  |  |  |  | 
R18 Proposal |  |  |  |  | 
R19 Proposal |  |  |  |  | 
Stage 2
Stage 2
Strict rules
Stage 3 PHY
Stage 3 PHY
Stage 3
Other
Stage 3
Other RAN
Perf.
Perf.
Stage 3
Other SA/CT
ASN.1 etc.
ASN.1 etc.
R19 Package
R19 Workshop