## Cover sheet
3GPP TSG RAN WG5#98 | [8 empty] | R5-230086
Athens, Greece, Feb 27th – March 3rd 2023
Agenda Item: | 7.4.2
Source: | China Telecom
Title: | WP for NR_PC2_CA_R17_2BDL_2BUL-UEConTest
Work item code: | NR_PC2_CA_R17_2BDL_2BUL-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The objective of this work item is to define the UE conformance test cases correspond to the defined test requirements in WI ‘High power UE for NR inter-band Carrier Aggregation with 2 bands downlink and x bands uplink (x=1,2)’. The scope of this WI includes all PC2 NR inter-band CA for 2 bands DL with 2 bands UL and PC1.5 and PC2 NR Inter-band CA for 2 bands DL with 1 band UL band combination configurations with the agreed baseline P-MPR based SAR solution defined in the RAN4 WID on High power UE (power class 2) for NR inter-band Carrier Aggregation with 2 bands downlink and 2 bands uplink, identified in clause 2.2.Only completed PC2 CA configurations in RAN4 are allowed to be introduced in RAN5.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases / configurations (Note 1) | Number of new test cases / configurations | Comments
Overall completion |  | 25%
Completion Compensation |  | -
| Note 1: | Only test cases / configurations completed for all applicable WP areas and sub-areas are counted. For completed test cases / configurations per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases / configurations | Number of new test cases / configurations | Comments
SA Option 2 (SA NR) (FR1) |  | 6%
FR1 |  | 6%
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS:Area Scope | TS/Area | Completion | Number of new completed test cases / configurations | Number of new test cases / configurations | FR1
[5 empty] | Completion | Number of new completed test cases / configurations | Number of new test cases / configurations
NEW TEST CASES
5 References
[1] RP-211140 | New WID on UE Conformance – High power UE for NR inter-band Carrier Aggregation with 2 bands downlink and x bands uplink (x=1,2)
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP for NR_PC2_CA_R17_2BDL_2BUL-UEConTest | [12 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | Relative weight of effort vs TS contribution | [8 empty] | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_PC2_CA_R17_2BDL_2BUL-UEConTest | [14 empty] | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 5 | 5
WP Scope: |  | The objective of this work item is to define the UE conformance test cases correspond to the defined test requirements in WI ‘High power UE for NR inter-band Carrier Aggregation with 2 bands downlink and x bands uplink (x=1,2)’. The scope of this WI includes all PC2 NR inter-band CA for 2 bands DL with 2 bands UL and PC1.5 and PC2 NR Inter-band CA for 2 bands DL with 1 band UL band combination configurations with the agreed baseline P-MPR based SAR solution defined in the RAN4 WID on High power UE (power class 2) for NR inter-band Carrier Aggregation with 2 bands downlink and 2 bands uplink, identified in clause 2.2.Only completed PC2 CA configurations in RAN4 are allowed to be introduced in RAN5. | [14 empty] | 38.508-1: Test frequencies | 38.508-2: UE capabilities | 38.521-x: Common Clause | 38.521-x: Tx test cases / 38.522: Test case applicability | 38.521-x: Rx test cases / 38.522 Test case applicability | 38.521-4: RF perfromance test cases / 38.522: Test case applicability | 38.533: RRM test cases / 38:.522 Test case applicability | 38.903: MU and TT | 38.905: Test point analysis
WP Resp: |  | Wu Jingzhou |  |  | wujingzhou@chinatelecom.cn | [7 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | N/A |  |  | N/A
WP Item ID | Is new configuration or test case? | Area | DL Configuration | UL configuration(s) | Type of change | Interested Operator | Company | Status | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1
6% (+0.1%)
260
258
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row. | [15 empty] | CALCULATED CELLS | TS STATUS INPUT
NEW HPUE CONFIGURATIONS
PC2 band combinations for Inter-band CA (2 bands UL and 2 bands DL)
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n1A-n78A | CA_n1A-n78A | New PC2 Config | China Telecom |  |  |  |  | NOTE: The introduction of PC2 for UL CA Config CA_n1A-n78A will be finished in NR_SAR_PC2_interB_SUL_2BUL-UEConTest WI as the example band combination. | 0
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n2A-n77A | CA_n2A-n77A | New PC2 Config | Verizon, AT&T | Verizon | Ongoing | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n2A-n77(2A) | CA_n2A-n77A | New PC2 Config | Verizon, AT&T |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n2A-n77C | CA_n2A-n77A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n2(2A)-n77A | CA_n2A-n77A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n2(2A)-n77(2A) | CA_n2A-n77A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n2(2A)-n77C | CA_n2A-n77A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
1 |  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n3A-n41A | CA_n3A-n41A | New PC2 Config | CMCC | CMCC | Ongoing | TBD | 38.521-1 Tx: R5-215986 R5-221898 |  | 1 | 23.1% | 23.1% |  | 23.08% | 0% | 0% |  | 100% | 0% |  |  |  | 0%
2 |  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n3A-n78A | CA_n3A-n78A | New PC2 Config | China Telecom | China Telecom | Ongoing | TBD | 38.521-1 Tx: R5-218373 R5-221897 R5-221898 R5-225704 |  | 1 | 43.8% (+20.8%) | 43.8% (+20.8%) |  | 43.85% | 0% | 0% |  | 100% | 90% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n5A-n77A | CA_n5A-n77A | New PC2 Config | Verizon, AT&T | Verizon | Ongoing | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n5A-n77(2A) | CA_n5A-n77A | New PC2 Config | Verizon, AT&T |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n5(2A)-n77A | CA_n5A-n77A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n5A-n77C | CA_n5A-n77A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n5(2A)-n77C | CA_n5A-n77A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n5B-n77A | CA_n5A-n77A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n5B-n77C | CA_n5A-n77A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n5A-n78A | CA_n5A-n78A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n7A-n78A | CA_n7A-n78A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n7B-n78A | CA_n7A-n78A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n12A-n77A | CA_n12A-n77A | New PC2 Config | AT&T |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n12A-n77(2A) | CA_n12A-n77A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n13A-n77A | CA_n13A-n77A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n14A-n77A | CA_n14A-n77A | New PC2 Config | AT&T |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n14A-n77(2A) | CA_n14A-n77A | New PC2 Config | AT&T |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n25A-n41A | CA_n25A-n41A | New PC2 Config | T-Mobile USA |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n25(2A)-n41A | CA_n25A-n41A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n25(2A)-n41C | CA_n25A-n41A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n25(2A)-n41(2A) | CA_n25A-n41A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n25A-n41C | CA_n25A-n41A | New PC2 Config | T-Mobile USA |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n25A-n41(2A) | CA_n25A-n41A | New PC2 Config | T-Mobile USA |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n25A-n41(3A) | CA_n25A-n41A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n25A-n41(A-C) | CA_n25A-n41A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n25A-n77A | CA_n25A-n77A | New PC2 Config | T-Mobile USA |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n25A-n77(2A) | CA_n25A-n77A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n25(2A)-n77A | CA_n25A-n77A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
15 |  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n28A-n41A | CA_n28A-n41A | New PC2 Config | CMCC |  | Ongoing | TBD | 38.521-1 Tx: R5-215988 R5-221898 |  | 1 | 30% | 30% |  | 30% | 0% | 0% |  | 100% |  |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n28A-n78A | CA_n28A-n78A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
16 |  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n28A-n79A | CA_n28A-n79A | New PC2 Config | CMCC |  | Ongoing | TBD | 38.521-1 Tx: R5-215987 R5-221898 |  | 1 | 30% | 30% |  | 30% | 0% | 0% |  | 100% |  |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n30A-n77A | CA_n30A-n77A | New PC2 Config | AT&T |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n30A-n77(2A) | CA_n30A-n77A | New PC2 Config | AT&T |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
17 |  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n40A-n41A | CA_n40A-n41A | New PC2 Config | CMCC |  | Ongoing | TBD | 38.521-1 Tx: R5-215989 R5-221898 |  | 1 | 30% | 30% |  | 30% | 0% | 0% |  | 100% |  |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n41A-n66A | CA_n41A-n66A | New PC2 Config | T-Mobile USA |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n41(2A)-n66A | CA_n41A-n66A | New PC2 Config | T-Mobile USA |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n41A-n66(2A) | CA_n41A-n66A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n41C-n66A | CA_n41A-n66A | New PC2 Config | T-Mobile USA |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n41C-n66(2A) | CA_n41A-n66A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n41(2A)-n66(2A) | CA_n41A-n66A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n41(3A)-n66A | CA_n41A-n66A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n41(A-C)-n66A | CA_n41A-n66A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n41A-n71A | CA_n41A-n71A | New PC2 Config | T-Mobile USA |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n41A-n71B | CA_n41A-n71A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n41A-n71(2A) | CA_n41A-n71A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n41C-n71A | CA_n41A-n71A | New PC2 Config | T-Mobile USA |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n41C-n71(2A) | CA_n41A-n71A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n41(2A)-n71A | CA_n41A-n71A | New PC2 Config | T-Mobile USA |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n41(2A)-n71(2A) | CA_n41A-n71A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n41(2A)-n71B | CA_n41A-n71A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n41(3A)-n71A | CA_n41A-n71A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n41(A-C)-n71A | CA_n41A-n71A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n41C-n71B | CA_n41A-n71A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n41A-n77A | CA_n41A-n77A | New PC2 Config | T-Mobile USA |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n41(2A)-n77A | CA_n41A-n77A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n41(3A)-n77A | CA_n41A-n77A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n41(A-C)-n77A | CA_n41A-n77A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n41C-n77A | CA_n41A-n77A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n41A-n77(2A) | CA_n41A-n77A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
3 |  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n41A-n79A | CA_n41A-n79A | New PC2 Config | CMCC | CMCC, Huawei, HiSilicon | Ongoing | TBD | 38.521-1 Tx: R5-225063 |  | 1 | 20.8% | 20.8% |  | 20.77% | 0% | 0% |  | 90% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n66A_n77A | CA_n66A_n77A | New PC2 Config | Verizon, AT&T | Verizon | Ongoing | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n66(2A)-n77A | CA_n66A-n77A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n66A-n77(2A) | CA_n66A-n77A | New PC2 Config | Verizon, AT&T |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n66(3A)-n77A | CA_n66A-n77A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n66(2A)-n77(2A) | CA_n66A-n77A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n66A_n77C | CA_n66A_n77A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n66(2A)-n77C | CA_n66A_n77A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n66B-n77A | CA_n66A_n77A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n66B-n77C | CA_n66A_n77A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n71A-n77A | CA_n71A-n77A | New PC2 Config | T-Mobile USA |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n71A-n77(2A) | CA_n71A-n77A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n71B-n77A | CA_n71A-n77A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 2 UL) | CA_n71(2A)-n77A | CA_n71A-n77A | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 0%
PC2 band combinations for Inter-band CA (1 band UL and 2 bands DL)
4 |  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n1A-n78A | n78 | New PC2 Config | China Telecom | China Telecom | Ongoing | TBD |  |  | 1 | 21.4% | 21.4% |  | 21.43% | 0% | 0% | 0% | 100% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n2A-n77A | n77 | New PC2 Config | Verizon, AT&T | Verizon | Ongoing | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n2A-n77(2A) | n77 | New PC2 Config | Verizon, AT&T |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n2A-n77C | n77 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n2(2A)-n77A | n77 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n2(2A)-n77(2A) | n77 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n2(2A)-n77C | n77 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
5 |  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n3A-n41A | n41 | New PC2 Config | CMCC | CMCC | Ongoing | TBD | 38.521-1 Tx: R5-215990 R5-221899 R5-221903 |  | 1 | 9.1% | 9.1% |  | 9.091% | 0% | 0% | 100% |  | 0% |  |  |  | 0%
6 |  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n3A-n78A | n78 | New PC2 Config | China Telecom | China Telecom | Ongoing | TBD | 38.521-1 Tx: R5-225704 |  | 1 | 9.1% | 9.1% |  | 9.091% | 0% | 0% | 100% |  | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n5A-n77A | n77 | New PC2 Config | Verizon, AT&T | Verizon | Ongoing | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n5A-n77(2A) | n77 | New PC2 Config | Verizon, AT&T |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n5(2A)-n77A | n77 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n5A-n77C | n77 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n5(2A)-n77C | n77 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n5B-n77A | n77 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n5B-n77C | n77 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n5A-n78A | n78 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n7A-n78A | n78 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n7B-n78A | n78 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n12A-n77A | n77 | New PC2 Config | AT&T |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n12A-n77(2A) | n77 | New PC2 Config | AT&T |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n13A-n77A | n77 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n14A-n77A | n77 | New PC2 Config | AT&T |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n14A-n77(2A) | n77 | New PC2 Config | AT&T |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n25A-n41A | n41 | New PC2 Config | T-Mobile USA |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n25(2A)-n41A | n41 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n25(2A)-n41C | n41 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n25(2A)-n41(2A) | n41 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n25A-n41C | n41 | New PC2 Config | T-Mobile USA |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n25A-n41(2A) | n41 | New PC2 Config | T-Mobile USA |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n25A-n41(3A) | n41 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n25A-n41(A-C) | n41 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n25A-n77A | n77 | New PC2 Config | T-Mobile USA |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n25A-n77(2A) | n77 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n25(2A)-n77A | n77 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
7 |  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n28A-n41A | n41 | New PC2 Config | CMCC | CMCC | Ongoing | TBD | 38.521-1 Tx: R5-215992 |  | 1 | 12.5% | 12.5% |  | 12.5% | 0% | 0% | 100% | [5 empty] | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n28A-n78A | n78 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
8 |  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n28A-n79A | n79 | New PC2 Config | CMCC | CMCC | Ongoing | TBD | 38.521-1 Tx: R5-215991 |  | 1 | 12.5% | 12.5% |  | 12.5% | 0% | 0% | 100% | [5 empty] | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n29A-n77A | n77 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n29A-n77(2A) | n77 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n30A-n77A | n77 | New PC2 Config | AT&T |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n30A-n77(2A) | n77 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
9 |  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n40A-n41A | n41 | New PC2 Config | CMCC | CMCC | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n41A-n66A | n41 | New PC2 Config | T-Mobile USA |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n41(2A)-n66A | n41 | New PC2 Config | T-Mobile USA |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n41A-n66(2A) | n41 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n41C-n66A | n41 | New PC2 Config | T-Mobile USA |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n41C-n66(2A) | n41 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n41(2A)-n66(2A) | n41 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n41(3A)-n66A | n41 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n41(A-C)-n66A | n41 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n41A-n71A | n41 | New PC2 Config | T-Mobile USA |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n41A-n71B | n41 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n41A-n71(2A) | n41 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n41C-n71A | n41 | New PC2 Config | T-Mobile USA |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n41C-n71(2A) | n41 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n41(2A)-n71A | n41 | New PC2 Config | T-Mobile USA |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n41(2A)-n71(2A) | n41 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n41(2A)-n71B | n41 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n41(3A)-n71A | n41 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n41(A-C)-n71A | n41 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n41C-n71B | n41 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n41A-n77A | n41 | New PC2 Config | T-Mobile USA |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n41A-n77A | n77 | New PC2 Config | T-Mobile USA |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n41(2A)-n77A | n41 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n41(2A)-n77A | n77 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n41(3A)-n77A | n41 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n41(3A)-n77A | n77 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n41(A-C)-n77A | n41 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n41(A-C)-n77A | n77 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n41C-n77A | n41 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n41C-n77A | n77 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n41A-n77(2A) | n41 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n41A-n77(2A) | n77 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
10 |  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n41A-n79A | n41 | New PC2 Config | CMCC | CMCC | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
11 |  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n41A-n79A | n79 | New PC2 Config | CMCC | CMCC | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n48A-n77A | n77 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n48A-n77C | n77 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n48(2A)-n77A | n77 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n48(2A)-n77C | n77 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n48B-n77A | n77 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n48B-n77C | n77 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n48(A-B)-n77A | n77 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n66A-n77A | n77 | New PC2 Config | Verizon, AT&T | Verizon | Ongoing | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n66(2A)-n77A | n77 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n66A-n77(2A) | n77 | New PC2 Config | Verizon, AT&T |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n66(3A)-n77A | n77 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n66(2A)-n77(2A) | n77 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n66A-n77C | n77 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n66(2A)-n77C | n77 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n66B-n77A | n77 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n66B-n77C | n77 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n71A-n77A | n77 | New PC2 Config | T-Mobile USA |  | Pending | TBD |  |  | 1 | 0% |  |  |  | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n71A-n77(2A) | n77 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% |  |  |  | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n71B-n77A | n77 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% |  |  |  | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Inter-band CA (2 DL and 1 UL) | CA_n71(2A)-n77A | n77 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% |  |  |  | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
PC2 band combinations for Intra-band CA
|  | PC2 Intra-band contiguous CA | CA_n41C | CA_n41C | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | [5 empty] | 0%
|  | PC2 Intra-band contiguous CA | CA_n77C | CA_n77C | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
12 |  | PC2 Intra-band contiguous CA | CA_n78C | CA_n78C | New PC2 Config | China Telecom | Huawei, HiSilicon | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Intra-band non-contiguous CA | CA_n41(2A) | CA_n41(2A) | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Intra-band non-contiguous CA | CA_n78(2A) | CA_n78(2A) | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
13 |  | PC2 Intra-band contiguous CA | CA_n41C | n41 | New PC2 Config | CMCC | CMCC | Ongoing | TBD | 38.521-1 Tx: R5-221902 |  | 1 | 12.5% | 12.5% |  | 12.5% | 0% | 0% | 100% | [5 empty] | 0%
|  | PC2 Intra-band non-contiguous CA | CA_n41(2A) | n41 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Intra-band non-contiguous CA | CA_n41(3A) | n41 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Intra-band non-contiguous CA | CA_n77(2A) | n77 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC2 Intra-band mixed intra-band contiguous and non-contiguous CA | CA_n41(A-C) | n41 | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
PC1.5 band combinations for Inter-band CA (1 band UL and 2 bands DL)
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n2A-n77A | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n2A-n77(2A) | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n2A-n77C | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n2(2A)-n77A | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n2(2A)-n77C | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n5A-n77A | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n5A-n77C | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n12A-n77A | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n12A-n77(2A) | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n13A-n77A | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n14A-n77A | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n14A-n77(2A) | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n25A-n41A | n41 | New PC1.5 Config | T-Mobile USA |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n25(2A)-n41A | n41 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n25(2A)-n41C | n41 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n25(2A)-n41(2A) | n41 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n25A-n41C | n41 | New PC1.5 Config | T-Mobile USA |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n25A-n41(2A) | n41 | New PC1.5 Config | T-Mobile USA |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n25A-n41(3A) | n41 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n25A-n41(A-C) | n41 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n25A-n77A | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n25A-n77(2A) | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n25(2A)-n77A | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n29A-n77A | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n29A-n77(2A) | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n30A-n77A | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n30A-n77(2A) | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n41A-n66A | n41 | New PC1.5 Config | T-Mobile USA |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n41(2A)-n66A | n41 | New PC1.5 Config | T-Mobile USA |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n41A-n66(2A) | n41 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n41C-n66A | n41 | New PC1.5 Config | T-Mobile USA |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n41C-n66(2A) | n41 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n41(2A)-n66(2A) | n41 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n41(3A)-n66A | n41 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n41(A-C)-n66A | n41 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n41A-n71A | n41 | New PC1.5 Config | T-Mobile USA |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n41A-n71B | n41 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n41A-n71(2A) | n41 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n41C-n71A | n41 | New PC1.5 Config | T-Mobile USA |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n41C-n71(2A) | n41 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n41(2A)-n71A | n41 | New PC1.5 Config | T-Mobile USA |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n41(2A)-n71(2A) | n41 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n41(2A)-n71B | n41 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n41(3A)-n71A | n41 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n41(A-C)-n71A | n41 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n41C-n71B | n41 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n41A-n77A | n41 | New PC1.5 Config | T-Mobile USA |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n41A-n77A | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n41(2A)-n77A | n41 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n41(2A)-n77A | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n41(3A)-n77A | n41 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n41(3A)-n77A | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n41(A-C)-n77A | n41 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n41(A-C)-n77A | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n41C-n77A | n41 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n41C-n77A | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n41A-n77(2A) | n41 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n41A-n77(2A) | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n48A-n77A | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n48A-n77C | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n48(2A)-n77A | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n48(2A)-n77C | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n48B-n77A | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n48B-n77C | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n48(A-B)-n77A | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n66A-n77A | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n66(2A)-n77A | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n66A-n77(2A) | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n66A-n77C | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n66(2A)-n77C | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n66B-n77A | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n66B-n77C | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n71A-n77A | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% |  |  |  | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n71A-n77(2A) | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% |  |  |  | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n71B-n77A | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% |  |  |  | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Inter-band CA (2 DL and 1 UL) | CA_n71(2A)-n77A | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% |  |  |  | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
PC1.5 band combinations for Intra-band CA
14 |  | PC1.5 Intra-band contiguous CA | CA_n41C | n41 | New PC1.5 Config | CMCC | CMCC | Ongoing | TBD | 38.521-1 Tx: R5-221902 | PC1.5 CA_n41C Tx TCs shall not be regarded as completed before PC1.5 n41 Tx TCs to be confirmed as completed. | 1 | 11.2% | 11.2% |  | 11.25% | 0% | 0% | 90% | [5 empty] | 0%
|  | PC1.5 Intra-band non-contiguous CA | CA_n41(2A) | n41 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Intra-band non-contiguous CA | CA_n41(3A) | n41 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Intra-band non-contiguous CA | CA_n77(2A) | n77 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
|  | PC1.5 Intra-band mixed intra-band contiguous and non-contiguous CA | CA_n41(A-C) | n41 | New PC1.5 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on S1: The TS's weight number is used to set the reletive weights between TS contributions used in the overall calculation of completeness of teh WP item. Setting it to 0 for a WP item means that it will not be included at all in the calculation.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new configuration or a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on M6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.
Note on Q12: Rapporteur guideline to assign applicable sub-areas for a WP item (columns S to X) To Set applicable sub-area(s) for a WP item do: - Copy the formula/cell content from one of the other non-empty cells under the "WP item status vs Area" section (columns S to X). To Clear applicable sub-area(s) for a WP item do: - Select the cell for teh WP item for the sub-area and press <Delete>-botton (clear content of the cell).