## Time_budget_request
|  |  |  | 1 TU = ~2h; RD: RRM/demodulation; see instructions/examples below |  |  |  |  | RAN | R1 | R2 | R3 | R4RF | R4RD | R6 | RAN | R1 | R2 | R3 | R4RF | R4RD | R1 | R2 | R3 | R4RF | R4RD | R6 | RAN | R1 | R2 | R3 | R4RF | R4RD | R6 | RAN | R1 | R2 | R3 | R4RF | R4RD | R6 | RAN | R1 | R2 | R3 | R4RF | R4RD | R6 | RAN | R1 | R2 | R3 | R4RF | R4RD | R1 | R2 | R3 | R4RF | R4RD | R6 | RAN | R1 | R2 | R3 | R4RF | R4RD | R6 | RAN | R1 | R2 | R3 | R4RF | R4RD | R6 | RAN
leading WG | RAT | WI code | WI or SI | Title | latest WID/SID | rapporteur | target | comment | 86 Dec.19 RAN1 deadline freeze | 100 | 109 | 107 | 94 | 94 | 15 | 87 March20 REL-16 freeze | 100bis | 109bis | 107bis | 94bis | 94bis | 101 | 110 | 108 | 95 | 95 | 16 | 88 June 20 REL-16 ASN.1 freeze | 102 | 111 | 109 | 96 | 96 | 17 | 89 Sep.20 | 103 | 112 | 110 | 97 | 97 | 18 | 90 Dec.20 | 104 | 113 | 111 | 98 | 98 | 19 | 91 March 21 | 104bis | 113bis | 111bis | 98bis | 98bis | 105 | 114 | 112 | 99 | 99 | 20 | 92 June 21 REL-17 freeze | 106 | 115 | 113 | 100 | 100 | 21 | 93 Sep.21 REL-17 ASN.1 freeze | 107 | 116 | 114 | 101 | 101 | 22 | 94 Nov.21
R1 | NR | FS_NR_redcap | SI | Study on support of reduced category NR devices | RP-201386 | Ericsson | RAN#88 --> RAN#90 | Postpone start from February 2020 to May 2020. Postpone end from May 2020 to December 2020. |  | 2 --> 0 | [6 empty] | 2 --> 0 | 0,5 --> 0 |  |  |  | 2 | 0,5 --> 0 | [5 empty] | 0 --> 2 | 0 --> 0,5 | [5 empty] | 0 --> 2 | 0 --> 0,5