3GPP TSG-RAN WG2 Meeting #119 Electronic	R2-2207803

Elbonia, 15 – 26 August 2022

Agenda item:	8.10.1

Source:	Rapporteurs (Xiaomi)

Title:	Work Plan for Rel-18 IDC

WID/SID:	NR_IDC_enh-Core - Release 18

Document for:	Information

# 1	Introduction

According to the WID [1] of the Rel-18 In-Device Co-existence (IDC) enhancements for NR and MR-DC, the Rel-18 IDC work needs to involve both RAN2 and RAN4. In this contribution, we provide the work plan for the Rel-18 IDC work so as to facilitate the study in both RAN2 and RAN4.

# 2	Timeline

Figure 1: Rel-18 IDC timeline

According to the timeline for the Rel-18 IDC work as illustrated in Figure 1, the targeted completion for the Rel-18 IDC work is RAN#100 June 2023 for RAN2 and RAN#101 September 2023 for RAN4.

# 3	Objectives

According to the WID [1], the objectives of IDC include the followings:

This WI expects to address interference between 3GPP (including various MR-DC architectures, i.e. NR-DC and EN-DC) and non-3GPP RAT (e.g. WiFi). - Enhancements to FDM solution, to allow more granular indication of affected frequencies (e.g. granularity of BWP or PRB level). (RAN2) Note: Enhancements to FDM solution is prioritized. - Introduction of TDM solution (e.g. indication of UE preferred TDM pattern for UL/DL). (RAN2, RAN4). Note: The TDM solution is considered complementary to the FDM solution. - Specify RRM requirements for TDM solution (RAN4) Note: LTE IDC solution should be considered as the baseline for the solutions developed in this WI.

# 4	Work plan

The suggested work plan for IDC is provided below:

Table 1: IDC work plan

| Date | RAN2 | RAN4 | RAN |
| --- | --- | --- | --- |
|  | RAN2#119 List all candidate IDC solutions for FDM and TDM, and select the IDC solutions for further study. | - |  |
| 2022-9 |  |  | RAN#97 RAN2 (30% completion) RAN4 (0% completion) |
|  | RAN2#120 Selection of the IDC solutions which are to be specified in Rel-18 and identify the stage-3 specification impacts. |  |  |
| 2022-12 |  |  | RAN#98 RAN2 (50% completion) RAN4 (0% completion) |
|  | RAN2#121 Start drafting the CRs including some stage-3 details for agreed solutions, and send an LS to RAN4 to inform the IDC solutions agreed by RAN2. |  |  |
| 2023-3 |  |  | RAN#99 RAN2 (70% completion) RAN4 (0% completion) |
|  | RAN2#122 Finalize the stage-3 CRs including the UE capability (if possible) | RAN4#107 Study the core requirement impacts based on the IDC solutions provided by RAN2 |  |
| 2023-6 |  |  | RAN#100 RAN2 (100% completion) RAN4 (50% completion) |
|  |  | RAN4#108 Finalize the stage-3 CRs for core requirement |  |
| 2023-9 |  |  | RAN#101 RAN2 (100% completion) RAN4 (100% completion) |

# Reference

[1] RP-221281, Xiaomi, “Revised WID: In-Device Co-existence (IDC) enhancements for NR and MR-DC”.