3GPP TSG-RAN WG2 Meeting #123                                                                 R2-2307602

Toulouse, France, August 21 – 25, 2023

Agenda item: 		7.12.1

Source: 		Qualcomm Incorporated (WI Rapporteur)

Title: 	Workplan for Rel-18 mobile IAB

Document for:	Information

# 1	Introduction

At RAN#94e, the Work Item on Mobile IAB (Integrated Access and Backhaul) for NR (NR_mobile_IAB) was agreed [1]. As WI Rapporteur, in this contribution, we recommend a work plan for RAN2, RAN3 and RAN4. The workplan captures interdependences among tasks and timeline for RAN2/3/4.

The WID [1] introduced the following objectives in the core part:

The detailed objectives of the WI are listed as follows: - Define Procedures for migration/topology adaptation to enable IAB-node mobility, including inter-donor migration of the entire mobile IAB-node (full migration) [RAN3, RAN2] - The mobile IAB-node can connect to a stationary (intermediate) IAB-node. Optimizations specific to the scenarios, where the mobile IAB-node connects to a stationary (intermediate) IAB-node, or where it directly connects to an IAB-donor-DU are de-prioritized. - The mobility of dual-connected IAB-nodes is down-prioritized. - Enhancements for mobility of an IAB-node together with its served UEs, including aspects related to group mobility. No optimizations for the targeting of surrounding UEs. [RAN3, RAN2] Note: Solutions should avoid touching upon topics where Rel-17 discussions already occurred and where the topic was excluded from Rel-17, except for enhancements that are specific to IAB-node mobility. - Mitigation of interference due to IAB-node mobility, including the avoidance of potential reference and control signal collisions (e.g. PCI, RACH). [RAN3, RAN2] The following principles should be respected: - Mobile IAB-nodes should be able to serve legacy UEs. - Solutions providing optimization for Mobile IAB may entail Rel-18 UE enhancements, provided that such enhancements are backwards compatible RAN4 is expected to study impact on RF and RRM requirements: - Conduct co-existence study to assess the impact of moving cells. Based on the study outcome, specify RF and RRM requirements and mechanisms for the mobile IAB-node to enable co-existence, if needed. - Specify RRM requirements for the mobile IAB-node to enable IAB-node mobility, if needed. The involvement of RAN1 may be needed, depending on work progress.

The WID [1] introduced the following objectives in the performance part:

- Specify RF conformance requirements for the mobile IAB-node, if needed. - Specify RRM and demodulation performance requirements for the mobile IAB-node by taking into account IAB-node mobility, if needed.

The WID further emphasizes on interaction with SA2:

- Alignment and coordination with Rel-18 SA2 work on VMR should be considered, if needed.

# 2	Workplan

## 2.1	Prioritization of efforts

This section captures prioritization of the various tasks defined as well as interdependences among these tasks handled by different RAN WGs.

RAN3/2-related efforts:

- Procedures for migration/topology adaptation to enable IAB-node mobility, including inter-donor migration of the entire mobile IAB-node (full migration):

This objective primarily focuses on the migration of the mobile IAB-node. The following topics should be considered:

  - Inter-donor migration of the entire IAB-node (full migration): RAN3 can be expected to take the lead in this effort. RAN3 can continue the discussion on full migration started in Rel-17. Since this discussion is expected to have impact on RAN2 and potentially also RAN1 and RAN4, RAN3 should start with this effort in the first meeting. RAN2 and potentially other RAN WGs may wait for RAN3 progress on this topic.

  - Other new procedures or enhancements to existing procedures related to this objective can be defined by RAN3 and RAN2. New procedures should be identified at the beginning of the WI since such work typically takes significant time and may further affect other RAN WGs. As always, new functionality that is necessary to support IAB-node mobility should be given higher priority than optimizations to existing functionality.

  - Topology adaptation in absence of Xn was identified in Rel-18 SA2 Study on VMR as part of key issue #3. RAN3 may want to consider discussing the relevance of this issue for RAN independent of SA2’s effort. This discussion should start early in case interaction with SA2 is necessary.

- Enhancements needed for the mobility of an IAB-node together with its served UEs, including aspects related to group mobility:

This objective primarily focuses on the impact on the UE connected to or camping on a mobile IAB-node cell. It can also include handover to and/or reselection of a mobile IAB-node cell. The objective allows for enhancements in a variety of areas; a few of them are given below. The discussion should include the consideration of the support for legacy UEs. RAN2 and RAN3 should identify the enhancements to be handled in Rel-18 at the beginning of the WI so that sufficient time remains for thorough discussion. In this discussion, the definition of new functionality should be given priority over optimizations. For new procedures, optimizations should only be considered after a baseline has been defined.

The following areas may be explored by RAN2 and RAN3:

  - Enhancements to cell (re-)selection between stationary network and mobile IAB-node, and between mobile IAB-nodes.

  - Enhancements to UE access to the mobile IAB-node vs. the stationary network.

  - Enhancements to UE handover between stationary network and mobile IAB-node and between mobile IAB-nodes.

  - Enhancements for location updates (TA, RNA) for UEs that are camping on or connected to mobile IAB-node cells. This issue was identified in Rel-18 SA2 Study on VMR as key issues #5 and #6. RAN3 and RAN2 may want to consider discussing the relevance of this issue for RAN independently of SA2’s effort.

  - Signalling optimizations due to collective migration of UEs connected to a mobile IAB-node. This may include the bundling of UE-associated information into one common message. RAN3 should consider optimizations of this nature at a later stage of the WI after the baseline procedures (i.e., w/o such bundling) have been established.

- Mitigation of interference due to IAB-node mobility, including the avoidance of potential reference and control signal collisions (e.g., PCI, RACH):

The following topics may be explored under this objective:

  - PCI collision avoidance: RAN3 may discuss means for PCI collision avoidance. RAN2 may discuss potential means for PCI collision detection.

  - RACH resource collision avoidance: RAN2 may discuss potential issues related to this topic.

  - Other issues related to interference mitigation may be identified and discussed in RAN2 and RAN3.

- Note on potential complexity related to multi-hop backhauling for mobile IAB:

  - Aspects of the potential complexity related to multi-hop backhauling should be briefly discussed at the beginning of the WI in RAN2 and RAN3.

RAN4-related efforts (Core Part):

- Co-existence study to assess the impact of moving cells.

  - The co-existence criteria defined in Rel-16/17 only apply to stationary IAB-nodes, and they were based on a specific minimum distance between IAB-nodes and macro-cell. For mobile IAB-nodes, the assumption on the minimum distance and the implications on power control, receiver dynamic range, etc. need to be revised. RAN4 may need to consider if additional simulation work is needed. These topics should be discussed early during the RAN4 effort since they are expected to consume a lot of time.

- RRM requirements for the mobile IAB-node to enable IAB-node mobility.

  - RRM requirements defined in Rel-16/17 only included RLF recovery. For mobile IAB, the IAB-node is expected to undergo frequent topology adaptations. The associated RRM requirements need to be discussed. This discussion should include identification of the relevant mobile IAB scenarios. The prior RAN work on high-speed trains should be included into these considerations. These topics should be discussed early since they are expected to consume a lot of time.

RAN4-led efforts (Performance Part):

- The topics related to the performance part need to be handled based on the progress of the discussion on the Core Part.

Alignment and coordination with Rel-18 SA2 work on VMR

- RAN WGs should try to align efforts on mobile IAB with SA2 normative work on VMR if such normative work is agreed by SA2. It is expected that such alignment will be discussed by TSG RAN before.

- RAN WGs may want to include into the discussion all aspects related to the key issues identified by the SA2 Study on VMR that have RAN impact and are aligned with the RAN WI objectives. The above outline has captured some aspects that might be considered.

## 2.2	Timeline

Table 1 summarizes a timeline for RAN2/3/4. This timeline is based on RP-221060 [2].

Table 1: Timeline for RAN2, 3, 4 efforts

| TSG/WG | Meeting Number | Date | TU | Task |
| --- | --- | --- | --- | --- |
| RAN2 | #123 | Aug 2023 | 0.5 | AI 7.12.2.1: Mobility Enhancements – Connected Mode - RACH-less handover RAN2 has still not concluded if RACH-less handover should be supported. - At this stage of the WI, RAN2 should converge if it wants to support RACH-less handover or not. In last meeting, there were some doubts on the benefits of RACH-less handover for DU migration. RAN2 should discuss the benefits of RAN-less handover. - Based on last meeting’s agreements, RAN2 expects to align RACH-less HO, if supported, with other WI. For this purpose, RAN2 needs to discuss and converge, which enhancements would be needed for mIAB, and which of the other WI’s supporting RACH-less HO could deliver these enhancements. AI 7.12.2.2: Mobility Enhancements – Idle/Inactive Mode - Mobile-IAB-node broadcast - RAN2 agreed in the last meeting: - R2 direction (solution agreements at later stage, no other directions will be considered): - RAN2 acknowledges following two problems to be addressed for idle/inactive UEs: - -Problem 1: For a UE that is physically on a moving vehicle but not camped on its mobile IAB-cell yet (i.e. the UE is camped on a stationary cell), how to help such UE(s) to identify a neighbour mobile IAB-cell, prioritize mobile IAB-cell (frequency and cell) and to be "pulled" into this mobile IAB-cell, especially for inter-frequency scenario where the mobile IAB-cell's frequency priority is low. - - Problem 2: After the UE physically on a moving vehicle is camped on the mobile IAB cell, how to avoid it reselecting other non-mIAB-(stationary) cells. - - Such UE may prioritize a highest ranked cell at a frequency, if it broadcasts a mIAB-cell type indicator in SIB1 for cell reselection. UE may use the SIB4 assistance information to identify the presence of such mobile IAB-cell(s), if broadcasted. A SIB4 assistance information may include mIAB-cell frequencies. FFS on stage-2/3 to clarify the UE in problem 1 and 2. - RAN2 should discuss and converge on ST2 and ST3 aspects of this solution. Other solutions to these two problems can be proposed. AI 7.12.3: Other - BAP impact: - RAN2 agreed in last meeting: P1a: RAN2 assumes that there is no need to introduce logical-DU-specific default BAP configuration in mobile IAB from RAN2 perspective, unless requested by RAN3 otherwise (no LS for now). P1b: RAN2 understands that the F1AP (re)configured BAP configuration to one DU will not impact/override the usage of default BAP configuration by another DU. P2: RAN2 assumes there may be redundant BAP configuration entries for non-F1-U traffic and it is up to IAB node's implementation to decide which entry is selected. FFS if there is any specification impact. - RAN2 should discuss and converge on necessary changes to ST2 and BAP spec, if any. TAC/RANAC: Chairman notes from RAN2#122: Chair think we can come back to this topic if RAN2 TS impact is suggested / identified, or if other group asks explicit questions. Mitigation of interference: This topic was not handled in last meetings. Discuss if anything else is needed from RAN2 perspective. - Note that on PCI collision, RAN2 agreed that further work on this matter would be based on LS by RAN3. |
| RAN3 | #121 | Aug 2023 | 1.0 | AI 13.1 General: BL procedures LS by SA2 on IAB-node de-authorization handling in S2-2308158 - Discuss and converge on reply. LS by RAN2 on UE RACH-less handover for mobile IAB in R2-2306817 - Discuss and converge on reply. AI 13.2 IAB-node mobility ST2 procedures: Since there are only 3 meetings left, RAN3 should define baseline ST2 procedures for: - Sequential mIAB-MT migration via Xn: The ST2 procedure should leverage steps of the Rel-17 inter-donor partial migration, where possible. - Sequential mIAB-MT migration via NG: NG HO for the mIAB-MT NG HO was agreed by RAN3 and has been included by SA2 in 23.501 clause 5.35A.3.1. The baseline procedure should leave out all aspects RAN3 has not agreed, e.g., TMM over NG. - DU migration: There were various controversial issues in last meeting. We should try to define a baseline for ST2 that incorporates all those aspects that are non-controversial. - mIAB-node integration: We should try to define a baseline procedure for the present WA. Only non-controversial aspects should be included into this baseline. This would allow us to identify any potential issues with the WA. Network integration: - Discuss and converge whether WA is agreeable that DU’s CU and MT’s CU can be different. - Discuss and converge whether the DU’s CU can be selected by the MT’s CU. DU migration: - Discuss and converge between options: - Option 1: Use existing procedure(s) for triggering F1 Setup and for reporting the outcome of the F1Setup back to the DU´s source CU. Discuss procedures to be used. - Option 2: Use new procedure(s) for triggering F1 Setup and for reporting the outcome of the F1Setup back to the DU´s source. Discuss the types of procedures needed. - Converge whether WA is agreeable that the IAB-node may provide a mapping between source and target activated cells to the source DU’s CU. Discuss if this mapping information needs to include for all activated cells. Discuss whether RAN2 needs to be involved. Passing of gNB-ID of MT’s CU and MT’s XnAP UE ID to DU’s CU - This issue applies to network integration, DU migration and MT migration. This issue should be discussed commonly for all these scenarios. Passing of MT’s ULI info to DU’s CU to conform with SA2’s request - RAN3 promised to SA2 that this functionality would be supported. We need to converge on a solution. This solution may align with that of the issue above. NCGI reconfiguration by target CU: - Discuss whether there are other use cases requiring CGI re-configuration independent of CGI collision events. Operation in absence of Xn: - RAN3 agreed to support MT migration via NG. Discuss and converge how all information exchange between MT’s CU and DU’s CU is conducted in the absence of Xn. mIAB-node authorization: - Converge on handling of mIAB indicator in NGAP Initial UE message based on recent agreements in SA2 VMR WI captured in TS 23.501 clause 5.35A.1. - Discuss and converge on handling of mIAB authorization indicator and mIAB indication in HO Request based on recent agreements in SA2 VMR WI captured in TS 23.501 clause 5.35A.1. AI 13.3 Mobility Enhancements NR cell ID reconfiguration: - We agreed that the CU can reconfigure the NCGI, e.g., in case it observes NCGI collisions. This has some dependence on SA5’s feedback on the RAN3’s LS on this topic. We may want to wait for SA5’ feedback. TAC reconfiguration: - RAN3 agreed that the DU’s TAC can be have same value as or a different value than the TAC of the MT’s serving cell. Discuss how the DU’s TAC is configured in case it has different value than the MT’s TAC. Optimization for UE handover procedure during DU migration: - Discuss, whether any signaling optimizations in RAN3 scope are possible (beyond the Rel-15 HO procedure) and/or needed. AI 13.5 Others LS to SA2 on support of NRPPa with mobile TRP - Converge on a Reply LS to SA2 |
| RAN4RF | #108 | Aug 2023 | 0.5 | RF: Further discussion on RF requirements and conclusions on co-existence work |
| RAN4RD | #108 | Aug 2023 | 0.5 | RRM: Further discussions on RRM requirements |
| RAN | #101 | Sept 2023 |  |  |
| RAN2 | #123bis | Oct 2023 | 0.5 | Finalize St2 discussion |
| RAN3 | #121bis | Oct 2023 | 1.5 | Finalize St2 discussion |
| RAN4RF | #108bis | Oct 2023 | 0.5 | RF: Agreements on RF requirements and draft CR discussions |
| RAN4RD | #108bis | Oct 2023 | 0.5 | RRM: Agreements on RRM requirements and draft CR discussions |
| RAN2 | #124 | Nov 2023 | 0.5 | Finalize St3 discussion |
| RAN3 | #122 | Nov 2023 | 1.5 | Finalize St3 discussion |
| RAN4RF | #109 | Nov 2023 | 0.5 | RF: Agree CRs with RF requirements |
| RAN4RD | #109 | Nov 2023 | 0.5 | RRM: Agree CRs with RRM requirements |
| RAN3 | #109 | Nov 2023 | 0.25+0.25 Perf Part | Performance: Initial discussion on RF and RRM performance |
| RAN | #102 | Dec 2023 |  | Functional freeze |
| RAN4RF | #110 | Feb 2023 | 0.5 | RF: Maintenance as needed |
| RAN4RD | #110 | Feb 2023 | 0.5 | RRM: Maintenance as needed |
| RAN3 | #110 | Feb 2023 | 0.25+0.25 Perf Part | Performance: Agreement on scope and TP/CR split among companies |
| RAN | #103 | March 2023 |  | ASN.1 freeze |
| RAN3 | #110bis | April 2023 | 0.25+0.25 Perf Part | Performance: Initial TP/CR review and approvals |
| RAN3 | #111 | May 2023 | 0.25+0.25 Perf Part | Performance: TP/CR review and approvals, finalization of work |

# References

- RP-222671: Revised WID for NR_mobile_IAB; TSG RAN Meeting #97e, electronic meeting, Sept. 12 - 16, 2022

- RP-221060: Draft Status of TU RAN1 to 4 after RAN#96 v01, Budapest, Hungary, June 6 - 9, 2022