3GPP RAN WG3 Meeting #119bis-e	R3-231641

# Online, 17th – 26th April, 2023

Agenda Item:	21.1

Source:	Rapporteur (Ericsson)

Title:	WI work plan for Rel-18 RedCap

Document for:	Discussion

# 1	Introduction

This document provides a work plan for RAN WGs of the Rel-18 work item (WI) on enhanced support of reduced capability (“RedCap”) NR devices [1].

# 2	WI objective

Core part objective according to [1]:

The objective is to specify support for the following enhancements: Power saving/energy efficiency enhancements - Enhanced eDRX in RRC_INACTIVE (>10.24s) [RAN2, RAN3, RAN4] - Note that this objective requires SA2, CT1 and CT4 involvement Complexity/cost reduction - Further reduced UE complexity in FR1 [RAN1, RAN2, RAN4] - UE BB bandwidth reduction - 5 MHz BB bandwidth only for PDSCH (for both unicast and broadcast) and PUSCH, with 20 MHz RF bandwidth for UL and DL - The other physical channels and signals are still allowed to use a BWP up to the 20 MHz maximum UE RF+BB bandwidth. - Support additional separate early indication(s) [RAN1, RAN2] - UE peak data rate reduction - Relaxation of the constraint (vLayers·Qm·f ≥ 4) for peak data rate reduction - The relaxed constraint is, e.g., 1 (instead of 4). - The parameters (vLayers, Qm, f) can be as in Rel-17 RedCap. - Both 15 kHz SCS and 30 kHz SCS are supported. - Aim to define at most one Rel-18 RedCap UE type for further UE complexity reduction. - The existing UE capability framework is used, and changes to capability signalling are specified only if necessary. By default, all UE capabilities applicable to a Rel-17 RedCap UE are applicable unless otherwise specified. Notes: - The work defined as part of this WI is not to overlap with LPWA use cases. - Coexistence with non-RedCap UEs and Rel-17 RedCap UEs should be ensured. - This WI considers all applicable duplex modes unless otherwise specified. Check in RAN#99 regarding: - Whether UE peak data rate reduction for UE is limited only with UE BB bandwidth reduction or standalone

Performance part objective according to [1]:

Specify necessary performance requirements, measurement accuracy requirements and test cases related to the above-mentioned enhancements and core requirements [RAN4].

# 3	WI work plan

## 3.1	October 2022

RAN1#110bis-e (1 TU)

- Initial discussion on RAN1 impacts from further reduced UE complexity in FR1

## 3.2	November 2022

RAN1#111 (1 TU)

- Continue discussion on RAN1 impacts from further reduced UE complexity in FR1

## 3.3	February 2023

RAN1#112 (1 TU)

- Continue discussion on RAN1 impacts from further reduced UE complexity in FR1

RAN2#121 (1 TU)

- Initial discussion on enhanced eDRX in RRC_INACTIVE

- Initial discussion on further reduced UE complexity in FR1

RAN4#106 RF core (0.25 TU)

- Initial discussion to identify UE RF specification impact of further reduced UE complexity in FR1

RAN4#106 RD core (0.25 TU)

- Initial discussion to identify RRM impact of further reduced UE complexity in FR1

- Initial discussion to identify RRM impact of enhanced eDRX in RRC_INACTIVE (>10.24s)

## 3.4	April 2023

RAN1#112bis-e (1 TU)

- Continue discussion on RAN1 impacts from further reduced UE complexity in FR1

- Revisit earlier agreements if needed due to potential RAN#99 decisions

RAN2#121bis-e (1 TU)

- Continue discussion on enhanced eDRX in RRC_INACTIVE

- Continue discussion on further reduced UE complexity in FR1

RAN3#119bis-e (0.5 TU)

- Discussion on RAN3 impacts to support Extended DRX enhancements in RRC_INACTIVE (>10.24s), taking previous RAN3 and SA2 progress into account

- Discussion on other RAN3 identified impacts related to WI objectives, from CT4 LS on Paging Policy Information for Network Triggered Connection Resume and RAN2 LS on configuring RRC_INACTIVE long eDRX above 10.24 sec with SDT features.

RAN4#106bis-e RF core (0.5 TU)

- Continue discussion on identified UE RF specification impact of further reduced UE complexity in FR1

RAN4#106bis-e RD core (0.5 TU)

- Continue discussion on identified RRM impact of further reduced UE complexity in FR1

- Continue discussion on identified RRM impact of enhanced eDRX in RRC_INACTIVE (>10.24s)

## 3.5	May 2023

RAN1#113 (1 TU)

- Continue discussion on RAN1 impacts from further reduced UE complexity in FR1

- Provide initial RAN1 input to RAN2 work on RRC configuration parameters

RAN2#122 (1 TU)

- Continue discussion on enhanced eDRX in RRC_INACTIVE

- Continue discussion on further reduced UE complexity in FR1

RAN3#120 (0.5 TU)

- Continue discussion on RAN3 impacts to support Extended DRX enhancements in RRC_INACTIVE (>10.24s) and other RAN3 identified impacts (if any)

- Initial discussion on baseline CRs

RAN4#107 RF core (0.5 TU)

- Continue discussion on identified UE RF specification impact of further reduced UE complexity in FR1

- Initial discussion on draft CR for UE RF specification change

RAN4#107 RD core (0.5 TU)

- Continue discussion on identified RRM impact due to further reduced UE complexity in FR1 and enhanced eDRX and discuss possible need for simulations

## 3.6	August 2023

RAN1#114 (1 TU)

- Finalize discussion on RAN1 impacts from further reduced UE complexity in FR1

- Provide RAN1 input to RAN2 work on UE capabilities and RRC configuration parameters

- Provide RAN1 CR pack to RAN

RAN2#123 (1 TU)

- Finalize discussion on enhanced eDRX in RRC_INACTIVE

- Continue discussion on further reduced UE complexity in FR1

- Initial discussion on running CRs

RAN3#121 (0.5 TU)

- Finalize discussion on RAN3 impacts to support Extended DRX enhancements in RRC_INACTIVE (>10.24s) and other identified impacts (if any)

- Continue discussion on baseline CRs

RAN4#108 RF core (0.5 TU)

- Continue discussion on draft CR for UE RF specification change

RAN4#108 RD core (0.5 TU)

- Continue discussion on identified RRM impact and further discuss specification impact of the identified RRM impact due to further reduced UE complexity in FR1 and enhanced eDRX in RRC_INACTIVE (>10.24s)

- Discuss possible work split for the CR work

## 3.7	October 2023

RAN2#123bis-e (1 TU)

- Finalize discussion on further reduced UE complexity in FR1

- Continue discussion on running CRs

RAN3#121bis-e (0.5 TU)

- Finalize discussion on RAN3 impacts to support Extended DRX enhancements in RRC_INACTIVE (>10.24s) and other identified impacts (if any)

- Continue discussion on baseline CRs

RAN4#108bis-e RF core (0.5 TU)

- Continue discussion on draft CR and endorse draft CR

RAN4#108bis-e RD core (0.5 TU)

- Draft CRs are discussed

## 3.8	November 2023

RAN2#124 (1 TU)

- Finalize running CRs and provide CR pack to RAN

RAN3#122 (0.5 TU)

- Finalize baseline CRs and provide CR pack to RAN

RAN4#109 RF core (0.5 TU)

- Final CRs are discussed and agreed

RAN4#109 RD core (0.5 TU)

- Final CRs are discussed and agreed

## 3.9	February 2024

RAN4#110 RD perf (0.5 TU)

- Performance part work plan will be provided later

## 3.10	April 2024

RAN4#110bis RD perf (0.5 TU)

- Performance part work plan will be provided later

## 3.11	May 2024

RAN4#111 RD perf (0.5 TU)

- Performance part work plan will be provided later

# References

RP-223544, “Revised WID on Enhanced support of reduced capability NR devices”, RAN#98-e

SP-220803, “New WID: 5GS support of NR RedCap UE with long eDRX for RRC_INACTIVE State”, SP#97-e