3GPP TSG-RAN WG3 Meeting #126	R3-247741

Orlando, USA, 18-22 Nov 2024

Agenda Item:	11.1

Source:	ZTE Corporation, NEC

Title:	Work plan for Rel-19 Enhancements for AI/ML for NG-RAN

Document for:	Discussion and Decision

1	Introduction

The Work Item “Enhancements for Artificial Intelligence (AI)/Machine Learning (ML) for NG-RAN” was approved for Release 19 at the 3GPP TSG RAN #105 meeting [1].

In this contribution, we provide a work plan for the work item taking the objectives and time budget in related working groups into account.

2	Work plan

- Objectives of the WI

The aim of this work item is to specify new AI/ML-based use cases and introduce further enhancements to finalize the Rel-18 leftovers based on the conclusions captured in TR 38.743 [2].

The detailed objectives of the WI are listed as follows:

- Specify data collection enhancements and signaling support within existing NG-RAN interfaces and architecture (including non-split architecture and split architecture) for AI/ML-based Slicing and AI/ML based CCO. [RAN3]

- Support of the Leftovers in Rel-18 AI/ML for NG-RAN [RAN3]:

  - Mobility Optimization for NR-DC

  - Split architecture support for Rel-18 use cases

  - Continuous MDT collection targeting the same UE across RRC states

Note: Coordination with RAN2, SA5 when needed if any.

- Time budget of the WI

RAN3 is the responsible group of the WI, and the time budget that was approved at RAN#105 meeting was shown as below [2],

Table 1: Time budget allocation

| Date | 2024 Q4 |  | 2025 Q1 | 2025 Q2 |  | 2025 Q3 |
| --- | --- | --- | --- | --- | --- | --- |
| Meeting | R3#125bis | R3#126 | R3#127 | R3#127bis | R3#128 | R3#129 |
| TUs | 2 | 2 | 2 | 2 | 2 | 2 |

Note: subsequent RAN plenary may make further adjustments to the whole Rel-19 time frame, hence the time plan for this WI might be subject to such adjustments.

- Work Plan

In order to achieve the objectives specified in the WID [1] within the time budget, we propose the following work plan for discussion.

| Meeting time | TUs | Work plan |
| --- | --- | --- |
| 2024 Q4 RAN3#125bis | 2 TU | - BLCR assignment - Discuss and try to achieve initial agreements on specification impacts of AI/ML assisted Network Slicing, AI/ML assisted CCO and Rel-18 Leftovers. - Discuss and try to achieve initial agreements on collection enhancements and signalling support within existing NG-RAN interfaces and architecture (including non-split architecture and split architecture) for AI/ML assisted Network Slicing, AI/ML assisted CCO and Rel-18 Leftovers. - New signalling procedure or enhanced existing procedure to covey information over the interface - Try to reflect initial agreements into the stage 2 and stage 3 CRs |
| 2024 Q4 RAN3#126 | 2 TU | - Continue to specify specification impacts of AI/ML assisted Network Slicing, AI/ML assisted CCO and Rel-18 Leftovers. - Continue to specify data collection enhancements and signalling support for AI/ML assisted Network Slicing, AI/ML assisted CCO and Rel-18 Leftovers. - Reflect the agreements into the stage 2 and stage 3 CRs. |
| 2025 Q1 RAN3#127 | 2 TU | - Continue discussion. - Reflect the agreements into the stage 2 and stage 3 CRs |
| 2025 Q2 RAN3#127bis | 2 TU | - Continue discussion. - Reflect the agreements into the stage 2 and stage 3 CRs |
| 2025 Q2 RAN3#128 | 2 TU | - Continue discussion. - Reflect the agreements into the stage 2 and stage 3 CRs |
| 2025 Q3 RAN3#129 | 2 TU | - Finalization of the normative work. - Finalization of the stage 2 and stage 3 CRs. |

- BLCR Assignment

Following is the assignment of the BLCR:

38.300 	NEC

38.401 	CMCC

38.420 	China Telecom

38.423 	ZTE

38.470 	Nokia

38.473 	Ericsson

37.340 	Huawei

37.480 	CATT

37.483 	Samsung

38.413 (if any) Lenovo

37.320 (if any) Qualcomm

- It is proposed to endorse the Work Plan.

3	Conclusion

- It is proposed to endorse the Work Plan.

4	Reference

[1] 	3GPP RP-242385, “New WID on Enhancements for Artificial Intelligence (AI)/Machine Learning (ML) for NG-RAN”, ZTE Corporation, NEC

[2]	TR 38.743