## Cover sheet
3GPP TSG-RAN WG4 Meeting #59 MIMO OTA AH | R4-MIMOOTAah-0016
16 - 17 June, 2011, Aalborg, Denmark
Source: Vodafone
Title: Round robin measurement campaign schedule
Agenda item: 4.1
Document for: Discussion

## Previous Schedule
Month | Week |  | DUT Pool 1,2 | DUT Pool 3 | DUT Pool4 Sub 1 | DUT Pool4 Sub 2
|  |  | status | status | status | status | Legend:
January | 1w | 1 | [5 empty] | DUTs not available
| 2w | 2 | [5 empty] | To be planned
| 3w | 3 | R&S | ETSL |  |  |  | Shipping
| 4w | 4 | R&S | ETSL
February | 1w | 5 | R&S | ETSL |  |  | Group 1: Nokia, SATIMO, R&S, EMITE, Bluetest
| 2w | 6 | R&S | ETSL |  |  | Group 2: Huawei, CATR, Agilent, NTT DCM
| 3w | 7 | R&S | ETSL |  |  | Group 3: ETS Lingren, Azimuth Systems, Spirent, Qualcomm
| 4w | 8 | R&S | ETSL
March | 1w | 9 | R&S | ETSL
| 2w | 10 | SATIMO | Azimuth
| 3w | 11 | SATIMO | Azimuth
| 4w | 12 | SATIMO | Azimuth
April | 1w | 13 | NOKIA | Azimuth
| 2w | 14 | NOKIA | Spirent
| 3w | 15 | EMITE | Spirent
| 4w | 16 | EMITE | Spirent
May | 1w | 17 | EMITE | Qualcomm
| 2w | 18 | Bluetest | Qualcomm
| 3w | 19 | Bluetest | Qualcomm
| 4w | 20 | Bluetest | Qualcomm
June | 1w | 21 | NTT DCM | Qualcomm | R&S | NTT DCM
| 2w | 22 | NTT DCM | NTT DCM | R&S | NTT DCM | Check Point 1 | (NTT DCM testing on-going, all DUTs received safely)
| 3w | 23 | NTT DCM | NTT DCM | Bluetest | NTT DCM
| 4w | 24 | NTT DCM | NTT DCM | Bluetest | NTT DCM
July | 1w | 25 | CATR/Ag/H | NTT DCM | SATIMO | CATR/Ag/H
| 2w | 26 | CATR/Ag/H | CATR/Ag/H | SATIMO | CATR/Ag/H
| 3w | 27 | CATR/Ag/H | CATR/Ag/H | NOKIA | CATR/Ag/H
| 4w | 28 | CATR/Ag/H | CATR/Ag/H | NOKIA | CATR/Ag/H | Check Point 2
August | 1w | 29 |  | CATR/Ag/H | EMITE
| 2w | 30 | ETSL/Spirent |  |  | R&S
| 3w | 31 | ETSL/Spirent | R&S (No need) | Azimuth | R&S
| 4w | 32 | ETSL/Spirent | R&S (No need) | ETSL | SATIMO
September | 1w | 33 | Azimuth | SATIMO | ETSL | SATIMO | Check Point 3
| 2w | 34 | Azimuth | SATIMO |  | NOKIA
| 3w | 35 | R&S | NOKIA | SATIMO | NOKIA
| 4w | 36 | SATIMO | NOKIA | NOKIA (No need) |  | Check Point 4
Completion Gate 1
October | 1w | 37 | NOKIA | EMITE
| 2w | 38 |  | EMITE
| 3w | 39 |  | Bluetest
| 4w | 40 |  | Bluetest |  |  | Check Point 5
Completion Gate 2

## New schedule
Pool 1/2 | Schedule | Shipping
CATR/agilent/Huawei | Cancelled | Aug wk4 shipping?
ETSL/ Spirent | Sept Wk1 to Sept Wk 2? | sept wk3 shipping
Azimuth | Sept. W4 to Oct. Wk1? | Oct wk2 shipping
R&S | Cancelled | Aug wk4 shipping?
Satimo | Sept Wk1 to Sept Wk 2? | sept wk3 shipping
Nokia | Sept. W4 to Oct. Wk1? | Oct wk2 shipping
Pool 3
CATR/agilent/Huawei | Sept. Wk 4 to Oct. Wk 1 | Oct. Wk 2 shipping to Bluetest
R&S
Satimo | Sept. wk2 to Sept. wk3 | Sept Wk. 3 shipping to Agilent
Nokia
Emite | Aug. Wk.4 to Sept. Wk1 | Sept. wk 1 shipping to Satimo
Bluetest | Oct. Wk 3 to Oct. Wk 4 | Oct. Wk 4 shipping back to Vodafone
Pool 4 sub1
Emite | cancelled
Azimuth | Aug wk. 1 to Aug wk. 2 | Aug. Wk 2 shipping to ETSL
ETSL | Aug. wk 3 to Aug. wk 4 | Aug. Wk4 shipping to Satimo
Satimo | Sep. Wk 1 to Sept. Wk 2 | Sept. Wk 2 shipping to EMITE
Nokia
EMITE | Sep. wk3 to Sept. Wk 4 | Sept. Wk 4 Shipping To Vodafone
Pool 4 sub2
CATR/agilent/Huawei | Sept. wk4 to Oct. wk1 | Oct. wk 2 shipping to Vodafone
R&S
Satimo | Sept. wk2 to Sept. wk3 | Sept Wk. 3 shipping to Agilent
Nokia | Aug. Wk.4 to Sept. Wk1 | Sept. wk 1 shipping to Satimo
To be Planned!