## Cover sheet
3GPP TSG RAN WG5#99 | [10 empty] | R5-234774
<Toulouse, France, 21st Aug 2023 - 25th Aug 2023>
Agenda Item: | 7.4.2
Source: | China Unicom
Title: | UE Conformance – Support of reduced capability NR devices
Work item code: | NR_redcap_plus_ARCH-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0-7
1. Introduction
The objective of the UE Conformance – Support of reduced capability NR devices work item is to define the UE conformance requirements corresponding to WID on Support of reduced capability NR devices, analyse the test case impact, applicability, test environment, and update the relevant conformance specifications for the RedCap UE work item in Rel-17. At the RAN#95 meeting the Rel-17 RAN5 work item for UE Conformance – Support of reduced capability NR devices (NR_redcap_plus_ARCH-UEConTest) was approved [1]. The purpose of present document is to provide a work plan for the RAN5 work item. The work plan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 82% (+5%) | 80.5 (+27) | 151 (+1)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 81.8% (+5.4%) | 80.5 (+27) | 151 (+1)
FR1 |  | 83.4% (+7.2%) | 71.5 (+27) | 119.5 (+1)
FR2 |  | 78.9% (+2.1%) | 21 (+3) | 43.5 (+1)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 100% |  |  | 100% |  |  | 100%
Common ICS | 38.508-2 | 100% |  |  | 100% |  |  | 100%
NR RF/RRM
FR1 RF common parts | 38.521-1 | 100% |  |  | 100%
FR1 RF Tx test cases | 38.521-1 Tx | 100% |  |  | 100%
FR1 RF Rx test cases | 38.521-1 Rx | 100% | 5 | 5 | 100% | 5 | 5
FR2 RF common parts | 38.521-2 | 100% | [5 empty] | 100%
FR2 RF Tx test cases | 38.521-2 Tx | 70% (+0%) | [5 empty] | 70% (+0%)
FR2 RF Rx test cases | 38.521-2 Rx | 95% (-0%) | [5 empty] | 95%
RF Demod/QSI test cases | 38.521-4 | 71.9% (+15.6%) | 11 (+6) | 23 | 71.9% (+15.6%) | 11 (+6) | 23
RRM test cases | 38.533 | 61.4% (+5.5%) | 53.5 (+18) | 111 | 69.7% (+8.5%) | 43.5 (+18) | 79.5 | 45.9% (+0%) | 10 | 31.5
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 72.6% (+2.1%) |  |  | 90% (+3.3%) |  |  | 40%
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 52.2% (-0.1%) |  |  | 80% |  |  | 0%
Test Point analysis receiver and transmitter test cases | 38.905 | 3.3% (-0%) |  |  | 5% |  |  | 0%
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 99.9% (+4.9%) | 11 (+3) | 12 (+1) | 100% (+4.9%) | 12 (+3) | 12 (+1) | 99.8% (+4.9%) | 11 (+3) | 12 (+1)
Applicability Protocol test cases | 38.523-2 | 100% |  |  | 100% |  |  | 100%
Test suites (TTCN) | 38.523-3
5 References
[1] RP-220830 | New WID on UE Conformance – Support of reduced capability NR devices for RAN#95e
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance – Support of reduced capability NR devices | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_redcap_plus_ARCH-UEConTest
WP Scope: |  | The purpose of present document is to provide a workplan for the RAN5 work item Support of reduced capability NR devices comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID | [12 empty] | vs Area
WP Resp: |  | Yu Shi(China Unicom),Yang, Zhaobing (Huawei) ,Calle Hagenfeldt (Ericsson),Yogesh Tugnawat (Qualcomm) |  |  | shiyu19@chinaunicom.cn;yangzhaobing@hisilicon.com;calle.hagenfeldt@ericsson.com;yogesht@qti.qualcomm.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | N/A |  |  | N/A
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1 | FR2
[14 empty] | 83.4% (+7.2%) | 78.9% (+2.1%)
[14 empty] | 270 (+2) | 144 (+2)
[14 empty] | 212.1 (+1) | 113.6 (+2)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 38.508-1 | 4 | common test environment for RedCap | Definition of common test environment for RedCap | Huawei | RAN5#96 (Aug-22) | R5-223410 R5-222650 R5-223784 R5-224725 R5-225342 R5-225343 R5-225682 R5-225766 R5-227518 R5-227587 R5-230457 R5-230103 R5-231586 R5-233406 R5-235249 R5-235781 R5-235841 R5-235781 R5-235823 |  | 3 | 100% | 100% |  | 100% | 100%
2 |  | 38.508-1 | 5 | Test environments for RF test | Necessary changes to RF test environments | Huawei | RAN5#96 (Aug-22) |  |  | 3 | 100% | 100% |  | 100% | 100%
3 |  | 38.508-1 | 7 | Test environments for RRM tests | Necessary changes to RRM test environments | Huawei | RAN5#97(Nov-22) | R5-226110 |  | 3 | 100% | 100% |  | 100% | 100%
4 |  | 38.508-1 | Annex A | Connection Diagrams | Connection Diagrams | Ericsson | RAN5#99 (May-23) | R5-226684 |  | 1 | 100% | 100% |  | 100% | 100%
TS 38.508-2: Common ICS
5 |  | 38.508-2 | A.4 | ICS proforma tables | Introduction of common implementation conformance statement (ICS) for RedCap | Huawei | RAN5#99 (May-23) | R5-222827 R5-225767 R5-227894 R5-227708 R5-227521 R5-227588 R5-232929 R5-233034 |  | 3 | 100% | 100% |  | 100% | 100%
NR RF/RRM
TS 38.521-1: FR1 RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
6 |  | 38.521-1 | 3 | Definitions, symbols and abbreviations | definitions, symbols and abbreaviations respectively for RedCap | China Unicom | RAN5#96 (Aug-22) | R5-223790 R5-230888 |  | 2 | 100% | 100% |  | 100%
7 |  | 38.521-1 | 4 | General | Define categories of test requirements for R17 reduced capability NR devices | China Unicom | RAN5#96 (Aug-22) | R5-223790 R5-226765 |  | 2 | 100% | 100% |  | 100%
8 |  | 38.521-1 | 5 | Operating bands and Channel arrangement | Define the frequency bands and channel arragement for R17 reduced capability NR devices | China Unicom | RAN5#96 (Aug-22) | R5-223790 R5-231858 R5-231640 |  | 2 | 100% | 100% |  | 100%
9 |  | 38.521-1 | Annex |  | Check if necesarry to update Annex | ZTE | RAN5#100 (Aug-23) |  |  | 1 | 100% | 100% |  | 100%
TS 38.521-1: FR1 RF test cases - Tx
Transmitter characteristics (Clause 6)
10 |  | 38.521-1 Tx | 6.2I.1 | Maximum output power for RedCap | Adding TC of UE maximum output power for RedCap | Huawei | RAN5#96 (Aug-22) | R5-223785 R5-227116 R5-231255 R5-234119 R5-234169 |  | 5 | 100% | 100% |  | 100%
TS 38.521-1: FR1 RF test cases - Rx
Receiver characteristics(Clause 7)
11 |  | 38.521-1 Rx | 7.1I | General | Adding general info introudction for RedCap | China Unicom | RAN5#95e (May-22) | R5-223198 |  | 1 | 100% | 100% |  | 100%
12 |  | 38.521-1 Rx | 7.2 | Diversity characteristics | Update of diveristy characteristics intrdocution for RedCap | China Unicom | RAN5#95e (May-22) | R5-223198 R5-227935 |  | 5 | 100% | 100% |  | 100%
13 |  | 38.521-1 | 7.3I | Reference sensitivity for RedCap | sub-clause
14 |  | 38.521-1 Rx | 7.3I.1 | General | Adding general info introudction for RedCap | China Unicom | RAN5#96 (Aug-22) | R5-223789 R5-225683 R5-226595 R5-227935 |  | 5 | 100% | 100% |  | 100%
15 | Y | 38.521-1 Rx | 7.3I.2 | Reference sensitivity power level for RedCap | TC of reference sensitivity power level for RedCap | China Unicom | RAN5#96 (Aug-22) | R5-223789 R5-224245 R5-225683 R5-226595 R5-227935 R5-230998 R5-234907 R5-234169 |  | 5 | 100% | 100% |  | 100%
TS 38.521-2: FR1 RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
16 |  | 38.521-2 | 3 | Definitions, symbols and abbreviations | definitions, symbols and abbreaviations respectively for RedCap | China Unicom | RAN5#98 (Feb-23) | R5-227943 R5-231285 R5-233206 |  | 1 | 100% | 100% |  |  | 100%
17 |  | 38.521-2 | 5 | Operating bands and Channel arrangement | Define the frequency bands and channel arragement for R17 reduced capability NR devices | China Unicom | RAN5#98 (Feb-23) |  |  | 1 | 100% | 100% |  |  | 100%
18 |  | 38.521-2 | Annex F | Measurement uncertainties and Test Tolerances | Define measurement uncertainties and TT for PC7 |  |  | R5-234825 R5-234169 |  | 1 | 100% | 100% |  |  | 100%
TS 38.521-2: FR2 RF test cases - Tx
Transmitter characteristics (Clause 6)
|  | 38.521-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
19 |  | 38.521-2 Tx | 6.1 | General | adding PC7 common uplink configuration | Qualcomm | RAN5#97(Nov-22) | R5-227777 |  | 1 | 100% | 100% |  |  | 100%
20 |  | 38.521-2 Tx | 6.2.1.0 | General | adding Release-17 FR2 PC7 UE Type | Qualcomm | RAN5#97(Nov-22) | R5-227777 R5-233718 |  | 1 | 100% | 100% |  |  | 100%
21 |  | 38.521-2 Tx | 6.2.1.1 | UE maximum output power - EIRP and TRP | adding RF requirement for Release-17 FR2 PC7 UE | Qualcomm | RAN5#98 (Feb-23) | R5-231873 R5-233554 | MU and TT are still TBD | 1 | 90% | 90% |  |  | 90%
22 |  | 38.521-2 Tx | 6.2.1.1_1 | UE maximum output power - EIRP and TRP (Rel16 and forward) | adding RF requirement for Release-17 FR2 PC7 UE with enhanced beam correspondence side condition | Qualcomm | RAN5#98 (Feb-23) | R5-231873 R5-233554 | MU and TT are still TBD | 1 | 90% | 90% |  |  | 90%
23 |  | 38.521-2 Tx | 6.2.1.2 | UE maximum output power - Spherical coverage | adding UE spherical coverage for power class 7 | Qualcomm | RAN5#98 (Feb-23) | R5-231873 R5-233718 | MU and TT are still TBD | 1 | 90% | 90% |  |  | 90%
24 |  | 38.521-2 Tx | 6.2.1.2_1 | UE maximum output power - Spherical coverage (Rel16 and forward) | adding UE spherical coverage for power class 7 UE with enhanced beam correspondence side condition | Qualcomm | RAN5#99 (May-23) | R5-231873 R5-233554 | MU and TT are still TBD | 1 | 90% | 90% |  |  | 90%
25 |  | 38.521-2 Tx | 6.2.2 | UE maximum output power reduction | adding Release-17 FR2 PC7 UE MPR | ZTE | RAN5#100 (Aug-23) |  |  | 1 | 0% | 0% |  |  | 0%
26 |  | 38.521-2 Tx | 6.2.3 | UE maximum output power with additional requirements | adding Release-17 FR2 PC7 UE MPR for NS_202 and NS_203 | ZTE | RAN5#100 (Aug-23) |  |  | 1 | 0% | 0% |  |  | 0%
27 |  | 38.521-2 Tx | 6.3.1 | Minimum output power | adding Release-17 FR2 PC7 Minimum output power | ZTE | RAN5#100 (Aug-23) |  |  | 1 | 0% | 0% |  |  | 0%
28 |  | 38.521-2 Tx | 6.4.2.2 | Carrier leakage | adding Release-17 FR2 PC7 Carrier leakage | Nokia | RAN5#100 (Aug-23) | R5-233552 | Test Tolerance is FFS | 1 | 90% | 90% |  |  | 90%
29 |  | 38.521-2 Tx | 6.4.2.3 | In-band emissions | adding Release-17 FR2 PC7 In-band emissions | Nokia | RAN5#100 (Aug-23) | R5-233553 |  | 1 | 100% | 100% |  |  | 100%
30 |  | 38.521-2 Tx | 6.6.1 | Beam correspondence - EIRP | adding Release-17 FR2 PC7 Beam correspondence | Huawei | RAN5#100 (Aug-23) | R5-233554 |  | 1 | 100% | 100% |  |  | 100%
31 |  | 38.521-2 Tx | 6.6.2 | Enhanced Beam correspondence – EIRP | adding Release-17 FR2 PC7 Beam correspondence | Huawei | RAN5#100 (Aug-23) | R5-233554 |  | 1 | 100% | 100% |  |  | 100%
32 |  | 38.521-2 Tx | Multi places | Multi sections | Checking all test cases and adding PC7 to configuration tables where 'inner full configuration' is used for testing | Qualcomm | RAN5#99 (May-23) | R5-233206 R5-232618 |  | 1 | 30% | 30% |  |  | 30%
TS 38.521-2: FR2 RF test cases - Rx
Receiver characteristics(Clause 7)
33 |  | 38.521-2 Rx | 7.3.2 | Reference sensitivity power level | adding Release-17 FR2 PC7 Reference sensitivity power level | Qualcomm | RAN5#99 (May-23) | R5-232617 |  | 1 | 100% | 100% |  |  | 100%
34 |  | 38.521-2 Rx | 7.3.4 | EIS spherical coverage | adding Release-17 FR2 PC7 EIS spherical coverage | Qualcomm | RAN5#99 (May-23) | R5-233719 | Test Tolerance is FFS | 1 | 90% | 90% |  |  | 90%
TS 38.521-4: Demod/QSI reporting test cases
35 |  | 38.521-4 | 3 | Definitions, symbols and abbreviations | definitions, symbols and abbreaviations respectively for RedCap | Ericsson | RAN5#99 (May-23) | R5-226690 |  | 1 | 100% | 100% |  | 100%
36 |  | 38.521-4 | 5.1.1.11 | Applicability of requirements for RedCap | Add new table for Requirements applicability for RedCap | Ericsson | RAN5#99 (May-23) | R5-227806 |  | 1 | 100% | 100% |  | 100%
37 |  | 38.521-4 | 5.2.1 | 1RX requirements (Void) | Remove void | Ericsson | RAN5#99 (May-23) |  |  | 0 | 100% (+100%) | 100% (+100%) |  | 100%
38 |  | 38.521-4 | 5.2.1.1 | FDD | New caluse | Ericsson | RAN5#99 (May-23) |  |  | 0
39 | Y | 38.521-4 | 5.2.1.1.1 | 1Rx FDD FR1 PDSCH performance for RedCap | New test case | Ericsson | RAN5#99 (May-23) | R5-226687 R5-231697 R5-230682 R5-230683 R5-232569r1 R5-235686 | SNR in test requirements table is within square brackets. | 1 | 100% (+5%) | 100% (+5%) |  | 100%
40 |  | 38.521-4 | 5.2.1.2 | TDD | New caluse | Ericsson | RAN5#99 (May-23) |  |  | 0
41 | Y | 38.521-4 | 5.2.1.2.1 | 1Rx TDD FR1 PDSCH performance for RedCap | New test case | Ericsson | RAN5#99 (May-23) | R5-234548 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
42 | Y | 38.521-4 | 5.2.2.1.17 | 2Rx FDD FR1 PDSCH performance for RedCap | New test case | Ericsson | RAN5#99 (May-23) | R5-230702 R5-235689 |  | 1 | 100% | 100% |  | 100%
43 | Y | 38.521-4 | 5.2.2.2.18 | 2Rx TDD FR1 PDSCH performance for RedCap | New test case | Ericsson | RAN5#99 (May-23) | R5-230703 R5-233010r2 R5-235689 |  | 1 | 100% | 100% |  | 100%
44 |  | 38.521-4 | 5.3.1 | 1RX requirements (Void) | Remove void | Ericsson | RAN5#99 (May-23) |  |  | 0
45 |  | 38.521-4 | 5.3.1.1 | FDD | New caluse | Ericsson | RAN5#99 (May-23) |  |  | 0
46 | Y | 38.521-4 | 5.3.1.1.1 | 1Rx FDD FR1 PDCCH performance for RedCap | New test case | Ericsson | RAN5#99 (May-23) | R5-234550 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
47 |  | 38.521-4 | 5.3.1.2 | TDD | New caluse | Ericsson | RAN5#99 (May-23) |  |  | 0
48 | Y | 38.521-4 | 5.3.1.2.1 | 1Rx TDD FR1 PDCCH performance for RedCap | New test case | Ericsson | RAN5#99 (May-23) | R5-230706 R5-235690 R5-235687 |  | 1 | 100% | 100% |  | 100%
49 | Y | 38.521-4 | 5.3.2.1.4 | 2Rx FDD FR1 PDCCH performance for RedCap | New test case | Ericsson | RAN5#99 (May-23) | R5-233598 R5-235689 R5-235690 |  | 1 | 100% (+5%) | 100% (+5%) |  | 100%
50 | Y | 38.521-4 | 5.3.2.2.4 | 2Rx TDD FR1 PDCCH performance for RedCap | New test case | Ericsson | RAN5#99 (May-23) | R5-232568r2 R5-235689 R5-235690 | Core requirements has brackets | 1 | 95% | 95% |  | 95%
51 | Y | 38.521-4 | 5.5I.1 | Sustained downlink data rate provided by lower layers for RedCap | New test case | Qualcomm | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  | 0%
52 |  | 38.521-4 | 6.1.1 | Applicability of requirements | Updates as per 38.101-4 | Ericsson | RAN5#99 (May-23) | R5-226688 R5-230724 |  | 1 | 100% | 100% |  | 100%
53 |  | 38.521-4 | 6.1.1.6 | Applicability of requirements for RedCap | New clause | Ericsson | RAN5#99 (May-23) | R5-226688 R5-230724 R5-232570 |  | 1 | 100% | 100% |  | 100%
54 |  | 38.521-4 | 6.2.1 | 1RX requirements (Void) | Remove void | Ericsson | RAN5#99 (May-23) |  |  | 0
55 |  | 38.521-4 | 6.2.1.1 | FDD | New caluse | Ericsson | RAN5#99 (May-23) |  |  | 0
56 |  | 38.521-4 | 6.2.1.1.1 | CQI reporting definition under AWGN conditions | New caluse | Ericsson | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  | 0%
57 | Y | 38.521-4 | 6.2.1.1.1.1 | 1Rx FDD FR1 periodic CQI reporting under AWGN conditions for RedCap for SA | New test case | Ericsson | RAN5#99 (May-23) | R5-227807 R5-232571 | CQI/RI/PMI delay and SNR in test requirements table is within square brackets. | 1 | 95% | 95% |  | 95%
58 |  | 38.521-4 | 6.2.1.1.2 | CQI reporting definition under fading conditions | New caluse | Ericsson | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  | 0%
59 | Y | 38.521-4 | 6.2.1.1.2.1 | 1Rx FDD FR1 periodic wideband CQI reporting under fading conditions for RedCap for SA | New test case | Qualcomm | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  | 0%
60 |  | 38.521-4 | 6.2.1.2 | TDD | New caluse | Ericsson | RAN5#99 (May-23) | R5-232572 |  | 0
61 |  | 38.521-4 | 6.2.1.2.1 | CQI reporting definition under AWGN conditions | New caluse | Ericsson | RAN5#99 (May-23) | R5-232572 |  | 1 | 100% | 100% |  | 100%
62 | Y | 38.521-4 | 6.2.1.2.1.1 | 1Rx TDD FR1 periodic CQI reporting under AWGN conditions for RedCap | New test case | Ericsson | RAN5#99 (May-23) | R5-232572 |  | 1 | 100% | 100% |  | 100%
63 |  | 38.521-4 | 6.2.1.2.2 | CQI reporting definition under fading conditions | New caluse | Ericsson | RAN5#99 (May-23) | R5-232573 |  | 1 | 100% | 100% |  | 100%
64 | Y | 38.521-4 | 6.2.1.2.2.1 | 1Rx TDD FR1 periodic wideband CQI reporting under fading conditions for RedCap | New test case | Ericsson | RAN5#99 (May-23) | R5-232573 |  | 1 | 100% | 100% |  | 100%
65 | Y | 38.521-4 | 6.2.2.1.1.4 | 2Rx FDD FR1 periodic CQI reporting under AWGN conditions for RedCap for SA | New test case | Qualcomm | RAN5#99 (May-23) | R5-227809 R5-230057 R5-230707 R5-234274r1 R5-234916 | SNR still in [] | 1 | 95% | 95% |  | 95%
66 | Y | 38.521-4 | 6.2.2.1.2.4 | 2Rx FDD FR1 periodic wideband CQI reporting under fading conditions for RedCap for SA | New test case | Qualcomm | RAN5#99 (May-23) | R5-227810 R5-230707 R5-231305 R5-234274r1 R5-234916 | SNR still in [] MU and TT are still TBD | 1 | 90% | 90% |  | 90%
67 | Y | 38.521-4 | 6.2.2.2.1.5 | 2Rx TDD FR1 periodic CQI reporting under AWGN conditions for RedCap | New test case | Ericsson | RAN5#99 (May-23) | R5-235688 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
68 | Y | 38.521-4 | 6.2.2.2.2.4 | 2Rx TDD FR1 periodic wideband CQI reporting under fading conditions for RedCap | New test case | Ericsson | RAN5#99 (May-23) | R5-234824 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
69 |  | 38.521-4 | 6.3.1.1 | FDD | New clause | TBD | RAN5#99 (May-23) |  |  | 0
70 | Y | 38.521-4 | 6.3.1.1.1 | 1Rx FDD Single PMI with 4TX TypeI-SinglePanel Codebook for RedCap | New test case | TBD | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  | 0%
71 |  | 38.521-4 | 6.3.1.2 | TDD | New clause | TBD | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  | 0%
72 | Y | 38.521-4 | 6.3.1.2.1 | 1Rx TDD Single PMI with 4TX TypeI-SinglePanel Codebook for RedCap | New test case | TBD | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  | 0%
73 | Y | 38.521-4 | 6.3.2.2.7 | 2Rx TDD Single PMI with 4TX TypeI-SinglePanel Codebook for RedCap | New test case | TBD | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  | 0%
74 | Y | 38.521-4 | 6.4.2.1.1 | 2Rx FDD FR1 RI reporting for RedCap | New test case | Ericsson | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  | 0%
75 | Y | 38.521-4 | 6.4.2.2.1 | 2Rx TDD FR1 RI reporting for RedCap | New test case | Ericsson | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  | 0%
76 |  | 38.521-4 | 7.1.1 | Applicability of requirements | Updates as per 38.101-4 | Ericsson | RAN5#99 (May-23) | R5-230724 R5-234279 |  | 1 | 100% | 100% |  | 100%
77 |  | 38.521-4 | 7.1.1.7 | Applicability of requirements for RedCap | New clause | Ericsson | RAN5#99 (May-23) | R5-230724 R5-234279 |  | 1 | 100% | 100% |  | 100%
78 | Y | 38.521-4 | 7.5I.1 | FR2 Sustained downlink data rate performance for single carrier for RedCap | Update table 7.5.1.3-1 as per 38.101-4 | Qualcomm | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  | 0%
79 |  | 38.521-4 | 8.1.1 | Applicability of requirements | Updates as per 38.101-4 | Ericsson | RAN5#99 (May-23) | R5-230724 R5-234279 |  | 1 | 100% | 100% |  | 100%
80 |  | 38.521-4 | 8.1.1.6 | Applicability of requirements for RedCap | New clause | Ericsson | RAN5#99 (May-23) | R5-230724 R5-234279 |  | 1 | 100% | 100% |  | 100%
81 |  | 38.521-4 | Annex A | Measurement channels | Table A.4-1 as per 38.101-4 | Ericsson | RAN5#99 (May-23) | R5-226690 R5-235691 |  | 1 | 100% | 100% |  | 100%
82 |  | 38.521-4 | Annex B | Propagation conditions | B.1.0 as per 38.101-4 | Ericsson | RAN5#99 (May-23) | R5-226690 |  | 1 | 100% | 100% |  | 100%
x |  | 38.521-4 | Annex F | Measurement uncertainties and test tolerances for FR1 | MU and TT for newly introduced RedCap Demod and CQI test cases | Ericsson | RAN5#99 (May-23) | R5-234825 |  | 1 |  |  |  | 100%
83 |  | 38.521-4 | Annex G | Minimum test time | To add minimum test time for RedCap Demod Test | Ericsson | RAN5#99 (May-23) | R5-226682 R5-230683 R5-233714 R5-233599 R5-232577 |  | 1 | 100% | 100% |  | 100%
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
84 |  | 38.522 | 4 | Test case conditions and selection criteria | Add test case applicability statements for the new test cases introduced for 38.521-1. | All test case owners | RAN5#100 (Aug-23) | R5-234667 R5-234673 |  | 1 | 100% | 100% |  | 100%
84 |  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Add test case applicability statements for the new test cases introduced for 38.521-1. | All test case owners | RAN5#100 (Aug-23) | R5-223791 R5-227117 R5-227874 R5-231813 R5-231814 R5-233715 |  | 1 | 100% | 100% |  | 100%
85 |  | 38.522 | 4.1.3 | NR interworking between NR FR1 and NR FR2 and between NR and LTE conformance test cases | Add test case applicability statements for the new test cases introduced for 38.521-2. | All test case owners | RAN5#100 (Aug-23) |  |  | 1 | 0% | 0% |  |  | 0%
86 |  | 38.522 | 4.1.4 | Performance conformance test cases | Add test case applicability statements for the new test cases introduced for 38.521-4. | All test case owners | RAN5#100 (Aug-23) | R5-226702 R5-230679 R5-232578 R5-234826 |  | 1 | 80% | 80% |  | 80%
87 |  | 38.522 | 4.2 | RRM conformance test cases | Add test case applicability statements for the new test cases introduced for 38.533. | All test case owners | RAN5#100 (Aug-23) | R5-226112 R5-230458 R5-232458 R5-232928 R5-235799 R5-234667 R5-234690 |  | 1 | 80% | 80% |  | 80% | 80%
TS 38.533: RRM test cases
|  | 38.533 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD | 0% | 0% |  | 0%
88 |  | 38.533 | 16 | NR standalone tests with all NR cells in FR1 for RedCap | New clause header |  | TBD |  |  | 0
89 |  | 38.533 | 16.1 | RRC_IDLE state mobility for RedCap | New sub-clause header |  |  |  |  | 0
90 |  | 38.533 | 16.1.1 | NR cell re-selection for RedCap | New sub-clause header |  |  |  |  | 0
91 | Y | 38.533 | 16.1.1.1 | NR SA FR1 Cell reselection to FR1 intra-frequency NR case for 1 Rx UE | Test in A.16.1.1.1 in TS 38.133 | Ericsson | RAN5#99 (May-23) | R5-227828 R5-231732 R5-233610 R5-233016r1 R5-234919 R5-234920r1 R5-234921 | RAN4 Phase 1 -TT analysis is missing. | 0.5 | 95% | 95% |  | 95%
92 | Y | 38.533 | 16.1.1.2 | NR SA FR1 Cell reselection to FR1 intra-frequency NR case for 2 Rx UE | Test in A.16.1.1.2 in TS 38.133 | Ericsson | RAN5#99 (May-23) | R5-227211 R5-231760 R5-233016r1 R5-234920r1 R5-234921 | RAN4 Phase 1 -TT analysis is missing. | 0.5 | 90% | 90% |  | 90%
93 | Y | 38.533 | 16.1.1.3 | NR SA FR1-FR1 Cell reselection to FR1 inter-frequency NR case for 1 Rx UE | Test in A.16.1.1.3 in TS 38.133 | Ericsson | RAN5#99 (May-23) | R5-227212 R5-231733 R5-234921 R5-235725 | RAN4 Phase 1 | 0.5 | 100% (+10%) | 100% (+10%) |  | 100%
94 | Y | 38.533 | 16.1.1.4 | NR SA FR1-FR1 Cell reselection to FR1 inter-frequency NR case for 2 Rx UE | Test in A.16.1.1.4 in TS 38.133 | Ericsson | TBD | R5-227213 R5-231761 R5-234921 | RAN4 Phase 1 Editor's Note: This test case is incomplete in following aspects: -Message contents are missing. -Test applicability is missing -Cell mapping is missing in Annex E -TT analysis is missing. | 0.5 | 90% | 90% |  | 90%
95 | Y | 38.533 | 16.1.1.5 | NR SA FR1 Cell reselection to FR1 intra-frequency NR case for UE fulfilling stationary relaxed measurement criterion for 1 Rx UE | Test in A.16.1.1.5 in TS 38.133 | Ericsson | RAN5#99 (May-23) | R5-227214 R5-231734 R5-235696 R5-234921 R5-235726 | RAN4 Phase 1 | 0.5 | 100% (+10%) | 100% (+10%) |  | 100%
96 | Y | 38.533 | 16.1.1.6 | NR SA FR1 Cell reselection to FR1 intra-frequency NR case for UE fulfilling stationary relaxed measurement criterion for 2 Rx UE | Test in A.16.1.1.6 in TS 38.133 | Ericsson | RAN5#99 (May-23) | R5-227215 R5-231746 R5-235696 R5-234921 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
97 | Y | 38.533 | 16.1.1.7 | NR SA FR1-FR1 Cell reselection to FR1 inter-frequency NR case for UE fulfilling stationary relaxed measurement criterion for 1 Rx UE | Test in A.16.1.1.7 in TS 38.133 | Ericsson | RAN5#99 (May-23) | R5-227216 R5-231735 R5-235696 R5-234921 R5-235727 | RAN4 Phase 1 | 0.5 | 100% (+10%) | 100% (+10%) |  | 100%
98 | Y | 38.533 | 16.1.1.8 | NR SA FR1-FR1 Cell reselection to FR1 inter-frequency NR case for UE fulfilling stationary relaxed measurement criterion for 2 Rx UE | Test in A.16.1.1.8 in TS 38.133 | Ericsson | RAN5#99 (May-23) | R5-227217 R5-231747 R5-235696 R5-234921 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
99 |  |  | 16.1.2 | NR - E-UTRA cell re-selection for RedCap | New sub-clause header |  | TBD | R5-227829 |  | 0
100 | Y | 38.533 | 16.1.2.1 | NR SA FR1 - E-UTRA Cell reselection to higher priority E-UTRA for 1RX | Test in A.16.1.2.1 in TS 38.133 | Ericsson | RAN5#99 (May-23) | R5-231123 R5-233616 R5-234000 R5-235728 | RAN4 Phase 1 | 0.5 | 100% (+10%) | 100% (+10%) |  | 100%
101 | Y | 38.533 | 16.1.2.2 | NR SA FR1 - E-UTRA Cell reselection to higher priority E-UTRA for 2RX | Test in A.16.1.2.2 in TS 38.133 | Ericsson | RAN5#99 (May-23) | R5-231124 R5-233616 R5-234000 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
102 | Y | 38.533 | 16.1.2.3 | NR SA FR1 - E-UTRA Cell reselection to lower priority E-UTRA for 1RX | Test in A.16.1.2.3 in TS 38.133 | Ericsson | RAN5#99 (May-23) | R5-231125 R5-233616 R5-234000 R5-235729 | RAN4 Phase 1 | 0.5 | 100% (+10%) | 100% (+10%) |  | 100%
103 | Y | 38.533 | 16.1.2.4 | NR SA FR1 - E-UTRA Cell reselection to lower priority E-UTRA for 2RX | Test in A.16.1.2.4 in TS 38.133 | Ericsson | RAN5#99 (May-23) | R5-231126 R5-233616 R5-234000 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
104 | Y | 38.533 | 16.1.2.5 | NR SA FR1 - E-UTRA Cell reselection to lower priority E-UTRA for UE fulfilling stationary relaxed measurement criterion for 1 Rx UE | Test in A.16.1.2.5 in TS 38.133 | Ericsson | RAN5#99 (May-23) | R5-231127 R5-233616 R5-235696 R5-234983r2 | RAN4 Phase 1 | 0.5 | 100% (+5%) | 100% (+5%) |  | 100%
105 | Y | 38.533 | 16.1.2.6 | NR SA FR1 - E-UTRA Cell reselection to lower priority E-UTRA for UE fulfilling stationary relaxed measurement criterion for 2 Rx UE | Test in A.16.1.2.6 in TS 38.133 | Ericsson | RAN5#99 (May-23) | R5-231128 R5-233616 R5-235696 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
106 |  |  | 16.2 | RRC_INACTIVE state mobility for RedCap | New sub-clause header
107 |  |  | 16.2.1 | Configured Grant based Small Data Transmissions for RedCap | New sub-clause header
108 | Y | 38.533 | 16.2.1.1 | NR SA FR1 CG-SDT for 1Rx UE | Test in A.16.2.1.1 in TS 38.133 | Huawei | RAN5#99 (May-23) |  |  | 0.5 | 0% | 0% |  | 0%
109 | Y | 38.533 | 16.2.1.2 | NR SA FR1 CG-SDT for 2Rx UE | Test in A.16.2.1.2 in TS 38.133 | Huawei | RAN5#99 (May-23) |  |  | 0.5 | 0% | 0% |  | 0%
110 |  |  | 16.3 | RRC_CONNECTED state mobility for RedCap | New sub-clause header |  |  | R5-226113
111 |  |  | 16.3.1 | Handover for RedCap | New sub-clause header |  |  | R5-226113
112 | Y | 38.533 | 16.3.1.1 | NR SA FR1 Intra-frequency handover from FR1 to FR1 with known target cell for 1 Rx UE | Test in A.16.3.1.1 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-230459 R5-234397 | RAN4 Phase 1 | 0.5 | 100% (+10%) | 100% (+10%) |  | 100%
113 | Y | 38.533 | 16.3.1.2 | NR SA FR1 Intra-frequency handover from FR1 to FR1 with known target cell for 2 Rx UE | Test in A.16.3.1.2 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-230460 R5-235701 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
114 | Y | 38.533 | 16.3.1.3 | NR SA FR1 Intra-frequency handover from FR1 to FR1 with unknown target cell for 1 Rx UE | Test in A.16.3.1.3 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-230461 R5-232459 R5-234398 | RAN4 Phase 1 | 0.5 | 100% (+10%) | 100% (+10%) |  | 100%
115 | Y | 38.533 | 16.3.1.4 | NR SA FR1 Intra-frequency handover from FR1 to FR1 with unknown target cell for 2 Rx UE | Test in A.16.3.1.4 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-230462 R5-232459 R5-234399 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
116 | Y | 38.533 | 16.3.1.5 | NR SA FR1-FR1 Inter-frequency handover from FR1 to FR1 with unknown target cell for 1 Rx UE | Test in A.16.3.1.5 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-230463 R5-232459 R5-234400 | RAN4 Phase 1 | 0.5 | 100% (+10%) | 100% (+10%) |  | 100%
117 | Y | 38.533 | 16.3.1.6 | NR SA FR1-FR1 Inter-frequency handover from FR1 to FR1 with unknown target cell for 2 Rx UE | Test in A.16.3.1.6 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-230464 R5-232459 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
118 | Y | 38.533 | 16.3.1.7 | NR - E-UTRA handover for 1Rx UE | Test in A.16.3.1.7 in TS 38.133 | Huawei | TBD | R5-226114 | TT analysis is still missing | 0.5 | 90% | 90% |  | 90%
119 | Y | 38.533 | 16.3.1.8 | NR - E-UTRA handover for 2Rx UE | Test in A.16.3.1.8 in TS 38.133 | Huawei | TBD | R5-228013 |  | 0.5 | 100% | 100% |  | 100%
120 | Y | 38.533 | 16.3.1.9 | NR - E-UTRA handover with unknown target cell for 1 Rx UE | Test in A.16.3.1.9 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-226116 | RAN4 Phase 1 TT analysis is still missing | 0.5 | 90% | 90% |  | 90%
121 | Y | 38.533 | 16.3.1.10 | NR - E-UTRA handover with unknown target cell for 2 Rx UE | Test in A.16.3.1.10 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-228014 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
122 |  |  | 16.3.2 | RRC Connection Mobility Control for RedCap | New sub-clause header |  |  | R5-226118
123 |  |  | 16.3.2.1 | RRC Re-establishment for RedCap | New sub-clause header |  |  | R5-226118
124 | Y | 38.533 | 16.3.2.1.1 | NR SA FR1 Intra-frequency RRC Re-establishment in FR1 for 1 Rx UE | Test in A.16.3.2.1.1 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-226119 | RAN4 Phase 1 TT analysis is still missing | 0.5 | 90% | 90% |  | 90%
125 | Y | 38.533 | 16.3.2.1.2 | NR SA FR1 Intra-frequency RRC Re-establishment in FR1 for 2 Rx UE | Test in A.16.3.2.1.2 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-226120 R5-232172 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
126 | Y | 38.533 | 16.3.2.1.3 | NR SA FR1-FR1 Inter-frequency RRC Re-establishment in FR1 for 1 Rx UE | Test in A.16.3.2.1.3 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-226121 | RAN4 Phase 1 TT analysis is still missing | 0.5 | 90% | 90% |  | 90%
127 | Y | 38.533 | 16.3.2.1.4 | NR SA FR1-FR1 Inter-frequency RRC Re-establishment in FR1 for 2 Rx UE | Test in A.16.3.2.1.4 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-226122 R5-232172 R5-235701 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
128 | Y | 38.533 | 16.3.2.1.5 | NR SA FR1 Intra-frequency RRC Re-establishment in FR1 for 1 Rx UE without serving cell timing | Test in A.16.3.2.1.5 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-226123 R5-235701 | RAN4 Phase 1 TT analysis is still missing | 0.5 | 100% (+10%) | 100% (+10%) |  | 100%
129 | Y | 38.533 | 16.3.2.1.6 | NR SA FR1 Intra-frequency RRC Re-establishment in FR1 for 2 Rx UE without serving cell timing | Test in A.16.3.2.1.6 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-226124 R5-232172 R5-235701 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
130 |  | 38.533 | 16.3.2.2 | Random Access for RedCap for RedCap |  |  | TBD | R5-226125 |  | 1
131 | Y | 38.533 | 16.3.2.2.1 | NR SA FR1 4-step RA type contention based random access test in FR1 for NR standalone for 1 Rx UE | Test in A.16.3.2.2.1 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-226126 | RAN4 Phase 1 TT analysis is still missing | 0.5 | 90% | 90% |  | 90%
132 | Y | 38.533 | 16.3.2.2.2 | NR SA FR1 4-step RA type contention based random access test in FR1 for NR standalone for 2 Rx UE | Test in A.16.3.2.2.2 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-226127 R5-232172 R5-235700 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
133 | Y | 38.533 | 16.3.2.2.3 | NR SA FR1 4-step RA type non-contention based random access test in FR1 for NR standalone for 1 Rx UE | Test in A.16.3.2.2.3 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-226128 | RAN4 Phase 1 TT analysis is still missing | 0.5 | 90% | 90% |  | 90%
134 | Y | 38.533 | 16.3.2.2.4 | NR SA FR1 4-step RA type non-contention based random access test in FR1 for NR standalone for 2 Rx UE | Test in A.16.3.2.2.4 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-226129 R5-232172 R5-235700 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
135 | Y | 38.533 | 16.3.2.2.5 | NR SA FR1 2-step RA type contention based random access test in FR1 for NR standalone for 1 Rx UE | Test in A.16.3.2.2.5 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-228015 | RAN4 Phase 1 TT analysis is still missing | 0.5 | 90% | 90% |  | 90%
136 | Y | 38.533 | 16.3.2.2.6 | NR SA FR1 2-step RA type contention based random access test in FR1 for NR standalone for 2 Rx UE | Test in A.16.3.2.2.6 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-228016 R5-232172 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
137 | Y | 38.533 | 16.3.2.2.7 | NR SA FR1 2-step RA type non-contention based test in FR1 for NR standalone for 1 RX UE | Test in A.16.3.2.2.7 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-228017 | RAN4 Phase 1 | 0.5 | 90% | 90% |  | 90%
138 | Y | 38.533 | 16.3.2.2.8 | NR SA FR1 2-step RA type non-contention based test in FR1 for NR standalone for 2 RX UE | Test in A.16.3.2.2.8 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-228018 R5-232172 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
139 |  |  | 16.3.2.3 | RRC Connection Release with Redirection for RedCap | New sub-clause header |  |  | R5-226134
140 | Y | 38.533 | 16.3.2.3.1 | NR SA FR1-FR1 Redirection from NR in FR1 to NR in FR1 for 1 Rx UE | Test in A.16.3.2.3.1 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-226135 | RAN4 Phase 1 TT analysis is still missing | 0.5 | 90% | 90% |  | 90%
141 | Y | 38.533 | 16.3.2.3.2 | NR SA FR1-FR1 Redirection from NR in FR1 to NR in FR1 for 2 Rx UE | Test in A.16.3.2.3.2 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-228019 R5-232172 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
142 | Y | 38.533 | 16.3.2.3.3 | NR SA FR1-FR1 Redirection from NR in FR1 to E-UTRAN for 1 Rx UE | Test in A.16.3.2.3.3 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-228020 | RAN4 Phase 1 | 0.5 | 90% | 90% |  | 90%
143 | Y | 38.533 | 16.3.2.3.4 | NR SA FR1-FR1 Redirection from NR in FR1 to E-UTRAN for 2 Rx UE | Test in A.16.3.2.3.4 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-228021 R5-232172 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
144 |  |  | 16.4 | Timing for RedCap | New sub-clause header |  |  | R5-226139
145 |  |  | 16.4.1 | UE transmit timing for RedCap | New sub-clause header |  |  | R5-226139
146 | Y | 38.533 | 16.4.1.1 | NR SA FR1 NR UE Transmit Timing Test for FR1 for 1Rx RedCap UE | Test in A.16.4.1.1 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-228022 R5-234999 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
147 | Y | 38.533 | 16.4.1.2 | NR SA FR1 NR UE Transmit Timing Test for FR1 for 2Rx RedCap UE | Test in A.16.4.1.2 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-228023 R5-234999 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
148 |  |  | 16.4.2 | UE timer accuracy for RedCap | New sub-clause header
149 |  |  | 16.4.3 | Timing advance for RedCap | New sub-clause header
150 | Y | 38.533 | 16.4.3.1 | NR SA FR1 SA FR1 timing advance adjustment accuracy for 1 Rx UE | Test in A.16.4.3.1 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-230465 R5-234999 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
151 | Y | 38.533 | 16.4.3.2 | NR SA FR1 SA FR1 timing advance adjustment accuracy for 2 Rx UE | Test in A.16.4.3.2 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-230466 R5-234999 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
152 |  |  | 16.5 | Signalling characteristics for RedCap | New sub-clause header |  |  | R5-226142
153 |  |  | 16.5.1 | Radio link Monitoring for RedCap | New sub-clause header |  |  | R5-226142
154 | Y | 38.533 | 16.5.1.1 | NR SA FR1 Radio Link Monitoring Out-of-sync Test for FR1 PCell configured with SSB-based RLM RS in non-DRX mode for 1 Rx UE | Test in A.16.5.1.1 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-226143 R5-234401 | RAN4 Phase 2 | 0.5 | 100% (+10%) | 100% (+10%) |  | 100%
155 | Y | 38.533 | 16.5.1.2 | NR SA FR1 Radio Link Monitoring Out-of-sync Test for FR1 PCell configured with SSB-based RLM RS in non-DRX mode for 2 Rx UE | Test in A.16.5.1.2 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-226144 R5-235702 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
156 | Y | 38.533 | 16.5.1.3 | NR SA FR1 Radio Link Monitoring In-sync Test for FR1 PCell configured with SSB-based RLM RS in non-DRX mode for 1 Rx UE | Test in A.16.5.1.3 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-226145 R5-234402 | RAN4 Phase 2 | 0.5 | 100% (+10%) | 100% (+10%) |  | 100%
157 | Y | 38.533 | 16.5.1.4 | NR SA FR1 Radio Link Monitoring In-sync Test for FR1 PCell configured with SSB-based RLM RS in non-DRX mode for 2 Rx UE | Test in A.16.5.1.4 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-226146 R5-235702 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
158 | Y | 38.533 | 16.5.1.5 | NR SA FR1 Radio Link Monitoring Out-of-sync Test for FR1 PCell configured with SSB-based RLM RS in DRX mode for 1 Rx UE | Test in A.16.5.1.5 in TS 38.133 | Qualcomm | RAN5#101 (Nov-23) | R5-233612 R5-233998 R5-234664 | RAN4 Phase 2 | 0.5 | 100% (+10%) | 100% (+10%) |  | 100%
159 | Y | 38.533 | 16.5.1.6 | NR SA FR1 Radio Link Monitoring Out-of-sync Test for FR1 PCell configured with SSB-based RLM RS in DRX mode for 2 Rx UE | Test in A.16.5.1.6 in TS 38.133 | Qualcomm | RAN5#101 (Nov-23) | R5-233612 R5-233998 R5-234664 | RAN4 Phase 2 | 0.5 | 100% (+10%) | 100% (+10%) |  | 100%
160 | Y | 38.533 | 16.5.1.7 | NR SA FR1 Radio Link Monitoring In-sync Test for FR1 PCell configured with SSB-based RLM RS in DRX mode for 1 Rx UE | Test in A.16.5.1.7 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-226147 R5-234404 | RAN4 Phase 2 | 0.5 | 100% (+10%) | 100% (+10%) |  | 100%
161 | Y | 38.533 | 16.5.1.8 | NR SA FR1 Radio Link Monitoring In-sync Test for FR1 PCell configured with SSB-based RLM RS in DRX mode for 2 Rx UE | Test in A.16.5.1.8 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-226148 R5-235702 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
162 | Y | 38.533 | 16.5.1.9 | NR SA FR1 Radio Link Monitoring Out-of-sync Test for FR1 PCell configured with CSI-RS-based RLM in non-DRX mode for 1 Rx UE | Test in A.16.5.1.9 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230467 R5-234405 | RAN4 Phase 2 | 0.5 | 100% (+10%) | 100% (+10%) |  | 100%
163 | Y | 38.533 | 16.5.1.10 | NR SA FR1 Radio Link Monitoring Out-of-sync Test for FR1 PCell configured with CSI-RS-based RLM in non-DRX mode for 2 Rx UE | Test in A.16.5.1.10 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230468 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
164 | Y | 38.533 | 16.5.1.11 | NR SA FR1 Radio Link Monitoring In-sync Test for FR1 PCell configured with CSI-RS-based RLM in non-DRX mode for 1 Rx UE | Test in A.16.5.1.11 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230469 R5-234406 | RAN4 Phase 2 | 0.5 | 100% (+10%) | 100% (+10%) |  | 100%
165 | Y | 38.533 | 16.5.1.12 | NR SA FR1 Radio Link Monitoring In-sync Test for FR1 PCell configured with CSI-RS-based RLM in non-DRX mode for 2 Rx UE | Test in A.16.5.1.12 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230470 R5-235702 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
166 | Y | 38.533 | 16.5.1.13 | NR SA FR1 Radio Link Monitoring Out-of-sync Test for FR1 PCell configured with CSI-RS-based RLM in DRX mode for 1 Rx UE | Test in A.16.5.1.13 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230471 R5-234407 | RAN4 Phase 2 | 0.5 | 100% (+10%) | 100% (+10%) |  | 100%
167 | Y | 38.533 | 16.5.1.14 | NR SA FR1 Radio Link Monitoring Out-of-sync Test for FR1 PCell configured with CSI-RS-based RLM in DRX mode for 2 Rx UE | Test in A.16.5.1.14 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-231759 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
168 | Y | 38.533 | 16.5.1.15 | NR SA FR1 Radio Link Monitoring In-sync Test for FR1 PCell configured with CSI-RS-based RLM in DRX mode for 1 Rx UE | Test in A.16.5.1.15 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230473 R5-234408 | RAN4 Phase 2 | 0.5 | 100% (+10%) | 100% (+10%) |  | 100%
169 | Y | 38.533 | 16.5.1.16 | NR SA FR1 Radio Link Monitoring In-sync Test for FR1 PCell configured with CSI-RS-based RLM in DRX mode for 2 Rx UE | Test in A.16.5.1.16 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230474 R5-235702 R5-235121r1 R5-235251 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
170 |  |  | 16.5.2 | Beam Failure Detection and Link recovery procedures for RedCap | New sub-clause header |  |  | R5-226149
171 | Y | 38.533 | 16.5.2.1 | NR SA FR1 Beam Failure Detection and Link Recovery Test for FR1 PCell configured with SSB-based BFD and LR in non-DRX mode for 1 Rx UE | Test in A.16.5.5.1 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-226150 R5-232460 | RAN4 Phase 2 TT analysis is still missing | 0.5 | 90% | 90% |  | 90%
172 | Y | 38.533 | 16.5.2.2 | NR SA FR1 Beam Failure Detection and Link Recovery Test for FR1 PCell configured with SSB-based BFD and LR in non-DRX mode for 2 Rx UE | Test in A.16.5.5.2 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-228024 R5-232460 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
173 | Y | 38.533 | 16.5.2.3 | NR SA FR1 Beam Failure Detection and Link Recovery Test for FR1 PCell configured with SSB-based BFD and LR in DRX mode for 1 Rx UE | Test in A.16.5.5.3 in TS 38.133 | Qualcomm | RAN5#101 (Nov-23) | R5-233613 R5-233998 R5-234664 | RAN4 Phase 2 | 0.5 | 100% (+10%) | 100% (+10%) |  | 100%
174 | Y | 38.533 | 16.5.2.4 | NR SA FR1 Beam Failure Detection and Link Recovery Test for FR1 PCell configured with SSB-based BFD and LR in DRX mode for 2 Rx UE | Test in A.16.5.5.4 in TS 38.133 | Qualcomm | RAN5#101 (Nov-23) | R5-233613 R5-234664 | RAN4 Phase 2 | 0.5 | 100% (+10%) | 100% (+10%) |  | 100%
175 | Y | 38.533 | 16.5.2.5 | NR SA FR1 Beam Failure Detection and Link Recovery Test for FR1 PCell configured with CSI-RS-based BFD and LR in non-DRX mode for 1 Rx UE | Test in A.16.5.5.5 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230475 | RAN4 Phase 2 TT analysis is still missing | 0.5 | 90% | 90% |  | 90%
176 | Y | 38.533 | 16.5.2.6 | NR SA FR1 Beam Failure Detection and Link Recovery Test for FR1 PCell configured with CSI-RS-based BFD and LR in non-DRX mode for 2 Rx UE | Test in A.16.5.5.6 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230476 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
177 | Y | 38.533 | 16.5.2.7 | NR SA FR1 Beam Failure Detection and Link Recovery Test for FR1 PCell configured with CSI-RS-based BFD and LR in DRX mode for 1 Rx UE | Test in A.16.5.5.7 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230477 | RAN4 Phase 2 TT analysis is still missing | 0.5 | 90% | 90% |  | 90%
178 | Y | 38.533 | 16.5.2.8 | NR SA FR1 Beam Failure Detection and Link Recovery Test for FR1 PCell configured with CSI-RS-based BFD and LR in DRX mode for 2 Rx UE | Test in A.16.5.5.8 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230478 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
179 |  | 38.533 | 16.5.3 | Active BWP switch | New sub-clause header
180 |  | 38.533 | 16.5.3.1 | DCI-based and Timer-based Active BWP Switch | New sub-clause header
181 | Y | 38.533 | 16.5.3.1.1 | NR SA FR1 NR SA FR1 DL active BWP switch with non-DRX in SA for 1 Rx UE | Test in A.16.5.3.1.1 in TS 38.133 | Qualcomm | RAN5#101 (Nov-23) | R5-233614 R5-234664 R5-234999 | RAN4 Phase 2 | 0.5 | 100% (+10%) | 100% (+10%) |  | 100%
182 | Y | 38.533 | 16.5.3.1.2 | NR SA FR1 NR SA FR1 DL active BWP switch with non-DRX in SA for 2 Rx UE | Test in A.16.5.3.1.2 in TS 38.133 | Qualcomm | RAN5#101 (Nov-23) | R5-233614 R5-234664 R5-234999 | RAN4 Phase 2 | 0.5 | 100% (+10%) | 100% (+10%) |  | 100%
183 |  |  | 16.5.3.2 | RRC-based Active BWP Switch for RedCap | New sub-clause header
184 | Y | 38.533 | 16.5.3.2.1 | NR SA FR1 NR SA FR1 DL active BWP switch of Cell with non-DRX in SA for 1 Rx UE | Test in A.16.5.3.2.1 in TS 38.133 | Qualcomm | RAN5#101 (Nov-23) | R5-233615 R5-233889 R5-233998 R5-234664 | RAN4 Phase 2 | 0.5 | 100% (+10%) | 100% (+10%) |  | 100%
185 | Y | 38.533 | 16.5.3.2.2 | NR SA FR1 NR SA FR1 DL active BWP switch of Cell with non-DRX in SA for 2 Rx UE | Test in A.16.5.3.2.2 in TS 38.133 | Qualcomm | RAN5#101 (Nov-23) | R5-233615 R5-233889 R5-233998 R5-234664 | RAN4 Phase 2 | 0.5 | 100% (+10%) | 100% (+10%) |  | 100%
186 |  |  | 16.5.4 | UE specific CBW change for RedCap | New sub-clause header
187 | Y | 38.533 | 16.5.4.1 | NR SA FR1 UE specific CBW change on PCell in FR1 in non-DRX for 1 Rx UE | Test in A.16.5.8.1 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230479 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
188 | Y | 38.533 | 16.5.4.2 | NR SA FR1 UE specific CBW change on PCell in FR1 in non-DRX for 2 Rx UE | Test in A.16.5.8.2 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230480 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
189 |  |  | 16.6 | Measurement procedure for RedCap | New sub-clause header |  |  | R5-226152
190 |  |  | 16.6.1 | Intra-frequency Measurements for RedCap | New sub-clause header |  |  | R5-226152
191 | Y | 38.533 | 16.6.1.1 | NR SA FR1 Event triggered reporting tests without gap under non-DRX for 1 Rx UE | Test in A.16.6.1.1 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230481 R5-232462 R5-234409 R5-235696 | RAN4 Phase 2 | 0.5 | 100% (+10%) | 100% (+10%) |  | 100%
192 | Y | 38.533 | 16.6.1.2 | NR SA FR1 Event triggered reporting tests without gap under non-DRX for 2 Rx UE | Test in A.16.6.1.2 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230482 R5-232462 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
193 | Y | 38.533 | 16.6.1.3 | NR SA FR1 Event triggered reporting tests without gap under DRX for 1 Rx UE | Test in A.16.6.1.3 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-226153 R5-232461 R5-233999 R5-234410 | RAN4 Phase 2 | 0.5 | 100% (+10%) | 100% (+10%) |  | 100%
194 | Y | 38.533 | 16.6.1.4 | NR SA FR1 Event triggered reporting tests without gap under DRX for 2 Rx UE | Test in A.16.6.1.4 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-226154 R5-232172 R5-232461 R5-233999 R5-234924 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
195 | Y | 38.533 | 16.6.1.5 | NR SA FR1 Event triggered reporting tests with per-UE gaps under non-DRX for 1 Rx UE | Test in A.16.6.1.5 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230483 R5-232461 R5-233999 R5-234924 | RAN4 Phase 2 | 0.5 | 100% (+10%) | 100% (+10%) |  | 100%
196 | Y | 38.533 | 16.6.1.6 | NR SA FR1 Event triggered reporting tests with per-UE gaps under non-DRX for 2 Rx UE | Test in A.16.6.1.6 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230484 R5-232461 R5-234924 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
197 | Y | 38.533 | 16.6.1.7 | NR SA FR1 Event triggered reporting tests with per-UE gaps under DRX for 1 Rx UE | Test in A.16.6.1.7 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-226155 R5-232461 R5-235695 R5-233999 R5-234412 R5-234924 | RAN4 Phase 2 | 0.5 | 100% (+10%) | 100% (+10%) |  | 100%
198 | Y | 38.533 | 16.6.1.8 | NR SA FR1 Event triggered reporting tests with per-UE gaps under DRX for 2 Rx UE | Test in A.16.6.1.8 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-226156 R5-232171 R5-232172 R5-232461 R5-233999 R5-234924 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
199 | Y | 38.533 | 16.6.1.9 | NR SA FR1 Event triggered reporting tests without gap under non-DRX with SSB index reading for 1 Rx UE | Test in A.16.6.1.9 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230485 R5-232462 R5-234413 | RAN4 Phase 2 | 0.5 | 100% (+10%) | 100% (+10%) |  | 100%
200 | Y | 38.533 | 16.6.1.10 | NR SA FR1 Event triggered reporting tests without gap under non-DRX with SSB index reading for 2 Rx UE | Test in A.16.6.1.10 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230486 R5-232462 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
201 | Y | 38.533 | 16.6.1.11 | NR SA FR1 Event triggered reporting tests with per-UE gaps under non-DRX with SSB index reading for 1 Rx UE | Test in A.16.6.1.11 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-226157 R5-232461 R5-235695 R5-234414 R5-234924 | RAN4 Phase 2 | 0.5 | 100% (+10%) | 100% (+10%) |  | 100%
202 | Y | 38.533 | 16.6.1.12 | NR SA FR1 Event triggered reporting tests with per-UE gaps under non-DRX with SSB index reading for 2 Rx UE | Test in A.16.6.1.12 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-226158 R5-232171 R5-232172 R5-232461 R5-234924 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
203 |  |  | 16.6.2 | Inter-frequency Measurements for RedCap | New sub-clause header
204 | Y | 38.533 | 16.6.2.1 | NR SA FR1-FR1 Event triggered reporting tests for FR1 without SSB time index detection when DRX is used for 1 Rx UE | Test in A.16.6.2.1 in TS 38.133 | Ericsson | RAN5#101 (Nov-23) | R5-234984r2 | RAN4 Phase 2 Editor’s note: This test case is incomplete in following aspects: - TT analysis is still missing. - Minimum conformance requirements contains [ ] - Applicability is missing in 38.522 | 0.5 | 90% (+90%) | 90% (+90%) |  | 90%
205 | Y | 38.533 | 16.6.2.2 | NR SA FR1-FR1 Event triggered reporting tests for FR1 without SSB time index detection when DRX is used for 2 Rx UE | Test in A.16.6.2.2 in TS 38.133 | Ericsson | RAN5#101 (Nov-23) | R5-234985r1 | RAN4 Phase 2 Editor’s note: This test case is incomplete in following aspects: - TT analysis is still missing. - Minimum conformance requirements contains [ ] - Applicability is missing in 38.522 | 0.5 | 90% (+90%) | 90% (+90%) |  | 90%
206 | Y | 38.533 | 16.6.2.3 | NR SA FR1-FR1 Event triggered reporting tests for FR1 without SSB time index detection when DRX is used for 1 Rx UE | Test in A.16.6.2.3 in TS 38.133 | Ericsson | RAN5#101 (Nov-23) | R5-234986r1 | RAN4 Phase 2 Editor’s note: This test case is incomplete in following aspects: - TT analysis is still missing. - Minimum conformance requirements contains [ ] - Applicability is missing in 38.522 | 0.5 | 90% (+90%) | 90% (+90%) |  | 90%
207 | Y | 38.533 | 16.6.2.4 | NR SA FR1-FR1 Event triggered reporting tests for FR1 without SSB time index detection when DRX is used for 2 Rx UE | Test in A.16.6.2.4 in TS 38.133 | Ericsson | RAN5#101 (Nov-23) | R5-234987r1 | RAN4 Phase 2 Editor’s note: This test case is incomplete in following aspects: - TT analysis is still missing. - Minimum conformance requirements contains [ ] - Applicability is missing in 38.522 | 0.5 | 90% (+90%) | 90% (+90%) |  | 90%
208 | Y | 38.533 | 16.6.2.5 | NR SA FR1-FR1 Event triggered reporting tests for FR1 with SSB time index detection when DRX is not used for 1 Rx UE | Test in A.16.6.2.5 in TS 38.133 | Ericsson | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
209 | Y | 38.533 | 16.6.2.6 | NR SA FR1-FR1 Event triggered reporting tests for FR1 with SSB time index detection when DRX is not used for 2 Rx UE | Test in A.16.6.2.6 in TS 38.133 | Ericsson | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
210 | Y | 38.533 | 16.6.2.7 | NR SA FR1-FR1 Event triggered reporting tests for FR1 with SSB time index detection when DRX is used for 1 Rx UE | Test in A.16.6.2.7 in TS 38.133 | Ericsson | RAN5#101 (Nov-23) | R5-234990r1 | RAN4 Phase 2 Editor’s note: This test case is incomplete in following aspects: - TT analysis is still missing. - Minimum conformance requirements contains [ ] - Applicability is missing in 38.522 | 0.5 | 90% (+90%) | 90% (+90%) |  | 90%
211 | Y | 38.533 | 16.6.2.8 | NR SA FR1-FR1 Event triggered reporting tests for FR1 with SSB time index detection when DRX is used for 2 Rx UE | Test in A.16.6.2.8 in TS 38.133 | Ericsson | RAN5#101 (Nov-23) | R5-234991r1 | RAN4 Phase 2 Editor’s note: This test case is incomplete in following aspects: - TT analysis is still missing. - Minimum conformance requirements contains [ ] - Applicability is missing in 38.522 | 0.5 | 90% (+90%) | 90% (+90%) |  | 90%
212 | Y | 38.533 | 16.6.2.9 | NR SA FR1-FR1 Event triggered reporting tests with additional mandatory gap pattern for 1 Rx UE | Test in A.16.6.2.9 in TS 38.133 | Ericsson | RAN5#101 (Nov-23) | R5-234992r1 | RAN4 Phase 2 Editor’s note: This test case is incomplete in following aspects: - TT analysis is still missing. - Minimum conformance requirements contains [ ] - Applicability is missing in 38.522 | 0.5 | 90% (+90%) | 90% (+90%) |  | 90%
213 | Y | 38.533 | 16.6.2.10 | NR SA FR1-FR1 Event triggered reporting tests with additional mandatory gap pattern for 2 Rx UE | Test in A.16.6.2.10 in TS 38.133 | Ericsson | RAN5#101 (Nov-23) | R5-234993r1 | RAN4 Phase 2 Editor’s note: This test case is incomplete in following aspects: - TT analysis is still missing. - Minimum conformance requirements contains [ ] - Applicability is missing in 38.522 | 0.5 | 90% (+90%) | 90% (+90%) |  | 90%
214 | Y | 38.533 | 16.6.2.11 | NR SA FR1-FR1 Event triggered reporting tests for FR1 when DRX is used for 1 Rx UE | Test in A.16.6.2.11 in TS 38.133 | Ericsson | RAN5#101 (Nov-23) | R5-234994r1 | RAN4 Phase 2 Editor’s note: This test case is incomplete in following aspects: - TT analysis is still missing. - Minimum conformance requirements contains [ ] - Applicability is missing in 38.522 | 0.5 | 90% (+90%) | 90% (+90%) |  | 90%
215 | Y | 38.533 | 16.6.2.12 | NR SA FR1-FR1 Event triggered reporting tests for FR1 when DRX is used for 2 Rx UE | Test in A.16.6.2.12 in TS 38.133 | Ericsson | RAN5#101 (Nov-23) | R5-234995r1 | RAN4 Phase 2 Editor’s note: This test case is incomplete in following aspects: - TT analysis is still missing. - Minimum conformance requirements contains [ ] - Applicability is missing in 38.522 | 0.5 | 90% (+90%) | 90% (+90%) |  | 90%
216 |  |  | 16.6.3 | Inter-RAT Measurements for RedCap | New sub-clause header
217 | Y | 38.533 | 16.6.3.1 | NR - E-UTRA event-triggered reporting in non-DRX in FR1 for 1 Rx UE | Test in A.16.6.3.1 in TS 38.133 | Ericsson | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
218 | Y | 38.533 | 16.6.3.2 | NR - E-UTRA event-triggered reporting in non-DRX in FR1 for 2 Rx UE | Test in A.16.6.3.2 in TS 38.133 | Ericsson | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
219 | Y | 38.533 | 16.6.3.3 | NR - E-UTRA event-triggered reporting in DRX in FR1 for 1 Rx UE | Test in A.16.6.3.3 in TS 38.133 | Ericsson | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
220 | Y | 38.533 | 16.6.3.4 | NR - E-UTRA event-triggered reporting in DRX in FR1 for 2 Rx UE | Test in A.16.6.3.4 in TS 38.133 | Ericsson | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
221 |  | 38.533 | 16.6.4 | L1-RSRP measurement for beam reporting for RedCap | New sub-clause header |  |  | R5-226159 |  | 0
222 | Y | 38.533 | 16.6.4.1 | NR SA FR1 SSB based L1-RSRP measurement when DRX is not used for 1 Rx UE | Test in A.16.6.4.1 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-226160 R5-234415 | RAN4 Phase 2 | 0.5 | 100% (+10%) | 100% (+10%) |  | 100%
223 | Y | 38.533 | 16.6.4.2 | NR SA FR1 SSB based L1-RSRP measurement when DRX is not used for 2 Rx UE | Test in A.16.6.4.2 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-228025 R5-235698 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
224 | Y | 38.533 | 16.6.4.3 | NR SA FR1 SSB based L1-RSRP measurement when DRX is used for 1 Rx UE | Test in A.16.6.4.3 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-226162 R5-234416 | RAN4 Phase 2 | 0.5 | 100% (+10%) | 100% (+10%) |  | 100%
225 | Y | 38.533 | 16.6.4.4 | NR SA FR1 SSB based L1-RSRP measurement when DRX is used for 2 Rx UE | Test in A.16.6.4.4 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-228026 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
226 | Y | 38.533 | 16.6.4.5 | NR SA FR1 CSI-RS based L1-RSRP measurement when DRX is not used for 1 Rx UE | Test in A.16.6.4.5 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230487 R5-234417 | RAN4 Phase 2 | 0.5 | 100% (+10%) | 100% (+10%) |  | 100%
227 | Y | 38.533 | 16.6.4.6 | NR SA FR1 CSI-RS based L1-RSRP measurement when DRX is not used for 2 Rx UE | Test in A.16.6.4.6 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230488 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
228 | Y | 38.533 | 16.6.4.7 | NR SA FR1 CSI-RS based L1-RSRP measurement when DRX is used for 1 Rx UE | Test in A.16.6.4.7 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230489 R5-234418 | RAN4 Phase 2 | 0.5 | 100% (+10%) | 100% (+10%) |  | 100%
229 | Y | 38.533 | 16.6.4.8 | NR SA FR1 CSI-RS based L1-RSRP measurement when DRX is used for 2 Rx UE | Test in A.16.6.4.8 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230490 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
230 |  | 38.533 | 16.6.7 | NR measurements with autonomous gaps | New sub-clause header |  |  |  |  | 0.5 | 0% | 0% |  | 0%
231 | Y | 38.533 | 16.6.7.1 | NR SA FR1 intra-frequency CGI identification of NR neighbor cell in FR1 for 1 Rx UE | Test in A.16.6.7.1 in TS 38.133 | Nokia | RAN5#101 (Nov-23) | R5-234356 | RAN4 Phase 2 TT analysis is still missing Test procedure and message contents are still missing | 0.5 | 50% (+50%) | 50% (+50%) |  | 50%
232 | Y | 38.533 | 16.6.7.2 | NR SA FR1 intra-frequency CGI identification of NR neighbor cell in FR1 for 2 Rx UE | Test in A.16.6.7.2 in TS 38.133 | Nokia | RAN5#101 (Nov-23) | R5-234357 | RAN4 Phase 2 TT analysis is still missing Test procedure and message contents are still missing | 0.5 | 50% (+50%) | 50% (+50%) |  | 50%
233 | Y | 38.533 | 16.6.7.3 | NR SA FR1 Identification of a new CGI of inter-RAT E-UTRA cell using autonomous gaps in NR SA for 1 Rx UE | Test in A.16.6.7.3 in TS 38.133 | Huawei | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
234 | Y | 38.533 | 16.6.7.4 | NR SA FR1 Identification of a new CGI of inter-RAT E-UTRA cell using autonomous gaps in NR SA for 2 Rx UE | Test in A.16.6.7.4 in TS 38.133 | Huawei | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
235 |  |  | 16.7 | Measurement Performance requirements for RedCap | New sub-clause header
236 |  |  | 16.7.1 | SS-RSRP | New sub-clause header
237 | Y | 38.533 | 16.7.1.1_1 | NR SA FR1 Intra-frequency case absolute measurement accuracy with FR1 serving cell and FR1 target cell for 1 Rx UE | Test in A.16.7.1.1 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
238 | Y | 38.533 | 16.7.1.1_2 | NR SA FR1 Intra-frequency case relative measurement accuracy with FR1 serving cell and FR1 target cell for 1 Rx UE | Test in A.16.7.1.1 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
239 | Y | 38.533 | 16.7.1.2_1 | NR SA FR1 Intra-frequency absolute case measurement accuracy with FR1 serving cell and FR1 target cell for 2Rx UE | Test in A.16.7.1.2 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
240 | Y | 38.533 | 16.7.1.2_2 | NR SA FR1 Intra-frequency absolute case measurement accuracy with FR1 serving cell and FR1 target cell for 2Rx UE | Test in A.16.7.1.2 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
241 | Y | 38.533 | 16.7.1.3_1 | NR SA FR1-FR1 Inter-frequency absolute measurement accuracy with FR1 serving cell and FR1 target cell for 1 Rx UE | Test in A.16.7.1.3 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
242 | Y | 38.533 | 16.7.1.3_2 | NR SA FR1-FR1 Inter-frequency relative measurement accuracy with FR1 serving cell and FR1 target cell for 1 Rx UE | Test in A.16.7.1.3 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
243 | Y | 38.533 | 16.7.1.4_1 | NR SA FR1-FR1 Inter-frequency absolute measurement accuracy with FR1 serving cell and FR1 target cell for 2 Rx UE | Test in A.16.7.1.4 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
244 | Y | 38.533 | 16.7.1.4_2 | NR SA FR1-FR1 Inter-frequency relative measurement accuracy with FR1 serving cell and FR1 target cell for 2 Rx UE | Test in A.16.7.1.4 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
245 |  |  | 16.7.2 | SS-RSRQ | New sub-clause header
246 | Y | 38.533 | 16.7.2.1 | NR SA FR1 Intra-frequency measurement accuracy with FR1 serving cell and FR1 target cell for 1 Rx UE | Test in A.16.7.2.1 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
247 | Y | 38.533 | 16.7.2.2 | NR SA FR1 Intra-frequency measurement accuracy with FR1 serving cell and FR1 target cell for 2 Rx UE | Test in A.16.7.2.2 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
248 | Y | 38.533 | 16.7.2.3_1 | NR SA FR1-FR1 Inter-frequency absolute measurement accuracy with FR1 serving cell and FR1 target cell for 1 Rx UE | Test in A.16.7.2.3 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
249 | Y | 38.533 | 16.7.2.3_2 | NR SA FR1-FR1 Inter-frequency relative measurement accuracy with FR1 serving cell and FR1 target cell for 1 Rx UE | Test in A.16.7.2.3 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
250 | Y | 38.533 | 16.7.2.4_1 | NR SA FR1-FR1 Inter-frequency absolute measurement accuracy with FR1 serving cell and FR1 target cell for 2 Rx UE | Test in A.16.7.2.4 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
251 | Y | 38.533 | 16.7.2.4_2 | NR SA FR1-FR1 Inter-frequency relative measurement accuracy with FR1 serving cell and FR1 target cell for 2 Rx UE | Test in A.16.7.2.4 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
252 |  |  | 16.7.3 | SS-SINR | New sub-clause header
253 | Y | 38.533 | 16.7.3.1 | NR SA FR1 Intra-frequency measurement accuracy with FR1 serving cell and FR1 target cell for 1 Rx UE | Test in A.16.7.3.1 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
254 | Y | 38.533 | 16.7.3.2 | NR SA FR1 Intra-frequency measurement accuracy with FR1 serving cell and FR1 target cell for 2 Rx UE | Test in A.16.7.3.2 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
255 | Y | 38.533 | 16.7.3.3_1 | NR SA FR1-FR1 Inter-frequency absloute measurement accuracy with FR1 serving cell and FR1 target cell for 1 Rx UE | Test in A.16.7.3.3 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
256 | Y | 38.533 | 16.7.3.3_2 | NR SA FR1-FR1 Inter-frequency relative measurement accuracy with FR1 serving cell and FR1 target cell for 1 Rx UE | Test in A.16.7.3.3 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
257 | Y | 38.533 | 16.7.3.4_1 | NR SA FR1-FR1 Inter-frequency absolute measurement accuracy with FR1 serving cell and FR1 target cell for 2 Rx UE | Test in A.16.7.3.4 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
258 | Y | 38.533 | 16.7.3.4_2 | NR SA FR1-FR1 Inter-frequency relative measurement accuracy with FR1 serving cell and FR1 target cell for 2 Rx UE | Test in A.16.7.3.4 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
259 |  |  | 16.7.4 | L1-RSRP measurement for beam reporting | New sub-clause header
260 | Y | 38.533 | 16.7.4.1_1 | NR SA FR1 SSB based L1-RSRP absolute measurement for 1 Rx UE | Test in A.16.7.4.1 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
261 | Y | 38.533 | 16.7.4.1_2 | NR SA FR1 SSB based L1-RSRP relative measurement for 1 Rx UE | Test in A.16.7.4.1 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
262 | Y | 38.533 | 16.7.4.2_1 | NR SA FR1 SSB based L1-RSRP absolute measurement for 2 Rx UE | Test in A.16.7.4.2 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
263 | Y | 38.533 | 16.7.4.2_2 | NR SA FR1 SSB based L1-RSRP relative measurement for 2 Rx UE | Test in A.16.7.4.2 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
264 | Y | 38.533 | 16.7.4.3_1 | NR SA FR1 CSI-RS based L1-RSRP absolute measurement on resource set with repetition off for 1 Rx UE | Test in A.16.7.4.3 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
265 | Y | 38.533 | 16.7.4.3_2 | NR SA FR1 CSI-RS based L1-RSRP relative measurement on resource set with repetition off for 1 Rx UE | Test in A.16.7.4.3 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
266 | Y | 38.533 | 16.7.4.4_1 | NR SA FR1 CSI-RS based L1-RSRP absolute measurement on resource set with repetition off for 2 Rx UE | Test in A.16.7.4.4 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
267 | Y | 38.533 | 16.7.4.4_2 | NR SA FR1 CSI-RS based L1-RSRP relative measurement on resource set with repetition off for 2 Rx UE | Test in A.16.7.4.4 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
268 |  |  | 16.7.5 | E-UTRAN RSRP | New sub-clause header
269 | Y | 38.533 | 16.7.5.1 | NR SA FR1 - E-UTRA Measurement accuracy with FR1 serving cell for 1 Rx UE | Test in A.16.7.5.1 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
270 | Y | 38.533 | 16.7.5.2 | NR SA FR1 - E-UTRA Measurement accuracy with FR1 serving cell for 2 Rx UE | Test in A.16.7.5.2 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
271 |  |  | 16.7.6 | E-UTRAN RSRQ | New sub-clause header | Rohde & Schwarz
272 | Y | 38.533 | 16.7.6.1 | NR SA FR1 - E-UTRA Measurement accuracy with FR1 serving cell for 1 Rx UE | Test in A.16.7.6.1 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
273 | Y | 38.533 | 16.7.6.2 | NR SA FR1 - E-UTRA Measurement accuracy with FR1 serving cell for 2 Rx UE | Test in A.16.7.6.2 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
274 |  |  | 16.7.7 | E-UTRAN RS-SINR | New sub-clause header | Rohde & Schwarz
275 | Y | 38.533 | 16.7.7.1 | NR SA FR1 - E-UTRA Measurement accuracy with FR1 serving cell for 1 Rx UE | Test in A.16.7.7.1 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
276 | Y | 38.533 | 16.7.7.2 | NR SA FR1 - E-UTRA Measurement accuracy with FR1 serving cell for 2 Rx UE | Test in A.16.7.7.2 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  | 0%
277 |  |  | 17 | NR standalone tests with one or more NR cells in FR2 for RedCap | New clause header | [9 empty] | 0%
278 |  |  | 17.1 | RRC_IDLE state mobility for RedCap | New sub-clause header | [9 empty] | 0%
279 |  |  | 17.1.1 | Cell re-selection to NR for RedCap | New sub-clause header | [9 empty] | 0%
280 | Y | 38.533 | 17.1.1.1 | NR SA FR2 Cell reselection to FR2 intra-frequency NR case for 2 Rx | Test in A.17.1.1.1 in TS 38.133 | Ericsson | RAN5#99 (May-23) | R5-231130 R5-232923 R5-235696 | RAN4 Phase 1 TT analysis is still missing | 0.5 | 90% | 90% |  |  | 90%
281 | Y | 38.533 | 17.1.1.2 | NR SA FR2-FR2 Cell reselection to FR2 inter-frequency NR case | Test in A.17.1.1.2 in TS 38.133 | Ericsson | RAN5#99 (May-23) | R5-231131 R5-232924 R5-235696 | RAN4 Phase 1 TT analysis is still missing | 0.5 | 90% | 90% |  |  | 90%
282 | Y | 38.533 | 17.1.1.3 | NR SA FR2 Cell reselection to FR2 intra-frequency NR case for UE fulfilling stationary relaxed measurement criterion for 2 Rx UE | Test in A.17.1.1.3 in TS 38.133 | Ericsson | RAN5#99 (May-23) | R5-231132 R5-232925 | RAN4 Phase 1 TT analysis is still missing | 0.5 | 90% | 90% |  |  | 90%
283 | Y | 38.533 | 17.1.1.4 | NR SA FR2-FR2 Cell reselection to FR2 inter-frequency NR case for UE fulfilling stationary mobility relaxed measurement criterion for 2 Rx UE | Test in A.17.1.1.4 in TS 38.133 | Ericsson | RAN5#99 (May-23) | R5-231133 R5-232926 | RAN4 Phase 1 TT analysis is still missing | 0.5 | 90% | 90% |  |  | 90%
284 |  |  | 17.2 | RRC_INACTIVE state mobility for RedCap | New sub-clause header
285 |  |  | 17.2.1 | Configured Grant based Small Data Transmissions for RedCap | New sub-clause header
286 | Y | 38.533 | 17.2.1.1 | NR SA FR2 TA validation for CG-SDT for 2 Rx | Test in A.17.2.1.1 in TS 38.133 | Huawei | RAN5#99 (May-23) |  |  | 0.5 | 0% | 0% |  |  | 0%
287 |  |  | 17.3 | RRC_CONNECTED state mobility for RedCap | New sub-clause header
288 |  |  | 17.3.1 | Handover for RedCap | New sub-clause header
289 | Y | 38.533 | 17.3.1.1 | NR SA FR2 Intra-frequency handover from FR2 to FR2; unknown target cell for 2 Rx | Test in A.17.3.1.1 in TS 38.133 | Huawei | RAN5#99 (May-23) |  | RAN4 Phase 1 | 0.5 | 0% | 0% |  |  | 0%
290 | Y | 38.533 | 17.3.1.2 | NR SA FR2-FR2 Inter-frequency handover from FR2 to FR2; unknown target cell for 2 Rx | Test in A.17.3.1.2 in TS 38.133 | Huawei | RAN5#99 (May-23) |  | RAN4 Phase 1 | 0.5 | 0% | 0% |  |  | 0%
291 |  |  | 17.3.2 | RRC Connection Mobility Control for RedCap | New sub-clause header |  |  | R5-226164
292 |  |  | 17.3.2.1 | RRC Re-establishment for RedCap | New sub-clause header |  |  | R5-226164
293 | Y | 38.533 | 17.3.2.1.1 | NR SA FR2 Intra-frequency RRC Re-establishment in FR2 | Test in A.17.3.2.1.1 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-226165 | RAN4 Phase 1 | 0.5 | 100% | 100% |  |  | 100%
294 | Y | 38.533 | 17.3.2.1.2 | NR SA FR2-FR2 Inter-frequency RRC Re-establishment in FR2 | Test in A.17.3.2.1.2 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-226166 | RAN4 Phase 1 | 0.5 | 100% | 100% |  |  | 100%
295 | Y | 38.533 | 17.3.2.1.3 | NR SA FR2 Intra-frequency RRC Re-establishment in FR2 without serving cell timing | Test in A.17.3.2.1.3 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-226167 | RAN4 Phase 1 TT analysis is still missing | 0.5 | 90% | 90% |  |  | 90%
296 |  |  | 17.3.2.2 | Random Access for RedCap | New sub-clause header |  |  |  |  | 0.5
297 | Y | 38.533 | 17.3.2.2.1 | NR SA FR2 4-step RA type contention based random access test in FR2 for NR Standalone | Test in A.17.3.2.2.1 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-230491 | RAN4 Phase 1 TT analysis is still missing | 0.5 | 90% | 90% |  |  | 90%
298 | Y | 38.533 | 17.3.2.2.2 | NR SA FR2 4-step RA type non-contention based random access test in FR2 for NR Standalone | Test in A.17.3.2.2.2 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-230492 | RAN4 Phase 1 TT analysis is still missing | 0.5 | 90% | 90% |  |  | 90%
299 | Y | 38.533 | 17.3.2.2.3 | NR SA FR2 2-step RA type contention based random access test in FR2 for NR Standalone | Test in A.17.3.2.2.3 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-230493 | RAN4 Phase 1 TT analysis is still missing | 0.5 | 90% | 90% |  |  | 90%
300 | Y | 38.533 | 17.3.2.2.4 | NR SA FR2 2-step RA type non-contention based random access test in FR2 for NR Standalone | Test in A.17.3.2.2.4 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-230494 | RAN4 Phase 1 TT analysis is still missing | 0.5 | 90% | 90% |  |  | 90%
301 |  |  | 17.3.2.3 | SA: RRC Connection Release with Redirection for RedCap | New sub-clause header
302 | Y | 38.533 | 17.3.2.3.1 | NR SA FR2-FR2 Redirection from NR in FR2 to NR in FR2 | Test in A.17.3.2.3.1 in TS 38.133 | Huawei | RAN5#99 (May-23) |  | RAN4 Phase 1 | 0.5 | 0% | 0% |  |  | 0%
303 |  |  | 17.4 | Timing for RedCap | New sub-clause header
304 |  |  | 17.4.1 | UE transmit timing for RedCap | New sub-clause header
305 | Y | 38.533 | 17.4.1.1 | NR SA FR2 NR UE Transmit Timing Test for FR2 | Test in A.17.4.1.1 in TS 38.133 | Huawei | TBD |  |  | 0.5 | 0% | 0% |  |  | 0%
306 |  |  | 17.4.2 | UE timer accuracy for RedCap | New sub-clause header
307 |  |  | 17.4.3 | Timing advance for RedCap | New sub-clause header
308 | Y | 38.533 | 17.4.3.1 | NR SA FR2 SA FR2 timing advance adjustment accuracy | Test in A.17.4.3.1 in TS 38.133 | Huawei | RAN5#99 (May-23) |  | RAN4 Phase 1 | 0.5 | 0% | 0% |  |  | 0%
309 |  |  | 17.5 | Signaling characteristics for RedCap | New sub-clause header
310 |  |  | 17.5.1 | Radio link Monitoring for RedCap | New sub-clause header |  |  | R5-226168
311 | Y | 38.533 | 17.5.1.1 | NR SA FR2 Radio Link Monitoring Out-of-sync Test for FR2 PCell configured with SSB-based RLM RS in non-DRX mode | Test in A.17.5.1.1 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-226169 | RAN4 Phase 2 | 0.5 | 100% | 100% |  |  | 100%
312 | Y | 38.533 | 17.5.1.2 | NR SA FR2 Radio Link Monitoring In-sync Test for FR2 PCell configured with SSB-based RLM RS in non-DRX mode | Test in A.17.5.1.2 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-226170 R5-232463 R5-234386 | RAN4 Phase 2 | 0.5 | 100% | 100% |  |  | 100%
313 | Y | 38.533 | 17.5.1.3 | NR SA FR2 Radio Link Monitoring Out-of-sync Test for FR2 PCell configured with SSB-based RLM RS in DRX mode | Test in A.17.5.1.3 in TS 38.133 | Qualcomm | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  |  | 0%
314 | Y | 38.533 | 17.5.1.4 | NR SA FR2 Radio Link Monitoring In-sync Test for FR2 PCell configured with SSB-based RLM RS in DRX mode | Test in A.17.5.1.4 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-226171 | RAN4 Phase 2 | 0.5 | 100% | 100% |  |  | 100%
315 | Y | 38.533 | 17.5.1.5 | NR SA FR2 Radio Link Monitoring Out-of-sync Test for FR2 PCell configured with CSI-RS-based RLM in non-DRX mode | Test in A.17.5.1.5 in TS 38.133 | Huawei | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  |  | 0%
316 | Y | 38.533 | 17.5.1.6 | NR SA FR2 Radio Link Monitoring In-sync Test for FR2 PCell configured with CSI-RS-based RLM in non-DRX mode | Test in A.17.5.1.6 in TS 38.133 | Huawei | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  |  | 0%
317 | Y | 38.533 | 17.5.1.7 | NR SA FR2 Radio Link Monitoring Out-of-sync Test for FR2 PCell configured with CSI-RS-based RLM in DRX mode | Test in A.17.5.1.7 in TS 38.133 | Huawei | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  |  | 0%
318 | Y | 38.533 | 17.5.1.8 | NR SA FR2 Radio Link Monitoring In-sync Test for FR2 PCell configured with CSI-RS-based RLM in DRX mode | Test in A.17.5.1.8 in TS 38.133 | Huawei | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  |  | 0%
319 | Y | 38.533 | 17.5.1.9 | NR SA FR2 UE Radio Link Monitoring Scheduling Restrictions on FR2 | Test in A.17.5.1.9 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230495 | RAN4 Phase 2 TT analysis is still missing | 0.5 | 90% | 90% |  |  | 90%
320 |  |  | 17.5.2 | Beam Failure Detection and Link recovery procedures for RedCap | New sub-clause header
321 | Y | 38.533 | 17.5.2.1 | NR SA FR2 Beam Failure Detection and Link Recovery Test for FR2 PCell configured with SSB-based BFD and LR in non-DRX mode | Test in A.17.5.2.1 in TS 38.133 | Qualcomm | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  |  | 0%
322 | Y | 38.533 | 17.5.2.2 | NR SA FR2 Beam Failure Detection and Link Recovery Test for FR2 PCell configured with SSB-based BFD and LR in DRX mode | Test in A.17.5.2.2 in TS 38.133 | Qualcomm | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  |  | 0%
323 | Y | 38.533 | 17.5.2.3 | NR SA FR2 Beam Failure Detection and Link Recovery Test for FR2 PCell configured with CSI-RS-based BFD and LR in non-DRX mode | Test in A.17.5.2.3 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-231721 R5-233654 | RAN4 Phase 2 | 0.5 | 100% | 100% |  |  | 100%
324 | Y | 38.533 | 17.5.2.4 | NR SA FR2 Beam Failure Detection and Link Recovery Test for FR2 PCell configured with CSI-RS-based BFD and LR in DRX mode | Test in A.17.5.2.4 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-231722 R5-233655 | RAN4 Phase 2 | 0.5 | 100% | 100% |  |  | 100%
325 | Y | 38.533 | 17.5.2.5 | NR SA FR2 Scheduling availability restriction during Beam Failure Detection and Link Recovery for FR2 PCell configured with SSB-based BFD and LR in non-DRX mode | Test in A.17.5.2.5 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-231723 R5-233656 | RAN4 Phase 2 | 0.5 | 100% | 100% |  |  | 100%
326 |  |  | 17.5.3 | Active BWP switch for RedCap | New sub-clause header
327 |  |  | 17.5.3.1 | DCI-based and Timer-based Active BWP Switch | New sub-clause header
328 | Y | 38.533 | 17.5.3.1.1 | NR SA FR2 NR SA FR2 DL active BWP switch with non-DRX in SA | Test in A.17.5.3.1.1 in TS 38.133 | Huawei | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  |  | 0%
329 |  |  | 17.5.3.2 | NR SA FR2 DL active BWP switch with non-DRX in SA | New sub-clause header
330 | Y | 38.533 | 17.5.3.2.1 | NR SA FR2 NR SA FR2 DL active BWP switch of PCell with non-DRX in SA | Test in A.17.5.3.2.1 in TS 38.133 | Huawei | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  |  | 0%
331 |  |  | 17.5.4 | Active TCI state switch delay for RedCap | New sub-clause header
332 |  |  | 17.5.4.1 | MAC-CE based active TCI state switch for RedCap | New sub-clause header
333 | Y | 38.533 | 17.5.4.1.1 | NR SA FR2 NR PCell FR2 active TCI state switch for a known TCI state | Test in A.17.5.4.1.1 in TS 38.133 | Huawei | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  |  | 0%
334 |  |  | 17.5.4.2 | RRC based active TCI state switch for RedCap | New sub-clause header
335 | Y | 38.533 | 17.5.4.2.1 | NR SA FR2 NR PCell FR2 active TCI state switch for a known TCI state | Test in A.17.5.4.2.1 in TS 38.133 | Huawei | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  |  | 0%
336 |  |  | 17.5.5 | Uplink spatial relation switch delay | New sub-clause header
337 |  |  | 17.5.5.1 | MAC-CE based Spatial Relation switch | New sub-clause header
338 | Y | 38.533 | 17.5.5.1.1 | NR SA FR2 NR PCell FR2 spatial relation associated with known DL-RS | Test in A.17.5.5.1.1 in TS 38.133 | Huawei | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  |  | 0%
339 |  |  | 17.5.5.2 | RRC based spatial relation switch for RedCap | New sub-clause header
340 | Y | 38.533 | 17.5.5.2.1 | NR SA FR2 NR PCell FR2 spatial relation switch associated with a known DL-RS | Test in A.17.5.5.2.1 in TS 38.133 | Huawei | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  |  | 0%
341 |  |  | 17.5.6 | UE specific CBW change for RedCap | New sub-clause header
342 | Y | 38.533 | 17.5.6.1 | NR SA FR2 NR SA FR2 UE specific CBW change of PCell with non-DRX in SA | Test in A.17.5.6.1 in TS 38.133 | Huawei | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  |  | 0%
343 |  |  | 17.6 | Measurement procedure for RedCap | New sub-clause header |  |  | R5-226172
344 |  |  | 17.6.1 | Intra-frequency Measurements for RedCap | New sub-clause header |  |  | R5-226172
345 | Y | 38.533 | 17.6.1.1 | NR SA FR2 Event triggered reporting test without gap under non-DRX | Test in A.17.6.1.1 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-226173 R5-232467 | RAN4 Phase 2 | 0.5 | 100% | 100% |  |  | 100%
346 | Y | 38.533 | 17.6.1.2 | NR SA FR2 Event triggered reporting test without gap under DRX | Test in A.17.6.1.2 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-233657 | RAN4 Phase 2 | 0.5 | 100% | 100% |  |  | 100%
347 | Y | 38.533 | 17.6.1.3 | NR SA FR2 Event triggered reporting test with per-UE gaps under non-DRX | Test in A.17.6.1.3 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230499 R5-232469 | RAN4 Phase 2 | 0.5 | 100% | 100% |  |  | 100%
348 | Y | 38.533 | 17.6.1.4 | NR SA FR2 Event triggered reporting test with per-UE gaps under DRX | Test in A.17.6.1.4 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230500 R5-232469 | RAN4 Phase 2 | 0.5 | 100% | 100% |  |  | 100%
349 |  |  | 17.6.2 | Inter-frequency Measurements for RedCap | New sub-clause header
350 | Y | 38.533 | 17.6.2.1 | NR SA FR2-FR2 Event triggered reporting tests For FR2 without SSB time index detection when DRX is not used (PCell in FR2) | Test in A.17.6.2.1 in TS 38.133 | Ericsson | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  |  | 0%
351 | Y | 38.533 | 17.6.2.2 | NR SA FR2-FR2 Event triggered reporting tests For FR2 without SSB time index detection when DRX is used (PCell in FR2) | Test in A.17.6.2.2 in TS 38.133 | Ericsson | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  |  | 0%
352 | Y | 38.533 | 17.6.2.3 | NR SA FR2-FR2 Event triggered reporting tests For FR2 with SSB time index detection when DRX is not used (PCell in FR2) | Test in A.17.6.2.3 in TS 38.133 | Ericsson | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  |  | 0%
353 | Y | 38.533 | 17.6.2.4 | NR SA FR2-FR2 Event triggered reporting tests For FR2 with SSB time index detection when DRX is used (PCell in FR2) | Test in A.17.6.2.4 in TS 38.133 | Ericsson | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  |  | 0%
354 |  |  | 17.6.3 | L1-RSRP measurement for beam reporting for RedCap | New sub-clause header
355 | Y | 38.533 | 17.6.3.1 | NR SA FR2 SSB based L1-RSRP measurement when DRX is not used | Test in A.17.6.3.1 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-231724 R5-233647 | RAN4 Phase 2 | 0.5 | 100% | 100% |  |  | 100%
356 | Y | 38.533 | 17.6.3.2 | NR SA FR2 SSB based L1-RSRP measurement when DRX is used | Test in A.17.6.3.2 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230502 R5-232472 | RAN4 Phase 2 | 0.5 | 100% | 100% |  |  | 100%
357 | Y | 38.533 | 17.6.3.3 | NR SA FR2 CSI-RS based L1-RSRP measurement when DRX is not used | Test in A.17.6.3.3 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230503 R5-232473 | RAN4 Phase 2 | 0.5 | 100% | 100% |  |  | 100%
358 | Y | 38.533 | 17.6.3.4 | NR SA FR2 CSI-RS based L1-RSRP measurement when DRX is used | Test in A.17.6.3.4 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230504 R5-232474 | RAN4 Phase 2 | 0.5 | 100% | 100% |  |  | 100%
359 |  |  | 17.6.4 | NR Measurements with autonomous gaps for RedCap | New sub-clause header
360 | Y | 38.533 | 17.6.4.1 | NR SA FR2 Interfrequency CGI reporting in autonomous gaps test (PCell in FR2) | Test in A.17.6.4.1 in TS 38.133 | Huawei | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  |  | 0%
361 |  |  | 17.7 | Measurement Performance requirements for RedCap | New sub-clause header
362 |  |  | 17.7.1 | SS-RSRP | New sub-clause header
363 | Y | 38.533 | 17.7.1.1 | NR SA FR2 Intra-frequency case measurement accuracy with FR2 serving cell and FR2 target cell | Test in A.17.7.1.1 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  |  | 0%
364 | Y | 38.533 | 17.7.1.2 | NR SA FR2-FR2 Inter-frequency case measurement accuracy with FR2 serving cell and FR2 target cell | Test in A.17.7.1.2 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  |  | 0%
365 |  |  | 17.7.2 | SS-RSRQ | New sub-clause header
366 | Y | 38.533 | 17.7.2.1 | NR SA FR2 Intra-frequency measurement accuracy with FR2 serving cell and FR2 target cell | Test in A.17.7.2.1 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  |  | 0%
367 | Y | 38.533 | 17.7.2.2 | NR SA FR2-FR2 Inter-frequency measurement accuracy with FR2 serving cell and FR2 TDD target cell | Test in A.17.7.2.2 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  |  | 0%
368 | Y | 38.533 | 17.7.2.3 | NR SA FR2-FR2 Inter-frequency measurement accuracy with FR2 serving cell and FR2 TDD target cell | Test in A.17.7.2.3 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  |  | 0%
369 |  |  | 17.7.3 | L1-RSRP measurement for beam reporting for RedCap | New sub-clause header
370 | Y | 38.533 | 17.7.3.1 | NR SA FR2 SSB based L1-RSRP measurement | Test in A.17.7.3.1 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  |  | 0%
371 | Y | 38.533 | 17.7.3.2 | NR SA FR2 CSI-RS based L1-RSRP measurement on resource set with repetition off | Test in A.17.7.3.2 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  |  | 0%
372 |  | 38.533 | 17.7.4 | SS-SINR measurement for RedCap | New sub-clause header |  |  |  |  | 0.5 | 0% | 0% |  |  | 0%
373 | Y | 38.533 | 17.7.4.1 | NR SA FR2 intra-frequency case measurement accuracy with FR2 serving cell and FR2 target cell for 2Rx UE | Test in A.17.7.4.1 in TS 38.133 |  | RAN5#101 (Nov-23) |  | RAN4 Phase 2 | 0.5 | 0% | 0% |  |  | 0%
374 |  |  | 18 | E-UTRA standalone tests for NR RRM for RedCap | New clause header
375 |  |  | 18.1 | RRC_IDLE state mobility for RedCap | New sub-clause header
376 |  |  | 18.1.1 | Inter-RAT NR Cell re-selection for RedCap | New sub-clause header
377 | Y | 38.533 | 18.1.1.1 | E-UTRA - NR SA FR1 E-UTRA Cell reselection to higher priority NR target Cell in FR1 | Test in A.18.1.1.1 in TS 38.133 | Ericsson | RAN5#99 (May-23) | R5-231134 R5-235696 | RAN4 Phase 1 TT analysis is still missing | 0.5 | 100% (+10%) | 100% (+10%) |  | 100%
378 |  |  | 18.2 | RRC_CONNECTED state mobility for RedCap | New sub-clause header |  |  | R5-226174
379 |  |  | 18.2.1 | Handover for RedCap | New sub-clause header |  |  | R5-226174 | RAN4 Phase 1
380 | Y | 38.533 | 18.2.1.1 | E-UTRA - NR SA FR1 E-UTRAN - NR handover in FR1 | Test in A.18.2.1.1 in TS 38.133 | Huawei |  | R5-226175 |  | 0.5 | 100% | 100% |  | 100%
381 |  |  | 18.2.2 | RRC connection release with redirection for RedCap | New sub-clause header |  |  | R5-226176
382 | Y | 38.533 | 18.2.2.1 | E-UTRA - NR SA FR1 Redirection from E-UTRA to NR SA FR1 for redcap UE | Test in A.18.2.2.1 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-226177 R5-232475 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
383 |  |  | 18.3 | Measurement procedure for RedCap | New sub-clause header
384 |  |  | 18.3.1 | E-UTRA - NR Measurements for RedCap | New sub-clause header
385 | Y | 38.533 | 18.3.1.1 | E-UTRA - NR SA FR1 Event triggered reporting tests for FR1 without SSB time index detection when DRX is not used | Test in A.18.3.1.1 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230505 R5-234671 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
386 | Y | 38.533 | 18.3.1.2 | E-UTRA - NR SA FR1 Event triggered reporting tests for FR1 without SSB time index detection when DRX is used | Test in A.18.3.1.2 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230506 R5-234671 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
387 | Y | 38.533 | 18.3.1.3 | E-UTRA - NR SA FR1 Event triggered reporting tests for FR1 with SSB time index detection when DRX is not used | Test in A.18.3.1.3 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230507 R5-234671 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
388 | Y | 38.533 | 18.3.1.4 | E-UTRA - NR SA FR1 Event triggered reporting tests for FR1 with SSB time index detection when DRX is used | Test in A.18.3.1.4 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230508 R5-234671 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
389 | Y | 38.533 | 18.3.1.5 | E-UTRA - NR SA FR2 Event triggered reporting tests for FR2 without SSB time index detection when DRX is not used | Test in A.18.3.1.5 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230509 R5-232476r1 | RAN4 Phase 2 | 0.5 | 100% | 100% |  |  | 100%
390 | Y | 38.533 | 18.3.1.6 | E-UTRA - NR SA FR2 Event triggered reporting tests for FR2 without SSB time index detection when DRX is used | Test in A.18.3.1.6 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230510 R5-232477r1 | RAN4 Phase 2 | 0.5 | 100% | 100% |  |  | 100%
391 | Y | 38.533 | 18.3.1.7 | E-UTRA - NR SA FR2 Event triggered reporting tests for FR2 with SSB time index detection when DRX is not used | Test in A.18.3.1.7 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230511 R5-232478r1 | RAN4 Phase 2 | 0.5 | 100% | 100% |  |  | 100%
392 | Y | 38.533 | 18.3.1.8 | E-UTRA - NR SA FR2 Event triggered reporting tests for FR2 with SSB time index detection when DRX is used | Test in A.18.3.1.8 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230512 R5-232479r2 | RAN4 Phase 2 | 0.5 | 100% | 100% |  |  | 100%
393 |  | 38.533 | Clause 1-3 and Annex | Adding definition, RMC, side condition, cell mapping, uncertainty and test method for RedCap RRM test cases | Adding definition, RMC, side condition, cell mapping, uncertainty and test method for RedCap RRM test cases | Huawei | RAN5#97(Nov-22) | R5-226178 R5-227827 R5-226180 R5-226181 R5-227845 R5-226183 R5-230513 R5-230514 R5-230515 R5-231135 R5-232480 R5-233611 R5-232482 R5-233617 R5-235724 R5-234662 R5-234925r1 R5-235697 R5-234997 R5-235730 R5-235699 |  | 0.5 | 85% | 85% |  |  | 85%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
|  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
394 |  | 38.903 | 8 and attachment | Grouping and TT analysis of test cases defined in TS 38.533 | TT analysis grouping for RRM test cases |  | TBD | R5-227846,R5-227847 R5-227848,R5-227849 R5-227850,R5-227851 R5-227852,R5-227853 R5-227854,R5-226428 R5-227855,R5-227856 R5-227857,R5-227858 R5-227859,R5-226434 R5-226435,R5-226436 R5-226437,R5-226438 R5-226439,R5-227860 R5-231762,R5-230517 R5-230518,R5-230519 R5-230520,R5-230521 R5-230522,R5-230523 R5-230524,R5-230525 R5-231763,R5-231138 R5-231139,R5-231140 R5-231141,R5-231142 R5-232483,R5-232484 R5-232485,R5-232486 R5-232487,R5-232488 R5-233299,R5-235731 R5-234421,R5-234422 R5-234423,R5-234424 R5-235732,R5-234663 R5-234665,R5-234666 R5-234668,R5-234669 R5-234670,R5-234965r1 R5-234966,R5-234967 R5-234968r1,R5-234969 R5-234970 |  | 1 | 80% | 80% |  | 80%
395 |  | 38.903 | Annex B | Acceptable uncertainty of test system for test cases defined in TS 38.521-2 for radiative testing | MU analysis for Power class 7 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
TR 38.905: Test Point analysis receiver and transmitter test cases
396 |  | 38.905 | 4 | Test coverage analysis | Add header, general text and table to list test point analysis for RedCap | Huawei | RAN5#98 (Feb-23) | R5-222903 |  | 1 | 2.5% | 2.5% |  | 5% | 0%
RAN and CN protocol
TS 38.523-1: Protocol test cases
397 |  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
Idle Mode
398 | Y | 38.523-1 | 6.1.2.26 | Cell Selection / Redcap | **** TP1: [Ref: 38.304 clause 5.3.1] WITH: UE surpporting Redcap and in NR RRC_IDLE state WHEN: a cell fulfils the requirements for a suitable cell except cell Barred status "true" for Redcap THEN: the UE considers the cell as barred and no camping on this cell can take place **** TP2: [Ref: 38.304 clause 5.3.1] WITH: UE surpporting Redcap and in NR RRC_IDLE state WHEN: a cell fulfils the requirements for a suitable cell except intraFreqReselectionRedCap in SIB1 is absent THEN: the UE considers the cell as barred and no camping on this cell can take place **** TP3: [Ref: 38.304 clause 5.3.1] WITH: UE surpporting Redcap and in NR RRC_IDLE state WHEN: a cell fulfils the requirements for a suitable cell except cell Barred status not "true" for Redcap THEN: the UE considers the cell suitable and camps on it | Huawei, Hisilicon | RAN5#96 (Aug-22) | R5-225346 R5-227156 R5-231531 R5-232981 |  | 1 | 100% | 100% |  | 100% | 100%
399 | Y | 38.523-1 | 6.1.2.27 | Cell reselection / inter-freguency / Redcap | **** TP1: [Ref: 38.331 clause 6.3.1] WITH: UE surpporting Redcap and in NR RRC_IDLE state WHEN: the serving cell broadcasts SIB4 with system information indication of frequencies which accept RedCap UEs THEN: the UE reselects the inter-frequency neighbor cell depending on SIB4 indication | Qualcomm | RAN5#96 (Aug-22) | R5-227536 R5-230435 R5-231532 |  | 1 | 100% | 100% |  | 100% | 100%
Layer 2
400 | Y | 38.523-1 | 7.1.1.1.15 | Random access procedure / RedCap UE / SI request | **** TP1: [Ref: ] WITH: UE in RRC_Idle State and initialUplinkBWP-RedCap and si-RequestConfigRedCap is configured in SIB1 of Serving Cell WHEN: one System information,which si-BroadcastStatus is set to notBroadcasting, is updated THEN: UE transmitted PRACH preamble for System information request using the PRACH preamble(s) and PRACH resource(s) in si-RequestConfigRedcap and retransmitted PRACH preamble when ra-ResponseWindow has expired **** TP2: [Ref: ] WITH: UE in RRC_Idle State and transmitted PRACH preamble for System information request WHEN: UE received a RAR message addressed to RA-RNTI and including matching RAPID only THEN: UE considers the RACH procedure to be successfully completed and informs the upper layer | Huawei, Hisilicon | RAN5#96 (Aug-22) | R5-232940 |  | 1 | 100% | 100% |  | 100% | 100%
401 | Y | 38.523-1 | 7.1.1.1.16 | Random access procedure / Redcap UE identification / Msg3-based / CCCH1 | **** TP1: [Ref: 38.321 clause 5.1 and 6.2.1] WITH: UE surpporting Redcap and in NR RRC_Inactive state WHEN: UE starts Random Access procedure THEN: the UE uses the Redcap specific LCID in Mag3 | Huawei, Hisilicon | RAN5#96 (Aug-22) | R5-225345 |  | 1 | 100% | 100% |  | 100% | 100%
402 | Y | 38.523-1 | 7.1.1.1.17 | Random access procedure / Redcap UE identification / Msg1-based | **** TP1: [Ref: 38.321 clause 5.1] WITH: UE surpporting Redcap and in NR RRC_IDLE state WHEN: UE starts Random Access procedure THEN: the UE uses the Redcap specific random access resource in Msg1 **** TP2: [Ref: 38.321 clause 6.2.1] WITH: UE supporting RedCap and in NR RRC_IDLE state WHEN: UE starts Random Access procedure THEN: the UE uses the RedCap specific LCID in Msg3 | Huawei, Hisilicon | RAN5#96 (Aug-22) | R5-225347 R5-227533 R5-231529 |  | 1 | 100% | 100% |  | 100% | 100%
403 | Y | 38.523-1 | 7.1.1.8.3 | Separate BWP / IDLE / Redcap | **** TP1: [Ref: 38.321 clause 5.15.1] WITH: UE surpporting Redcap and in NR RRC_IDLE state WHEN: initialDownlinkBWP-RedCap is configured THEN: the UE shall monitor the PDCCH on the BWP configured by initialDownlinkBWP-RedCap **** TP2: [Ref: 38.321 clause 5.15.1] WITH: UE surpporting Redcap and in NR RRC_IDLE state WHEN: initialUplinkBWP-RedCap is configured and the UE needs to perform the Random Access procedure THEN: the UE shall perform the Random Access procedure by using the BWP configured by initialUplinkBWP-RedCap | Huawei, Hisilicon | RAN5#96 (Aug-22) | R5-225344 R5-227530 R5-231530 |  | 1 | 100% | 100% |  | 100% | 100%
404 | Y | 38.523-1 | 7.1.1.8.4 | Separate BWP / RedCap-specific initial DL BWP without CORESET#0 / NCD-SSB | **** TP1 WITH: UE supporting RedCap and in NR RRC_IDLE state WHEN: initialDownlinkBWP-RedCap does not contain the entire CORESET#0 THEN: UE uses this BWP for receiving DL messages during initial access and after initial access **** TP2 WITH: UE in NR RRC_CONNECTED and the active BWP is RedCap-specific initial downlink BWP and this BWP does not include CD-SSB and the entire CORESET#0 WHEN: NCD-SSB is configured for a RedCap UE in RRCSetup THEN: UE replies RRCSetupComplete **** TP3 WITH: UE in NR RRC_CONNECTED and the active BWP is RedCap-specific initial downlink BWP and this BWP does not include CD-SSB and the entire CORESET#0 WHEN: SS sends RRCRelease to trigger UE move to RRC_IDLE THEN: UE shall monitor paging in the initial DL BWP that includes CORESET#0 | Huawei, Hisilicon | RAN5#100 (Aug-23) | R5-235315 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
RRC
405 |  | 38.523-1 | 8.1.3.1.24 | Void | Void | Huawei, Hisilicon | RAN5#97(Nov-22) |  | no need to provide test coverage in SIG since RRM will cover this | 0
406 | Y | 38.523-1 | 8.1.5.10.4 | UE Assistance Information / RRM measurement relaxation / RedCap | **** TP1: [Ref: 38.304 clause 5.2.4.9, 38.331 clause 5.7.4] WITH: UE surpporting Redcap and in NR RRC_Connected state and configured RRM measurement relaxation Stationary criterion WHEN: the criterion is fulfilled and the UE does not transmit a UEAssistanceInformation message with rrm-MeasRelaxationFulfilment as true since it was configured to provide indications of RRM measurement relaxation criterion fulfilment THEN: the UE initiates transmission of the UEAssistanceInformation message to indicate that the criterion for RRM measurement relaxation for connected mode is fulfilled **** TP2: [Ref: 38.304 clause 5.2.4.9, 38.331 clause 5.7.4] WITH: UE surpporting Redcap and in NR RRC_Connected state and configured RRM measurement relaxation Stationary criterion WHEN: the criterion is not fulfilled and the last UEAssistanceInformation message indicated fulfilment of the criterion with rrm-MeasRelaxationFulfilment as true THEN: the UE initiates transmission of the UEAssistanceInformation message to indicate that the criterion for RRM measurement relaxation for connected mode is not fulfilled **** TP3: [Ref: 38.304 clause 5.2.4.9, 38.331 clause 5.7.4] WITH: UE surpporting Redcap and in NR RRC_Connected state and configured RRM measurement relaxation Stationary criterion WHEN: the criterion is fulfilled and the last UEAssistanceInformation message indicated the criterion is not fulfilled with rrm-MeasRelaxationFulfilment as false THEN: the UE initiates transmission of the UEAssistanceInformation message to indicate that the criterion for RRM measurement relaxation for connected mode is fulfilled | Ericsson | RAN5#96 (Aug-22) | R5-225348 R5-227589 R5-231587 | Editor's note: FR2 power levels are still FFS | 1 | 95% | 95% |  | 100% | 90%
NAS
407 | Y | 38.523-1 | 8.1.5.2.3 | eDRX / IDLE / Paging for notification of BCCH modification | **** TP1: [Ref: ] WITH: UE in NR RRC_IDLE state using eDRX cycle longer than the BCCH modification period WHEN: UE receives a Short Message and the systemInfoModification-eDRX bit is set to indicate BCCH modification THEN: UE applies the SI acquisition procedure to update the new system information **** TP2: [Ref: ] WITH: UE in NR RRC_IDLE state using eDRX cycle shorter than the BCCH modification period WHEN: UE receives a Short Message and the systemInfoModification bit is set to indicate BCCH modification THEN: UE applies the SI acquisition procedure to update the new system information | Qualcomm | RAN5#100 (Aug-23) | R5-235343 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
408 |  | 38.523-1 | 11.7 | eDRX | Sub-clause heading |  |  |  |  | 0.1 | 100% | 100% |  | 100% | 100%
409 | Y | 38.523-1 | 11.7.1 | eDRX / IDLE | **** TP1: [Ref: 24.501 clause 5.3.16] WITH : UE having sent an REGISTRATION REQUEST message with extended DRX parameters IE WHEN : the UE receives the extended DRX parameters in the REGISTRATION ACCEPT message THEN: the UE sends a REGISTRATION COMPLETE message **** TP2: [Ref: 24.501 clause 5.3.16] WITH: UE in NR RRC_IDLE state and configured eDRX (eDRX cycle >= 10.24s) WHEN: network sends Paging message within a Paging Time Window(PTW) THEN: UE establishes RRC connection **** TP3: [Ref: 24.501 clause 5.3.16] WITH: UE in NR RRC_IDLE state and configured eDRX (eDRX cycle <= 10.24s) WHEN: network sends Paging message within a paging occassion THEN: UE establishes RRC connection **** TP4: [Ref: 24.501 clause 5.3.16] WITH: UE in NR RRC_IDLE state and configured eDRX WHEN: network changes SIB1 to exclude eDRX-AllowedIdle IE THEN: UE applies the new system information about eDRX not allowed and stops using extended DRX for CN paging in RRC_IDLE state | Qualcomm | RAN5#96 (Aug-22) | R5-227522 R5-231534 R5-233411 R5-235344 | Optional supported by UE | 1 | 100% | 100% |  | 100% | 100%
410 | Y | 38.523-1 | 11.7.2 | eDRX / Inactive / RAN-initiated paging | **** TP1: [Ref: 24.501 clause 5.3.16] WITH: UE having sent an REGISTRATION REQUEST message with extended DRX parameters IE WHEN: the UE receives the extended DRX parameters in the REGISTRATION ACCEPT message THEN: the UE sends a REGISTRATION COMPLETE message **** TP2: [Ref: 24.501 clause 5.3.16] WITH: UE in NR RRC_Inactive state and configured eDRX and RAN Extended Paging Cycle equals to the IDLE mode eDRX cycle WHEN:the network sends a RAN-initiated Paging message within a paging occassion THEN:the UE resumes RRC connection **** TP3: [Ref: 24.501 clause 5.3.16] WITH: UE in NR RRC_Inactive state and configured eDRX and RAN Extended Paging Cycle shorter than the IDLE mode eDRX cycle WHEN: the network sends a RAN-initiated Paging message within a paging occassion THEN:the UE applies the value of ran-ExtendedPagingCycle for RAN-initiated paging and resumes RRC connection **** TP4: [Ref: 24.501 clause 5.3.16] WITH: UE in NR RRC_ INACTIVE state and configured eDRX WHEN: network changes SIB1 to exclude eDRX-AllowedInactive IE THEN: UE applies the new system information and stops using extended DRX for RAN paging in RRC_INACTIVE state | Ericsson | RAN5#96 (Aug-22) | R5-225173 R5-227590 R5-231535 R5-233412 R5-235345 | Optional supported by UE | 1 | 100% | 100% |  | 100% | 100%
411 | Y | 38.523-1 | 11.7.3 | eDRX / Inactive / CN-initiated paging / eDRX Allowed / Not Allowed | **** TP1: [Ref: ] WITH: UE in NR RRC_Inactive state and configured eDRX WHEN: the network sends a CN-initiated Paging message within a paging occassion THEN: the UE goes to RRC_IDLE state and establishes an RRC connection **** TP2: [Ref: ] WITH: UE in NR RRC_ INACTIVE state and configured eDRX WHEN: network changes SIB1 to exclude eDRX-AllowedIdle and eDRX-AllowedInactive IEs THEN: UE applies the new system information and stops using extended DRX for CN-initiated paging in RRC_INACTIVE state | Mediatek | RAN5#100 (Aug-23) | R5-235346 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
Legacy testcases adjustment
412 |  | 38.523-1 | 6 | Idle mode and RRC Inactive state operations | Update the legacy test cases to support RedCap UE | Huawei, Hisilicon | RAN5#97(Nov-22) |  |  | 1 | 100% | 100% |  | 100% | 100%
413 |  | 38.523-1 | 7 | Layer 2 | Update the legacy test cases to support RedCap UE | Huawei, Hisilicon | RAN5#97(Nov-22) |  |  | 1 | 100% | 100% |  | 100% | 100%
414 |  | 38.523-1 | 7.1.1.1.1 | Correct selection of RACH parameters / Random access preamble and PRACH resource explicitly signalled to the UE by RRC / contention free random access procedure | Update the legacy test cases to support RedCap UE HD-FDD mode | Huawei，hisilicon | RAN5#99 (May-23) | R5-232938 |  | 1 | 100% | 100% |  | 100% | 100%
415 |  | 38.523-1 | 7.1.1.1.1a | Correct selection of RACH parameters / Random access preamble and PRACH resource explicitly signalled to the UE by PDCCH Order / contention free random access procedure | Update the legacy test cases to support RedCap UE HD-FDD mode | Huawei，hisilicon | RAN5#99 (May-23) | R5-232938 |  | 1 | 100% | 100% |  | 100% | 100%
416 |  | 38.523-1 | 7.1.1.1.2 | Random access procedure / Successful / C-RNTI Based / Preamble selected by MAC itself | Update the legacy test cases to support RedCap UE HD-FDD mode | Huawei，hisilicon | RAN5#99 (May-23) | R5-233408 |  | 1 | 100% | 100% |  | 100% | 100%
417 |  | 38.523-1 | 7.1.1.1.8 | Correct selection of RACH parameters / 2-step RACH/MSGA and PRACH resource explicitly signalled to the UE by RRC / contention free random access procedure | Update the legacy test cases to support RedCap UE HD-FDD mode | Huawei，hisilicon | RAN5#99 (May-23) | R5-232938 |  | 1 | 100% | 100% |  | 100% | 100%
418 |  | 38.523-1 | 7.1.1.3.4 | Correct handling of MAC control information / Buffer status / UL data arrive in the UE Tx buffer / Regular BSR | Update the legacy test cases to support RedCap UE | Huawei, Hisilicon | RAN5#97(Nov-22) | R5-227162 |  | 1 | 100% | 100% |  | 100% | 100%
419 |  | 38.523-1 | 7.1.1.3.12 | Correct Handling of UL HARQ process / PUSCH Repetition Type B | Update the legacy test cases to support RedCap UE HD-FDD mode | Huawei，hisilicon | RAN5#99 (May-23) | R5-233409 |  | 1 | 100% | 100% |  | 100% | 100%
420 |  | 38.523-1 | 7.1.1.4.1.1 | DL-SCH transport block size selection / DCI format 1_0 | Update the legacy test cases to support RedCap UE | Huawei, Hisilicon | RAN5#97(Nov-22) | R5-227163 |  | 1 | 100% | 100% |  | 100% | 100%
421 |  | 38.523-1 | 7.1.1.4.2.1 | UL-SCH transport block size selection / DCI format 0_0 / Transform precoding disabled | Update the legacy test cases to support RedCap UE | Huawei, Hisilicon | RAN5#97(Nov-22) | R5-227166 |  | 1 | 100% | 100% |  | 100% | 100%
422 |  | 38.523-1 | 7.1.1.4.2.3 | UL-SCH transport block size selection / DCI format 0_1 / RA type 0/RA Type 1 / Transform precoding disabled | Update the legacy test cases to support RedCap UE | Huawei, Hisilicon | RAN5#97(Nov-22) | R5-227167 |  | 1 | 100% | 100% |  | 100% | 100%
423 |  | 38.523-1 | 7.1.1.4.2.4 | UL-SCH transport block size selection / DCI format 0_1 / RA type 0/RA Type 1 / 256QAM / Transform precoding disabled | Update the legacy test cases to support RedCap UE | Huawei, Hisilicon | RAN5#97(Nov-22) | R5-227168 |  | 1 | 100% | 100% |  | 100% | 100%
424 |  | 38.523-1 | 7.1.1.4.2.5 | UL-SCH transport block size selection / DCI format 0_0 / Transform precoding disabled | Update the legacy test cases to support RedCap UE | Huawei, Hisilicon | RAN5#97(Nov-22) | R5-227169 |  | 1 | 100% | 100% |  | 100% | 100%
XXX |  | 38.523-1 | 7.1.1.5.0 | DRX Common Definitions | Update the legacy MAC CDRX TC to support RedCap UE HD-FDD mode | Huawei, Hisilicon | RAN5#100 (Aug-23) | R5-234454 |  | 1 | 100% | 100% |  | 100% | 100%
425 |  | 38.523-1 | 7.1.1.9.1 | MAC Reset | Update the legacy test cases to support RedCap UE | Huawei, Hisilicon | RAN5#97(Nov-22) | R5-227170 |  | 1 | 100% | 100% |  | 100% | 100%
426 |  | 38.523-1 | 7.1.2.3.3 | AM RLC / 12-bit SN / Correct use of sequence numbering | Update the legacy test cases to support RedCap UE | Huawei, Hisilicon | RAN5#97(Nov-22) | R5-227523 |  | 1 | 100% | 100% |  | 100% | 100%
427 |  | 38.523-1 | 7.1.2.3.5 | AM RLC / 12-bit SN / Control of transmit window/Control of receive window | Update the legacy test cases to support RedCap UE | Huawei, Hisilicon | RAN5#97(Nov-22) | R5-227528 |  | 1 | 100% | 100% |  | 100% | 100%
428 |  | 38.523-1 | 7.1.2.3.6 | AM RLC / Polling for status | Update the legacy test cases to support RedCap UE | Huawei, Hisilicon | RAN5#97(Nov-22) | R5-226947 R5-233410 |  | 1 | 100% | 100% |  | 100% | 100%
429 |  | 38.523-1 | 7.1.2.3.7 | AM RLC / Receiver status triggers | Update the legacy test cases to support RedCap UE | Huawei, Hisilicon | RAN5#97(Nov-22) | R5-227164 |  | 1 | 100% | 100% |  | 100% | 100%
430 |  | 38.523-1 | 7.1.2.3.8 | AM RLC / Reconfiguration of RLC parameters by upper layers | Update the legacy test cases to support RedCap UE | Huawei, Hisilicon | RAN5#97(Nov-22) | R5-226948 |  | 1 | 100% | 100% |  | 100% | 100%
431 |  | 38.523-1 | 7.1.2.3.9 | AM RLC / Re-ordering of RLC PDU segments | Update the legacy test cases to support RedCap UE | Huawei, Hisilicon | RAN5#97(Nov-22) | R5-227529 |  | 1 | 100% | 100% |  | 100% | 100%
432 |  | 38.523-1 | 7.1.2.3.10 | AM RLC / Re-transmission of RLC PDU with and without re-segmentation | Update the legacy test cases to support RedCap UE | Huawei, Hisilicon | RAN5#97(Nov-22) | R5-227601 |  | 1 | 100% | 100% |  | 100% | 100%
433 |  | 38.523-1 | 7.1.3.4.1 | PDCP handover / Lossless handover / PDCP sequence number maintenance/PDCP status report to convey the information on missing or acknowledged PDCP SDUs at handover/ In-order delivery and duplicate elimination in the downlink | Update the legacy test cases to support RedCap UE | Huawei, Hisilicon | RAN5#97(Nov-22) | R5-227535 |  | 1 | 100% | 100% |  | 100% | 100%
434 |  | 38.523-1 | 7.1.3.5.4 | PDCP handover / Lossless handover / PDCP sequence number maintenance/PDCP status report to convey the information on missing or acknowledged PDCP SDUs at handover/ In-order delivery and duplicate elimination in the downlink | Update the legacy test cases to support RedCap UE | Huawei, Hisilicon | RAN5#98(Mar-23) | R5-231533 |  | 1 | 100% | 100% |  | 100% | 100%
435 |  | 38.523-1 | 8 | RRC | Update the legacy test cases to support RedCap UE | Qualcomm | RAN5#97(Nov-22) |  |  | 1 | 100% | 100% |  | 100% | 100%
436 |  | 38.523-1 | 8.1.5.1.1 | UE capability transfer / Success | Update the legacy test cases to support RedCap UE | Qualcomm | RAN5#97(Nov-22) | R5-227571 R5-233070 |  | 1 | 100% | 100% |  | 100% | 100%
437 |  | 38.523-1 | 8.1.5.2.2 | SI change / Notification of BCCH modification / Short message for SI update in NR RRC_CONNECTED state | Update the legacy test cases to support RedCap UE and HD-FDD mode | Qualcomm | RAN5#97(Nov-22) | R5-227531 R5-233408 |  | 1 | 100% | 100% |  | 100% | 100%
438 |  | 38.523-1 | 8.1.5.8.1 | SI change / Notification of BCCH modification / Short message for SI update in NR RRC_CONNECTED state | Update the legacy test cases to support RedCap UE HD-FDD mode | Huawei，hisilicon | RAN5#99(May-23) | R5-233071 |  | 1 | 100% | 100% |  | 100% | 100%
439 |  | 38.523-1 | 9 | Mobility management | Update the legacy test cases to support RedCap UE |  | RAN5#97(Nov-22) | No Document needed |  | 1 | 100% | 100% |  | 100% | 100%
440 |  | 38.523-1 | 10 | Session management | Update the legacy test cases to support RedCap UE |  | RAN5#97(Nov-22) | No Document needed |  | 1 | 100% | 100% |  | 100% | 100%
441 |  | 38.523-1 | 11 | Multi-layer and Services | Update the legacy test cases to support RedCap UE | Huawei, Hisilicon | RAN5#97(Nov-22) | No Document needed |  | 1 | 100% | 100% |  | 100% | 100%
TS 38.523-2: Applicability for Protocol test cases
442 |  | 38.523-2 | 4.1 | Protocol conformance test cases applicability | Add applicability for NR Redcap |  |  | R5-227591 R5-227541 R5-227602 R5-227537 R5-231536 R5-232943 R5-234006 R5-234007 R5-235347 R5-235316 |  | 1 | 100% | 100% |  | 100% | 100%
443 |  | 38.523-2 | 4.2 | Protocol conformance test cases Applicability Condition | Add applicability for NR Redcap |  |  | R5-225350 R5-225174 R5-227591 R5-227541 R5-227602 R5-231588 R5-231536 R5-232943 R5-234006 |  | 1 | 100% | 100% |  | 100% | 100%
TS 38.523-3: Protocol test suites (TTCN)
444 |  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD | 100% | 100% |  | 100% | 100%
445 |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD | R5-230104 R5-232191 |  | TBD | 100% | 100% |  | 100% | 100%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.