## Cover sheet
3GPP TSG-RAN WG5 Meeting #104 | [10 empty] | R5-244214
Maastricht, Netherlands, 19th Aug 2024 - 23rd Aug 2024
Agenda Item: | 7.5.2
Source: | MediaTek Inc., China Telecom
Title: | WP UE Conformance - Introduction of FDD LTE band (L+S band) for IoT NTN operation
Work item code: | IoT_NTN_FDD_LS_band-UEConTest
Release: | Rel-18
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
The objective of this work item is to provide conformance tests for the Introduction of FDD LTE band (L+S band) for IoT NTN operation: At the RAN#104 meeting in Jun 2024, Rel-18 RAN5 work item for UE Conformance - Introduction of FDD LTE band (L+S band) for IoT NTN operation [1] was approved. The purpose of present document is to provide a work plan for the RAN5 work item on the conformance test cases for the core requirement introduced by the core and performance work items. The work plan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 95% | 0 | 0
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
LTE (Applications) |  | 95% | 0 | 0
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FDD |  |  | TDD
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
EPS
EPS Common
Common test environment | 36.508 | 100% |  |  | 100%
EPS RAN and CN protocols
Common ICS for RF | 36.521-2 | 100% | 0 | 0 | 100% | 0 | 0
RRM test cases | 36.521-3 | 100% | 0 | 0 | 100% | 0 | 0
RF test cases | 36.521-4 | 90% | 0 | 0 | 90% | 0 | 0
Protocol test cases | 36.523-1 | 100% | 0 | 0 | 100% | 0 | 0
Common ICS for SIG | 36.523-2 | 100% |  |  | 100%
5 References
[1] RP-241354 | New WID on UE Conformance – Introduction of FDD LTE band (L+S band) for IoT NTN operation；MediaTek Inc., China Telecom
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP UE Conformance - Introduction of FDD LTE band (L+S band) for IoT NTN operation | [12 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | [8 empty] | End of workplan columns. Note! Do not remove this column. |  | Current meeting status | [9 empty] | Previous meeting status baseline | [8 empty] | WP rapporteur's private information. These columns will be removed in the clean copy created by "Create clean WP for publishing".
WI code |  | IoT_NTN_FDD_LS_band-UEConTest
WP Scope: |  | The purpose of present document is to provide a work plan for the RAN5 work item UE Conformance - Introduction of FDD LTE band (L+S band) for IoT NTN operation comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core requirement (relevant core spec WIs indicated in the WID). | [14 empty] | vs Area
WP Resp: |  | Daiwei Zhou, MediaTek Inc. |  |  | daiwei.zhou@mediatek.com | [5 empty] | WP item completion |  |  |  |  | N/A |  |  | N/A |  |  | N/A
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [21 empty] | WP rapporteur internal notes |  | Company <-> Contact email address(es)
[27 empty] | Start of source data | [18 empty] | <Internal note column#1> | <Internal note column#2> | Company | E-mail address(es)
[14 empty] | Overall |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | Start of Current Meeting Data | [9 empty] | End of Current Meeting Data
[14 empty] | Number of WP items |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | Sum weight of WP items |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | Contribution by work plan analysis |  | 5% | [10 empty] | 5% | [9 empty] | 0.05
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
NTN IoT
LTE Common
TS 36.508: Common test environment
|  | 36.508 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 0 | [16 empty] | #NAME?
1 |  | 36.508 | 4.3.1.1.254 | FDD reference test frequencies for operating band 254 | Addition of test frequency for band 254 | MediaTek Inc. | RAN5#104 (Aug-24) | R5-244218 |  | 0.5 | 100% | 100% |  | 100% | [12 empty] | #NAME?
2 |  | 36.508 | 6.2.3.1 | Test frequencies for signalling test | Addition of SIG test frequency for band 254 | MediaTek Inc. | RAN5#104 (Aug-24) | R5-244228 |  | 1 | 100% | 100%
3 |  | 36.508 | 8.1.3.1 | NB-IoT Test frequencies | Addition of NB-IoT SIG test frequency for band 254 | MediaTek Inc. | RAN5#104 (Aug-24) | R5-244218 |  | 1 | 100% | 100%
4 |  | 36.508 | 8.3.2.3 | NB-IoT Default test frequencies | Addition of NB-IoT default test frequency for band 254 | MediaTek Inc. | RAN5#104 (Aug-24) | R5-244228 |  | 1 | 100% | 100%
RAN RRM
TS 36.521-2: Applicability for RF test cases
|  | 36.521-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 0
5 |  | 36.521-2 | 2 | References | Addition of reference to TS 36.102 | MediaTek Inc. | RAN5#104 (Aug-24) | R5-245862 |  | 0.5 | 100% | 100%
6 |  | 36.521-2 | 4.3 | RF and RRM conformance test cases for NB-IoT/eMTC NTN | Tested Bands Selection Criteria for addition of band 254 | MediaTek Inc. | RAN5#104 (Aug-24) | R5-245862 |  | 1 | 100% | 100%
7 |  | 36.521-2 | A.4.3 | Baseline Implementation Capabilities | Addition of PICS for band 254 | MediaTek Inc. | RAN5#104 (Aug-24) | R5-245862 |  | 1 | 100% | 100% |  | 100%
RAN RRM
TS 36.521-3: RRM test cases
|  | 36.521-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 0
8 |  | 36.521-3 | 3.5.1A | Groups of bands for satellite access | Addition of band 254 for band grouping | MediaTek Inc. | RAN5#104 (Aug-24) | R5-244219 |  | 1 | 100% | 100%
RAN RF/Demod
TS 36.521-4: RF and performance test cases
|  | 36.521-4 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 0
9 |  | 36.521-4 | 5.2 | Operating bands | Addition of band 254 | MediaTek Inc. | RAN5#104 (Aug-24) | R5-244220 |  | 1 | 100% | 100% |  | 100%
10 |  | 36.521-4 | 5.2B | Operating bands for category NB1 and NB2 | Addition of band 254 for NB-IoT NTN | MediaTek Inc. | RAN5#104 (Aug-24) | R5-244220 |  | 1 | 100% | 100%
11 |  | 36.521-4 | 5.4A.2 | Channel raster, carrier frequency and EARFCN | Addition of channel numbers for band 254 | MediaTek Inc. | RAN5#104 (Aug-24) | R5-244220 |  | 1 | 100% | 100%
12 |  | 36.521-4 | 5.4A.3 | TX–RX frequency separation | Addition of TX–RX frequency separation for band 254 | MediaTek Inc. | RAN5#104 (Aug-24) | R5-244220 |  | 1 | 100% | 100%
13 |  | 36.521-4 | 6.2A.1 | UE maximum output power for category M1 | Addition of band 254 for maximum output power TC | MediaTek Inc. | RAN5#104 (Aug-24) | R5-244127 |  | 1 | 100% | 100%
14 |  | 36.521-4 | 6.2B.1 | UE maximum output power for category NB1 and NB2 | Addition of band 254 for maximum output power TC | MediaTek Inc. | RAN5#104 (Aug-24) | R5-244129 |  | 1 | 100% | 100%
15 |  | 36.521-4 | 6.2B.3 | UE additional maximum output power reduction for category NB1 and NB2 UE | Addition of band 254 for additional maximum output power reduction TC | MediaTek Inc. | RAN5#106 (Feb-25) |  | To be clarified in RAN4 | 1 | 0% | 0%
16 |  | 36.521-4 | 6.5A.4.3 | Spurious emission band UE co-existence for category M1 | Addition of band 254 for Spurious emission band UE co-existence TC | MediaTek Inc. | RAN5#104 (Aug-24) | R5-244130 |  | 1 | 100% | 100%
17 |  | 36.521-4 | 6.5A.4.4 | Additional spurious emissions for category M1 | Addition of band 254 for additional spurious emissions TC | MediaTek Inc. | RAN5#106 (Feb-25) | R5-244135 |  | 1 | 100% | 100%
18 |  | 36.521-4 | 6.5B.4.3 | Spurious emission band UE co-existence for category NB1 and NB2 | Addition of band 254 for Spurious emission band UE co-existence TC | MediaTek Inc. | RAN5#104 (Aug-24) | R5-244131 |  | 1 | 100% | 100%
19 |  | 36.521-4 | 6.5B.4.4 | Additional spurious emissions for category NB1 and NB2 | Addition of band 254 for additional spurious emissions TC | MediaTek Inc. | RAN5#106 (Feb-25) | R5-244457 |  | 1 | 100% | 100%
20 |  | 36.521-4 | 7.3A | Reference sensitivity power level for UE category M1 | Addition of band 254 for Reference sensitivity power level TC | MediaTek Inc. | RAN5#104 (Aug-24) | R5-245861 |  | 1 | 100% | 100%
21 |  | 36.521-4 | 7.6A.2 | In-band blocking for category M1 | Addition of band 254 for In-band blocking TC | MediaTek Inc. | RAN5#104 (Aug-24) | R5-244133 |  | 1 | 100% | 100%
22 |  | 36.521-4 | 7.6A.3 | Out-of-band blocking for category M1 | Addition of band 254 for Out-of-band blocking TC | MediaTek Inc. | RAN5#104 (Aug-24) | R5-244134 |  | 1 | 100% | 100%
23 |  | 36.521-4 | 7.6B.3 | Out-of-band blocking for category NB1 and NB2 | Addition of band 254 for Out-of-band blocking TC | MediaTek Inc. | RAN5#104 (Aug-24) | R5-244136 |  | 1 | 100% | 100%
RAN and CN protocol | [26 empty] | #NAME?
TS 36.523-1: Protocol test cases | [26 empty] | #NAME?
|  | 36.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 0 | [16 empty] | #NAME?
24 |  | 36.523-1 | 22.4.13a | NB-IoT / NTN / UE capability transfer / Success | Update this case to include band 254 | China Telecom | RAN5#104 (Aug-24) | R5-245216 |  | 1 | 100% | 100% |  | 100% | [12 empty] | #NAME?
TS 36.523-2: Applicability for Protocol test cases
|  | 36.523-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 0
25 |  | 36.523-2 | 2 | References | Addition of reference to TS 36.102 | China Telecom | RAN5#104 (Aug-24) | R5-245217 |  | 0.5 | 100% | 100%
26 |  | 36.523-2 | A.4.3.1 | RF Baseline Implementation Capabilities | Addition of PICS for band 254 | China Telecom | RAN5#104 (Aug-24) | R5-245217 |  | 1 | 100% | 100%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.