## Cover sheet
3GPP TSG RAN WG5#104 | [8 empty] | R5-244786
<Maastricht , NL, 19th Aug – 23th Aug, 2024>
Agenda Item: | 7.5.2
Source: | China Unicom
Title: | UE Conformance – Enhanced support of reduced capability NR devices plus CT1 aspects
Work item code: | NR_redcap_enh_plus_CT1-UEConTest
Release: | Rel-18
Document for: | Information
RAN5 WP template v2.0-7
1. Introduction
The objective of the UE Conformance – Enhanced support of reduced capability NR devices plus CT1 aspects work item is to define the UE conformance requirements corresponding to WID on NR_redcap_enh_plus_CT1-UEConTests, analyse the test case impact, applicability, test environment, and update the relevant conformance specifications for the RedCap UE work item in Rel-18. At the RAN#103 meeting the Rel-18 RAN5 work item for UE Conformance – Enhanced support of reduced capability NR devices plus CT1 aspects(NR_redcap_enh_plus_CT1-UEConTest) was approved , the WID is in [1]. The purpose of present document is to provide a work plan for the RAN5 work item. The work plan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 28% (+23%) | 0 | 31 (+10)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR1) |  | 28.3% (+23.3%) | 0 | 31 (+10)
FR1 |  | 28.3% (+23.3%) | 0 | 31 (+10)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 6% (+6%) |  |  | 6% (+6%)
Common ICS | 38.508-2 | 30% (+30%) |  |  | 30% (+30%)
NR RF/RRM
FR1 RF common parts | 38.521-1 | 0% |  |  | 0%
FR1 RF Tx test cases | 38.521-1 Tx | 80% (+80%) |  |  | 80% (+80%)
FR1 RF Rx test cases | 38.521-1 Rx | 41.7% (+41.7%) | 0 | 5 (+5) | 41.7% (+41.7%) | 0 | 5 (+5)
FR2 RF common parts | 38.521-2
FR2 RF Tx test cases | 38.521-2 Tx
FR2 RF Rx test cases | 38.521-2 Rx
RF Demod/QSI test cases | 38.521-4 | 23.4% (+23.4%) | 0 | 14 (+2) | 23.4% (+23.4%) | 0 | 14 (+2)
RRM test cases | 38.533 | 0% |  |  | 0%
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 32.5% (+32.5%) |  |  | 32.5% (+32.5%)
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 0% |  |  | 0%
Test Point analysis receiver and transmitter test cases | 38.905 | 0% |  |  | 0%
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 24.4% (+24.4%) | 0 | 12 (+3) | 24.4% (+24.4%) | 0 | 12 (+3)
Applicability Protocol test cases | 38.523-2 | 6.7% (+6.7%) |  |  | 6.7% (+6.7%)
Protocol Test suites (TTCN) | 38.523-3 | 0% |  |  | 0%
5 References
[1] RP-240920 | Revised WID on UE Conformance – Enhanced support of reduced capability NR devices plus CT1 aspects
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance – Enhanced support of reduced capability NR devices plus CT1 aspect | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_redcap_enh_plus_CT1-UEConTest
WP Scope: |  | The purpose of present document is to provide a workplan for the RAN5 work item UE Conformance – Enhanced support of reduced capability NR devices plus CT1 aspect comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID
WP Resp: |  | Yu Shi(China Unicom),Kolodzie, Kuba（Ericsson）,Zhao, Ya(Huawei) |  |  | shiyu19@chinaunicom.cn;kuba.kolodziej@ericsson.com;zhaoya@hisilicon.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | N/A |  |  | N/A
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1
28.3% (+23.3%)
65 (+12)
73
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 38.508-1 | 4 | common test environment for eRedCap | Definition of common test environment for eRedCap | China Unicom | RAN5#105 (Nov-24) | R5-245313(test channel bandwidth) R5-245624(sib1) |  | 1 | 30% (+30%) | 30% (+30%) |  | 30%
2 |  | 38.508-1 | 5 | Test environments for RF test | Necessary changes to RF test environments |  |  |  |  | 1 | 0% | 0% |  | 0%
3 |  | 38.508-1 | 6 | Test environments for Signalling test | Necessary changes to Signalling test environments |  |  |  |  | 1 | 0% | 0% |  | 0%
4 |  | 38.508-1 | 7 | Test environments for RRM tests | Necessary changes to RRM test environments |  |  |  |  | 1 | 0% | 0% |  | 0%
5 |  | 38.508-1 | Annex A | Connection Diagrams | Connection Diagrams |  |  |  |  | 1 | 0% | 0% |  | 0%
TS 38.508-2: Common ICS
6 |  | 38.508-2 | A.4 | ICS proforma tables | Introduction of common implementation conformance statement (ICS) for eRedCap | all | RAN5#109 (Nov-25) | R5-245811 (RF) R5-245625(eRedCap PICs) |  | 1 | 30% (+30%) | 30% (+30%) |  | 30%
NR RF/RRM
TS 38.521-1: FR1 RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
7 |  | 38.521-1 | 3 | Definitions, symbols and abbreviations |  | Ericsson | RAN5#106 (Feb-25) |  |  | 1 | 0% | 0% |  | 0%
8 |  | 38.521-1 | 4 | General |  | Ericsson | RAN5#106 (Feb-25) |  |  | 1 | 0% | 0% |  | 0%
9 |  | 38.521-1 | 5 | Operating bands and Channel arrangement |  | China Unicom | RAN5#106 (Feb-25) | R5-245218 |  | 1 | 0% | 0% |  | 0%
10 |  | 38.521-1 | Annex |  | Check if necesarry to update Annex | China Unicom | RAN5#106 (Feb-25) | R5-245309 |  | 1 | 0% | 0% |  | 0%
TS 38.521-1: FR1 RF test cases - Tx
Transmitter characteristics (Clause 6)
11 |  | 38.521-1 Tx | 6.2I | Transmitter power for RedCap | Check if necesarry to update Tx TCs for eRedCap | China Unicom | RAN5#106 (Feb-25) |  |  | 0
11 |  | 38.521-1 Tx | 6.2I.1 | Maximum output power for RedCap | Check if necesarry to update Tx TCs for eRedCap | China Unicom | RAN5#106 (Feb-25) | R5-245830 |  | 5 | 80% (+80%) | 80% (+80%) |  | 80%
TS 38.521-1: FR1 RF test cases - Rx
Receiver characteristics(Clause 7)
12 |  | 38.521-1 Rx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). |  | Ericsson | RAN5#106 (Feb-25) |  |  | 1 | 0% | 0% |  | 0%
13 | Y | 38.521-1 Rx | 7.3I.3 | Reference sensitivity power level for eRedCap | Update of diveristy characteristics intrdocution for eRedCap | China Unicom | RAN5#106 (Feb-25) | R5-245831 |  | 5 | 50% (+50%) | 50% (+50%) |  | 50%
TS 38.521-4: Demod/QSI reporting test cases
|  | 38.521-4 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 1 | 0% | 0% |  | 0%
14 |  | 38.521-4 | 3 | Definitions, symbols and abbreviations |  | Ericsson | RAN5#106 (Feb-25) | R5-245877 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
15 |  | 38.521-4 | 5.1.1.14 | Applicability of requirements for eRedCap |  | Ericsson | RAN5#106 (Feb-25) | R5-245876 | Update .x when defined in 38.101-4 | 1 | 100% (+100%) | 100% (+100%) |  | 100%
16 | Y | 38.521-4 | 5.2.1.1.2 | 1Rx FDD FR1 PDSCH performance for eRedCap |  | Ericsson | RAN5#106 (Feb-25) | R5-245873 |  | 1 | 75% (+75%) | 75% (+75%) |  | 75%
17 | Y | 38.521-4 | 5.2.1.2.2 | 1Rx TDD FR1 PDSCH performance for eRedCap |  | Ericsson | RAN5#106 (Feb-25) | R5-245874 |  | 1 | 75% (+75%) | 75% (+75%) |  | 75%
18 | Y | 38.521-4 | 5.2.2.1.23 | 2Rx FDD FR1 PDSCH performance for eRedCap |  | Ericsson | RAN5#106 (Feb-25) |  | Update .x when defined in 38.101-4 | 1 | 0% | 0% |  | 0%
19 | Y | 38.521-4 | 5.2.2.2.24 | 2Rx TDD FR1 PDSCH performance for eRedCap |  | Ericsson | RAN5#106 (Feb-25) |  | Update .x when defined in 38.101-4 | 1 | 0% | 0% |  | 0%
21 |  | 38.521-4 | 5.5.1 | FR1 single carrier requirements |  | Ericsson | RAN5#106 (Feb-25) |  | Align clause with 38.101-4 | 1 | 0% | 0% |  | 0%
22 | Y | 38.521-4 | 5.5.4 | FR1 Sustained downlink data rate performance for eRedCap |  | Ericsson | RAN5#106 (Feb-25) |  |  | 1 | 0% | 0% |  | 0%
23 |  | 38.521-4 | 6.1.1.7 | Applicability of requirements for eRedCap |  | Ericsson | RAN5#106 (Feb-25) |  |  | 1 | 0% | 0% |  | 0%
24 | Y | 38.521-4 | 6.2.1.1.1.2 | 1Rx FDD FR1 periodic CQI reporting under AWGN conditions for eRedCap |  | Ericsson | RAN5#106 (Feb-25) | R5-245875 |  | 1 | 75% (+75%) | 75% (+75%) |  | 75%
25 | Y | 38.521-4 | 6.2.1.2.1.2 | 1Rx TDD FR1 periodic CQI reporting under AWGN conditions for eRedCap |  | Ericsson | RAN5#106 (Feb-25) |  |  | 1 | 0% | 0% |  | 0%
26 | Y | 38.521-4 | 6.2.2.1.1.5 | 2Rx FDD FR1 periodic CQI reporting under AWGN conditions for eRedCap |  | Ericsson | RAN5#106 (Feb-25) |  |  | 1 | 0% | 0% |  | 0%
27 | Y | 38.521-4 | 6.2.2.2.1.6 | 2Rx TDD FR1 periodic CQI reporting under AWGN conditions for eRedCap |  | Ericsson | RAN5#106 (Feb-25) |  | req misplaced in 38.101-4 | 1 | 0% | 0% |  | 0%
28 | Y | 38.521-4 | [6.3.1.1.2] | [1Rx FDD Single PMI with 4TX TypeI-SinglePanel Codebook for eRedCap] |  |  | RAN5#106 (Feb-25) |  | RAN4 CR in Maasstricht | 1 | 0% | 0% |  | 0%
29 | Y | 38.521-4 | [6.3.1.2.2] | [1Rx TDD Single PMI with 4TX TypeI-SinglePanel Codebook for eRedCap] |  |  | RAN5#106 (Feb-25) |  | RAN4 CR in Maasstricht | 1 | 0% | 0% |  | 0%
30 | Y | 38.521-4 | [6.3.2.1.10] | [2Rx FDD Single PMI with 4TX TypeI-SinglePanel Codebook for eRedCap] |  |  | RAN5#106 (Feb-25) |  | RAN4 CR in Maasstricht | 1 | 0% | 0% |  | 0%
30 | Y | 38.521-4 | [6.3.2.2.10] | [2Rx TDD Single PMI with 4TX TypeI-SinglePanel Codebook for eRedCap] |  |  | RAN5#106 (Feb-25) |  | RAN4 CR in Maasstricht | 1 | 0% | 0% |  | 0%
31 | Y | 38.521-4 | Annex A | Reference measurement channels and Mapping of CQI Index to Information Bit payload | A.3, A.4 | Ericsson | RAN5#106 (Feb-25) | R5-245868 |  | 1 | 80% (+80%) | 80% (+80%) |  | 80%
32 |  | 38.521-4 | Annex B | Propagation conditions |  | Ericsson |  |  |  | 1 | 0% | 0% |  | 0%
33 |  | 38.521-4 | Annex F | Measurement uncertainties and test tolerances for FR1 |  |  |  | R5-245878 |  | 1 | 10% (+10%) | 10% (+10%) |  | 10%
34 |  | 38.521-4 | Annex G | Minimum test time | [5 empty] | 1 | 0% | 0% |  | 0%
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
35 |  | 38.522 | 4 | Test case conditions and selection criteria | Add test case applicability statements for the new test cases introduced for 38.521-1. |  |  | R5-246008 |  | 1 | 50% (+50%) | 50% (+50%) |  | 50%
36 |  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Add test case applicability statements for the new test cases introduced for 38.521-1. |  |  | R5-246008 |  | 1 | 50% (+50%) | 50% (+50%) |  | 50%
38 |  | 38.522 | 4.1.4 | Performance conformance test cases | Add test case applicability statements for the new test cases introduced for 38.521-4. |  | RAN5#109 (Nov-25) | R5-245919 |  | 1 | 30% (+30%) | 30% (+30%) |  | 30%
39 |  | 38.522 | 4.2 | RRM conformance test cases | Add test case applicability statements for the new test cases introduced for 38.533. |  |  |  | may no RRM TC needed | 1 | 0% | 0% |  | 0%
TS 38.533: RRM test cases
40 |  | 38.533 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 1 | 0% | 0% |  | 0%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
41 |  | 38.903 | 8 and attachment | Grouping and TT analysis of test cases defined in TS 38.533 | TT analysis grouping for RRM test cases |  |  |  |  | 1 | 0% | 0% |  | 0%
TR 38.905: Test Point analysis receiver and transmitter test cases
43 |  | 38.905 | 4 | Test coverage analysis | Add header, general text and table to list test point analysis for RedCap |  |  |  |  | 1 | 0% | 0% |  | 0%
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 1 | 0% | 0% |  | 0%
Idle Mode
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 1 | 0% | 0% |  | 0%
44 | Y | 38.523-1 | 6.1.2.34 | Cell Selection / eRedCap | TP1:[TS 38.331 clause 5.2.2.4.2, 5.2.2.5 ] WITH: UE supporting eRedCap and in NR RRC_IDLE state. WHEN: a cell fulfils the requirements for a suitable cell except that the UE supported Rx is barred by cellBarred-eRedCap1Rx or/and cellBarred-eRedCap2Rx in the SIB1. THEN: the UE considers the cell as barred and no camping on this cell can take place. TP2:[TS 38.331 clause 5.2.2.4.2, 5.2.2.5 ] WITH: UE supporting eRedCap and in NR RRC_IDLE state. WHEN: a cell fulfils the requirements for a suitable cell except intraFreqReselection-eRedCap in SIB1 is absent. THEN: the UE considers the cell as barred and no camping on this cell can take place. TP3:[TS 38.331 clause 5.2.2.4.2, 5.2.2.5 ] WITH: UE supporting eRedCap and in NR RRC_IDLE state. WHEN:a cell fulfils the requirements for a suitable cell. THEN: the UE considers the cell suitable and camps on it. | Huawei,Hisilicon | RAN5#106 (Feb-25) | R5-245628 |  | 1 | 85% (+85%) | 85% (+85%) |  | 85%
45 | Y | 38.523-1 | 6.1.2.35 | Cell Selection / eRedCap / emergency calls | TP1: WITH: UE supporting eRedCap and in NR RRC_IDLE state. WHEN: a cell fulfils the requirements for a suitable cell except that the UE supported Rx is barred by cellBarred-eRedCap1Rx or/and cellBarred-eRedCap2Rx in the SIB1, barringExempt-eRedCap is set to “true” in SIB1, and user initiates an Emergency call. THEN: the UE considers the cell as not barred and successfully completes the Emergency call. | Huawei,Hisilicon | RAN5#106 (Feb-25) | R5-245629 |  | 1 | 85% (+85%) | 85% (+85%) |  | 85%
46 | Y | 38.523-1 | 6.1.2.36 | Cell reselection / inter-frequency / eRedCap | TP1:[TS 38.331 clause 5.2.2.4.5, 5.2.2.5 ] WITH: UE supporting eRedCap and in NR RRC_IDLE state. WHEN: serving cell broadcasts SIB4 with interFreqCarrierFreqList-v1800 is absent, and inter-frequency neighbour cell fulfils reselection criteria. THEN: UE reselects the inter-frequency neighbour cell. TP1:[TS 38.331 clause 5.2.2.4.5, 5.2.2.5 ] WITH: UE supporting eRedCap and in NR RRC_IDLE state. WHEN: serving cell broadcasts SIB4 with eRedCapAccessAllowed is present in interFreqCarrierFreqList-v1800, and inter-frequency neighbour cell fulfils reselection criteria. THEN: UE reselects the inter-frequency neighbour cell. TP1:[TS ] WITH: UE supporting eRedCap and in NR RRC_IDLE state. WHEN: serving cell broadcasts SIB4 with eRedCapAccessAllowed is not present in interFreqCarrierFreqList-v1800, and inter-frequency neighbour cell fulfils reselection criteria. THEN: UE does not reselect the inter-frequency neighbour cell. | QC | RAN5#106 (Feb-25) |  |  | 1 | 0% | 0% |  | 0%
47 | Y | 38.523-1 | 6.1.2.37 | Cell Selection / eRedCap / halfDuplexRedCapAllowed | same as 6.1.2.29 |  | RAN5#106 (Feb-25) |  |  | 1 | 0% | 0% |  | 0%
48 | Y | 38.523-1 | 6.1.2.38 | Cell Selection / eRedCap / halfDuplexRedCapAllowed / MFBI | same as 6.1.2.30 |  | RAN5#106 (Feb-25) |  |  | 1 | 0% | 0% |  | 0%
Layer 2
49 | Y | 38.523-1 | 7.1.1.1.24 | Random access procedure / eRedCap UE identification / Msg3-based / CCCH1 | same as 7.1.1.1.16 with exception 1. only test in FR1 2. different LCID in step 5. TP1:[TS 38.321 clause 6.2.1] WITH: UE supporting eRedCap and in NR RRC_Inactive state and useFullResumeID is signalled in SIB1. WHEN: UE starts Random Access procedure. THEN: the UE uses the eRedCap specific LCID in Msg3. | QC | RAN5#106 (Feb-25) |  |  | 1 | 0% | 0% |  | 0%
50 | Y | 38.523-1 | 7.1.1.1.25 | Random access procedure / eRedCap UE identification / Msg1-based / Contention based / Msg3-based / CCCH / Correct handling of contention Resolution with large bandwidth | TP1:[TS 38.321 clause 5.1.1b,5.1.1c ] WITH: UE supporting eRedCap and in NR RRC_IDLE state . WHEN: UE starts Random Access procedure and there is a set of configured RA resources with eRedCap indication. THEN: the UE uses the eRedCap specific random access resource in Msg1. TP2:[TS 38.321 clause 5.1.1b,5.1.1c; TS 38.331 clause 6.3.2] WITH: UE supporting eRedCap and in NR RRC_IDLE state. WHEN: UE starts Random Access procedure and there is no set of configured RA resources with eRedCap indication and there is a set of configured RA resources with RedCap indication. THEN: the UE uses the RedCap specific random access resource in Msg1. TP3:[TS 38.321 clause 5.1.1b,5.1.1c ] WITH: UE supporting eRedCap and in NR RRC_IDLE state . WHEN: UE starts Random Access procedure. THEN: the UE uses the eRedCap specific LCID in Msg3 regardless whether (e)RedCap specific Random Access configuration is configured. TP4:[TS 38.321 clause 5.1.5 ] WITH: UE supporting eRedCap and in NR RRC_IDLE state and UE has send Msg3 including CCCH SDU. WHEN: UE detects that PDSCH transmission scheduled by PDCCH has a larger bandwidth than UE can receive or process per slot, and the PDCCH is addressed by TEMPORARY_C-RNTI. THEN: the UE stops ra-ContentionResolutionTimer and considers this Contention Resolution not successful. | Huawei,Hisilicon | RAN5#106 (Feb-25) | R5-245627 |  | 1 | 75% (+75%) | 75% (+75%) |  | 75%
51 | Y | 38.523-1 | 7.1.1.1.26 | Random access procedure / eRedCap UE identification / Msg1-based / Contention free | TP1:[TS 38.321 clause 5.1.1b ] WITH: UE supporting eRedCap and in NR RRC_CONNECTED state. WHEN: UE performs handover to the target cell and starts random Access procedure, and contention-free Random Access Resources have been provided for this Random Access procedure and eRedCap is applicable for the current Random Access procedure and there is one set of Random Access resources available that is only configured with eRedCap indication. THEN: the UE selects the set of Random Access resources configured with eRedCap indication for this Random Access procedure. TP2:[TS 38.321 clause 5.1.1b ] WITH: UE supporting eRedCap and in NR RRC_CONNECTED state. WHEN: UE performs handover to the target cell and starts random Access procedure, and contention-free Random Access Resources have been provided for this Random Access procedure and eRedCap is applicable for the current Random Access procedure and there is no set of Random Access resources available that is only configured with eRedCap indication and there is one set of Random Access resources available that is only configured with RedCap indication. THEN: the UE selects the set of Random Access resources configured with RedCap indication for this Random Access procedure. | Huawei,Hisilicon | RAN5#106 (Feb-25) |  |  | 1 | 0% | 0% |  | 0%
52 | Y | 38.523-1 | 7.1.1.1.27 | Random access procedure / eRedCap UE / SI request | same as 7.1.1.1.15 with exception 1. only test in FR1 |  | RAN5#106 (Feb-25) |  |  | 1 | 0% | 0% |  | 0%
53 | Y | 38.523-1 | 7.1.1.8.5 | Separate BWP / IDLE / eRedCap | same as 7.1.1.8.3 with exception 1. only test in FR1 2. different LCID in step 5. |  | RAN5#106 (Feb-25) |  |  | 1 | 0% | 0% |  | 0%
54 | Y | 38.523-1 | 7.1.1.8.6 | Separate BWP / RedCap-specific initial DL BWP without CORESET#0 / NCD-SSB /eRedCap | same as 7.1.1.8.4 with exception 1. only test in FR1 |  | RAN5#106 (Feb-25) |  |  | 1 | 0% | 0% |  | 0%
RRC
55 |  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 1 | 0% | 0% |  | 0%
NAS
56 | Y | 38.523-1 | 11.7.4 | eDRX / Inactive / CN-initiated paging / RAN-initiated paging | TP1:[TS 38.304 clause 7.1] WITH: UE in NR RRC_INACTIVE state and configured eDRX (TeDRX, RAN > 10.24s and TeDRX, CN > TeDRX, RAN) . WHEN: In an overlapped PH, during the overlapped part of CN configured PTW and RAN configured PTW , the network sends a CN-initiated Paging message within a paging occasion. THEN: UE goes to RRC_IDLE state and establishes an RRC connection. TP2:[TS 38.304 clause 7.1] WITH: UE in NR RRC_INACTIVE state and configured eDRX (TeDRX, RAN > 10.24s and TeDRX, CN > TeDRX, RAN) . WHEN: In an overlapped PH, during CN configured PTW and outside RAN configured PTW , the network sends a CN-initiated Paging message within a paging occasion. THEN: UE goes to RRC_IDLE state and establishes an RRC connection. TP3:[TS 38.304 clause 7.1] WITH: UE in NR RRC_INACTIVE state and configured eDRX (TeDRX, RAN > 10.24s and TeDRX, CN > TeDRX, RAN) . WHEN: In a non-overlapped PH, during CN configured PTW and outside RAN configured PTW , the network sends a CN-initiated Paging message within a paging occasion. THEN: UE goes to RRC_IDLE state and establishes an RRC connection. TP4:[TS 38.304 clause 7.1] WITH: UE in NR RRC_INACTIVE state and configured eDRX (TeDRX, RAN > 10.24s and TeDRX, CN > TeDRX, RAN). WHEN: In an overlapped PH, outside CN configured PTW and during RAN configured PTW , the network sends a RAN-initiated Paging message within a paging occasion. THEN: UE resumes RRC connection. TP5:[TS 38.304 clause 7.1] WITH: UE in NR RRC_INACTIVE state and configured eDRX (TeDRX, RAN > 10.24s and TeDRX, CN > TeDRX, RAN). WHEN: In a non-overlapped PH, outside CN configured PTW and during RAN configured PTW , the network sends a RAN-initiated Paging message within a paging occasion. THEN: UE resumes RRC connection. TP6:[TS 38.331 clause 6.2.2] WITH: UE in NR RRC_INACTIVE state and configured eDRX (TeDRX, RAN > 10.24s and TeDRX, CN > TeDRX, RAN) . WHEN: the network changes SIB1 to exclude eDRX-AllowedInactive-r18. THEN: UE applies the new system information and stops using extended DRX for RAN-initiated paging in RRC_INACTIVE state. | Huawei,Hisilicon | RAN5#106 (Feb-25) | R5-245661 |  | 1 | 85% (+85%) | 85% (+85%) |  | 85%
57 |  | 38.523-1 | 11.7.5 | eDRX / Inactive / RAN-initiated paging / Correct using ran-ExtendedPagingCycleConfig-r18 and ran-ExtendedPagingCycle-r17 | TP1:[TS 38.304 clause 7.4; TS 38.331 clause 6.2.2 ] WITH: UE in NR RRC_INACTIVE state and configured different eDRX in ran-ExtendedPagingCycleConfig-r18 and ran-ExtendedPagingCycle-r17. WHEN: UE camps on the NR Cell with eDRX-AllowedInactive-r18 signalling in SIB1 , the network sends a RAN-initiated Paging message within a paging occasion. THEN: UE resumes RRC connection. TP2:[TS 38.304 clause 7.4; TS 38.331 clause 6.2.2 ] WITH: UE in NR RRC_INACTIVE state and configured different eDRX in ran-ExtendedPagingCycleConfig-r18 and ran-ExtendedPagingCycle-r17. WHEN: UE moves to a NR Cell with only eDRX-AllowedInactive-r17 signalling in SIB1 , the network sends a RAN-initiated Paging message within a paging occasion. THEN: UE resumes RRC connection. | Huawei,Hisilicon | RAN5#106 (Feb-25) | R5-245626 |  | 1 | 85% (+85%) | 85% (+85%) |  | 85%
Legacy testcases adjustment
58 |  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 1 | 0% | 0% |  | 0%
TS 38.523-2: Applicability for Protocol test cases
59 |  | 38.523-2 | <Clause> | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | <Describe task> |  |  |  |  | 1 | 0% | 0% |  | 0%
60 |  | 38.523-2 | 4.1 | Protocol conformance test cases applicability | Add applicability for NR Redcap |  |  | R5-245662 | Test applicability of Legacy R16/R17 /R18 features for RedCap UE is out of scope of this WI, and will be tracked in the TEI maintainace WIs | 1 | 10% (+10%) | 10% (+10%) |  | 10%
60 |  | 38.523-2 | 4.2 | Protocol conformance test cases Applicability Condition | Add applicability for NR Redcap |  |  | R5-245662 | Test applicability of Legacy R16/R17 /R18 features for RedCap UE is out of scope of this WI, and will be tracked in the TEI maintainace WIs | 1 | 10% (+10%) | 10% (+10%) |  | 10%
TS 38.523-3: Protocol test suites (TTCN)
61 |  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 1 | 0% | 0% |  | 0%
TS 34.229-2: ICS for IMS test cases
62 |  | 34.229-2 | <Clause> | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | <Describe task> |  |  |  |  | 1 | 0% | 0% |  | 0%
63 |  | 34.229-2 | <Clause> | <Title of task> | <Describe task> |  |  |  |  | 1 | 0% | 0% |  | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.