## Cover sheet
3GPP TSG-RAN5 Meeting #104 | [8 empty] | R5-244947
Maastricht, Netherlands, 19th Aug 2024 - 23rd Aug 2024
Agenda Item: | 7.5.2
Source: | NIST
Title: | WP Protocol enhancements for Mission Critical Services for Rel-16 (MCPTT, MCVideo, MCData)
Work item code: | MCProtoc16_enh2MCPTT_eMCData2-ConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0-9
1. Introduction
The goal of this work item is to update the existing 36.579 family of Mission Critical Services test specifications to Rel-16. (UID = 970077)
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 100% (+18%) | 52 (+15) | 52 (+4)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
LTE (Mission Critical Services) |  | 100% (+18%) | 52 (+15) | 52 (+4)
Mission Critical Services |  | 100% (+18%) | 52 (+15) | 52 (+4)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | Mission Critical Services
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
LTE
Mission Critical Services
MC Common test environment | 36.579-1 | 100% (+12.5%) | 10 (+6) | 10 (+4) | 100% (+12.5%) | 10 (+6) | 10 (+4)
MCPTT UE test cases | 36.579-2 | 100% | 5 | 5 | 100% | 5 | 5
Applicability and ICS MC test cases | 36.579-4 | 100% (+30%) |  |  | 100% (+30%)
MC Test suite (TTCN) | 36.579-5 | 100% (+30%) |  |  | 100% (+30%)
MCVideo UE test cases | 36.579-6 | 100% | 7 | 7 | 100% | 7 | 7
MCData UE test cases | 36.579-7 | 100% (+30%) | 30 (+9) | 30 | 100% (+30%) | 30 (+9) | 30
5 References
[1] RP-222549 | New WID on Conformance Test Aspects - Protocol enhancements for Mission Critical Services for Rel-16 (MCPTT, MCVideo, MCData)
[2] R5-244948 | Revised WID Protocol enhancements for Mission Critical Services for Rel-16 (MCPTT, MCVideo, MCData)
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | Conformance Test Aspects - Protocol enhancements for Mission Critical Services for Rel-16 (MCPTT, MCVideo, MCData) | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | MCProtoc16_enh2MCPTT_eMCData2-ConTest
WP Scope: |  | Rel-16 Mission Critical Services Conformance test aspects with the 36.579 family of specifications
WP Resp: |  | Jason Kahn |  |  | jason.kahn@nist.gov | [5 empty] | WP item completion |  |  | LTE
TS Resp: |  | Jason Kahn |  |  | jason.kahn@nist.gov
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | LTE |  | Mission Critical Services
100% (+18%)
85 (-26)
72.4 (+11.7)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
Mission Critical Services
TS 36.579-1: MC Common test environment
|  | 36.579-1 | [7 empty] | 0
1 |  | 36.579-1 | 5.3.3 | MCX pre-established session establishment | Add new parameters for Rel-16 | NIST, MCC TF160 | RAN5#104 (Aug-24) | R5-233490, R5-234572 |  | 1 | 100% | 100% |  | 100%
2 | Y | 36.579-1 | 5.3.36 | UE initiated MCX functional alias status determination and subscription | New generic procedure | NIST | RAN5#104 (Aug-24) | R5-233293 |  | 1 | 100% | 100% |  | 100%
3 | Y | 36.579-1 | 5.3.37 | UE initiated MCX functional alias status change | New generic procedure | NIST | RAN5#104 (Aug-24) | R5-233293 |  | 1 | 100% | 100% |  | 100%
4 |  | 36.579-1 | 5.5.3.16 | MCS-Regroup Default | see 24.379 clause 16 | NIST, MCC TF160 | RAN5#104 (Aug-24) | R5-237437 |  | 1 | 100% | 100% |  | 100%
5 | Y | 36.579-1 | 5.3C.12 | CO MCData call establishment using a pre-established session | New generic procedure | NIST | RAN5#104 (Aug-24) | R5-235403 |  | 1 | 100% | 100% |  | 100%
6 | Y | 36.579-1 | 5.3C.13 | MCData CO call release keeping the pre-established session | New generic procedure | NIST | RAN5#104 (Aug-24) | R5-235404 |  | 1 | 100% | 100% |  | 100%
7 | Y | 36.579-1 | 5.3C.14 | Message Store Function Upload | New generic procedure | NIST | RAN5#104 (Aug-24) | R5-244953 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
8 | Y | 36.579-1 | 5.3C.15 | Message Store Function Delete | New generic procedure | NIST | RAN5#104 (Aug-24) | R5-244954 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
9 | Y | 36.579-1 | 5.3C.16 | Message Store Function Retrieve | New generic procedure | NIST | RAN5#104 (Aug-24) | R5-244955 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
10 | Y | 36.579-1 | 5.3C.17 | Message Store Function Post Request | New generic procedure | NIST | RAN5#104 (Aug-24) | R5-244956 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
11 | Y | 36.579-1 | 5.3C.18 | Message Store Function Put Request | New generic procedure | NIST | RAN5#104 (Aug-24) | R5-244957 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
12 | Y | 36.579-1 | 5.3C.19 | Message Store Function Post Notification | New generic procedure | NIST | RAN5#104 (Aug-24) | R5-244958 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
13 |  | 36.579-1 | 5.5.3.1 | SDP Message | Add new parameters for Rel-16 | NIST | RAN5#104 (Aug-24) | R5-233294, R5-233492 |  | 1 | 100% | 100% |  | 100%
14 |  | 36.579-1 | 5.5.3.2 | MCS Info Lists | Add new parameters for Rel-16 | NIST, MCC TF160 | RAN5#104 (Aug-24) | R5-233491, R5-244417 |  | 1 | 100% | 100% |  | 100%
15 |  | 36.579-1 | 5.5.3.3 | Resource-lists | Add new parameters for Rel-16 | NIST | RAN5#104 (Aug-24) | R5-234585, R5-240897 |  | 1 | 100% | 100% |  | 100%
16 |  | 36.579-1 | 5.5.3.4 | Location-info | Add new parameters for Rel-16 | NIST, MCC TF160 | RAN5#104 (Aug-24) | R5-240898, R5-244417 |  | 1 | 100% | 100% |  | 100%
17 |  | 36.579-1 | 5.5.3.5 | PIDF | Add new parameters for Rel-16 | NIST | RAN5#104 (Aug-24) | R5-233489 |  | 1 | 100% | 100% |  | 100%
18 |  | 36.579-1 | 5.5.3.8.5 | FD SIGNALLING PAYLOAD message from the UE |  | MCC TF160 | RAN5#104 (Aug-24) | R5-244417 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
19 |  | 36.579-1 | 5.5.3.8.6 | FD SIGNALLING PAYLOAD message from the SS |  | MCC TF160 | RAN5#104 (Aug-24) | R5-244417 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
20 |  | 36.579-1 | 5.5.4 | HTTP Messages |  | NIST | RAN5#104 (Aug-24) | R5-245671 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
21 |  | 36.579-1 | 5.5.6 | Default MCPTT media plane control messages and other information elements |  | MCC TF160 | RAN5#104 (Aug-24) | R5-244417 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
22 |  | 36.579-1 | 5.5.8.3 | MCPTT User Profile | Add new parameters for Rel-16 | NIST | RAN5#104 (Aug-24) | R5-231917, R5-236601 | New for RAN5#98 | 1 | 100% | 100% |  | 100%
23 |  | 36.579-1 | 5.5.8.4 | MCPTT Service Configuration |  | MCC TF160 | RAN5#104 (Aug-24) | R5-244417 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
24 |  | 36.579-1 | 5.5.8.8 | MCVideo Service Configuration |  | MCC TF160 | RAN5#104 (Aug-24) | R5-244417 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
25 |  | 36.579-1 | 5.5.8.12 | MCData Service Configuration |  | MCC TF160 | RAN5#104 (Aug-24) | R5-244417 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
26 |  | 36.579-1 | 5.5.8.11 | MCData User Profile | Add new parameters for Rel-16 | NIST, MCC TF160 | RAN5#104 (Aug-24) | R5-233488, R5-244960 |  | 1 | 100% | 100% |  | 100%
27 |  | 36.579-1 | 5.5.8.12 | MCData Service Configuration | Add new parameters for Rel-16 | NIST, MCC TF160 | RAN5#104 (Aug-24) | R5-233488 |  | 1 | 100% | 100% |  | 100%
28 |  | 36.579-1 | 5.5.11 | Default MCVideo Transmission Control Messages and other Information Elements |  | MCC TF160 | RAN5#104 (Aug-24) | R5-244417 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
29 |  | 36.579-7 | 5.5.15 | Default MCData call control messages and other information elements |  | NIST | RAN5#104 (Aug-24) | R5-244961 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
TS 36.579-2: MCPTT UE test cases
|  | 36.579-2 | [7 empty] | 0
30 | Y | 36.579-2 | 5.9 | Configuration / Functional Alias / Location based functional alias status change | 24.379 9A.2.1.4 | NIST, MCC TF160 | RAN5#104 (Aug-24) | R5-231918, R5-233829 |  | 1 | 100% | 100% |  | 100%
31 | Y | 36.579-2 | 5.1 | Configuration / Rules based affiliation status change | 24.379 9.2.1.7 | NIST, MCC TF160 | RAN5#104 (Aug-24) | R5-236603, R5-243274, R5-244418 |  | 1 | 100% | 100% |  | 100%
32 |  | 36.579-2 | 6.5 | Group regroup using a preconfigured group | New sub-clause header | NIST, MCC TF160 | RAN5#104 (Aug-24) | R5-237438 |  | 0 | 100% | 100% |  | 100%
33 | Y | 36.579-2 | 6.5.1 | On-network / Group regroup using a preconfigured group / Requesting a group regroup using a preconfigured group / Removing a regroup using preconfigured group / Client Originated (CO) | 24.379 16.2.1.1, 16.2.1.2, Annex F.7 | NIST, MCC TF160 | RAN5#104 (Aug-24) | R5-237438 |  | 1 | 100% | 100% |  | 100%
34 | Y | 36.579-2 | 6.5.2 | On-network / Group regroup using a preconfigured group / Receiving a notification of creation of a regroup using preconfigured group / Receiving notification of removal of a regroup using preconfigured group / Client Terminated (CT) | 24.379 16.2.1.3, 16.2.1.4, Annex F.7 | NIST, MCC TF160 | RAN5#104 (Aug-24) | R5-237439 |  | 1 | 100% | 100% |  | 100%
35 |  | 36.579-2 | 6.5.3 | On-network / User regroup using a preconfigured group / Requesting a user regroup using a preconfigured group / Removing a regroup using preconfigured group / Client Originated (CO) | 24.379 16.3.1.1, 16.3.1.2, Annex F.7 | NIST, MCC TF160 | RAN5#104 (Aug-24) | R5-237440 |  | 1 | 100% | 100% |  | 100%
36 | Y | 36.579-2 | 6.5.4 | On-network / User regroup using a preconfigured group / Creating a user regroup using preconfigured group / Removing a user regroup using preconfigured group / Client Terminated (CT) | 24.379 16.3.1.3, 16.3.1.4, Annex F.7 | NIST, MCC TF160 | RAN5#104 (Aug-24) | R5-237441 |  | 1 | 100% | 100% |  | 100%
TS 36.579-4: Applicability and ICS MC test cases
|  | 36.579-4 | [7 empty] | 0
37 |  | 36.579-4 | 4 | Recommended Test Case Applicability | Add test case applicability statements for the new test cases introduced in 37.579-x. | NIST, MCC TF160, Ericsson | RAN5#104 (Aug-24) | R5-231919, R5-234573, R5-237442, R5-240901, R5-244419, R5-244587, R5-245672, R5-245673, R5-245708 |  | 0.1 | 100% (+30%) | 100% (+30%) |  | 100%
38 |  | 36.579-4 | A.4 | ICS proforma tables | Edits for the new specs | NIST | RAN5#104 (Aug-24) | R5-240901 |  | 0.1 | 100% (+30%) | 100% (+30%) |  | 100%
TS 36.579-5: MC Test suite (TTCN)
|  | 36.579-5 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 0
39 |  | 36.579-5 | 2 | References | Edits for the new specs | NIST, MCC TF160 | RAN5#104 (Aug-24) | R5-245674 |  | 0 | 100% (+30%) | 100% (+30%) |  | 100%
40 |  | 36.579-5 | 7 | Test methods and design considerations | TBD | NIST, MCC TF160 | RAN5#104 (Aug-24) | R5-245674 |  | 0.1 | 100% (+30%) | 100% (+30%) |  | 100%
41 |  | 36.579-5 | 9 | IXIT Proforma | New PIXITs | NIST, MCC TF160 | RAN5#104 (Aug-24) | R5-240902, R5-245674 |  | 0.1 | 100% (+30%) | 100% (+30%) |  | 100%
TS 36.579-6: MC Video UE test cases
|  | 36.579-6 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 0
42 | Y | 36.579-6 | 6.1.1.14 | On-network / On-demand Pre-arranged Group Call / Re-join procedure / Client Originated (CO) | 24.281 9.2.1.2.4.1 | NIST | RAN5#104 (Aug-24) | R5-241595, R5-242311 |  | 1 | 100% | 100% |  | 100%
43 | Y | 36.579-6 | 6.4.2 | On-network / Video pull call / One-to-one video pull call / Client Terminated (CT) | 24.281 12.2.2.2 | NIST, MCC TF160 | RAN5#104 (Aug-24) | R5-231920, R5-233830 |  | 1 | 100% | 100% |  | 100%
44 | Y | 36.579-6 | 6.5.2 | On-network / Video push call / One-to-server video push call / Client Originated (CO) | 24.281 13.2.2.4, 13.2.2.5 | NIST | RAN5#104 (Aug-24) | R5-241596 |  | 1 | 100% | 100% |  | 100%
45 | Y | 36.579-6 | 6.7.3 | On-network / On-demand ambient viewing call / Locally initiated ambient viewing call / Client Originated (CO) | 24.281 15.2.1.1 (locally initiated) | NIST | RAN5#104 (Aug-24) | R5-237443 |  | 1 | 100% | 100% |  | 100%
46 | Y | 36.579-6 | 6.7.4 | On-network / On-demand ambient viewing call / Locally initiated ambient viewing call / Client Terminated (CT) | 24.282 15.2.1.2 (locally initiated) | NIST | RAN5#104 (Aug-24) | R5-237444 |  | 1 | 100% | 100% |  | 100%
47 |  | 36.579-6 | 6.9 | Location | New sub-clause header | NIST | RAN5#104 (Aug-24) | R5-240909 |  | 0 | 100% | 100% |  | 100%
48 | Y | 36.579-6 | 6.9.1 | On-network / Location/ Location Information Request | 24.281 18.3.2, 18.3.3 | NIST | RAN5#104 (Aug-24) | R5-240909, R5-242312, R5-243271 |  | 1 | 100% | 100% |  | 100%
49 | Y | 36.579-6 | 6.9.2 | On-network / Location / Report triggering | 24.281 18.3.2, 18.3.4 | NIST | RAN5#104 (Aug-24) | R5-240910, R5-243271 |  | 1 | 100% | 100% |  | 100%
TS 36.579-7: MCData UE test cases
|  | 36.579-7 | [7 empty] | 0
50 | Y | 36.579-7 | 5.5 | Configuration / Pre-established Session Establishment / Pre-established Session Release | 18.3.2.1 MCData client procedures 18.3.3.1.1 MCData client initiated release 18.3.3.2.1 MCData client initiated release | TBD | RAN5#104 (Aug-24) | R5-232594 |  | 1 | 100% | 100% |  | 100%
51 | Y | 36.579-7 | 5.6 | Configuration / Download CSK | 24.282 7.2.5 (also see 36.579-2 5.6) | NIST, MCC TF160 | RAN5#104 (Aug-24) | R5-232595, R5-233831 |  | 1 | 100% | 100% |  | 100%
52 | Y | 36.579-7 | 5.7 | Configuration / Functional Alias / Functional alias status determination / Activate functional alias / Deactivate functional alias | 22.2.1.2 22.2.1.3 | NIST, MCC TF160 | RAN5#104 (Aug-24) | R5-233493, R5-233832 |  | 1 | 100% | 100% |  | 100%
53 | Y | 36.579-7 | 5.8 | Configuration / Rules based affiliation status change | 8.2.6 | TBD | RAN5#104 (Aug-24) | R5-243572 |  | 1 | 100% | 100% |  | 100%
54 | Y | 36.579-7 | 5.9 | Configuration / Functional Alias / Location based functional alias status change | 24.282 22.2.1.4 | TBD | RAN5#104 (Aug-24) | R5-243573 |  | 1 | 100% | 100% |  | 100%
55 | Y | 36.579-7 | 6.1.13 | On-network / Short Data Service (SDS) / Standalone SDS Using Media Plane / One-to-one Standalone SDS / Pre-established session / Client Originated (CO) | 9.2.5.2.1.1, 9.2.5.4.1.1 | NIST | RAN5#104 (Aug-24) | R5-235405 |  | 1 | 100% | 100% |  | 100%
56 | Y | 36.579-7 | 6.1.14 | On-network / Short Data Service (SDS) / Standalone SDS Using Media Plane / One-to-one Standalone SDS / Pre-established session / Client Terminated (CT) | 9.2.5.2.1.2, 9.2.5.4.1.2 | NIST | RAN5#104 (Aug-24) | R5-235406 |  | 1 | 100% | 100% |  | 100%
57 | Y | 36.579-7 | 6.1.15 | On-network / Short Data Service (SDS) / SDS Session / One-to-one SDS Session / Pre-established session / Client Originated (CO) | 9.2.5.2.1.1, 9.2.5.4.1.1 | NIST | RAN5#104 (Aug-24) | R5-235407 |  | 1 | 100% | 100% |  | 100%
58 | Y | 36.579-7 | 6.1.16 | On-network / Short Data Service (SDS) / SDS Session / One-to-one SDS Session / Pre-established session / Client Terminated (CT) | 9.2.5.2.1.2, 9.2.5.4.1.2 | NIST | RAN5#104 (Aug-24) | R5-235408 |  | 1 | 100% | 100% |  | 100%
59 | Y | 36.579-7 | 6.1.17 | On-network / Short Data Service (SDS) / SDS Session / One-to-one SDS Session / Pre-established session / Client Terminated (CT) | 9.2.5.2.1.2, 9.2.5.4.1.2 | NIST | RAN5#104 (Aug-24) | R5-235409 |  | 1 | 100% | 100% |  | 100%
60 | Y | 36.579-7 | 6.1.18 | On-network / Short Data Service (SDS) / SDS Session / One-to-one SDS Session / Pre-established session / Client Terminated (CT) | 9.2.5.2.1.2, 9.2.5.4.1.2 | NIST | RAN5#104 (Aug-24) | R5-235410 |  | 1 | 100% | 100% |  | 100%
61 | Y | 36.579-7 | 6.1.19 | On-network / Short Data Service (SDS) / SDS Session / Group SDS Session / Pre-established session / Client Originated (CO) | 9.2.5.3.1.1, 9.2.5.4.1.1 | NIST | RAN5#104 (Aug-24) | R5-235411 |  | 1 | 100% | 100% |  | 100%
62 | Y | 36.579-7 | 6.1.20 | On-network / Short Data Service (SDS) / SDS Session / Group SDS Session / Pre-established session / Client Terminated (CT) | 9.2.5.3.1.2, 9.2.5.4.1.2 | NIST | RAN5#104 (Aug-24) | R5-235412 |  | 1 | 100% | 100% |  | 100%
63 | Y | 36.579-7 | 6.1.21 | On-network / Short Data Service (SDS) / Standalone SDS using signalling control plane / One-to-one Standalone SDS / Active functional alias / Client Originated (CO) | 9.2.2.2.1 6.2.2.1 6.2.4.1 12.2.1.2 | NIST | RAN5#104 (Aug-24) | R5-234583 |  | 1 | 100% | 100% |  | 100%
64 | Y | 36.579-7 | 6.1.22 | On-network / Short Data Service (SDS) / Standalone SDS Using Media Plane / One-to-one Standalone SDS / Active functional alias / Client Originated (CO) | TS 24.282, clauses 9.2.3.2.3, 9.2.3.2.1, 13.2.2.2.2.1, 12.2.1.2, TS 24.582 clauses 6.1.1.2.1, 6.1.1.2.2, 6.1.1.2.3, 6.1.1.2.4 | NIST | RAN5#104 (Aug-24) | R5-235413 |  | 1 | 100% | 100% |  | 100%
65 | Y | 36.579-7 | 6.2.14 | On-network / File Distribution (FD) / FD Using HTTP / One-to-one Standalone FD / Non-Mandatory Download / Active functional alias / Client Originated (CO) | TS 24.282, clauses 10.2.1.3.2, 10.2.2.1, 10.2.4.2.1, 12.2.1.2 | NIST | RAN5#104 (Aug-24) | R5-237445 |  | 1 | 100% | 100% |  | 100%
66 | Y | 36.579-7 | 6.2.15 | On-network / File Distribution (FD) / FD Using Media Plane / One-to-one Standalone FD / Active Functional Alias / Client Originated (CO) | TS 24.282, clauses 10.2.5.2.3, 6.2.2.3, 12.2.1.2, TS 24.582 clause 7.1.2.1 | NIST | RAN5#104 (Aug-24) | R5-236611 |  | 1 | 100% | 100% |  | 100%
67 |  | 36.579-7 | 6.4 | Emergency Alert | New sub-clause header | NIST | RAN5#104 (Aug-24) | R5-240903 |  | 0 | 100% | 100% |  | 100%
68 | Y | 36.579-7 | 6.4.1 | On-network / Emergency Alert / Cancel Emergency Alert / Client Originated (CO) | 16.2.1.1 Emergency alert origination; 16.2.1.2 Emergency alert cancellation | NIST | RAN5#104 (Aug-24) | R5-241593 |  | 1 | 100% | 100% |  | 100%
69 | Y | 36.579-7 | 6.4.2 | On-network / Emergency Alert / Client Terminated (CT) | 16.2.1.3 MCData client receives an MCData emergency alert or communication notification | NIST | RAN5#104 (Aug-24) | R5-241594 |  | 1 | 100% | 100% |  | 100%
70 |  | 36.579-7 | 6.5 | Location | New sub-clause header | NIST | RAN5#104 (Aug-24) | R5-243570 |  | 0 | 100% | 100% |  | 100%
71 | Y | 36.579-7 | 6.5.1 | On-network / Location / Event Triggered Location Information report | 17.3.2 Location reporting configuration 17.3.4.1 Report triggering 17.3.4.2 Sending location information report | NIST | RAN5#104 (Aug-24) | R5-243570 |  | 1 | 100% | 100% |  | 100%
72 | Y | 36.579-7 | 6.5.2 | On-network / Location/ On-demand Location Information Request | 17.3.2 Location reporting configuration 17.3.3 Location information request 17.3.4.2 Sending location information report | NIST | RAN5#104 (Aug-24) | R5-243571 |  | 1 | 100% | 100% |  | 100%
73 |  | 36.579-7 | 6.6 | MBMS transmission usage | New sub-clause header | NIST | RAN5#104 (Aug-24) | R5-244964 |  | 0 | 100% (+100%) | 100% (+100%) |  | 100%
74 | Y | 36.579-7 | 6.6.1 | On-network / MBMS / MBMS Bearer Announcement / MBMS Bearer Listening Status / Transition to MBMS from Unicast / Transition to Unicast from MBMS | 24.282 = 19.3.3.2 Sending the MBMS bearer listening or suspension status report 24.582 = 6.5.2.1 Handling the MSRP connection 6.5.2.2 Receiving Map Group To Bearer and Unmap Group To Bearer 6.5.2.3 Receiving media packets | NIST | RAN5#104 (Aug-24) | R5-244964 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
75 |  | 36.579-7 | 6.7 | IP Connectivity | New sub-clause header | NIST | RAN5#104 (Aug-24) | R5-244965 |  | 0 | 100% (+100%) | 100% (+100%) |  | 100%
76 | Y | 36.579-7 | 6.7.1 | On-network / IP Connectivity / Client Originated (CO) | 20.2.1 | NIST | RAN5#104 (Aug-24) | R5-244965 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
77 | Y | 36.579-7 | 6.7.2 | On-network / IP Connectivity / Client Terminated (CT) | 20.2.2 | NIST | RAN5#104 (Aug-24) | R5-244966 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
78 |  | 36.579-7 | 6.8 | MCData Message Store | New sub-clause header | NIST | RAN5#104 (Aug-24) | R5-245675 |  | 0 | 100% (+100%) | 100% (+100%) |  | 100%
79 | Y | 36.579-7 | 6.8.1 | On-network / MCData Message Store / Objects / Object upload / Object search / Update Object / Object retrieval / Delete stored object | 21.2.15 Object(s) upload procedure 21.2.2 Object search procedure 21.2.3 Update object(s) procedure 21.2.1 Object retrieval procedure 21.2.4 Delete stored object(s) procedure | NIST, MCC TF160 | RAN5#104 (Aug-24) | R5-245675 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
80 | Y | 36.579-7 | 6.8.2 | On-network / MCData Message Store / Folders / Create a folder / Object and folder copy / List subfolders of a given folder / Folder search / Moving object(s) and folder(s) / Deleting a folder | 21.2.8 Create a folder procedure 21.2.6 Object and folder copy procedure 21.2.18 List subfolders of a given folder 21.2.11 Folder search procedure 21.2.10 Moving object(s) and folder(s) procedure 21.2.7 Deleting a folder procedure | NIST, MCC TF160 | RAN5#104 (Aug-24) | R5-245676 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
81 | Y | 36.579-7 | 6.8.3 | On-network / MCData Message Store / Subscription / Create a subscription to notifications / Update a subscription to notifications / Delete a subscription to notifications | 21.2.12A Create a subscription to notifications 21.2.14A Update a subscription to notifications 21.2.13A Delete a subscription to notifications | NIST, MCC TF160 | RAN5#104 (Aug-24) | R5-245677 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
82 | Y | 36.579-7 | 6.8.4 | On-network / MCData Message Store / Synchronization / Synchronization notifications / Search-based synchronization | 21.2.16 Synchronization notifications 21.2.17 Search-based synchronization | NIST, MCC TF160 | RAN5#104 (Aug-24) | R5-245678 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
83 |  | 36.579-7 | 7.3 | Emergency Alert | New sub-clause header | NIST | RAN5#104 (Aug-24) | R5-244971 |  | 0 | 100% (+100%) | 100% (+100%) |  | 100%
84 | Y | 36.579-7 | 7.3.1 | Off-network / Emergency Alert / Emergency Alert Retransmission / Cancel Emergency Alert / Client Originated (CO) | 16.3.3.1 Originating user sending emergency alert 16.3.3.2 Emergency alert retransmission 16.3.3.5 Originating user cancels emergency alert | NIST | RAN5#104 (Aug-24) | R5-244971 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
85 | Y | 36.579-7 | 7.3.2 | Off-network / Emergency Alert / Emergency Alert Retransmission / Cancel Emergency Alert / Client Terminated (CT) | 16.3.3.3 Terminating user receiving emergency alert 16.3.3.4 Terminating user receiving retransmitted emergency alert 16.3.3.6 Terminating user receives GROUP EMERGENCY ALERT CANCEL message | NIST | RAN5#104 (Aug-24) | R5-244972 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.