## Cover sheet
EXAMPLE FRAMEWORK
3GPP TSG-RAN WG5 meeting #105
Orlando, Florida November 18-22, 2024
Agenda Item:
Source: | Apple
Title: | Internal WP for Incorporation of Rel-18 NR RF FR2 Enhanced Test Methods and Rel-17 Maintainence
Work item code: | Not Applicable
Release: | Rel-18/Rel-17 Maintainence
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The objective of this work item is to incorporate the outcomes of the FR2 Enhanced Test Methods into RAN5 specifications.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 0% | - | -
Completion Compensation |  | -
| Note 1: | No new tests are added as part of this WP. The count refers to any additional tests on which impact due to the FR2 Enhanced Test Methods was identified
5 References
[1] RP-210363 | 5GS UE Conformance Test Aspects
[2] RP-212304 | Study on FR2 RF Enhanced Test Methods
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | Incorporation of Rel-18 NR RF FR2 Enhanced Test Methods and Rel-17 Maintainence | [12 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | Not Applicable
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item UE Conformance Test Aspects for FR2 RF Enhanced Test Methods comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID).
WP Resp: |  | Ashwin Mohan, Apple |  |  | ashwin_mohan@apple.com | [7 empty] | WP item completion |  |  | SA Option 2 (SA NR) | NSA Option 3
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is Pending RAN4? | TS/area | Impacted Clause | Impacted test title | Task (FR2 test methods enhancements) | Company | Target | Release Applicability for Test Method/Enhancement in Column F | Associated WIC to bring in Contribution (Contributors to check and re-confirm) | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR2 | FR2
[16 empty] | 0% | 0%
[9 empty] | NR_RF_FR2_req_Ph3-UEConTest NR_HST_FR2_enh-UEConTest NR_FR2_multiRX_DL-UEConTest | [6 empty] | 0 | 0
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). |  |  |  |  | TEI15_test, 5GS_NR_LTE-UEConTest |  |  | TBD
3 |  | 38.508-1 | 5 | Test environments for RF test | New testing methodologies needs to be added also to section 5.1.1.3 and associated sub-clauses |  |  |  | NR_RF_FR2_req_Ph3-UEConTest NR_HST_FR2_enh-UEConTest NR_FR2_multiRX_DL-UEConTest |  | NF based test methods are currently deprioritized and can be revisited in Release 18 -> previous agreement | 0.1 | 0% | 0% |  | 0% | 0%
3 |  | 38.508-1 | Annex A | Connection Diagrams | New testing methodologies related Annex A (for example connection diagram updates) |  |  |  | NR_RF_FR2_req_Ph3-UEConTest NR_HST_FR2_enh-UEConTest NR_FR2_multiRX_DL-UEConTest |  | Add specific line items on open issues for each item | 0.1 | 0% | 0% |  | 0% | 0%
|  | 38.508-1 | Annex B |  | Will require updates if new test methodologies are finally accepted after analysis and discussion | Keysight |  |  | TEI15_Test |  |  |  | 100% | 100% |  | 100% | 100%
NR RF/RRM
TS 38.521-2: FR2 RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [7 empty] | TBD
|  | 38.521-2 | 3 | Definitions, symbols and abbreviations | 3 subsections which define definitions, symbols and abbreviations respectively |  |  |  | TEI15_test, 5GS_NR_LTE-UEConTest |  |  | 0.5 | 0% | 0% |  | 0% | 0%
|  | 38.521-2 | 4 | General | Incorporate applicability statement from TR 38.884 for the enhanced FR2 RF test methods |  |  |  | TEI15_test, 5GS_NR_LTE-UEConTest |  |  | 0.5 | 0% | 0% |  | 0% | 0%
|  | 38.521-2 | 5 | Operating bands and Channel arrangement | Frequency Separation Classes, Intra-band and Inter-band CA configuration updates |  |  |  | TEI15_test, 5GS_NR_LTE-UEConTest |  |  | 0.5 | 0% | 0% |  | 0% | 0%
|  | 38.521-2 | Annex A | Measurement channels | Pending review of new test methodologies and any changes to the test parameters brought in by the same. *NOTE* |  |  |  | TEI15_test, 5GS_NR_LTE-UEConTest |  |  | 0.5 | 0% | 0% |  | 0% | 0%
|  | 38.521-2 | Annex B | Propagation conditions | Pending review of new test methodologies and any changes to the test parameters brought in by the same. *NOTE* |  |  |  | TEI15_test, 5GS_NR_LTE-UEConTest |  |  | 0.5 | 0% | 0% |  | 0% | 0%
|  | 38.521-2 | Annex C | Downlink physical channels | Pending review of new test methodologies and any changes to the test parameters brought in by the same. *NOTE* |  |  |  | TEI15_test, 5GS_NR_LTE-UEConTest |  |  | 0.5 | 0% | 0% |  | 0% | 0%
|  | 38.521-2 | Annex D | Interfering signals | Define any updates to characteristics of the interfering signal updates in Rel-16 NR RF FR2 tests |  |  |  | TEI15_test, 5GS_NR_LTE-UEConTest |  |  | 0.5 | 0% | 0% |  | 0% | 0%
|  | 38.521-2 | Annex E | Global In-Channel TX-Test | - Testability updates pertaining to UL-256 QAM EVM - Pending review of new test methodologies and any changes to the test parameters brought in by the same. |  |  |  | NR_RF_FR2_req_Ph3-UEConTest NR_HST_FR2_enh-UEConTest |  | Add specific line items on open issues for each item | 0.5 | 0% | 0% |  | 0% | 0%
|  | 38.521-2 | Annex F | Measurement uncertainties and Test Tolerances | Track MU/TT related issues and outcomes for new test metodologies |  |  |  | NR_RF_FR2_req_Ph3-UEConTest NR_HST_FR2_enh-UEConTest NR_FR2_multiRX_DL-UEConTest |  | Add specific line items on open issues for each item | 1 | 0% | 0% |  | 0% | 0%
|  | 38.521-2 | Annex G | Uplink Physical Channels | TBD | [6 empty] | 0.5 | 0% | 0% |  | 0% | 0%
|  | 38.521-2 | Annex H | Statistical Testing | TBD | [6 empty] | 0.5 | 0% | 0% |  | 0% | 0%
|  | 38.521-2 | Annex J |  | Will require updates if new test methodologies are eventually accepted after analysis and discussion |  |  |  | NR_FR2_multiRX_DL-UEConTest NR_HST_FR2_enh-UEConTest |  | Add specific line items on open issues for each item | 0 | 0% | 0% |  | 0% | 0%
|  | 38.521-2 | Annex K | EIRP, TRP, EIS Measurement Procedures | Multi-Rx Sph Coverage Measurement Procedures |  |  |  | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | Add specific line items on open issues for each item | 0.5 | 0% | 0% |  | 0% | 0%
|  | 38.521-2 | Annex M | Measurement Grids | Measurement Grids for Multi-Rx Meausrement Procedures |  |  |  | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | MU impact assessment requires TE vendor expertise | 0.5 | 0% | 0% |  | 0% | 0%
TS 38.521-2: FR2 RF test cases - Tx
|  | 38.521-2 Tx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [7 empty] | TBD
|  | 38.521-2 Tx | 6.3.1 | Minimum output power | High DL Power/ Low UL Power *NOTE 2* |  |  |  | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | See NOTE2. Initial Evaluation completed in Release 17 and further details are part of future study/release | 1 | 0% | 0% |  | 0% | 0%
|  | 38.521-2 Tx | 6.3.2 | Transmit OFF power | High DL Power/ Low UL Power *NOTE 2* |  |  |  | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | See NOTE2. Initial Evaluation completed in Release 17 and further details are part of future study/release | 1 | 0% | 0% |  | 0% | 0%
|  | 38.521-2 Tx | 6.3.3 | Transmit ON/OFF time mask | High DL Power/ Low UL Power *NOTE 2* |  |  |  | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | See NOTE2. Initial Evaluation completed in Release 17 and further details are part of future study/release | 1 | 0% | 0% |  | 0% | 0%
|  | 38.521-2 Tx | 6.5.1 | Occupied bandwidth | High DL Power/ Low UL Power *NOTE 2* |  |  |  | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | See NOTE2. Initial Evaluation completed in Release 17 and further details are part of future study/release | 0 | 0% | 0% |  | 0% | 0%
|  | 38.521-2 Tx | 6.5.2.3 | Adjacent channel leakage ratio | High DL Power/ Low UL Power *NOTE 2* |  |  |  | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | See NOTE2. Initial Evaluation completed in Release 17 and further details are part of future study/release | 1 | 0% | 0% |  | 0% | 0%
|  | 38.521-2 Tx | 6.5.3.2 | Additional spurious emissions | High DL Power/ Low UL Power *NOTE 2* |  |  |  | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | See NOTE2. Initial Evaluation completed in Release 17 and further details are part of future study/release | 0 | 0% | 0% |  | 0% | 0%
|  | 38.521-2 Tx | 6.4.1 | Frequency Error | UL Demod Measurement Enhancements |  |  |  | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  |  | 1 | 0% | 0% |  | 0% | 0%
|  | 38.521-2 Tx | 6.4.2 | Transmit Modulation Quality | UL Demod Measurement Enhancements |  |  |  | NR_RF_FR2_req_enh2-UEConTest/TEI16_Test |  | NOTE 1 | 1 | 0% | 0% |  | 0% | 0%
|  | 38.521-2 Tx | 6.4.2.1 | Error Vector Magnitude | UL Demod Measurement Enhancements, Details related to AP#96e.29 and AP#96e.30 (see Note Below) will also be covered in this Work Plan |  |  |  | NR_RF_FR2_req_enh2-UEConTest/TEI16_Test |  | NOTE 1 | 1 | 0% | 0% |  | 0% | 0%
|  | 38.521-2 Tx | 6.4.2.2 | Carrier Leakage | UL Demod Measurement Enhancements |  |  |  | NR_RF_FR2_req_enh2-UEConTest/TEI16_Test |  | NOTE 1 | 1 | 0% | 0% |  | 0% | 0%
|  | 38.521-2 Tx | 6.4.2.3 | In-band Emissions | UL Demod Measurement Enhancements |  |  |  | NR_RF_FR2_req_enh2-UEConTest/TEI16_Test |  | NOTE 1 | 1 | 0% | 0% |  | 0% | 0%
|  | 38.521-2 Tx | 6.4.2.4 | EVM equalizer spectrum flatness | UL Demod Measurement Enhancements, Details related to AP#96e.29 and AP#96e.30 (see Note Below) will also be covered in this Work Plan |  |  |  | NR_RF_FR2_req_enh2-UEConTest/TEI16_Test |  | NOTE 1 | 1 | 0% | 0% |  | 0% | 0%
|  | 38.521-2 Tx | 6.4.2.5 | EVM spectral flatness for pi/2 BPSK modulation | UL Demod Measurement Enhancements, Details related to AP#96e.29 and AP#96e.30 (see Note Below) will also be covered in this Work Plan |  |  |  | NR_RF_FR2_req_enh2-UEConTest/TEI16_Test |  | NOTE 1 | 1 | 0% | 0% |  | 0% | 0%
|  | 38.521-2 Tx | 6.6.3 | Beam Correspondence - Initial Access (PC3) | - Measurement Setup with Full Degrees of Freedom for AoA1 with Fixed Angular Offset(s) Between AoA1 and AoA2 Chosen as Rel-18 Baseline. - Absolute Probe Locations - Minimum and Maximum Angular Separation between Probes - Impact of probe locations and 3D scans on DL directions Full 3D scan can be performed in various ways. Optimal ways to perform the rotation were studied. AoA1-AoA2 directionality vector |  |  |  | NR_FR2_multiRX_DL-UEConTest
| Yes | 38.521-2 Tx | 6.6.3 | Beam Correspondence - Initial Access (PC6) | Test Methodology to cover |  |  |  | NR_RF_FR2_req_Ph3-UEConTest |  | RAN4 Analysis is Pending as no methodology has been evaluated for PC6 Ues
|  | 38.521-2 Tx | 6.4.2.1 | Error Vector Magnitude | Minimum conformance updates related to UL-256 QAM requirements in Rel-18. FR2 EVM testability issues | [5 empty] | Track Global In-Channel test updates related issues for UL-256 QAM EVM
Equivalent CA tests to be analyzed for applicability here
TBD |  | 38.521-2 Annex |  |  | Incorporation of 6x2 Measurement Grids in TS 38.521-2 |  |  |  | NR_RF_FR2_req_enh2-UEConTest |  |  | 1 | 0% | 0% |  | 0% | 0%
TS 38.521-2: FR2 RF test cases - Rx
|  | 38.521-2 Rx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [7 empty] | TBD
|  | 38.521-2 Rx | 7.4 | Maximum input power | High DL Power/ Low UL Power *NOTE 2* |  |  |  | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | See NOTE2. Evaluation completed in Release 17 and further details are part of future study/release | 1 | 0% | 0% |  | 0% | 0%
|  | 38.521-2 Rx | 7.5 | Adjacent channel selectivity (case 1) | High DL Power/ Low UL Power *NOTE 2* |  |  |  | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | See NOTE2. Evaluation completed in Release 17 and further details are part of future study/release | 0 | 0% | 0% |  | 0% | 0%
|  | 38.521-2 Rx | 7.5 | Adjacent channel selectivity (case 2) | High DL Power/ Low UL Power *NOTE 2* |  |  |  | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | See NOTE2. Evaluation completed in Release 17 and further details are part of future study/release | 1 | 0% | 0% |  | 0% | 0%
|  | 38.521-2 Rx | 7.6.2 | In-band blocking | High DL Power/ Low UL Power *NOTE 2* |  |  |  | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | See NOTE2. Evaluation completed in Release 17 and further details are part of future study/release | 0 | 0% | 0% |  | 0% | 0%
|  | 38.521-2 Rx | 7.9 | Receiver spurious emissions | High DL Power/ Low UL Power *NOTE 2* |  |  |  | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | See NOTE2. Evaluation completed in Release 17 and further details are part of future study/release | 1 | 0% | 0% |  | 0% | 0%
|  | 38.521-2 Rx |  | Receiver Inter-band CA tests (expand List of tests) | Inter-band CA Test Enhancements |  |  |  | FFS |  | Has to be evaluated for IBM and CBM combos in Rel17
Equivalent CA tests to be analyzed for applicability here
TS 38.521-3: EN-DC FR2 RF test cases - necessary updates
|  | 38.521-3 | 6.3B.1.4 | Minimum output power for inter-band EN-DC including FR2 (1 NR CC) | High DL Power/ Low UL Power *NOTE 2* |  |  |  | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | See NOTE2. Evaluation completed in Release 17 and further details are part of future study/release | 1 | 0% | 0% |  | 0% | 0%
|  | 38.521-3 | 6.3B.2.4 | Transmit OFF Power for inter-band EN-DC including FR2 (1 NR CC) | High DL Power/ Low UL Power *NOTE 2* |  |  |  | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | See NOTE2. Evaluation completed in Release 17 and further details are part of future study/release | 1 | 0% | 0% |  | 0% | 0%
|  | 38.521-3 | 6.5B.1.4 | Occupied bandwidth for inter-band EN-DC including FR2 (1 NR CC) | High DL Power/ Low UL Power *NOTE 2* |  |  |  | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | See NOTE2. Evaluation completed in Release 17 and further details are part of future study/release | 1 | 0% | 0% |  | 0% | 0%
|  | 38.521-3 | 6.5B.2.4.3 | Adjacent channel leakage ratio for Inter-band EN-DC including FR2 (1 NR CC) | High DL Power/ Low UL Power *NOTE 2* |  |  |  | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | See NOTE2. Evaluation completed in Release 17 and further details are part of future study/release | 1 | 0% | 0% |  | 0% | 0%
|  | 38.521-3 | 6.4B.1.4 | Frequency Error for inter-band EN-DC including FR2 (1 NR CC) | UL Demod Measurement Enhancements - NOTE 1 |  |  |  | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | NOTE 1 | 1 | 0% | 0% |  | 0% | 0%
|  | 38.521-3 | 6.4B.2.4 | Transmit Modulation Quality for inter-band EN-DC including FR2 |  |  |  |  | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | NOTE 1 | 1 | 0% | 0% |  | 0% | 0%
|  | 38.521-3 | 6.4B.2.4.1 | Error Vector Magnitude for inter-band EN-DC including FR2 (1 NR CC) | UL Demod Measurement Enhancements |  |  |  | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | NOTE 1 | 1 | 0% | 0% |  | 0% | 0%
|  | 38.521-3 | 7.4B.4 | Maximum Input Level for inter-band EN-DC including FR2 (1 NR CC) | High DL Power/ Low UL Power *NOTE 2* |  |  |  | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | See NOTE2. Evaluation completed in Release 17 and further details are part of future study/release | 1 | 0% | 0% |  | 0% | 0%
|  | 38.521-3 | 7.5B.4 | Adjacent Channel Selectivity for inter-band EN-DC including FR2 (1 NR CC) | High DL Power/ Low UL Power *NOTE 2* |  |  |  | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | See NOTE2. Evaluation completed in Release 17 and further details are part of future study/release | 1 | 0% | 0% |  | 0% | 0%
|  | 38.521-3 | 7.6B.2.4 | Inband blocking for inter-band EN-DC including FR2 (2 CCs) | High DL Power/ Low UL Power *NOTE 2* |  |  |  | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | See NOTE2. Evaluation completed in Release 17 and further details are part of future study/release | 1 | 0% | 0% |  | 0% | 0%
|  | 38.521-3 | 7.9B.4 | Spurious Emissions for inter-band EN-DC including FR2 (1 NR CC) | High DL Power/ Low UL Power *NOTE 2* |  |  |  | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | See NOTE2. Evaluation completed in Release 17 and further details are part of future study/release | 1 | 0% | 0% |  | 0% | 0%
Equivalent CA tests to be analyzed for applicability here
|  | 38.521-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
|  | 38.521-3 | Annex G | Uplink Physical Channels | TBD | [6 empty] | 0.1
|  | 38.521-3 | Annex H | Statistical Testing | TBD | [6 empty] | 0.1
|  | 38.521-3 | Annex K | EIRP, TRP, EIS Measurement Procedures | Add RSRP-B based Peak Beam Search Fast Spherical Coverage Single Link Polarization Measurement |  |  |  | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | Completed. Check for maintainence updates | 1 | 0% | 0% |  | 0% | 0%
TBD | Y | 38.521-3
TS 38.521-4: SA/NSA FR2 Demod Perf test cases - necessary updates
|  | 38.521-4 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [7 empty] | TBD
TBD | Y | 38.521-4 | XYZ | 2AoA multi-Rx Test Case |  |  |  |  | NR_FR2_multiRX_DL-UEConTest |  | Add specific line items on open issues for each item | 1 | 0% | 0% |  | 0% | 0%
TS 38.533: SA/NSA FR2 RRM test cases - necessary updates
|  | 38.533 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
TBD | Y | 38.533 | XYZ | 2AoA multi-Rx Test Case |  |  |  |  | NR_FR2_multiRX_DL-UEConTest |  | Add specific line items on open issues for each item | 1 | 0% | 0% |  | 0% | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note 1
| AP#96e.29 | RF | Study if all the UE tolerance factors affecting the UE output power in FR2 EVM test case (peakEIRP, MBR, MPR, T(MPR), polarisation mismatch) is expected to be constant over time (10 subframes) and the correlation between the factors
| AP#96e.30 | RF | Evaluate if TT is to be made dependent on margin of UE output power in the FR2 EVM test case.
NOTE 2: Analysis of near-field (i.e. Direct Near Field (DNF), Combined Far-Field/Direct Near Field (CFFDNF), and Combined Far-Field/Near Field (CFFNF)) methods is low priority in FR2 RF Enhanced Test Methods Work Plan. Need forANY NF method analysis whatsoever in the current work plan shall be revisited once n262 testability work is complete
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on M6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.

## Sheet1
Topic Name | Topic Details | Comments/Follow-up in RAN5
Objective | Define and incorporate the FR2 enhanced test methods and testability topics associated with the FR2 RF requirements defined in : | Incorporate into RAN5 test specifications after topic-level detailed study
- NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 (UID-1030065) - NR_RF_FR2_req_Ph3-UEConTest
- Enhanced NR support for high speed train scenario in frequency range 2 (FR2) (UID-1030071) NR_HST_FR2_enh-UEConTest
- Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception (UID-1040113) NR_FR2_multiRX_DL-UEConTest
Beam correspondence - Initial Access | Verify beam correspondence performance during in initial access and in RRC_INACTIVE | Evaluation any test method improvements/adjustments and/or the need for test function in order to verify beam correspondence performance during initial access
UL-256 QAM (PC1) | Evaluate testability details for performance verification of FR2 UL-256 QAM | Incorporate into RAN5 test specifications after topic-level detailed study
2AoA spherical coverage for power class 6 (HST) | The requirements for a power class 6 UE are applicable with network signalling highSpeedDeploymentTypeFR2-r17 configured as bidirectional. UE spherical coverage evaluation areas are found in Table 6.2.1.6-3a in clause 6.2.1.6, by consisting of Area-1 and Area-2, in the reference coordinate system in Annex K.1. The requirement is verified with a 150° angular separation between 2AoAs. The requirement is verified with the test metric of Throughput (Link=2AoA Spherical coverage grid, Meas=Link angle).
UE RF testing methodology for multi-Rx chain DL reception (38.871) | Below test setups were evaluated as part of the study
| - Measurement Setup with Full Degree of Rotation Freedom for Each AoA | No discussion needed in RAN5
| - Measurement Setup with Full Degrees of Freedom for AoA1 with Fixed Angular Offset(s) Between AoA1 and AoA2 | Chosen as Rel-18 Baseline.
Similar to baseline setups for 2 AoA RRM testing OR FR2 MIMO OTA testing or Enhanced IFF setup with multiple TRPs
| - Measurement Setup with Full Degrees of Freedom for AoA1 with Variable Angular Offset(s) between AoA1 and AoA2 | No discussion needed in RAN5
| - Measurement Setup with Full Degrees of Freedom for AoA1 with Partial Freedom of Variable Angular Offset(s) between AoA1 and AoA2 | No discussion needed in RAN5
| - Measurement Setup with Full Degrees of Freedom for AoA1 with Fixed AoA2/Anchor in NF | No discussion needed in RAN5
| - Measurement Setup with Test Modes | No discussion needed in RAN5. Specifically avoid additional test mode discussion in RAN5..?
| - Measurement Setup to reduce sensitivity to UE orientation in holder with full degrees of freedom for AoA1 with fixed angular offset(s) between AoA1 and AoA2 | No discussion needed in RAN5
Test System Aspects
| Absolute Probe Locations | Incorporate into alignment options statements and Annex K
The plots of the perceived DL directions from different, fixed probes demonstrate the need to define the absolute probe locations/directions for UE RF systems so that different test systems yield the same results
| Minimum and Maximum Angular Separation between Probes | Incorporate into alignment options statements and Annex K. MU element on accuracy of angular separation might have to be considered
Minimum 30 degrees (to account for both DFF - 5deg and IFF - 30 deg)
Maximum 150 degrees (180 degrees results in blocking with positioner)
| Impact of probe locations and 3D scans on DL directions | Further study and understanding needed in RAN5 to incorporate in Annex
Full 3D scan can be performed in various ways. Optimal ways to perform the rotation were studied.
Based on the observations made in this section, the following decisions were made:
- For optimized AoA1 and AoA2 test point/perceived DL direction coverage, apply a full rotation in theta and a half rotation in phi.
- For optimized AoA1 and AoA2 test point/perceived DL direction coverage, utilize constant-step size grids only.
- For optimized AoA1 and AoA2 test point/perceived DL direction coverage, place the AoA2 probes in the xz plane
| AoA1-AoA2 directionality vector | Possible impact on MU of test procedure.
Was agreed that the directionality of the AoA1-AoA2 DL orientation vectors matters. For simulations, testing both +AoA offset and –AoA offset for each test point was considered the starting point. The intention is to accommodate the impact from directionality of the AoA1-AoA2 DL orientation vectors, i.e., to ensure no testing bias is introduced or whether it needs to be compensated somehow.
| Far Field Criteria - Reuse criteria from what was described in baseline IFF and DFF setups. | Align accordingly in RAN5 specs
Calibration | The IFF/CATR calibration system setup per AoA for EIRP as well as the calibration measurement procedure per probe is documented | Include in Annex of RAN5 test specifications
Test Procedure | Detailed test procedure flowchart for per AoA measurement in line with requirements defined in TS 38.101-2 (R4-2321722) | Incorporate in CRs to TS 38.521-2
UE RRM test methodology for multi-Rx DL chain reception | The principle of selecting measurement setup for UE RRM testing is to reuse measurement setup for UE RF testing as much as possible to reduce the test system complexity and test cost.
Baseline Methodology | The test scenarios of UE RRM testing for multi-Rx chain DL reception can be divided into two categories depending on whether dual DCI simultaneously switching needs to be supported by measurement setup or not:
- Category 1: All the RRM test cases expect Dual TCI switching
- Category 2: Dual TCI switching test case
Measurement Baseline for Category 1 scenario - Based on legacy 2AoA RRM setup
For Category 2 following scenarios were analyzed (dual TCI switching)
| - Option 1: Dual TCI switches simultaneously, probe number for multiple AoA test system is at least 4 | No discussion needed in RAN5
| - Option 2: Dual TCI switches from one probe to two probes simultaneously, probe number for multiple AoA test system is at least 3 | Measurement setup for Option 2 with at least 3 probes is selected as the baseline in Rel-18. Incorporate in RAN5 test specifications after further study and confirmation
| Option 3: Dual TCI switches simultaneously, but the beam directions are not changed, probe number for multiple AoA test system is at least 2 | No discussion needed in RAN5
| - Option 4: Switching AoAs of the Rx beam from AoA1 to AoA2 or vice versa during the TCI switching test. Probe number for multiple AoA test system is at least 2. | No discussion needed in RAN5
Test Parameters | For multi-Rx with non-overlapping scheme, the interference between two AoAs can be ignored. Then the test parameters for Mode 2 in the legacy RRM test methodology specified in [3] can be reused. | Align in RAN5 test specifications
UE Demodulation and CSI testing methodology for multi-Rx DL chain reception
Baseline methodology | Virtual cable setup is adopted for the baseline measurement setup, also referred as wireless cable mode | Align in RAN5 test specifications after further study
For baseline measurement setup based on DFF and IFF, the reference point is located at the centre of the QZ. From the UE perspective the reference point is the input of UE antenna array.
Far field criteria | - The Far-field criteria defined for the IFF UE RF testing methodology described in clause 5.3.6 of 38.871 can be applied. | Align in RAN5 test specifications after further study
Test parameters | Noc level configuration is defined
| Criteria of UE test directions | Align in RAN5 test specifications after further study
The test directions and AoA separation for demodulation test can be declared by UE. The UE declared test directions shall satisfy the following 3 criteria:
-- Minimum isolation shall be at least [-12]dB
-- Rank number shall be higher or same as intended rank for a given test case
-- Each direction of AoA pair shall pass legacy REFSENS requirements with [3] dB degradation.
Recommended MU for multi-Rx related test method enhancements | MU budget for UE RF test methodology | Further study and analysis in RAN5 before finalization
| MU budget for UE RRM test methodology | Further study and analysis in RAN5 before finalization
| MU budget for UE Demos and CSI test methodology | Further study and analysis in RAN5 before finalization
FR2 mult-Rx test method enhancements pertaining to FR2 HST requirements | The requirements for a power class 6 UE are applicable with network signalling highSpeedDeploymentTypeFR2-r17 configured as bidirectional. The requirement is verified with a 150° angular separation between 2AoAs. The requirement is verified with the test metric of Throughput (Link=2AoA Spherical coverage grid, Meas=Link angle). | Further study and analysis in RAN5 before finalization