## Cover sheet
3GPP TSG-RAN WG5 Meeting #105 | [8 empty] | R5-246922
Orlando, United States, Nov 18-22, 2024
Agenda Item: | 7.5.2
Source: | Huawei, Hisilicon
Title: | WP UE Conformance - 4Rx handheld UE for low NR bands (<1GHz) and/or 3Tx for NR inter-band UL Carrier Aggregation (CA) and EN-DC
Work item code: | 4Rx_low_NR_band_handheld_3Tx_NR_CA_ENDC-UEConTest
Release: | Rel-18
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The objective of UE Conformance - 4Rx handheld UE for low NR bands (<1GHz) and/or 3Tx for NR inter-band UL Carrier Aggregation (CA) and EN-DC is to define the UE conformance requirements corresponding to WID on 4Rx handheld UE for low NR bands (<1GHz) and/or 3Tx for NR inter-band UL Carrier Aggregation (CA) and EN-DC, analyse the test case impact, applicability, test environment, and update the relevant conformance specifications for Rel-18. At the RAN#102 meeting in Dec. 2023 the Rel-18 RAN5 work item for UE Conformance - 4Rx handheld UE for low NR bands (<1GHz) and/or 3Tx for NR inter-band UL Carrier Aggregation (CA) and EN-DC was approved [1]. The purpose of present document is to provide a workplan for the RAN5 work item on the conformance test cases for the core requirement introduced by the core work item. The workplan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 77% (+32%) | 62 (+35) | 84 (+6)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR1) |  | 76.2% (+27%) | 28 (+12) | 38 (-2)
FR1 |  | 76.2% (+27%) | 28 (+12) | 38 (-2)
NSA Option 3 (EN-DC) |  | 77.7% (+37.6%) | 34 (+23) | 46 (+8)
FR1 |  | 77.7% (+37.6%) | 34 (+23) | 46 (+8)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) |  |  |  |  | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  |  |  | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases |  |  | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 50% |  |  | 50% |  |  |  |  | 50%
Common ICS | 38.508-2 | 100% |  |  | 100% |  |  |  |  | 100%
NR RF/RRM
FR1 RF common parts | 38.521-1 | 100% |  |  | 100%
FR1 RF Tx test cases | 38.521-1 Tx | 75.3% (+32.1%) | 28 (+12) | 38 (-2) | 75.3% (+32.1%) | 28 (+12) | 38 (-2)
FR1 RF Rx test cases | 38.521-1 Rx | 50% |  |  | 50%
FR1 and FR2 Interworking operation with other radios RF common parts | 38.521-3 | 100% | [7 empty] | 100%
FR1 and FR2 Interworking operation with other radios RF Tx test cases | 38.521-3 Tx | 74.9% (+43.3%) | 34 (+23) | 46 (+8) | [5 empty] | 74.9% (+43.3%) | 34 (+23) | 46 (+8)
FR1 and FR2 Interworking operation with other radios RF Rx test cases | 38.521-3 Rx | 100% | [7 empty] | 100%
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 100% |  |  | 100% |  |  |  |  | 100%
Test Point analysis receiver and transmitter test cases | 38.905 | 100% |  |  | 100% |  |  |  |  | 100%
5 References
[1] RP-233771 | New WID on UE Conformance - 4Rx handheld UE for low NR bands (<1GHz) and/or 3Tx for NR inter-band UL Carrier Aggregation (CA) and EN-DC
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP UE Conformance - 4Rx handheld UE for low NR bands (<1GHz) and/or 3Tx for NR inter-band UL Carrier Aggregation (CA) and EN-DC | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | 4Rx_low_NR_band_handheld_3Tx_NR_CA_ENDC-UEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item UE Conformance Test Aspects for 4Rx handheld UE for low NR bands (<1GHz) and/or 3Tx for NR inter-band UL Carrier Aggregation (CA) and EN-DC comprising the necessary new clauses/test cases and updates to existing clauses/test cases.
WP Resp: |  | Yaping Zhang |  |  | zhangyaping13@huawei.com | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) | NSA Option 3 (EN-DC)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) |  | FR1 | FR1
[15 empty] | 76.2% (+27%) | 77.7% (+37.6%)
[15 empty] | 71 (-4) | 105 (+9)
[15 empty] | 47.8 (-2.6) | 57.4 (+7.2)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
1 |  | 38.508-1 | 4.6.3 | Radio resource control information elements | Update message contents |  | TBD |  |  | 0.1 | 0% | 0% | 0% |  | 0% | 0%
2 |  | 38.508-1 | A.3 | Set up diagrams | Introduce new connection diagrams | Huawei | RAN5#103 (May-24) | R5-242919 |  | 0.1 | 100% | 100% | 100% |  | 100% | 100%
TS 38.508-2: Common ICS
3 |  | 38.508-2 | A.x | Annex A (normative):ICS proforma for NR/5GS Generation User Equipment | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. | Huawei | RAN5#103 (May-24) | R5-243606 R5-246036 |  | 0.1 | 100% | 100% | 100% |  | 100% | 100%
NR RF/RRM
TS 38.521-1: FR1 RF test cases - Common parts (general clauses, Annexes)
4 |  | 38.521-1 | 4.3 | Specification suffix information | New definition of suffix I for CA with TxD |  | TBD |  |  | 0.1 | 100% | 100% |  |  | 100%
5 |  | 38.521-1 | 5.5A.3.1 | Configurations for inter-band CA (two bands) | Indicate the configurations that support 3Tx | Huawei | RAN5#103 (May-24) | R5-245149 |  | 0.1 | 100% | 100% |  |  | 100%
6 |  | 38.521-1 | F.1.2 | Measurement of transmitter | Add MU for inter-band UL CA | Huawei | RAN5#103 (May-24) | R5-242926 R5-245814 |  | 0.1 | 100% | 100% |  |  | 100%
7 |  | 38.521-1 | F.3.2 | Measurement of transmitter | Add TT for inter-band UL CA | Huawei | RAN5#103 (May-24) | R5-242926 R5-245814 |  | 0.1 | 100% | 100% |  |  | 100%
TS 38.521-1: FR1 RF test cases - Tx
8 |  | 38.521-1 Tx | 6.2A.4.1.3 | Configured transmitted power for Inter-band CA | Update PCMAX tolerance for PC 1.5 CA | Huawei | RAN5#103 (May-24) | R5-242921 |  | 0.3 | 100% | 100% |  |  | 100%
6.2H Transmitter power for CA with UL MIMO
9 |  | 38.521-1 Tx | 6.2H.3 | Transmitter power for inter-band UL CA with UL MIMO | New sub-clause header | Huawei | RAN5#103 (May-24) | R5-242922 |  | 0.1 | 100% | 100% |  |  | 100%
10 | Y | 38.521-1 Tx | 6.2H.3.1 | UE maximum output power for inter-band UL CA with UL MIMO | Specify the new test case for PC2 and PC 1.5 inter-band UL CA with UL MIMO | Huawei | RAN5#103 (May-24) | R5-242922 |  | 1 | 100% | 100% |  |  | 100%
11 | Y | 38.521-1 Tx | 6.2H.3.2 | UE maximum output power reduction for inter-band UL CA with UL MIMO | Specify the new test case for PC2 and PC 1.5 inter-band UL CA with UL MIMO | Huawei | RAN5#103 (May-24) | R5-240375 R5-242923 |  | 1 | 100% | 100% |  |  | 100%
12 | Y | 38.521-1 Tx | 6.2H.3.3 | UE additional maximum output power reduction for inter-band UL CA with UL MIMO | Specify the new test case for PC2 and PC 1.5 inter-band UL CA with UL MIMO | Huawei | RAN5#103 (May-24) | R5-242923 |  | 1 | 100% | 100% |  |  | 100%
13 | Y | 38.521-1 Tx | 6.2H.3.4 | Configured transmitted power for inter-band UL CA with UL MIMO | Specify the new test case for PC2 and PC 1.5 inter-band UL CA with UL MIMO | Huawei | RAN5#103 (May-24) | R5-242923 |  | 1 | 100% | 100% |  |  | 100%
6.2L Transmitter power for CA with Tx Diversity
14 |  | 38.521-1 Tx | 6.2L | Transmitter power for CA with Tx Diversity | New sub-clause header | Huawei | RAN5#103 (May-24) | R5-242924 |  | 0.1 | 100% | 100% |  |  | 100%
15 |  | 38.521-1 Tx | 6.2L.3 |  | New sub-clause header | Huawei | RAN5#103 (May-24) | R5-242924 |  | 0.1 | 100% | 100% |  |  | 100%
16 | Y | 38.521-1 Tx | 6.2L.3.1 | UE maximum output power for inter-band UL CA with Tx Diversity | Specify the new test case for PC2 and PC 1.5 inter-band UL CA with TxD | Huawei | RAN5#103 (May-24) | R5-242924 |  | 1 | 100% | 100% |  |  | 100%
17 | Y | 38.521-1 Tx | 6.2L.3.2 | UE maximum output power reduction for inter-band UL CA with Tx Diversity | Specify the new test case for PC2 and PC 1.5 inter-band UL CA with TxD | Huawei | RAN5#103 (May-24) | R5-243628 |  | 1 | 100% | 100% |  |  | 100%
18 | Y | 38.521-1 Tx | 6.2L.3.3 | UE additional maximum output power reduction for inter-band UL CA with Tx Diversity | Specify the new test case for PC2 and PC 1.5 inter-band UL CA with TxD | Huawei | RAN5#103 (May-24) | R5-243628 |  | 1 | 100% | 100% |  |  | 100%
19 | Y | 38.521-1 Tx | 6.2L.3.4 | Configured transmitted power for inter-band UL CA with Tx Diversity | Specify the new test case for PC2 and PC 1.5 inter-band UL CA with TxD | Huawei | RAN5#103 (May-24) | R5-243628 |  | 1 | 100% | 100% |  |  | 100%
6.3H Output power dynamics for CA with UL MIMO
20 |  | 38.521-1 Tx | 6.3H.3 | Output power dynamics for inter-band UL CA with UL MIMO | New sub-clause header | TTA | RAN5#103 (May-24) | R5-243626 |  | 0.1 | 100% | 100% |  |  | 100%
21 | Y | 38.521-1 Tx | 6.3H.3.1 | Minimum output power for inter-band UL CA with UL MIMO | Specify the new test case for PC2 and PC 1.5 inter-band UL CA with UL MIMO | TTA | RAN5#103 (May-24) | R5-243626 |  | 1 | 100% | 100% |  |  | 100%
22 | Y | 38.521-1 Tx | 6.3H.3.2 | Transmit OFF power for inter-band UL CA with UL MIMO | Specify the new test case for PC2 and PC 1.5 inter-band UL CA with UL MIMO | Huawei | RAN5#105 (Nov-24) | R5-246912 |  | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
23 | Y | 38.521-1 Tx | 6.3H.3.3 | Transmit ON/OFF time mask for inter-band UL CA with UL MIMO | Specify the new test case for PC2 and PC 1.5 inter-band UL CA with UL MIMO | Huawei | RAN5#105 (Nov-24) | R5-246912 |  | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
6.3L Output power dynamics for CA with Tx Diversity
29 |  | 38.521-1 Tx | 6.3L | Output power dynamics for CA with Tx Diversity | New sub-clause header | TTA | RAN5#103 (May-24) | R5-244690 |  | 0.1 | 100% | 100% |  |  | 100%
30 |  | 38.521-1 Tx | 6.3L.3 | Output power dynamics for inter-band UL CA with Tx Diversity | New sub-clause header | TTA | RAN5#103 (May-24) | R5-244690 |  | 0.1 | 100% | 100% |  |  | 100%
31 | Y | 38.521-1 Tx | 6.3L.3.1 | Minimum output power for inter-band UL CA with Tx Diversity | Specify the new test case for PC2 and PC 1.5 inter-band UL CA with TxD | TTA | RAN5#103 (May-24) | R5-244690 |  | 1 | 100% | 100% |  |  | 100%
32 | Y | 38.521-1 Tx | 6.3L.3.2 | Transmit OFF power for inter-band UL CA with Tx Diversity | Specify the new test case for PC2 and PC 1.5 inter-band UL CA with TxD | Huawei | RAN5#105 (Nov-24) | R5-246913 |  | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
33 | Y | 38.521-1 Tx | 6.3L.3.3 | Transmit ON/OFF time mask for inter-band UL CA with Tx Diversity | Specify the new test case for PC2 and PC 1.5 inter-band UL CA with TxD | Huawei | RAN5#105 (Nov-24) | R5-246913 |  | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
6.4H Transmit signal quality for CA with UL MIMO
39 |  | 38.521-1 Tx | 6.4H.3 | Transmit signal quality for inter-band UL CA with UL MIMO | New sub-clause header | Huawei, SRTC | RAN5#105 (Nov-24) | R5-246914 |  | 0.1 | 100% (+100%) | 100% (+100%) |  |  | 100%
40 | Y | 38.521-1 Tx | 6.4H.3.1 | Frequency error for inter-band UL CA with UL MIMO | Specify the new test case for PC2 and PC 1.5 inter-band UL CA with UL MIMO | Huawei, SRTC | RAN5#105 (Nov-24) | R5-246914 |  | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
41 |  | 38.521-1 Tx | 6.4H.3.2 | Transmit modulation quality for inter-band UL CA with UL MIMO | New sub-clause header | Huawei, SRTC | RAN5#105 (Nov-24) | R5-246914 |  | 0.1 | 100% (+100%) | 100% (+100%) |  |  | 100%
169 | Y | 38.521-1 Tx | 6.4H.3.2.1 | Error Vector Magnitude for inter-band UL CA with UL MIMO | Specify the new test case for PC2 and PC 1.5 inter-band UL CA with UL MIMO | Huawei, SRTC | RAN5#105 (Nov-24) | R5-246914 |  | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
170 | Y | 38.521-1 Tx | 6.4H.3.2.2 | Carrier leakage for inter-band UL CA with UL MIMO | Specify the new test case for PC2 and PC 1.5 inter-band UL CA with UL MIMO | Huawei, SRTC | RAN5#105 (Nov-24) | R5-246914 |  | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
171 | Y | 38.521-1 Tx | 6.4H.3.2.3 | In-band emissions for inter-band UL CA with UL MIMO | Specify the new test case for PC2 and PC 1.5 inter-band UL CA with UL MIMO | Huawei, SRTC | RAN5#105 (Nov-24) | R5-246914 |  | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
6.4L Transmit signal quality for CA with Tx Diversity
42 |  | 38.521-1 Tx | 6.4L.3 | Transmit signal quality for CA with Tx Diversity | New sub-clause header | Huawei, SRTC | RAN5#105 (Nov-24) | R5-246915 |  | 0.1 | 100% (+100%) | 100% (+100%) |  |  | 100%
43 | Y | 38.521-1 Tx | 6.4L.3.1 | Frequency error for inter-band UL CA with Tx Diversity | Specify the new test case for PC2 and PC 1.5 inter-band UL CA with TxD | Huawei, SRTC | RAN5#105 (Nov-24) | R5-246915 |  | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
44 |  | 38.521-1 Tx | 6.4L.3.2 | Transmit modulation quality for inter-band UL CA with Tx Diversity | New sub-clause header | Huawei, SRTC | RAN5#105 (Nov-24) | R5-246915 |  | 0.1 | 100% (+100%) | 100% (+100%) |  |  | 100%
172 | Y | 38.521-1 Tx | 6.4L.3.2.1 | Error Vector Magnitude for inter-band UL CA with Tx Diversity | Specify the new test case for PC2 and PC 1.5 inter-band UL CA with TxD | Huawei, SRTC | RAN5#105 (Nov-24) | R5-246915 |  | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
173 | Y | 38.521-1 Tx | 6.4L.3.2.2 | Carrier leakage for inter-band UL CA with Tx Diversity | Specify the new test case for PC2 and PC 1.5 inter-band UL CA with TxD | Huawei, SRTC | RAN5#105 (Nov-24) | R5-246915 |  | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
174 | Y | 38.521-1 Tx | 6.4L.3.2.3 | In-band emissions for inter-band UL CA with Tx Diversity | Specify the new test case for PC2 and PC 1.5 inter-band UL CA with TxD | Huawei, SRTC | RAN5#105 (Nov-24) | R5-246915 |  | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
6.5H Output RF spectrum emissions for CA with UL MIMO
45 |  | 38.521-1 Tx | 6.5H.3 | Output RF spectrum emissions for inter-band UL CA with UL MIMO | New sub-clause header | TTA | RAN5#103 (May-24) | R5-243627 |  | 0.1 | 100% | 100% |  |  | 100%
46 | Y | 38.521-1 Tx | 6.5H.3.1 | Occupied bandwidth for inter-band UL CA with UL MIMO | Specify the new test case for PC2 and PC 1.5 inter-band UL CA with UL MIMO | TTA | RAN5#103 (May-24) | R5-243627 |  | 1 | 100% | 100% |  |  | 100%
47 |  | 38.521-1 Tx | 6.5H.3.2 | Out of band emission for inter-band UL CA with UL MIMO | New sub-clause header |  | TBD |  |  | 0.1 | 0% | 0% |  |  | 0%
48 |  | 38.521-1 Tx | 6.5H.3.2.0 | Minimum conformance requirements | Add the minimum requirements |  | TBD |  |  | 0.1 | 0% | 0% |  |  | 0%
49 | Y | 38.521-1 Tx | 6.5H.3.2.1 | Spectrum emission mask for inter-band UL CA with UL MIMO | Specify the new test case for PC2 and PC 1.5 inter-band UL CA with UL MIMO |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
50 | Y | 38.521-1 Tx | 6.5H.3.2.2 | Additional spectrum emission mask for inter-band UL CA with UL MIMO | Specify the new test case for PC2 and PC 1.5 inter-band UL CA with UL MIMO |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
51 | Y | 38.521-1 Tx | 6.5H.3.2.3 | NR ACLR for inter-band UL CA with UL MIMO | Specify the new test case for PC2 and PC 1.5 inter-band UL CA with UL MIMO |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
52 |  | 38.521-1 Tx | 6.5H.3.3 | Spurious emission for inter-band UL CA with UL MIMO | New sub-clause header | Huawei | RAN5#104 (Aug-24) | R5-246037 |  | 0.1 | 100% | 100% |  |  | 100%
123 |  | 38.521-1 Tx | 6.5H.3.3.0 | Minimum conformance requirements | Add the minimum requirements | Huawei | RAN5#104 (Aug-24) | R5-246037 |  | 1 | 100% | 100% |  |  | 100%
53 | Y | 38.521-1 Tx | 6.5H.3.3.1 | General spurious emissions for inter-band UL CA with UL MIMO | Specify the new test case for PC2 and PC 1.5 inter-band UL CA with UL MIMO | Huawei | RAN5#104 (Aug-24) | R5-246037 |  | 1 | 100% | 100% |  |  | 100%
54 | Y | 38.521-1 Tx | 6.5H.3.3.2 | Spurious emissions for UE co-existence for inter-band UL CA with UL MIMO | Specify the new test case for PC2 and PC 1.5 inter-band UL CA with UL MIMO | Huawei | RAN5#104 (Aug-24) | R5-245151 |  | 1 | 100% | 100% |  |  | 100%
55 | Y | 38.521-1 Tx | 6.5H.3.3.3 | Additional spurious emissions for inter-band UL CA with UL MIMO | Specify the new test case for PC2 and PC 1.5 inter-band UL CA with UL MIMO |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
56 | Y | 38.521-1 Tx | 6.5H.3.4 | Transmit intermodulation for inter-band UL CA with UL MIMO | Specify the new test case for PC2 and PC 1.5 inter-band UL CA with UL MIMO |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
6.5L Output RF spectrum emissions for CA with Tx Diversity
57 |  | 38.521-1 Tx | 6.5L.3 | Output RF spectrum emissions for inter-band UL CA with Tx Diversity | New sub-clause header | TTA | RAN5#103 (May-24) | R5-244746 |  | 0.1 | 100% | 100% |  |  | 100%
58 | Y | 38.521-1 Tx | 6.5L.3.1 | Occupied bandwidth for inter-band UL CA with Tx Diversity | Specify the new test case for PC2 and PC 1.5 inter-band UL CA with TxD | TTA | RAN5#103 (May-24) | R5-244746 |  | 1 | 100% | 100% |  |  | 100%
59 |  | 38.521-1 Tx | 6.5L.3.2 | Out of band emission for inter-band UL CA with Tx Diversity | New sub-clause header |  | TBD |  |  | 0.1 | 0% | 0% |  |  | 0%
60 |  | 38.521-1 Tx | 6.5L.3.2.0 | Minimum conformance requirements | Add the minimum requirements |  | TBD |  |  | 0.1 | 0% | 0% |  |  | 0%
61 | Y | 38.521-1 Tx | 6.5L.3.2.1 | Spectrum emission mask for inter-band UL CA with Tx Diversity | Specify the new test case for PC2 and PC 1.5 inter-band UL CA with TxD |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
62 | Y | 38.521-1 Tx | 6.5L.3.2.2 | Additional spectrum emission mask for inter-band UL CA with Tx Diversity | Specify the new test case for PC2 and PC 1.5 inter-band UL CA with TxD |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
63 | Y | 38.521-1 Tx | 6.5L.3.2.3 | NR ACLR for inter-band UL CA with Tx Diversity | Specify the new test case for PC2 and PC 1.5 inter-band UL CA with TxD |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
64 |  | 38.521-1 Tx | 6.5L.3.3 | Spurious emission for inter-band UL CA with Tx Diversity | New sub-clause header | Huawei | RAN5#104 (Aug-24) | R5-246038 |  | 0.1 | 100% | 100% |  |  | 100%
124 |  | 38.521-1 Tx | 6.5L.3.3.0 | Minimum conformance requirements | Add the minimum requirements | Huawei | RAN5#104 (Aug-24) | R5-246038 |  | 1 | 100% | 100% |  |  | 100%
65 | Y | 38.521-1 Tx | 6.5L.3.3.1 | General spurious emissions for inter-band UL CA with Tx Diversity | Specify the new test case for PC2 and PC 1.5 inter-band UL CA with TxD | Huawei | RAN5#104 (Aug-24) | R5-246038 |  | 1 | 100% | 100% |  |  | 100%
66 | Y | 38.521-1 Tx | 6.5L.3.3.2 | Spurious emissions for UE co-existence for inter-band UL CA with Tx Diversity | Specify the new test case for PC2 and PC 1.5 inter-band UL CA with TxD | Huawei | RAN5#104 (Aug-24) | R5-245153 |  | 1 | 100% | 100% |  |  | 100%
67 | Y | 38.521-1 Tx | 6.5L.3.3.3 | Additional spurious emissions for inter-band UL CA with Tx Diversity | Specify the new test case for PC2 and PC 1.5 inter-band UL CA with TxD |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
68 | Y | 38.521-1 Tx | 6.5L.3.4 | Transmit intermodulation for inter-band UL CA with Tx Diversity | Specify the new test case for PC2 and PC 1.5 inter-band UL CA with TxD |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
TS 38.521-1: FR1 RF test cases - Rx
69 |  | 38.521-1 Rx | 7.1 | General | Add general requirements for 3Tx combos |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
70 |  | 38.521-1 Rx | 7.3.2 | Reference sensitivity power level | New test requirements for NR bands when 4Rx is supported by handheld UE | Huawei | RAN5#104 (Aug-24) | R5-245146 R5-247366 |  | 1 | 100% | 100% |  |  | 100%
71 |  | 38.521-1 Rx | 7.3A.1_1 | Reference sensitivity power level for 2DL CA exceptions | 1. New test requiremnts for NR CA configurations when 4Rx is supported by handheld UE. 2. New exception requirements for PC 1.5 CA with 3Tx | Huawei | RAN5#104 (Aug-24) | R5-245147 R5-245155 |  | 1 | 50% | 50% |  |  | 50%
TS 38.521-3: FR1 and FR2 Interworking operation with other radios RF test cases - Common parts (general clauses, Annexes)
72 |  | 38.521-3 | 4.2 | Applicability of minimum requirements | Applicability for EN-DC with 3Tx | Huawei | RAN5#103 (May-24) | R5-243221 |  | 0.1 | 100% |  | 100% |  |  | 100%
73 |  | 38.521-3 | 4.3 | Specification suffix information | New definition of suffix I for EN-DC with UL-MIMO | Huawei | RAN5#103 (May-24) | R5-243221 |  | 0.1 | 100% |  | 100% |  |  | 100%
74 |  | 38.521-3 | 5.5B.4.1 | Inter-band EN-DC configurations within FR1 (two bands) | Indicate the EN-DC configurations that support 3Tx | Huawei | RAN5#103 (May-24) | R5-243221 R5-245816 |  | 0.3 | 100% |  | 100% |  |  | 100%
75 |  | 38.521-3 | F.1.2 | Measurement of transmitter | Add MU for inter-band EN-DC | Huawei | RAN5#103 (May-24) | R5-243220 R5-245815 R5-256920 |  | 0.3 | 100% |  | 100% |  |  | 100%
76 |  | 38.521-3 | F.3.2 | Measurement of transmitter | Add TT for inter-band EN-DC | Huawei | RAN5#103 (May-24) | R5-243220 R5-245815 R5-256920 |  | 0.3 | 100% |  | 100% |  |  | 100%
TS 38.521-3: FR1 and FR2 Interworking operation with other radios RF test cases - Tx
6.2H Transmitter power for DC with UL MIMO
77 |  | 38.521-3 Tx | 6.2H | Transmitter power for DC with UL MIMO | New sub-clause header | Huawei | RAN5#103 (May-24) | R5-242928 |  | 0.1 | 100% |  | 100% |  |  | 100%
78 |  | 38.521-3 Tx | 6.2H.1 | UE maximum output power for DC with UL MIMO | New sub-clause header | Huawei | RAN5#103 (May-24) | R5-242928 |  | 0.1 | 100% |  | 100% |  |  | 100%
79 | Y | 38.521-3 Tx | 6.2H.1.3 | UE maximum output power for inter-band EN-DC with UL MIMO within FR1 | Specify the new test case for PC2 inter-band EN-DC with UL MIMO | Huawei | RAN5#103 (May-24) | R5-242928 |  | 1 | 100% |  | 100% |  |  | 100%
80 |  | 38.521-3 Tx | 6.2H.2 | UE maximum output power reduction for DC with UL MIMO | New sub-clause header | Huawei | RAN5#103 (May-24) | R5-241725 |  | 0.1 | 100% |  | 100% |  |  | 100%
81 | Y | 38.521-3 Tx | 6.2H.2.3 | UE maximum output power reduction for inter-band EN-DC with UL MIMO within FR1 | Specify the new test case for PC2 inter-band EN-DC with UL MIMO | Huawei | RAN5#103 (May-24) | R5-241725 R5-242929 |  | 1 | 100% |  | 100% |  |  | 100%
82 |  | 38.521-3 Tx | 6.2H.3 | UE additional maximum output power reduction for EN-DC with UL MIMO | New sub-clause header | Huawei | RAN5#103 (May-24) | R5-242929 |  | 0.1 | 100% |  | 100% |  |  | 100%
83 | Y | 38.521-3 Tx | 6.2H.3.3 | UE additional maximum output power reduction for inter-band EN-DC with UL MIMO within FR1 | Specify the new test case for PC2 inter-band EN-DC with UL MIMO | Huawei | RAN5#103 (May-24) | R5-242929 |  | 1 | 100% |  | 100% |  |  | 100%
84 |  | 38.521-3 Tx | 6.2H.4 | Configured output power for DC with UL MIMO | New sub-clause header | Huawei | RAN5#103 (May-24) | R5-242929 |  | 0.1 | 100% |  | 100% |  |  | 100%
85 |  | 38.521-3 Tx | 6.2H.4.1 | Configured output power level | New sub-clause header | Huawei | RAN5#103 (May-24) | R5-242929 |  | 0.1 | 100% |  | 100% |  |  | 100%
86 | Y | 38.521-3 Tx | 6.2H.4.1.3 | Configured output power level for inter-band EN-DC with UL MIMO within FR1 | Specify the new test case for PC2 inter-band EN-DC with UL MIMO | Huawei | RAN5#103 (May-24) | R5-242929 |  | 1 | 100% |  | 100% |  |  | 100%
6.2L Transmitter power for DC with Tx Diversity
127 |  | 38.521-3 Tx | 6.2L | Transmitter power for DC with Tx Diversity | New sub-clause header | Huawei | RAN5#103 (May-24) | R5-242930 |  | 0.1 | 100% |  | 100% |  |  | 100%
128 |  | 38.521-3 Tx | 6.2L.1 | UE maximum output power for DC with Tx Diversity | New sub-clause header | Huawei | RAN5#103 (May-24) | R5-242930 |  | 0.1 | 100% |  | 100% |  |  | 100%
129 | Y | 38.521-3 Tx | 6.2L.1.3 | UE maximum output power for inter-band EN-DC with Tx Diversity within FR1 | Specify the new test case for PC2 inter-band EN-DC with TxD | Huawei | RAN5#103 (May-24) | R5-242930 |  | 1 | 100% |  | 100% |  |  | 100%
130 |  | 38.521-3 Tx | 6.2L.2 | UE maximum output power reduction for DC with Tx Diversity | New sub-clause header | Huawei | RAN5#103 (May-24) | R5-242931 |  | 0.1 | 100% |  | 100% |  |  | 100%
131 | Y | 38.521-3 Tx | 6.2L.2.3 | UE maximum output power reduction for inter-band EN-DC with Tx Diversity within FR1 | Specify the new test case for PC2 inter-band EN-DC with TxD | Huawei | RAN5#103 (May-24) | R5-242931 |  | 1 | 100% |  | 100% |  |  | 100%
132 |  | 38.521-3 Tx | 6.2L.3 | UE additional maximum output power reduction for EN-DC with Tx Diversity | New sub-clause header | Huawei | RAN5#103 (May-24) | R5-242931 |  | 0.1 | 100% |  | 100% |  |  | 100%
133 | Y | 38.521-3 Tx | 6.2L.3.3 | UE additional maximum output power reduction for inter-band EN-DC with Tx Diversity within FR1 | Specify the new test case for PC2 inter-band EN-DC with TxD | Huawei | RAN5#103 (May-24) | R5-242931 |  | 1 | 100% |  | 100% |  |  | 100%
134 |  | 38.521-3 Tx | 6.2L.4 | Configured output power for DC with Tx Diversity | New sub-clause header | Huawei | RAN5#103 (May-24) | R5-242931 |  | 0.1 | 100% |  | 100% |  |  | 100%
135 |  | 38.521-3 Tx | 6.2L.4.1 | Configured output power level | New sub-clause header | Huawei | RAN5#103 (May-24) | R5-242931 |  | 0.1 | 100% |  | 100% |  |  | 100%
136 | Y | 38.521-3 Tx | 6.2L.4.1.3 | Configured output power level for inter-band EN-DC with Tx Diversity within FR1 | Specify the new test case for PC2 inter-band EN-DC with TxD | Huawei | RAN5#103 (May-24) | R5-242931 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  | 100%
6.3H Output power dynamics for DC with UL MIMO
87 |  | 38.521-3 Tx | 6.3H | Output power dynamics for DC with UL MIMO | New sub-clause header | Huawei, SRTC | RAN5#105 (Nov-24) | R5-246916 |  | 0.1 | 100% (+100%) |  | 100% (+100%) |  |  | 100%
89 |  | 38.521-3 Tx | 6.3H.3 | Output power dynamics for inter-band EN-DC with UL MIMO | New sub-clause header | Huawei, SRTC | RAN5#105 (Nov-24) | R5-246916 |  | 0.1 | 100% (+100%) |  | 100% (+100%) |  |  | 100%
90 | Y | 38.521-3 Tx | 6.3H.3.1 | Minimum output power for inter-band EN-DC with UL MIMO | Specify the new test case for PC2 inter-band EN-DC with UL MIMO | Huawei, SRTC | RAN5#105 (Nov-24) | R5-246916 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  | 100%
91 | Y | 38.521-3 Tx | 6.3H.3.2 | Transmit OFF power for inter-band EN-DC with UL MIMO | Specify the new test case for PC2 inter-band EN-DC with UL MIMO | Huawei, SRTC | RAN5#105 (Nov-24) | R5-246916 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  | 100%
92 | Y | 38.521-3 Tx | 6.3H.3.3 | Transmit ON/OFF time mask for inter-band EN-DC with UL MIMO | Specify the new test case for PC2 inter-band EN-DC with UL MIMO | Huawei, SRTC | RAN5#105 (Nov-24) | R5-246916 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  | 100%
93 |  | 38.521-3 Tx | 6.3H.3.4 | Power control for inter-band EN-DC with UL MIMO | New sub-clause header | Huawei, SRTC | RAN5#105 (Nov-24) | R5-246916 |  | 0.1 | 100% (+100%) |  | 100% (+100%) |  |  | 100%
94 | Y | 38.521-3 Tx | 6.3H.3.4.1 | Absolute power tolerance for inter-band EN-DC with UL MIMO | Specify the new test case for PC2 inter-band EN-DC with UL MIMO | Huawei, SRTC | RAN5#105 (Nov-24) | R5-246916 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  | 100%
95 | Y | 38.521-3 Tx | 6.3H.3.4.2 | Relative power tolerance for inter-band EN-DC with UL MIMO | Specify the new test case for PC2 inter-band EN-DC with UL MIMO | Huawei, SRTC | RAN5#105 (Nov-24) | R5-246916 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  | 100%
96 | Y | 38.521-3 Tx | 6.3H3.4.3 | Aggregate power tolerance for inter-band EN-DC withlerance for inter-band EN-DC with UL MIMO | Specify the new test case for PC2 inter-band EN-DC with UL MIMO | Huawei, SRTC | RAN5#105 (Nov-24) | R5-246916 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  | 100%
6.3L Output power dynamics for DC with Tx Diversity
137 |  | 38.521-3 Tx | 6.3L | Output power dynamics for DC with Tx Diversity | New sub-clause header | Huawei, SRTC | RAN5#105 (Nov-24) | R5-246917 |  | 0.1 | 100% (+100%) |  | 100% (+100%) |  |  | 100%
139 |  | 38.521-3 Tx | 6.3L.3 | Output power dynamics for inter-band EN-DC with Tx Diversity | New sub-clause header | Huawei, SRTC | RAN5#105 (Nov-24) | R5-246917 |  | 0.1 | 100% (+100%) |  | 100% (+100%) |  |  | 100%
141 | Y | 38.521-3 Tx | 6.3L.3.1 | Minimum output power for inter-band EN-DC with Tx Diversity | Specify the new test case for PC2 inter-band EN-DC with TxD | Huawei, SRTC | RAN5#105 (Nov-24) | R5-246917 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  | 100%
142 | Y | 38.521-3 Tx | 6.3L.3.2 | Transmit OFF power for inter-band EN-DC with Tx Diversity | Specify the new test case for PC2 inter-band EN-DC with TxD | Huawei, SRTC | RAN5#105 (Nov-24) | R5-246917 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  | 100%
143 | Y | 38.521-3 Tx | 6.3L.3.3 | Transmit ON/OFF time mask for inter-band EN-DC with Tx Diversity | Specify the new test case for PC2 inter-band EN-DC with TxD | Huawei, SRTC | RAN5#105 (Nov-24) | R5-246917 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  | 100%
175 | Y | 38.521-3 Tx | 6.3L.3.3.1 | General ON/OFF time mask for inter-band EN-DC with Tx Diversity | Specify the new test case for PC2 inter-band EN-DC with TxD | Huawei, SRTC | RAN5#105 (Nov-24) | R5-246917 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  | 100%
176 | Y | 38.521-3 Tx | 6.3L.3.3.2 | PRACH time mask for inter-band EN-DC with Tx Diversity | Specify the new test case for PC2 inter-band EN-DC with TxD | Huawei, SRTC | RAN5#105 (Nov-24) | R5-246917 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  | 100%
177 | Y | 38.521-3 Tx | 6.3L.3.3.3 | SRS time mask for inter-band EN-DC with Tx Diversity | Specify the new test case for PC2 inter-band EN-DC with TxD | Huawei, SRTC | RAN5#105 (Nov-24) | R5-246917 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  | 100%
144 |  | 38.521-3 Tx | 6.3L.3.4 | Power control for inter-band EN-DC with Tx Diversity | New sub-clause header | Huawei, SRTC | RAN5#105 (Nov-24) | R5-246917 |  | 0.1 | 100% (+100%) |  | 100% (+100%) |  |  | 100%
145 | Y | 38.521-3 Tx | 6.3L.3.4.1 | Absolute power tolerance for inter-band EN-DC with Tx Diversity | Specify the new test case for PC2 inter-band EN-DC with TxD | Huawei, SRTC | RAN5#105 (Nov-24) | R5-246917 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  | 100%
146 | Y | 38.521-3 Tx | 6.3L.3.4.2 | Relative power tolerance for inter-band EN-DC with Tx Diversity | Specify the new test case for PC2 inter-band EN-DC with TxD | Huawei, SRTC | RAN5#105 (Nov-24) | R5-246917 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  | 100%
147 | Y | 38.521-3 Tx | 6.3L.3.4.3 | Aggregate power tolerance for inter-band EN-DC withlerance for inter-band EN-DC with Tx Diversity | Specify the new test case for PC2 inter-band EN-DC with TxD | Huawei, SRTC | RAN5#105 (Nov-24) | R5-246917 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  | 100%
6.4H Transmit signal quality for DC with UL MIMO
97 |  | 38.521-3 Tx | 6.4H | Transmit signal quality for DC with UL MIMO | New sub-clause header | Huawei | RAN5#105 (Nov-24) | R5-246918 |  | 0.1 | 100% (+100%) |  | 100% (+100%) |  |  | 100%
98 |  | 38.521-3 Tx | 6.4H.1 | Frequency error for DC with UL MIMO | New sub-clause header | Huawei | RAN5#105 (Nov-24) | R5-246918 |  | 0.1 | 100% (+100%) |  | 100% (+100%) |  |  | 100%
99 |  | 38.521-3 Tx | 6.4H.1.3 | Frequency error for inter-band EN-DC with UL MIMO within FR1 | Specify the new test case for PC2 inter-band EN-DC with UL MIMO | Huawei | RAN5#105 (Nov-24) | R5-246918 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  | 100%
178 |  | 38.521-3 Tx | 6.4H.2 | Transmit modulation quality for DC with UL MIMO within FR1 | New sub-clause header | Huawei | RAN5#105 (Nov-24) | R5-246918 |  | 0.1 | 100% (+100%) |  | 100% (+100%) |  |  | 100%
179 |  | 38.521-3 Tx | 6.4H.2.3 | Transmit modulation quality for inter-band EN-DC with UL MIMO within FR1 | New sub-clause header | Huawei | RAN5#105 (Nov-24) | R5-246918 |  | 0.1 | 100% (+100%) |  | 100% (+100%) |  |  | 100%
180 | Y | 38.521-3 Tx | 6.4H.2.3.1 | Error Vector Magnitude for inter-band EN-DC with UL MIMO within FR1 | Specify the new test case for PC2 and PC 1.5 inter-band EN-DC with UL MIMO | Huawei | RAN5#105 (Nov-24) | R5-246918 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  | 100%
181 | Y | 38.521-3 Tx | 6.4H.2.3.2 | Carrier leakage for inter-band EN-DC with UL MIMO within FR1 | Specify the new test case for PC2 and PC 1.5 inter-band EN-DC with UL MIMO | Huawei | RAN5#105 (Nov-24) | R5-246918 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  | 100%
182 | Y | 38.521-3 Tx | 6.4H.2.3.3 | In-band emissions for inter-band EN-DC with UL MIMO within FR1 | Specify the new test case for PC2 and PC 1.5 inter-band EN-DC with UL MIMO | Huawei | RAN5#105 (Nov-24) | R5-246918 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  | 100%
6.4L Transmit signal quality for DC with Tx Diversity
148 |  | 38.521-3 Tx | 6.4L | Transmit signal quality for DC with Tx Diversity | New sub-clause header | Huawei | RAN5#105 (Nov-24) | R5-246919 |  | 0.1 | 100% (+100%) |  | 100% (+100%) |  |  | 100%
149 |  | 38.521-3 Tx | 6.4L.1 | Frequency error for DC with Tx Diversity | New sub-clause header | Huawei | RAN5#105 (Nov-24) | R5-246919 |  | 0.1 | 100% (+100%) |  | 100% (+100%) |  |  | 100%
150 | Y | 38.521-3 Tx | 6.4L.1.3 | Frequency error for inter-band EN-DC with Tx Diversity within FR1 | Specify the new test case for PC2 inter-band EN-DC with TxD | Huawei | RAN5#105 (Nov-24) | R5-246919 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  | 100%
183 |  | 38.521-3 Tx | 6.4L.2 | Transmit modulation quality for DC with Tx Diversity within FR1 | New sub-clause header | Huawei | RAN5#105 (Nov-24) | R5-246919 |  | 0.1 | 100% (+100%) |  | 100% (+100%) |  |  | 100%
184 |  | 38.521-3 Tx | 6.4L.2.3 | Transmit modulation quality for inter-band EN-DC with Tx Diversity within FR1 | New sub-clause header | Huawei | RAN5#105 (Nov-24) | R5-246919 |  | 0.1 | 100% (+100%) |  | 100% (+100%) |  |  | 100%
185 | Y | 38.521-3 Tx | 6.4L.2.3.1 | Error Vector Magnitude for inter-band EN-DC with Tx Diversity within FR1 | Specify the new test case for PC2 and PC 1.5 inter-band EN-DC with Tx Diversity | Huawei | RAN5#105 (Nov-24) | R5-246919 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  | 100%
186 | Y | 38.521-3 Tx | 6.4L.2.3.2 | Carrier leakage for inter-band EN-DC with Tx Diversity within FR1 | Specify the new test case for PC2 and PC 1.5 inter-band EN-DC with Tx Diversity | Huawei | RAN5#105 (Nov-24) | R5-246919 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  | 100%
187 | Y | 38.521-3 Tx | 6.4L.2.3.3 | In-band emissions for inter-band EN-DC with Tx Diversity within FR1 | Specify the new test case for PC2 and PC 1.5 inter-band EN-DC with Tx Diversity | Huawei | RAN5#105 (Nov-24) | R5-246919 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  | 100%
6.5H Output RF spectrum emissions for DC with UL MIMO
100 |  | 38.521-3 Tx | 6.5H | Output RF spectrum emissions for DC with UL MIMO | New sub-clause header | Huawei | RAN5#104 (Aug-24) |  |  | 0.1 | 0% |  | 0% |  |  | 0%
101 |  | 38.521-3 Tx | 6.5H.1 | Occupied bandwidth for EN-DC with UL MIMO | New sub-clause header |  | TBD |  |  | 0.1 | 0% |  | 0% |  |  | 0%
102 | Y | 38.521-3 Tx | 6.5H.1.3 | Occupied bandwidth for inter-band EN-DC with UL MIMO within FR1 | Specify the new test case for PC2 inter-band EN-DC with UL MIMO |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
103 |  | 38.521-3 Tx | 6.5H.2 | Out-of-band emissions for DC with UL MIMO | New sub-clause header |  | TBD |  |  | 0.1 | 0% |  | 0% |  |  | 0%
104 |  | 38.521-3 Tx | 6.5H.2.3 | Out-of-band emissions for inter-band EN-DC with UL MIMO within FR1 | New sub-clause header |  | TBD |  |  | 0.1 | 0% |  | 0% |  |  | 0%
105 |  | 38.521-3 Tx | 6.5H.2.3.0 | Minimum conformance requirements | Add the minimum requirements |  | TBD |  |  | 0.1 | 0% |  | 0% |  |  | 0%
106 | Y | 38.521-3 Tx | 6.5H.2.3.1 | Spectrum emission mask for inter-band EN-DC with UL MIMO within FR1 | Specify the new test case for PC2 inter-band EN-DC with UL MIMO |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
107 | Y | 38.521-3 Tx | 6.5H.2.3.2 | Additional spectrum emission mask for inter-band UL CA with UL MIMO | Specify the new test case for PC2 inter-band EN-DC with UL MIMO |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
108 | Y | 38.521-3 Tx | 6.5H.2.3.3 | NR ACLR for inter-band UL CA with UL MIMO | Specify the new test case for PC2 inter-band EN-DC with UL MIMO |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
109 |  | 38.521-3 Tx | 6.5H.3 | Spurious emission for DC with UL MIMO | New sub-clause header | Huawei | RAN5#104 (Aug-24) | R5-245157 |  | 0.1 | 100% |  | 100% |  |  | 100%
110 |  | 38.521-3 Tx | 6.5H.3.3 | Spurious emission for inter-band EN-DC with UL MIMO within FR1 | New sub-clause header | Huawei | RAN5#104 (Aug-24) | R5-245157 |  | 0.1 | 100% |  | 100% |  |  | 100%
126 |  | 38.521-3 Tx | 6.5H.3.3.0 | Minimum conformance requirements | Add the minimum requirements | Huawei | RAN5#104 (Aug-24) | R5-245157 |  | 1 | 100% |  | 100% |  |  | 100%
111 | Y | 38.521-3 Tx | 6.5H.3.3.1 | General spurious emissions for inter-band EN-DC with UL MIMO within FR1 | Specify the new test case for PC2 inter-band EN-DC with UL MIMO | Huawei | RAN5#104 (Aug-24) | R5-245157 |  | 1 | 100% |  | 100% |  |  | 100%
112 | Y | 38.521-3 Tx | 6.5H.3.3.2 | Spurious emissions for UE co-existence for inter-band EN-DC with UL MIMO within FR1 | Specify the new test case for PC2 inter-band EN-DC with UL MIMO | Huawei | RAN5#104 (Aug-24) | R5-245158 |  | 1 | 100% |  | 100% |  |  | 100%
113 |  | 38.521-3 Tx | 6.5H.4 | Additional spurious emission for DC with UL MIMO | New sub-clause header |  | TBD |  |  | 0.1 | 0% |  | 0% |  |  | 0%
114 | Y | 38.521-3 Tx | 6.5H.4.3 | Additional spurious emission for inter-band EN-DC with UL MIMO within FR1 | Specify the new test case for PC2 inter-band EN-DC with UL MIMO |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
115 |  | 38.521-3 Tx | 6.5H.5 | Transmit intermodulation for DC with UL MIMO | New sub-clause header |  | TBD |  |  | 0.1 | 0% |  | 0% |  |  | 0%
116 | Y | 38.521-3 Tx | 6.5H.5.3 | Transmit intermodulation for inter-band EN-DC with UL MIMO within FR1 | Specify the new test case for PC2 inter-band EN-DC with UL MIMO |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
6.5L Output RF spectrum emissions for DC with Tx Diversity
151 |  | 38.521-3 Tx | 6.5L | Output RF spectrum emissions for DC with Tx Diversity | New sub-clause header | Huawei | RAN5#104 (Aug-24) |  |  | 0.1 | 0% |  | 0% |  |  | 0%
152 |  | 38.521-3 Tx | 6.5L.1 | Occupied bandwidth for EN-DC with Tx Diversity | New sub-clause header |  | TBD |  |  | 0.1 | 0% |  | 0% |  |  | 0%
153 | Y | 38.521-3 Tx | 6.5L.1.3 | Occupied bandwidth for inter-band EN-DC with Tx Diversity within FR1 | Specify the new test case for PC2 inter-band EN-DC with TxD |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
154 |  | 38.521-3 Tx | 6.5L.2 | Out-of-band emissions for DC with Tx Diversity | New sub-clause header |  | TBD |  |  | 0.1 | 0% |  | 0% |  |  | 0%
155 |  | 38.521-3 Tx | 6.5L.2.3 | Out-of-band emissions for inter-band EN-DC with Tx Diversity within FR1 | New sub-clause header |  | TBD |  |  | 0.1 | 0% |  | 0% |  |  | 0%
156 |  | 38.521-3 Tx | 6.5L.2.3.0 | Minimum conformance requirements | Add the minimum requirements |  | TBD |  |  | 0.1 | 0% |  | 0% |  |  | 0%
157 | Y | 38.521-3 Tx | 6.5L.2.3.1 | Spectrum emission mask for inter-band EN-DC with Tx Diversity within FR1 | Specify the new test case for PC2 inter-band EN-DC with TxD |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
158 | Y | 38.521-3 Tx | 6.5L.2.3.2 | Additional spectrum emission mask for inter-band UL CA with Tx Diversity | Specify the new test case for PC2 inter-band EN-DC with TxD |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
159 | Y | 38.521-3 Tx | 6.5L.2.3.3 | NR ACLR for inter-band UL CA with Tx Diversity | Specify the new test case for PC2 inter-band EN-DC with TxD |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
160 |  | 38.521-3 Tx | 6.5L.3 | Spurious emission for DC with Tx Diversity | New sub-clause header | Huawei | RAN5#104 (Aug-24) | R5-245159 |  | 0.1 | 100% |  | 100% |  |  | 100%
161 |  | 38.521-3 Tx | 6.5L.3.3 | Spurious emission for inter-band EN-DC with Tx Diversity within FR1 | New sub-clause header | Huawei | RAN5#104 (Aug-24) | R5-245159 |  | 0.1 | 100% |  | 100% |  |  | 100%
162 |  | 38.521-3 Tx | 6.5L.3.3.0 | Minimum conformance requirements | Add the minimum requirements | Huawei | RAN5#104 (Aug-24) | R5-245159 |  | 1 | 100% |  | 100% |  |  | 100%
163 | Y | 38.521-3 Tx | 6.5L.3.3.1 | General spurious emissions for inter-band EN-DC with Tx Diversity within FR1 | Specify the new test case for PC2 inter-band EN-DC with TxD | Huawei | RAN5#104 (Aug-24) | R5-245159 |  | 1 | 100% |  | 100% |  |  | 100%
164 | Y | 38.521-3 Tx | 6.5L.3.3.2 | Spurious emissions for UE co-existence for inter-band EN-DC with Tx Diversity within FR1 | Specify the new test case for PC2 inter-band EN-DC with TxD | Huawei | RAN5#104 (Aug-24) | R5-245160 |  | 1 | 100% |  | 100% |  |  | 100%
165 |  | 38.521-3 Tx | 6.5L.4 | Additional spurious emission for DC with Tx Diversity | New sub-clause header |  | TBD |  |  | 0.1 | 0% |  | 0% |  |  | 0%
166 | Y | 38.521-3 Tx | 6.5L.4.3 | Additional spurious emission for inter-band EN-DC with Tx Diversity within FR1 | Specify the new test case for PC2 inter-band EN-DC with TxD |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
167 |  | 38.521-3 Tx | 6.5L.5 | Transmit intermodulation for DC with Tx Diversity | New sub-clause header |  | TBD |  |  | 0.1 | 0% |  | 0% |  |  | 0%
168 | Y | 38.521-3 Tx | 6.5L.5.3 | Transmit intermodulation for inter-band EN-DC with Tx Diversity within FR1 | Specify the new test case for PC2 inter-band EN-DC with TxD |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
TS 38.521-3: FR1 and FR2 Interworking operation with other radios RF test cases - Rx
117 |  | 38.521-3 Rx | 7.1 | General | Add general requirements for 3Tx EN-DC configurations | Huawei | RAN5#104 (Aug-24) | R5-245162 |  | 0.3 | 100% |  | 100% |  |  | 100%
118 |  | 38.521-3 Rx | 7.3B.2.0 | Minimum Conformance Requirements of Reference sensitivity for EN-DC | Add minimum requirements for 3Tx EN-DC configurations | Huawei | RAN5#104 (Aug-24) | R5-245162 |  | 0.3 | 100% |  | 100% |  |  | 100%
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
119 |  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Add applicability for test cases in 38.521-1 | Huawei | RAN5#103 (May-24) | R5-242932 R5-245163 |  | 1 | 100% | 100% |  |  | 100%
120 |  | 38.522 | 4.1.3 | NR interworking between NR FR1 and NR FR2 and between NR and LTE conformance test cases | Add applicability for test cases in 38.521-3 | Huawei | RAN5#103 (May-24) | R5-242932 R5-245163 R5-246921 |  | 1 | 100% |  | 100% |  |  | 100%
TR 38.905: Test Point analysis receiver and transmitter test cases
121 |  | 38.905 | 4.1 | Test point analysis for FR1 test cases in TS 38.521-1 | Add TP analysis for test cases in 38.521-1 | Huawei | RAN5#103 (May-24) | R5-242933 R5-242934 R5-245164 |  | 1 | 100% | 100% |  |  | 100%
122 |  | 38.905 | 4.3 | Test point analysis for test cases in TS 38.521-3 | Add TP analysis for test cases in 38.521-3 | Huawei | RAN5#103 (May-24) | R5-242935 R5-242936 R5-245164 |  | 1 | 100% |  | 100% |  |  | 100%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.