## Cover sheet
3GPP TSG-RAN5 Meeting #105 | [10 empty] | R5-24xxxx
Orlando, Florida, USA, 18th November 2024 - 22nd November 2024
Agenda Item: | 7.5.2
Source: | Apple
Title: | WP - UE Conformance Aspects - NR RRM enhancements
Work item code: | NR_RRM_enh-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
The objective of this RAN5 WI is to enable UE conformance testing for the Release 16 RRM enhancements related requirements. RAN5 conformance test procedures will be created to verify test requirements as per the scope being covered in RAN4.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  |  | 8 (+8) | 36 (+36)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR)
FR1
FR2
FR1 + FR2
NSA Option 3 (EN-DC)
FR1
FR2
FR1 + FR2
LTE
FDD
TDD
FDD + TDD
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [8 empty] | NSA Option 3 (EN-DC) | [8 empty] | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 |  |  | FR1 + FR2 |  |  | FR1 |  |  | FR2 |  |  | FR1 + FR2 |  |  | FDD |  |  | TDD |  |  | FDD + TDD
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508
UE specific test functions | 36.509
LTE RF/RRM
RF common parts | 36.521-1
RF Rx test cases | 36.521-1 Rx
RF Tx test cases | 36.521-1 Tx
RF Demod test cases | 36.521-1 Demod
Applicability RF. Demod/QSI and RRM test cases | 36.521-2
RRM test cases | 36.521-3
Test Tolerances analysis RRM test cases | 36.903
Test Tolerances analysis receiver test cases | 36.904
Test Point analysis receiver and transmitter test cases | 36.905
LTE RAN and CN protocols
Protocol test cases | 36.523-1
Applicability Protocol test cases | 36.523-2
Test suites (TTCN) | 36.523-3
5GS
5GS Common
Common test environment | 38.508-1
Common ICS | 38.508-2
UE specific test functions | 38.509
NR RF/RRM
FR1 RF common parts | 38.521-1
FR1 RF Tx test cases | 38.521-1 Tx
FR1 RF Rx test cases | 38.521-1 Rx
FR2 RF common parts | 38.521-2
FR2 RF Tx test cases | 38.521-2 Tx
FR2 RF Rx test cases | 38.521-2 Rx
FR1 and FR2 Interworking operation with other radios RF common parts | 38.521-3
FR1 and FR2 Interworking operation with other radios RF Tx test cases | 38.521-3 Tx
FR1 and FR2 Interworking operation with other radios RF Rx test cases | 38.521-3 Rx
RF Demod/QSI test cases | 38.521-4
RRM test cases | 38.533 |  | 0 | 0
Applicability RF. Demod/QSI and RRM test cases | 38.522
Test Tolerances analysis RRM and RF Rx test cases | 38.903
Test Point analysis receiver and transmitter test cases | 38.905
5GS RAN and CN protocols
Protocol test cases | 38.523-1
Applicability Protocol test cases | 38.523-2
Test suites (TTCN) | 38.523-3
UE Positioning
UE Positioning Min. Performance test cases | 37.571-1
UE Positioning Protocol test cases | 37.571-2
Applicability and ICS UE Positioning test cases | 37.571-3
UE Positioning Test sutes (TTCN) | 37.571-4
UE Positioning test scenarios and assistance data | 37.571-5
IMS
IMS over LTE protocol test cases | 34.229-1
IMS over 5GS protocol test cases | 34.229-5
Applicability and ICS IMS test cases | 34.229-2
IMS Test suite (TTCN) | 34.229-3
Mission Critical Services
MC Common test environment | 36.579-1
MCPTT UE test cases | 36.579-2
MC Server Application test cases | 36.579-3
Applicability and ICS MC test cases | 36.579-4
MC Test suite (TTCN) | 36.579-5
MC Video UE test cases | 36.579-6
MC Data UE test cases | 36.579-7
5 References
[1] RP-yyxxxx | <WID document title>
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP - UE Conformance Aspects - NR RRM enhancements | [13 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | [8 empty] | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_RRM_enh-UEConTest
WP Scope: |  | The purpose of this document is to create and track development of test requirements and procedures for new Release 16 RRM Enhancements | [15 empty] | vs Area
WP Resp: |  | Xinrong Wang |  |  | xinrong_wang@apple.com | [6 empty] | WP item completion |  |  |  |  | SA Option 2 (SA NR) |  |  | NSA Option 3 (EN-DC) |  |  | LTE
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | WP - UE Conformance Aspects - NR RRM enhancements | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | TT | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) | LTE |  | FR1 | FR2 | FR1 + FR2 | FR1 | FR2 | FR1 + FR2 | FDD | TDD | FDD + TDD
Overall
[15 empty] | Number of WP items |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | Sum weight of WP items |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | Contribution by work plan analysis |  | 5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
TS 38.522: Applicability for RF, Demod/CSI reporting and RRM test cases
TBD |  | 38.522 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  |  | 0.1 | 100%
TBD |  | 38.522 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced for 38.521-x and 38.533. |  | TBD |  |  |  | 0.1 | 100%
TS 38.533: RRM test cases
EN_DC with all NR cells in FR1
|  | 38.533 | 4.5.2 | Interruption |  |  |  | R5-227188 |  |  | 0.1 | 100%
1 | Y | 38.533 | 4.5.2.8 | E-UTRAN - NR FR1 interruptions at NR SRS carrier based switching in asynchronous EN-DC | Rel16 test requirements for SRS carrier based switching | Ericsson | RAN5#98 (Feb-23) | R5-227189 R5-234977 R5-235463 R5-242641 R5-243754 R5-244769 | Done R5-242629 | Aligned with TS 38.133 Clause A.4.5.2.8 (R4-2103608) 38.533 title slightly different (Apple) | 1 | 95%
2 | Y | 38.533 | 4.5.2.9 | E-UTRAN – NR interruptions at E-UTRA SRS carrier based switching | Rel16 test requirements for SRS carrier based switching | Ericsson | RAN5#98 (Feb-23) | R5-227190 R5-234977 R5-235464 R5-242641 R5-243755 R5-244770 | Done R5-242629 | Aligned with TS 38.133 Clause A.4.5.2.9 (R4-2103608) 38.533 title slightly different (Apple) | 1 | 95%
|  | 38.533 | 4.5.3 | SCell activation and deactivation delay | [6 empty] | 0.1 | 100%
3 | Y | 38.533 | 4.5.3.4 | SCell Activation and deactivation of multiple unknown SCells in FR1 with single activation/deactivation command | Rel16 test requirements for Multiple Scell activation |  |  | Test case missing | TT missing | Aligned with TS 38.133 Clause A.4.5.3.4 (R4-2103608) TC (Apple) and TT missing | 1 | 0%
|  | 38.533 | 4.5.6 | Active BWP switch
|  | 38.533 | 4.5.6.3 | Simultaneous DCI-based and Timer-based Active BWP Switch on multiple CCs |  |  |  | R5-234428 |  |  | 0.1 | 100%
4 | Y | 38.533 | 4.5.6.3.1 | Simultaneous E-UTRAN – NR PSCell FR1 DL active BWP switch in non-DRX in EN-DC on multiple CCs | Rel16 test requirements for DCI-based and Timer-based Active BWP switch | Huawei, HiSilicon | RAN5#98 (Feb-23) | R5-234428 | TT missing | Aligned with TS 38.133 Clause A.4.5.6.3.1 (R4-2103608) Test parameters in brackets (Apple) TT missing | 1 | 70%
|  | 38.533 | 4.5.6.4 | Simultaneous RRC-based Active BWP Switch on multiple CCs |  |  |  | R5-243235 |  |  | 0.1 | 100%
5 | Y | 38.533 | 4.5.6.4.1 | E-UTRAN – NR PSCell FR1 DL active BWP switch in non-DRX in synchronous EN-DC on multiple CCs | Rel16 test requirements for RRC based Active BWP switch | Huawei, HiSilicon | RAN5#98 (Feb-23) | R5-234429 Test case missing | TT missing | Aligned with TS 38.133 Rel-18 Clause A.4.5.6.4.1 (R4-2108421 with clause# 4.5.6.4. In Rel-16 it is 4.5.6.5.1, but in Rel-18 it is 4.5.6.4.1) Need to move the conents in 4.5.6.5 to 4.5.6.4. R5-234429 TC (Apple) and TT missing | 1 | 65%
|  | 38.533 | 4.5.9 | UE specific CBW change |  |  |  | R5-237183 |  |  | 0.1 | 100%
6 | Y | 38.533 | 4.5.9.1 | UE specific CBW change on FR1 NR PSCell with non-DRX in synchronous EN-DC | Rel16 test requirements for UE specific CBW change | Apple | RAN5#101 (Nov-23) | R5-237184 R5-241335 R5-241893 | Done R5-241337 | Aligned with TS 38.133 Clause A.4.5.9.1 (R4-2103608) Message contents missing (Apple) | 1 | 90%
|  | 38.533 | 4.6.6 | Measurements with Autonomous Gaps |  |  |  | R5-237185 |  |  | 0.1 | 100%
7 | Y | 38.533 | 4.6.6.1 | EN-DC intra-frequency CGI identification of NR FR1 cell with autonomous gaps in synchronous EN-DC | Rel16 test requirements for CGI Reading | Apple | RAN5#101 (Nov-23) | R5-237715 | TT missing | Aligned with TS 38.133 Clause A.4.6.6.1 (R4-2103608) Message contents (Apple) and TT missing | 1 | 70%
EN_DC with one or more NR cells in FR2
|  | 38.533 | 5.5.2 | Interruption |  |  |  | R5-227191 |  |  | 0.1 | 100%
8 | Y | 38.533 | 5.5.2.7 | E-UTRAN – NR FR2 interruptions at E-UTRA SRS carrier based switching | Rel16 test requirements for SRS carrier based switching | Ericsson | RAN5#99 (May-23) | R5-227192 R5-234977 R5-235900 R5-243706 | TT missing | Aligned with TS 38.133 Clause A.5.5.2.7 (R4-2103608) 38.533 title sightly different (Apple) Test applicability and procedure need more work. TT missing | 1 | 70%
9 | Y | 38.533 | 5.5.2.8 | E-UTRAN – NR FR2 interruptions at NR SRS carrier based switching | Rel16 test requirements for SRS carrier based switching | Ericsson | RAN5#99 (May-23) | R5-227193 R5-234977 R5-243706 | TT missing | Aligned with TS 38.133 Clause A.5.5.2.8 (R4-2103608) 38.533 title sightly different (Apple) Test applicability and procedure need more work. TT missing | 1 | 60%
|  | 38.533 | 5.5.3 | SCell Activation and Deactivation Delay |  |  |  | R5-243238 |  |  | 0.1 | 100%
10 | Y | 38.533 | 5.5.3.6 | Multiple SCell Activation and deactivation of one unknown SCell and one known SCell in FR2 | Rel16 test requirements for Multiple Scell activation and deactivation |  |  | Test case missing | TT missing | Aligned with TS 38.133 Clause A.5.5.3.6 (R4-2103608) TC (Apple) and TT missing | 1 | 0%
|  | 38.533 | 5.5.6 | Active BWP switch
|  | 38.533 | 5.5.6.3 | Simultaneous DCI-based and Timer-based Active BWP Switch on multiple CCs |  |  |  | R5-237187 |  |  | 0.1 | 100%
11 | Y | 38.533 | 5.5.6.3.1 | E-UTRAN – NR PSCell FR2 and NR SCell FR2 DL active BWP switch on multiple CCs in synchronous EN-DC | Rel16 test requirements forActive BWP Switch | Apple | RAN5#101 (Nov-23) | R5-237716 R5-241335 R5-241893 | Done R5-241894 | Aligned with TS 38.133 Clause A.5.5.6.3.1 (R4-2103608) Test procedure and message contents missing (Apple) | 1 | 90%
|  | 38.533 | 5.5.6.5 | Simultaneous RRC-based Active BWP Switch on multiple CC |  |  |  | R5-243239 |  |  | 0.1 | 100%
12 | Y | 38.533 | 5.5.6.5.1 | E-UTRAN – NR PSCell FR2 and NR SCell FR2 DL active BWP switch on multiple CCs with non-DRX in synchronous EN-DC | Rel16 test requirements for active BWP Switch |  |  | Test case missing | TT missing | Aligned with TS 38.133 Clause A.5.5.6.5.1 (R4-2108031 with clause# A.5.5.6.4.1. In the spec its clause# is 5.5.6.5.1) TC (Apple) and TT missing | 1 | 0%
|  | 38.533 | 5.5.9 | Uplink Spatial Relation Switch |  |  |  | R5-235166 |  |  | 0.1 | 100%
|  | 38.533 | 5.5.9.1 | MAC-CE based Uplink Spatial Relation Switch
13 | Y | 38.533 | 5.5.9.1.1 | E-UTRAN – NR PSCell FR2 uplink spatial relation switch for a known spatial relation | Rel16 test requirements for UE uplink spatial relation switch | Apple | RAN5#99 (May-23) | R5-235167 R5-235172 R5-235723 | Done R5-235736 | Aligned with TS 38.133 Clause A.5.5.9.1.1 (R4-2103608) 38.533 title sightly different (Apple) Message contents missing (Apple) | 1 | 90%
|  | 38.533 | 5.5.9.2 | RRC based Uplink Spatial Relation Switch |  |  |  | R5-235166 |  |  | 0.1 | 100%
14 | Y | 38.533 | 5.5.9.2.1 | E-UTRAN – NR PSCell FR2 spatial relation switch associated with a known DL-RS | Rel16 test requirements for UE uplink spatial relation switch | Apple | RAN5#99 (May-23) | R5-235168 R5-235172 R5-235723 | Done R5-235737 | Aligned with TS 38.133 Clause A.5.5.9.2.1 (R4-2103608) 38.533 title sightly different (Apple) Message contents missing (Apple) | 1 | 90%
|  | 38.533 | 5.5.10 | UE specific CBW change |  |  |  | R5-237191 |  |  | 0.1 | 100%
15 | Y | 38.533 | 5.5.10.1 | UE specific CBW change on FR2 NR PSCell | Rel16 test requirements for UE specific CBW change | Apple | RAN5#101 (Nov-23) | R5-237192 | TT missing | Aligned with TS 38.133 Clause A.5.5.10.1 (R4-2103608) Message contents (Apple) and TT missing | 1 | 70%
|  | 38.533 | 5.6.5 | Measurements with Autonomous Gaps |  |  |  | R5-237193 |  |  | 0.1 | 100%
16 | Y | 38.533 | 5.6.5.1 | EN-DC inter-frequency CGI identification of NR neighbor cell in FR2 | Rel16 test requirements for CGI Reading | Apple | RAN5#101 (Nov-23) | R5-237718 | TT missing | Aligned with TS 38.133 Clause A.5.6.5.1 (R4-2103608 with clause# 5.6.4.1. In the spec its clause# is 5.6.5.1) Message contents (Apple) and TT missing | 1 | 70%
NR Standalone in FR1
|  | 38.533 | 6.5.2 | Interruption |  |  |  | R5-227194 |  |  | 0.1 | 100%
17 | Y | 38.533 | 6.5.2.2 | SA interruptions at NR SRS carrier based switching | Rel16 test requirements for SRS carrier based switching | Ericsson | RAN5#99 (May-23) | R5-227830 R5-234432 R5-234977 R5-235902 R5-242641 R5-243756 R5-244771 | Done R5-242629 | Aligned with TS 38.133 Clause A.6.5.2.2 (R4-2103608) 38.533 title sightly different (Apple) | 1 | 100%
|  | 38.533 | 6.5.6 | Active BWP switch
|  | 38.533 | 6.5.6.3 | Simultaneous DCI-based and Timer-based Active BWP Switch on multiple CCs |  |  |  | R5-234430 |  |  | 0.1 | 100%
18 | Y | 38.533 | 6.5.6.3.1 | NR FR1- NR FR1 DL active BWP switch on multiple CCs with non-DRX in SA | Rel16 test requirements for UE Active BW Switch | Huawei, HiSilicon | RAN5#99 (May-23) | R5-234430 | TT missing | Aligned with TS 38.133 Clause A.6.5.6.3.1 (R4-2103608) Test parameters in brackets (Apple) TT missing | 1 | 70%
|  | 38.533 | 6.5.6.5 | Simultaneous RRC-based Active BWP Switch on multiple CCs |  |  |  | R5-234431 |  |  | 0.1 | 100%
19 | Y | 38.533 | 6.5.6.5.1 | NR FR1- NR FR1 DL active BWP switch on multiple CCs with non-DRX in SA | Rel16 test requirements for active BWP switch | Huawei, HiSilicon | RAN5#100 (Aug-23) | R5-234431 | TT missing | Aligned with TS 38.133 Clause A.6.5.6.5.1 (R4-2108030, A.6.5.6.X.1) 38.533 title sightly different (Apple) Test parameters in brackets (Apple) TT missing | 1 | 70%
|  | 38.533 | 6.5.8 | UE specific CBW change |  |  |  | R5-231884 |  |  | 0.1 | 100%
20 | Y | 38.533 | 6.5.8.1 | UE specific CBW change on PCell in FR1 in non-DRX | Rel16 test requirements for UE specific CBW change | Apple | RAN5#99 (May-23) | R5-230529 R5-230530 R5-231884 R5-232489 R5-236748 R5-240700 | Done R5-230531 | Aligned with TS 38.133 Clause A.6.5.8.1 (R4-2103608) | 1 | 100%
|  | 38.533 | 6.6.2 | Inter-frequency Measurement |  |  |  | R5-227196 |  |  | 0.1 | 100%
21 | Y | 38.533 | 6.6.2.9 | SA event triggered reporting tests with additional mandatory gap pattern | Rel16 test requirements for Mandatory Gap Patterns | Ericsson | RAN5#99 (May-23) | R5-227197 R5-237015 R5-237018 R5-237714 R5-241829 R5-242636 R5-242641 | Done R5-242636 | Aligned with TS 38.133 Clause A.6.6.2.9 (R4-2103608) 38.533 title slight different (Apple) | 1 | 100%
22 | Y | 38.533 | 6.6.2.10 | SA event triggered reporting tests for FR1 when DRX is used | Rel16 Inter-Frequency Measurement without MG | Ericsson | RAN5#99 (May-23) | R5-227198 R5-237018 R5-237712 R5-242637 R5-242641 | Done R5-242637 | Aligned with TS 38.133 Clause A.6.6.2.10 (R4-2103608) 38.533 title slight different (Apple) | 1 | 100%
23 | Y | 38.533 | 6.6.2.11 | SA event triggered reporting tests for FR1 without gap when DRX is not used | Rel16 Inter-Frequency Measurement without MG | Ericsson | RAN5#99 (May-23) | R5-227199 R5-237018 R5-237713 R5-242638 R5-242641 | Done R5-242638 | Aligned with TS 38.133 Clause A.6.6.2.11 (R4-2103608) 38.533 title slight different (Apple) | 1 | 100%
|  | 38.533 | 6.6.7 | NR Measurements with autonomous gaps |  |  |  | R5-237195 |  |  | 0.1 | 100%
24 | Y | 38.533 | 6.6.7.1 | SA intra-frequency CGI identification of NR neighbor cell in FR1 | Rel16 test requirements for CGI Reading | Apple | RAN5#101 (Nov-23) | R5-237760 | TT missing | Aligned with TS 38.133 Clause A.6.6.7.1 (R4-2103608) Message contents (Apple) and TT missing | 1 | 70%
25 | Y | 38.533 | 6.6.7.2 | Identification of a new CGI of inter-RAT E-UTRA cell using autonomous gaps in NR SA | Rel16 test requirements for CGI Reading | Apple | RAN5#101 (Nov-23) | R5-237761 | TT missing | Aligned with TS 38.133 Clause A.6.6.7.2 (R4-2103608) Message contents (Apple) and TT missing | 1 | 70%
NR Standalone in FR2
|  | 38.533 | 7.5.2 | Interruption |  |  |  | R5-237198 |  |  | 0.1 | 100%
26 | Y | 38.533 | 7.5.2.2 | SA interruptions at NR SRS carrier-based switching | Rel16 test requirements for Interruption | Apple | RAN5#101 (Nov-23) | R5-237762 | TT missing | Aligned with TS 38.133 Clause A.7.5.2.2 (R4-2103608) Test procedure, message contents (Apple) and TT missing | 1 | 60%
|  | 38.533 | 7.5.3 | SCell Activation and Deactivation Delay | [6 empty] | 0.1 | 100%
27 | Y | 38.533 | 7.5.3.3 | SCell Activation and deactivation for SCell in FR2 inter-band in non-DRX | Rel16 test requirements for FR2 Inter-Band CA | Nokia | RAN5#100 (Aug-23) | R5-233618 R5-233967 | Done R5-233966 | Aligned with TS 38.133 Clause A.7.5.3.3 (R4-2103608) | 1 | 100%
|  | 38.533 | 7.5.6 | Active BWP switch
|  | 38.533 | 7.5.6.3 | Simultaneous DCI-based and Timer-based Active BWP Switch on multiple CCs |  |  |  | R5-237200 |  |  | 0.1 | 100%
28 | Y | 38.533 | 7.5.6.3.1 | Active BWP switch on multiple SCells with non-DRX in SA | Rel16 test requirements for BWP switching on multiple CCs | Apple | RAN5#101 (Nov-23) | R5-237763 | TT missing | Aligned with TS 38.133 Clause A.7.5.6.3.1 (R4-2103608) Test procedure, message contents (Apple) and TT missing | 1 | 60%
|  | 38.533 | 7.5.6.5 | Simultaneous RRC-based Active BWP Switch on multiple CCs | [6 empty] | 0.1 | 100%
29 | Y | 38.533 | 7.5.6.5.1 | Active BWP switch on multiple SCells with non-DRX in SA | Rel16 test requirements for active BWP switch |  |  | Test case missing | TT missing | Aligned with TS 38.133 Clause A.7.5.6.5.1 (R4-2108027 with clause# 7.5.6.4.1) TC (Apple) and TT missing | 1 | 0%
|  | 38.533 | 7.5.9 | Uplink Spatial Relation Switch Delay |  |  |  | R5-235840 |  |  | 0.1 | 100%
|  | 38.533 | 7.5.9.1 | MAC-CE based Spatial Relation switch
30 | Y | 38.533 | 7.5.9.1.1 | NR PCell FR2 spatial relation associated with known DL-RS | Rel16 test requirements for UE uplink spatial relation switch | Apple | RAN5#100 (Aug-23) | R5-235170 R5-235172 R5-235735 | Done R5-235736 | Aligned with TS 38.133 Clause A.7.5.9.1.1 (R4-2103608) 38.533 title slight different (Apple) Message contents missing (Apple) | 1 | 90%
|  | 38.533 | 7.5.9.2 | RRC based spatial relation switch | [6 empty] | 0.1 | 100%
31 | Y | 38.533 | 7.5.9.2.1 | NR PCell FR2 spatial relation switch associated with a known DL-RS | Rel16 test requirements for UE uplink spatial relation switch | Apple | RAN5#100 (Aug-23) | R5-235171 R5-235172 R5-235735 | Done R5-235737 | Aligned with TS 38.133 Clause A.7.5.9.2.1 (R4-2103608) 38.533 title slight different (Apple) Message contents missing (Apple) | 1 | 90%
|  | 38.533 | 7.5.10 | UE specific CBW change |  |  |  | R5-237202 |  |  | 0.1 | 100%
32 | Y | 38.533 | 7.5.10.1 | NR FR2 UE specific CBW change of PCell with non-DRX in SA | Rel16 test requirements on UE specific CBW | Apple | RAN5#101 (Nov-23) | R5-237203 | TT missing | Aligned with TS 38.133 Clause A.7.5.10.1 (R4-2103608) Message contents (Apple) and TT missing | 1 | 70%
|  | 38.533 | 7.6.2 | Inter-frequency Measurements |  |  |  | R5-242647 |  |  | 0.1
33 | Y | 38.533 | 7.6.2.9 | SA event triggered reporting tests For FR2 without SSB time index detection when DRX is not used (PCell in FR2) (rel16 additional mandatory gap pattern 17) | Rel16 test requirements for Mandatory Gap Patterns | Apple | RAN5#101 (Nov-23) | R5-237764 | TT missing | Aligned with TS 38.133 Clause A.7.6.2.9 (R4-2103608, not mention on the cover page) Test procedure, message contents (Apple) and TT missing | 1 | 60%
34 | Y | 38.533 | 7.6.2.10 | SA event triggered reporting test without gap under non-DRX | Rel16 test requirements for Measurements without MG for Ues supporting interFrequencyMeas-NoGap-r16 | Ericsson | RAN5#102 (Feb-24) | R5-242641 R5-242646 R5-243757 | Done R5-243759 | Aligned with TS 38.133 Clause A.7.6.2.10 (R4-2103608, not mention on the cover page) 38.533 title slightly different (Apple) | 1 | 100%
35 | Y | 38.533 | 7.6.2.11 | SA event triggered reporting test without gap under DRX | Rel16 test requirements for Measurements without MG for Ues supporting interFrequencyMeas-NoGap-r16 | Ericsson | RAN5#102 (Feb-24) | R5-243758 R5-242641 | Done R5-242631 | Aligned with TS 38.133 Clause A.7.6.2.11 (R4-2103608, not mention on the cover page) 38.533 title slightly different (Apple) | 1 | 100%
|  | 38.533 | 7.6.5 | NR Measurements with autonomous gaps |  |  |  | R5-237205 |  |  | 0.1
36 | Y | 38.533 | 7.6.5.1 | SA inter frequency CGI reporting in autonomous gaps test (PCell in FR2) | Rel16 test requirements for Mandatory Gap Patterns | Apple | RAN5#101 (Nov-23) | R5-237765 | TT missing | Aligned with TS 38.133 Clause A.7.6.5.1 (R4-2103608) Message contents (Apple) and TT missing | 1 | 70%
Annex A
|  | 38.533 | Annex A.13 | Channel bandwidth (CBW) configurations | Rel16 updates for DL and UL CBW patterns for UE specific CBW configuration | Huawei, HiSilicon | RAN5#100 (Aug-23) | R5-230528 R5-232490 R5-233773 |  | Aligned with TS 38.133 clause A.3.25 (R4-2103608 clause# A.3.23) | 0.5 | 100%
|  | 38.533 | Annex A.15 | SRS configuration | SRS configuration | Ericsson | RAN5#100 (Aug-23) | R5-235903 |  | Aligned with TS 38.133 clause A.3.24 (R4-2103608 clause# A.3.24) | 0.5 | 100%
|  | 38.533 | Annex A.xx | Spatial relation configuration | Spatial relation configuration |  |  | Missing |  | Aligned with TS 38.133 clause A.3.23 (R4-2103608 clause# A.3.23) for A.5.5.9.1.1 etc. Missing (Apple) | 0.5 | 0%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
|  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | 0.1 | 100%
TBD |  | 38.903 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0.1 | 100%
TBD |  | 38.903 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  |  | 0.1 | 100%
TR 38.905: Test Point analysis receiver and transmitter test cases
|  | 38.905 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | 0.1 | 100%
TBD |  | 38.905 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0.1 | 100%
TBD |  | 38.905 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  |  | 0.1 | 100%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on L6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.

## mistakenly finished
Mistakenly finished under this WI (NR_RRM_enh-UEConTest)
TC (38.533) | TC Title | Tdoc | Correct WI Code | RAN4 Tdoc
4.7.8.1.1 | EN-DC FR1 CSI-RSRP absolute measurement accuracy [intra-frequency] | R5-241830 R5-244003 R5-244004 | NR_CSIRS_L3meas (RAN4: CATT, OPPO) (no associated RAN5 WI yet) | R4-2109086
4.7.8.2.1 | EN-DC FR1 CSI-RSRP absolute measurement accuracy [inter frequency] | R5-241198 R5-244003 R5-244004 | NR_CSIRS_L3meas | R4-2109086
5.5.7.1 | EN-DC FR2 Addition and Release Delay of NR PSCell | R5-245900 | NR_NewRAT | R4-2207541 (maintenance CR) R4-2115454 (maintenance CR) R4-2115457 (maintenance CR)
5.6.7.1 | EN-DC event triggered reporting test without gap under non-DRX | R5-243707 | NR_CSIRS_L3meas | R4-2109086
5.6.8.1 | EN-DC event triggered reporting tests for NR FR2 cell when DRX is used | R5-243708 R5-245930 R5-244778 | NR_CSIRS_L3meas | R4-2109086
5.7.7.1 | EN-DC intra-frequency case measurement accuracy with FR2 serving cell and FR2 target cell [CSI-RSRP] | R5-243709 R5-245931 R5-244781 | NR_CSIRS_L3meas | R4-2109086
5.7.7.2 | EN-DC inter-frequency case measurement accuracy with FR2 serving cell and FR2 target cell [CSI-RSRP] | R5-243710 R5-245932 R5-244784 | NR_CSIRS_L3meas | R4-2109086
5.7.8.1 | EN-DC intra-frequency measurement accuracy with FR2 serving cell and FR2 target cell [CSI-RSRQ] | R5-241317 R5-241318 R5-246047 R5-245732 R5-245736 | NR_CSIRS_L3meas | R4-2109086
5.7.8.2 | EN-DC Inter-frequency measurement accuracy with FR2 serving cell and FR2 TDD target cell [CSI-RSRQ] | R5-241319 R5-246048 R5-245733 R5-245737 | NR_CSIRS_L3meas | R4-2109086
5.7.9.1 | EN-DC intra-frequency measurement accuracy with FR2 serving cell and FR2 TDD target cell [CSI-SINR] | R5-241320 R5-241321 R5-246049 R5-245734 R5-245738 | NR_CSIRS_L3meas | R4-2109086
5.7.9.2 | EN-DC inter-frequency measurement accuracy with FR2 serving cell and FR2 TDD target cell [CSI-SINR] | R5-241322 R5-246050 R5-245735 R5-245739 | NR_CSIRS_L3meas | R4-2109086
6.7.10.1.1 | NR SA FR1 CSI-RSRP absolute measurement accuracy | R5-245894 | NR_CSIRS_L3meas | R4-2109086
6.7.10.1.2 | NR SA FR1 CSI-RSRP relative measurement accuracy | R5-245895 | NR_CSIRS_L3meas | R4-2109086
6.7.10.2.1 | NR SA FR1-FR1 CSI-RSRP absolute measurement accuracy | R5-245896 | NR_CSIRS_L3meas | R4-2109086
6.7.10.2.2 | NR SA FR1-FR1 CSI-RSRP relative measurement accuracy | R5-245897 | NR_CSIRS_L3meas | R4-2109086
7.7.7.1.1 | NR SA FR2 CSI-RSRP measurement accuracy | R5-245898 | NR_CSIRS_L3meas | R4-2109086
7.7.7.2.1 | NR SA FR2-FR2 CSI-RSRP measurement accuracy | R5-245899 | NR_CSIRS_L3meas | R4-2109086
7.7.8.1 | SA intra-frequency measurement accuracy with FR2 serving cell and FR2 target cell [CSI-RSRQ] | R5-241329 R5-241330 R5-246047 R5-245732 R5-245736 | NR_CSIRS_L3meas | R4-2109086
7.7.8.2 | SA inter-frequency measurement accuracy with FR2 serving cell and FR2 TDD target cell [CSI-RSRQ] | R5-241331 R5-246048 R5-245733 R5-245737 | NR_CSIRS_L3meas | R4-2109086
7.7.9.1 | SA intra-frequency case measurement accuracy with FR2 serving cell and FR2 target cell [CSI-SINR] | R5-241332 R5-241333 R5-246049 R5-245734 R5-245738 | NR_CSIRS_L3meas | R4-2109086
7.7.9.2 | SA inter-frequency measurement accuracy with FR2 serving cell and FR2 TDD target cell [CSI-SINR] | R5-241831 R5-246050 R5-245735 R5-245739 | NR_CSIRS_L3meas | R4-2109086

## NR_CSIRS_L3meas
TCs under WI: NR_CSIRS_L3meas
TC (38.533) | TC Title | Tdoc | Correct WI Code | RAN4 Tdoc | Notes
4.6.8.1 | EN-DC event triggered reporting tests without gap under DRX [CSI-RS] |  | NR_CSIRS_L3meas | R4-2109086 clause# 4.6.6.1
4.6.9.1 | EN-DC event triggered reporting tests for FR1 cell when non-DRX is used [CSI-RS] |  | NR_CSIRS_L3meas | R4-2109086 clause# 4.6.7.1
4.7.8.1.1 | EN-DC FR1 CSI-RSRP absolute measurement accuracy [intra-frequency] (EN-DC Intra-frequency measurement accuracy with FR1 serving cell and FR1 target cell) | R5-241830 R5-244003 R5-244004 | NR_CSIRS_L3meas (RAN4: CATT, OPPO) (no associated RAN5 WI yet) | R4-2109086 clause# 4.7.7.1 | Done
4.7.8.2.1 | EN-DC FR1 CSI-RSRP absolute measurement accuracy [inter frequency] (EN-DC inter-frequency measurement accuracy with FR1 serving cell and FR1 target cell) | R5-241198 R5-244003 R5-244004 | NR_CSIRS_L3meas | R4-2109086 clause# 4.7.7.2 | Done
4.7.9.1 | EN-DC Intra-frequency measurement accuracy with FR1 serving cell and FR1 target cell [CSI-RSRQ] |  | NR_CSIRS_L3meas | R4-2109086 clause# 4.7.8.1
4.7.9.2 | EN-DC Inter-frequency measurement accuracy with FR1 serving cell and FR1 target cell [CSI-RSRQ] |  | NR_CSIRS_L3meas | R4-2109086 clause# 4.7.8.2
4.7.10.1 | EN-DC Intra-frequency measurement accuracy with FR1 serving cell and FR1 target cell [CSI-SINR] |  | NR_CSIRS_L3meas | R4-2109086 clause# 4.7.9.1
4.7.10.2 | EN-DC Inter-frequency measurement accuracy with FR1 serving cell and FR1 target cell [CSI-SINR] |  | NR_CSIRS_L3meas | R4-2109086 clause# 4.7.9.2
5.6.7.1 | EN-DC event triggered reporting test without gap under non-DRX [CSI-RS] | R5-243707 | NR_CSIRS_L3meas | R4-2109086 clause# 5.6.4.1 | Done
5.6.8.1 | EN-DC event triggered reporting tests for NR FR2 cell when DRX is used [CSI-RS] | R5-243708 R5-245930 R5-244778 | NR_CSIRS_L3meas | R4-2109086 clause# 5.6.5.1 | Done
5.7.7.1 | EN-DC intra-frequency case measurement accuracy with FR2 serving cell and FR2 target cell [CSI-RSRP] | R5-243709 R5-245931 R5-244781 | NR_CSIRS_L3meas | R4-2109086 clause# 5.7.6.1 | Done
5.7.7.2 | EN-DC inter-frequency case measurement accuracy with FR2 serving cell and FR2 target cell [CSI-RSRP] | R5-243710 R5-245932 R5-244784 | NR_CSIRS_L3meas | R4-2109086 clause# 5.7.6.2 | Done
5.7.8.1 | EN-DC intra-frequency measurement accuracy with FR2 serving cell and FR2 target cell [CSI-RSRQ] | R5-241317 R5-241318 R5-246047 R5-245732 R5-245736 | NR_CSIRS_L3meas | R4-2109086 clause# 5.7.7.1 | Done
5.7.8.2 | EN-DC Inter-frequency measurement accuracy with FR2 serving cell and FR2 TDD target cell [CSI-RSRQ] | R5-241319 R5-246048 R5-245733 R5-245737 | NR_CSIRS_L3meas | R4-2109086 clause# 5.7.7.2 | Done
5.7.9.1 | EN-DC intra-frequency measurement accuracy with FR2 serving cell and FR2 TDD target cell [CSI-SINR] | R5-241320 R5-241321 R5-246049 R5-245734 R5-245738 | NR_CSIRS_L3meas | R4-2109086 clause# 5.7.8.1 | Done
5.7.9.2 | EN-DC inter-frequency measurement accuracy with FR2 serving cell and FR2 TDD target cell [CSI-SINR] | R5-241322 R5-246050 R5-245735 R5-245739 | NR_CSIRS_L3meas | R4-2109086 clause# 5.7.8.2 | Done
6.6.10.1 | SA event triggered reporting tests without gap under non-DRX [CSI-RS, intra-frequency] |  | NR_CSIRS_L3meas | R4-2109086 clause# 6.6.7.1
6.6.11.1 | SA event triggered reporting tests with gap under DRX [CSI-RS, inter frequency] |  | NR_CSIRS_L3meas | R4-2109086 clause# 6.6.8.1
6.7.10.1.1 | NR SA FR1 CSI-RSRP absolute measurement accuracy (SA: intra-frequency case measurement accuracy with FR1 serving cell and FR1 target cell) [CSI-RSRP] | R5-245894 | NR_CSIRS_L3meas | R4-2109086 clause# 6.7.9.1 | Done
6.7.10.1.2 | NR SA FR1 CSI-RSRP relative measurement accuracy (SA: intra-frequency case measurement accuracy with FR1 serving cell and FR1 target cell) [CSI-RSRP] | R5-245895 | NR_CSIRS_L3meas | R4-2109086 clause# 6.7.9.1 | Done
6.7.10.2.1 | NR SA FR1-FR1 CSI-RSRP absolute measurement accuracy (SA inter-frequency case measurement accuracy with FR1 serving cell and FR1 target cell) [CSI-RSRP] | R5-245896 | NR_CSIRS_L3meas | R4-2109086 clause# 6.7.9.2 | Done
6.7.10.2.2 | NR SA FR1-FR1 CSI-RSRP relative measurement accuracy (SA inter-frequency case measurement accuracy with FR1 serving cell and FR1 target cell) [CSI-RSRP] | R5-245897 | NR_CSIRS_L3meas | R4-2109086 clause# 6.7.9.2 | Done
6.7.11.1 | SA: Intra-frequency measurement accuracy with FR1 serving cell and FR1 target cell [CSI-RSRQ] |  | NR_CSIRS_L3meas | R4-2109086 clause# 6.7.10.1
6.7.11.2 | SA Inter-frequency measurement accuracy with FR1 serving cell and FR1 target cell [CSI-RSRQ] |  | NR_CSIRS_L3meas | R4-2109086 clause# 6.7.10.2
6.7.12.1 | SA intra-frequency measurement accuracy with FR1 serving cell and FR1 target cell [CSI-SINR] |  | NR_CSIRS_L3meas | R4-2109086 clause# 6.7.11.1
6.7.12.2 | SA Inter-frequency measurement accuracy with FR1 serving cell and FR1 target cell [CSI-SINR] |  | NR_CSIRS_L3meas | R4-2109086 clause# 6.7.11.2
7.6.7.1 | SA event triggered reporting test without gap under DRX for CSI-RS based intra-frequency measurement |  | NR_CSIRS_L3meas | R4-2109086 clause# 7.6.5.1
7.6.8.1 | SA event triggered reporting tests for FR2 CSI-RS based measurement when non-DRX is used (PCell in FR2) |  | NR_CSIRS_L3meas | R4-2109086 clause# 7.6.6.1
7.7.7.1.1 | NR SA FR2 CSI-RSRP measurement accuracy (SA intra-frequency case measurement accuracy with FR2 serving cell and FR2 target cell) [CSI-RSRP] | R5-245898 | NR_CSIRS_L3meas | R4-2109086 clause# 7.7.6.1 | Done
7.7.7.2.1 | NR SA FR2-FR2 CSI-RSRP measurement accuracy (SA inter-frequency case measurement accuracy with FR2 serving cell and FR2 target cell) [CSI-RSRP] | R5-245899 | NR_CSIRS_L3meas | R4-2109086 clause# 7.7.6.2 | Done
7.7.8.1 | SA intra-frequency measurement accuracy with FR2 serving cell and FR2 target cell [CSI-RSRQ] | R5-241329 R5-241330 R5-246047 R5-245732 R5-245736 | NR_CSIRS_L3meas | R4-2109086 clause# 7.7.7.1 | Done
7.7.8.2 | SA inter-frequency measurement accuracy with FR2 serving cell and FR2 TDD target cell [CSI-RSRQ] | R5-241331 R5-246048 R5-245733 R5-245737 | NR_CSIRS_L3meas | R4-2109086 clause# 7.7.7.2 | Done
7.7.9.1 | SA intra-frequency case measurement accuracy with FR2 serving cell and FR2 target cell [CSI-SINR] | R5-241332 R5-241333 R5-246049 R5-245734 R5-245738 | NR_CSIRS_L3meas | R4-2109086 clause# 7.7.8.1 | Done
7.7.9.2 | SA inter-frequency measurement accuracy with FR2 serving cell and FR2 TDD target cell [CSI-SINR] | R5-241831 R5-246050 R5-245735 R5-245739 | NR_CSIRS_L3meas | R4-2109086 clause# 7.7.8.2 | Done
A.13 | CSI-RS configurations for RRM | R5-245893 | NR_CSIRS_L3meas | R4-2109086 clause# A.3.25 | Done
B.2.1.4 | Gain to SS-RSRP and CSI-RSRP measurement point for FR1 |  | NR_CSIRS_L3meas | R4-2109086 maintenance
B.2.1.5 | Gain to SS-RSRP and CSI-RSRP measurement point for FR2 |  | NR_CSIRS_L3meas | R4-2109086 maintenance
B.2.8 | Conditions for NR CSI-RS based intra-frequency measurements |  | NR_CSIRS_L3meas | R4-2109086
B.2.9 | Conditions for NR CSI-RS based inter-frequency measurements |  | NR_CSIRS_L3meas | R4-2109086