## Cover sheet
3GPP TSG-RAN5 Meeting #105 | [10 empty] | R5-247240
Orlando, United States, 18th Nov 2024 - 22nd Nov 2024
Agenda Item: | 7.5.2
Source: | Nokia
Title: | WP for XR (eXtended Reality) enhancements for NR plus CT1 aspects
Work item code: | NR_XR_enh_plus_CT1-UEConTest
Release: | Rel-18
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
RAN2 has specified enhancements for following topics under the Rel-18 NR_XR_enh-Core work item: - The enhancements related to power saving - The enhancements related to capacity - The enhancements for XR Awareness The objective for RAN5 is to specify UE conformance specifications for the same. Objectives regarding the CT1 aspects will be clarified later on, when CT1 work is about to be finished.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 60% (+12%) | 9 (+5) | 20 (+1)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 60% (+12.1%) | 9 (+5) | 20 (+1)
FR1 |  | 56.4% (+11.3%) | 9 (+5) | 20 (+1)
FR2 |  | 64.1% (+12.9%) | 9 (+5) | 20 (+1)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1
Common ICS | 38.508-2
UE specific test functions | 38.509
NR RF/RRM
FR1 RF common parts | 38.521-1 | 0% |  |  | 0%
FR1 RF Rx test cases | 38.521-1 Rx | 15% |  |  | 15%
Applicability RF. Demod/QSI and RRM test cases | 38.522 | 0% |  |  | 0%
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 0% |  |  | 0%
Test Point analysis receiver and transmitter test cases | 38.905 | 0% |  |  | 0%
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 62.5% (+13.6%) | 9 (+5) | 20 (+1) | 62.5% (+13.6%) | 9 (+5) | 20 (+1) | 62.5% (+13.6%) | 9 (+5) | 20 (+1)
Applicability Protocol test cases | 38.523-2 | 32.5% (+12.5%) |  |  | 32.5% (+12.5%) |  |  | 32.5% (+12.5%)
Test suites (TTCN) | 38.523-3
5 References
[1] RP-yyxxxx | <WID document title>
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP for XR (eXtended Reality) enhancements for NR plus CT1 aspects | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_XR_enh_plus_CT1-UEConTest
WP Scope: |  | XR and 2Rx XR device testcase plan. | [12 empty] | vs Area
WP Resp: |  | Matti Kangas |  |  | matti.kangas@nokia.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | N/A |  |  | -
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1 | FR2
[14 empty] | 56.4% (+11.3%) | 64.1% (+12.9%)
[14 empty] | 28 (+1) | 22 (+1)
[14 empty] | 23.5 (+1) | 20.2 (+1)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.508-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.508-1 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
TS 38.508-2: Common ICS
28 |  | 38.508-2 | A.4.3.5 | MAC Implementation Capabilities | Addition of 2Rx XR PICS. Addition of DSR and non-integer DRX PICS. |  | RAN5#106 (Feb-25) | R5-245053, R5-245599 |  | TBD
29 |  | 38.508-2 | A.4.3.2 | Physical Layer Baseline Implementation Capabilities | Add new PICS for multi-PUSCH CG test cases |  | RAN5#106 (Feb-25) | R5-244795, R5-247232 |  | TBD
32 |  | 38.508-2 | A.4.3.3 | PDCP Implementation Capabilities | Add new PICS for SN gap reprting test cases |  | RAN5#106 (Feb-25) | R5-247232 |  | TBD
TBD |  | 38.508-2 | <Clause> | <Title> | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. |  | TBD |  |  | TBD
TS 38.509: UE specific testing functions
|  | 38.509 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.509 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.509 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
NR RF/RRM
TS 38.521-1: FR1 RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
15 |  | 38.521-1 | 3 | Definitions, symbols and abbreviations | Definitions, symbols and abbreaviations introduced by 2Rx XR. | Apple | RAN5#107 (May-25) |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
TS 38.521-1: FR1 RF test cases - Rx
|  | 38.521-1 Rx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
16 |  | 38.521-1 Rx | 7.3.2_1 | Reference sensitivity power level | Testcase of reference sensitivity power level for 2Rx XR. | Apple | RAN5#107 (May-25) | R5-245996 |  | 1 | 15% | 15% |  | 15%
24 |  | 38.521-1 Rx | Annex F | Measurement uncertainties and test tolerances | Capturing the MU/TT need for the XR RF test case | Apple | RAN5#107 (May-25) |  |  | TBD
TBD |  | 38.521-1 Rx | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
TS 38.522: Applicability for RF, Demod/CSI reporting and RRM test cases
|  | 38.522 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
17 |  | 38.522 | 4 | Test case conditions and selection criteria | Add test case applicability statements for the new test cases introduced for 38.521-1. | Apple | RAN5#107 (May-25) |  |  | 0.1 | 0% | 0% |  | 0%
18 |  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Add test case applicability statements for the new test cases introduced for 38.521-1. | Apple | RAN5#107 (May-25) |  |  | 0.1 | 0% | 0% |  | 0%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
|  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.903 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
22 |  | 38.903 | TBD | Reference sensitivity power level TT updates | To add TT analysis for NR REFSENS test for XR devices | Apple | RAN5#107 (May-25) |  |  | 1 | 0% | 0% |  | 0%
TR 38.905: Test Point analysis receiver and transmitter test cases
|  | 38.905 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.905 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
23 |  | 38.905 | TBD | Reference sensitivity power level | Add TP analysis for REFSENS test for XR devices | Apple | RAN5#107 (May-25) |  |  | 1 | 0% | 0% |  | 0%
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
Idle Mode
TBD |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
19 | Y | 38.523-1 | 6.1.2.31 | Cell reselection / 2Rx XR / Serving cell becomes barred | TS 38.304 Test Purpose 1: with { 2Rx XR UE in NR RRC_IDLE state on the cell where 4Rx antenna ports are mandated } ensure that { when { the serving cell becomes barred for 2Rx XR UEs and there is a suitable neighbour cell for 2Rx XR UEs } then { 2Rx XR UE selects the suitable neighbour cell } } | Motorola Mobility / Lenovo | RAN5#107 (May-25) | R5-245613 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
20 | Y | 38.523-1 | 6.1.2.32 | Cell reselection / 2Rx XR / Intra frequency reselection not allowed | TS 38.304 Test Purpose 1: with { 2Rx XR UE in NR RRC_IDLE state on the cell where 4Rx antenna ports are mandated } ensure that { when { the serving cell becomes barred for 2Rx XR UEs and broadcasting intraFreqReselection2RxXR to "not allowed" and 2Rx XR UE detects both intra-frequency and equal priority inter-frequency neighbour cells and the intra-frequency cell is the highest ranked cell } then { UE reselects the inter-frequency cell } } | Motorola Mobility / Lenovo | RAN5#107 (May-25) | R5-245614 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
21 | Y | 38.523-1 | 6.1.2.33 | Cell reselection / 2Rx XR / Access not allowed | TS 38.304 Test Purpose1: with { 2Rx XR UE in NR RRC_IDLE state } ensure that { when { 2Rx XR UE detects the cell reselection criteria are met for two cells on different frequencies and the serving cell is broadcasting accessAllowed2RxXR to "false" for the cell on the first frequency and "true" for the cell on the second frequency } then { UE reselects the cell which belongs to the frequency for which the serving cell is broadcasting accessAllowed2RxXR "true" } } | Motorola Mobility / Lenovo | RAN5#107 (May-25) | R5-245615 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
TBD | Y | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
Layer 2
|  | 38.523-1 | 7.1.1.3 | Uplink Data Transfer | Existing clause, added just for clarity here. |  | TBD |  |  | 0
1 | Y | 38.523-1 | 7.1.1.3.18 | Correct handling of MAC control information / Buffer status / UL data arrive in the UE Tx buffer / Refined BSR | TS 38.321 5.4.5 Test Purpose 1: with { UE in RRC_CONNECTED state } ensure that { when { UL data arrives in the UE transmission buffer for a logical channel in a LCG configured with additionalBS-TableAllowed, and there is no data available for transmission for any of the logical channels which belong to a LCG, and the amount of UL data available for transmission is within the buffer sizes specified in Table 6.1.3.1-3 } then { UE reports a Long Refined BSR } } Test Purpose 2: with { UE in RRC_CONNECTED state } ensure that { when { UL data arrives in the UE transmission buffer for a logical channel in a LCG configured with additionalBS-TableAllowed, and there is no data available for transmission for any of the logical channels which belong to a LCG, and the amount of UL data available for transmission when the MAC PDU containing the BSR is to be built is greater than the largest buffer size specified in Table 6.1.3.1-3 } then { UE reports a Long BSR } } Test Purpose 3: with { UE in RRC_CONNECTED state } ensure that { when { UL data arrives in the UE transmission buffer for a logical channel in a LCG configured with additionalBS-TableAllowed, and there is no data available for transmission for any of the logical channels which belong to a LCG, and the amount of UL data available for transmission when the MAC PDU containing the BSR is to be built is smaller than the smallest buffer size specified in Table 6.1.3.1-3 } then { UE reports a Long BSR } } | Motorola Mobility / Lenovo | RAN5#105 (Nov-24) | R5-245616 | R5-245616 sent for email agreement! | 1 | 100% | 100% |  | 100% | 100%
2 | Y | 38.523-1 | 7.1.1.3.19 | Correct handling of MAC control information / Buffer Status / UL resources are allocated / Refined BSR / Padding BSR | TS 38.321 5.4.5 Test Purpose 1: with { UE in RRC_CONNECTED state } ensure that { when { UE transmits a MAC PDU and the number of padding bits is equal to or larger than the size of the Refined Long BSR plus its subheader and, for at least one LCG configured with additionalBS-TableAllowed, the amount of UL data available for transmission is within the buffer sizes specified in Table 6.1.3.1-3} then { UE reports a Long refined BSR } } Test Purpose 2: with { UE in RRC_CONNECTED state } ensure that { when { UE transmits a MAC PDU and the number of padding bits is equal to or larger than the size of the Refined Long BSR plus its subheader and, for all the LCGs configured with additionalBS-TableAllowed, the amount of UL data available for transmission when the MAC PDU containing the BSR is to be built is greater than the largest buffer size specified in Table 6.1.3.1-3 } then { UE reports a Long refined BSR } } | Motorola Mobility / Lenovo | RAN5#105 (Nov-24) | R5-245617 | R5-245617 sent for email agreement! | 1 | 100% | 100% |  | 100% | 100%
3 | Y | 38.523-1 | 7.1.1.3.20 | Correct handling of MAC control information / Delay Status / Delay status reporting | TS 38.321 5.4.9: Test Purpose 1: with { UE in RRC_CONNECTED state } ensure that { when { smallest remaining value of the PDCP discardTimers among all the data buffered for the LCG becomes below remainingTimeThreshold of the LCG } then { UE reports a DSR including LCGi=1 and Remaining Timer and Buffer Size for the LCGi } } | Nokia | RAN5#105 (Nov-24) | R5-245601 | Splitted testcase into two testcases => 7.1.1.3.20 is testing DSR when UE doesn't inform additional BS tables capability & 7.1.1.3.20a is testing DSR when UE informs additional BS tables capability. | 1 | 65% | 65% |  | 65% | 65%
27 | Y | 38.523-1 | 7.1.1.3.20a | Correct handling of MAC control information / Delay Status / Refined delay status reporting | TS 38.321 5.4.9: Test Purpose 1: with { UE in RRC_CONNECTED state } ensure that { when {smallest remaining value of the PDCP discardTimers among all the data buffered for the LCG becomes below remainingTimeThreshold of the LCG and additionalBS-TableAllowed is set to false for all LCGs and regardless of the amount of delay-critical data to be reported} then { UE reports a DSR with BT indication 0 for all LCGs} } Test Purpose 2: with { UE in RRC_CONNECTED state } ensure that { when { smallest remaining value of the PDCP discardTimers among all the data buffered for the LCG becomes below remainingTimeThreshold of the LCG and additionalBS-TableAllowed is set to true for at least some LCGs and the amount of delay-critical data to be reported for the LCGs with additionalBS-TableAllowed=true is outside the range specified in Table 6.1.3.1-3 } then { UE reports a DSR with BT indication 0 for all LCGs} } Test Purpose 3: with { UE in RRC_CONNECTED state } ensure that { when { smallest remaining value of the PDCP discardTimers among all the data buffered for the LCG becomes below remainingTimeThreshold of the LCG and additionalBS-TableAllowed is set to true for at least some LCGs and the amount of delay-critical data to be reported for the LCGs with additionalBS-TableAllowed=true is inside the range specified in Table 6.1.3.1-3 } then { UE reports a DSR with BT indication 1 for LCGs with additionalBS-TableAllowed=true and 0 for all others } } | Nokia | RAN5#106 (Feb-25) | R5-247633 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
4 | Y | 38.523-1 | 7.1.1.3.21 | Correct handling of MAC control information / Delay Status / Triggering scheduling request | TS 38.321 5.4.9: Test Purpose 1: with { UE in RRC_CONNECTED state } ensure that { when { UE determines that a DSR has been triggered since the last transmission of a DSR and UE has no UL resources allocated for new transmission for this TTI } then { UE transmits a scheduling request } } | Nokia | RAN5#105 (Nov-24) | R5-245602 |  | 1 | 65% | 65% |  | 65% | 65%
|  | 38.523-1 | 7.1.1.5 | Discontinuous reception | Existing clause, added just for clarity here. |  | TBD |  |  | 0
5 | Y | 38.523-1 | 7.1.1.5.7 | Non-Integer DRX operation / Short cycle not configured / Parameters configured by RRC | TS 38.321 5.7: Test Purpose 1: with { UE in RRC_CONNECTED state } ensure that { when { Non-Integer Long DRX cycle is configured and drx-TimeReferenceSFN is configured and floor([(DRX_SFN_COUNTER × 10240) + (SFN × 10) + subframe number] modulo (drx-NonIntegerLongCycle)) = floor([(drx-TimeReferenceSFN × 10) + drx-StartOffset] modulo (drx-NonIntegerLongCycle)) } then { UE starts the OnDurationTimer and monitors the PDCCH for OnDurationTimer PDCCH-Occasions} } Test Purpose 2: with { UE in RRC_CONNECTED state } ensure that { when { Non-Integer Long DRX cycle is configured and a new DL transmission is indicated on the PDCCH during Active Time } then { UE starts or restarts the Drx-InactivityTimer and monitors the PDCCH for Drx-InactivityTimer PDCCH occasions starting from the next PDCCH occasion of the PDCCH occasion where the DL new transmission was indicated } } Test Purpose 3: with { UE in RRC_CONNECTED state } ensure that { when { Non-Integer Long DRX cycle is configured and if a HARQ RTT Timer expires in this PDCCH Occasion and the data in the soft buffer of the corresponding HARQ process was not successfully decoded } then { UE starts the drx-RetransmissionTimer-DL for the corresponding HARQ process and monitors the PDCCH for drx-RetransmissionTimer consecutive PDCCH Occasion } } Test Purpose 4: with { UE in RRC_CONNECTED state } ensure that { when { Non-Integer Long DRX cycle is configured and an uplink grant for a pending HARQ retransmission can occur in this PDCCH occasion} then { UE monitors the PDCCH in this PDCCH occasion } } | Nokia | RAN5#106 (Feb-25) | R5-245603 |  | 1 | 65% | 65% |  | 65% | 65%
6 | Y | 38.523-1 | 7.1.1.5.8 | Non-Integer DRX operation / Short cycle configured / Parameters configured by RRC | TS 38.321 5.7: Test Purpose 1: with { UE in RRC_CONNECTED state } ensure that { when { Non-Integer Short DRX cycle is configured and drx-TimeReferenceSFN is configured and drx-SlotOffset is configured and floor([(DRX_SFN_COUNTER × 10240) + (SFN × 10) + subframe number] modulo (drx-NonIntegerShortCycle)) = floor([(drx-TimeReferenceSFN × 10) + drx-StartOffset] modulo (drx-NonIntegerShortCycle)) } then { UE starts the OnDurationTimer after drx-SlotOffset and monitors the PDCCH for OnDurationTimer PDCCH-subframes } } Test Purpose 2: with { UE in RRC_CONNECTED state } ensure that { when { drxShortCycleTimer is expired and floor([(DRX_SFN_COUNTER × 10240) + (SFN × 10) + subframe number] modulo (drx-NonIntegerLongCycle)) = floor([(drx-TimeReferenceSFN × 10) + drx-StartOffset] modulo (drx-NonIntegerLongCycle)) } then { UE starts the OnDurationTimer after drx-SlotOffset and monitors the PDCCH for OnDurationTimer PDCCH-subframes } } | Nokia | RAN5#106 (Feb-25) | R5-245604 |  | 1 | 65% | 65% |  | 65% | 65%
7 | Y | 38.523-1 | 7.1.1.5.9 | Non-Integer DRX operation / Short cycle not configured / DRX_SFN_COUNTER reset after RRC re-configuration | TS 38.321 5.7: Test Purpose 1: with { UE in RRC_CONNECTED state } ensure that { when { Non-Integer Long DRX cycle is configured and RRC (re-)configuration message is received during the first half of a hyper frame and drx-TimeReferenceSFN is included } then { UE sets DRX_SFN_COUNTER to 1 in the first symbol of the slot immediately after the first PUSCH transmission which contains the RRCReconfigurationComplete message of the RRC (re-) configuration as specified in TS 38.331 } } Test Purpose 2: with { UE in RRC_CONNECTED state } ensure that { when { Non-Integer Long DRX cycle is configured and RRC (re-)configuration message is received during the first half of a hyper frame and drx-TimeReferenceSFN is not included } then { UE sets DRX_SFN_COUNTER to 0 in the first symbol of the slot immediately after the first PUSCH transmission which contains the RRCReconfigurationComplete message of the RRC (re-) configuration as specified in TS 38.331 } } | Nokia | RAN5#106 (Feb-25) |  |  | 1 | 0% | 0% |  | 0% | 0%
|  | 38.523-1 | 7.1.3.5 | PDCP other | Existing clause, added just for clarity here. |  | TBD |  |  | 0
8 | Y | 38.523-1 | 7.1.3.5.8 | PDCP Discard / PDU Set based discard | TS 38.323 5.2.1, 5.3: Test Purpose 1: with { UE in RRC_CONNECTED state } ensure that { when { PDU-SetDiscard is configured and discardTimer expires for a PDCP SDU in a PDU Set } then { UE discards all SDUs in the PDU Set } } | CMCC | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
9 | Y | 38.523-1 | 7.1.3.5.9 | PDCP Discard / PSI based discard | TS 38.323 5.2.1, 5.3: Test Purpose 1(s): with { UE in RRC_CONNECTED state } ensure that { when { discardTimerForLowImportance is configured and PSI based SDU discard is activated and discardTimerForLowImportance expires for a low importance PDCP SDU} then { UE discards the PDCP SDUs } } Test Purpose 2: with { UE in RRC_CONNECTED state } ensure that { when { discardTimerForLowImportance and PDU-SetDiscard are configured and PSI based SDU discard is activated and discardTimerForLowImportance expires for a PDCP SDU in a low importance PDU Set } then { UE discards all SDUs in the low importance PDU Set } } | CMCC | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
10 | Y | 38.523-1 | 7.1.3.5.10 | PDCP Discard / PSI based discard / DSR triggering | TS 38.323 5.2.1, 5.3: Test Purpose 1: with { UE in RRC_CONNECTED state } ensure that { when { discardTimerForLowImportance is configured and PSI based SDU discard is activated and the smallest remaining value of discardTimerForLowImportance among all the data buffered for a LCG becomes below remainingTimeThreshold } then { UE does not trigger a DSR} } Test Purpose 2: with { UE in RRC_CONNECTED state } ensure that { when { discardTimerForLowImportance is configured and PSI based SDU discard is activated and the smallest remaining value of discardTimer among all the data buffered for a LCG becomes below remainingTimeThreshold } then { UE triggers a DSR and Remaining Time and Buffer Size fields are only determined based on high importance data} } | CMCC | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
26 | Y | 38.523-1 | 7.1.3.5.11 | PDCP SN gap report / Transmit operation | TS: 38.323 5.16.1, 6.1.2, 6.2.3.5 Test Purpose(s): with { UE in RRC_CONNECTED state } ensure that { when { PDCP SDU has been discarded and at least one buffered PDCP SDU has COUNT value larger than the COUNT value of discarded PDCP SDU and the discarded PDCP SDU have not been submitted by RLC to lower layers to be transmitted } then { UE submits the PDCP SN gap report for lower layers to be sent for receiving PDCP entity } } | Nokia | RAN5#107 (May-25) | R5-247355 | RAN5#104: R2-2405932 introduced this functionality in Fukuoka (May/24) meeting. RP-104 accepted CR and functionality added to 38.323 in version 18.2.0. | 1
25 | Y | 38.523-1 | 7.1.3.5.12 | PDCP SN gap report / Receive operation | TS: 38.323 5.2.2, 5.16.2, 6.1.2, 6.2.3.5 Test Purpose 1: with { UE in RRC_CONNECTED state and the associated PDCP t-Reordering timer is running } ensure that { when { UE receives PDCP SN gap Report, RX_DELIV is less than any COUNT value associated with the discarded PDCP SDUs } then { UE does not update RX_DELIV, and UE does not deliver all stored PDCP SDU(s) with consecutively associated COUNT values starting from COUNT = RX_DELIV + 1 to upper layers } } Test Purpose 2: with { UE in RRC_CONNECTED state and the associated PDCP t-Reordering timer is running } ensure that { when { t-Reordering expires } then { UE updates RX_DELIV to the COUNT value of the first PDCP SDU with COUNT >= RX_REORD which has not been delivered to upper layers and is not considered as discarded, and UE deliver to the upper layers all stored PDCP SDU(s) with associated COUNT value(s) < RX_REORD and all stored PDCP SDU(s) with consecutively associated COUNT value(s) starting from RX_REORD, where consecutively associated COUNT value(s) include COUNT value(s) of both the stored PDCP SDU(s) and PDCP SDU(s) which are considered as discarded. } } Test Purpose 3: with { UE in RRC_CONNECTED state and the associated PDCP t-Reordering timer is running } ensure that { when { UE receives PDCP SN gap Report, RX_DELIV is equal to any COUNT value associated with the discarded PDCP SDUs } then { UE updates RX_DELIV, and deliver all stored PDCP SDU(s) with consecutively associated COUNT values starting from COUNT = RX_DELIV + 1 to upper layers where consecutively associated COUNT value(s) include COUNT value(s) of both the stored PDCP SDU(s) and PDCP SDU(s) which are considered as discarded } } Test Purpose 4: with { UE in RRC_CONNECTED state and the associated PDCP t-Reordering timer is not running } ensure that { when { UE receives PDCP SN gap Report, RX_DELIV is less than any COUNT value associated with the discarded PDCP SDUs, and RX_DELIV < RX_NEXT after updating RX_NEXT } then { UE starts t-reordering and UE does not update RX_DELIV } } Test Purpose 5: with { UE in RRC_CONNECTED state and the associated PDCP t-Reordering timer is running } ensure that { when { UE receives PDCP DATA COUNT = RX_DELIV } then { UE updates RX_DELIV to the COUNT value of the first PDCP SDU with COUNT value > RX_DELIV which has not been delivered to upper layers after the next step and is not considered as discarded, and UE deliver to the upper layers all stored PDCP SDU(s) with consecutively associated COUNT value(s) starting from RX_REORD, where consecutively associated COUNT value(s) include COUNT value(s) of both the stored PDCP SDU(s) and PDCP SDU(s) which are considered as discarded. } } | Huawei, HiSilicon | RAN5#106 (Feb-25) | R5-247631 | RAN5#104: R2-2405932 introduced this functionality in Fukuoka (May/24) meeting. RP-104 accepted CR and functionality added to 38.323 in version 18.2.0. | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
TBD |  | 38.523-1 | 7.1.1.6 | Semi-Persistent Scheduling | Existing clause, added just for clarity here. |  | TBD |  |  | 0
11 | Y | 38.523-1 | 7.1.1.6.6 | Correct handling of UL grant / Multiple CG PUSCH occasions per CG period / Configured grant Type 1 | TS 38.321 5.4.1, 5.8.2: Test Purpose 1: with {UE in RRC_Connected state with DRB established and sps-Configuration in UL is enabled with Configured grant type 1 } ensure that { when { The symbol in which equation [(SFN × numberOfSlotsPerFrame × numberOfSymbolsPerSlot) + (slot number in the frame × numberOfSymbolsPerSlot) + symbol number in the slot + k x numberOfSymbolsPerSlot] = (timeDomainOffset × numberOfSymbolsPerSlot + S + N × periodicity + k x numberOfSymbolsPerSlot) modulo (1024 × numberOfSlotsPerFrame × numberOfSymbolsPerSlot) is satisfied } then { UE starts transmitting UL MAC PDU periodically in the symbol associated with the new reconfigured grant } } | Huawei, HiSilicon | RAN5#106 (Feb-25) | R5-245611 |  | 1 | 100% | 100% |  | 100% | 100%
12 | Y | 38.523-1 | 7.1.1.6.7 | Correct handling of UL grant / Multiple CG PUSCH occasions per CG period / Configured grant Type 2 | TS 38.321 5.4.1, 5.8.2: Test Purpose 1: with {UE in RRC_Connected state with DRB established and sps-Configuration in UL is enabled with Configured grant type 1 } ensure that { when { The symbol in which equation [(SFN × numberOfSlotsPerFrame × numberOfSymbolsPerSlot) + (slot number in the frame × numberOfSymbolsPerSlot) + symbol number in the slot + k x numberOfSymbolsPerSlot] = (timeDomainOffset × numberOfSymbolsPerSlot + S + N × periodicity + k x numberOfSymbolsPerSlot) modulo (1024 × numberOfSlotsPerFrame × numberOfSymbolsPerSlot) is satisfied } then { UE starts transmitting UL MAC PDU periodically in the symbol associated with the new reconfigured grant } } | Huawei, HiSilicon | RAN5#106 (Feb-25) | R5-245600 |  | 1 | 100% | 100% |  | 100% | 100%
13 | Y | 38.523-1 | 7.1.1.6.8 | Correct handling of UL grant / Unused Transmission Occasion / Configured grant type 1 | TS 38.321 5.8.2: Test Purpose 1: with { UE in RRC_Connected state with DRB established and configured UL grant type 1 } ensure that { when { the UE determines that buffered data can be transmitted using N CG occasion (N>0, N<nrofBitsInUTO-UCI-r18) and UE transmits for the first time in CG occasion m } then { UE transmits UTO-UCI with at least one bit set to 1 (unused) for the first time in CG occasion m+X (0≤X≤N). The first N-X-1 bits of UTO-UCI are set to 0 (used) and bits from N-X to nrofBitsInUTO-UCI-r18 set to 1 (unused) } } | Nokia | RAN5#107 (May-25) | R5-247230 |  | 1 | 90% (+90%) | 90% (+90%) |  | 90% | 90%
31 | Y | 38.523-1 | 7.1.1.6.9(?) | Correct handling of UL grant / Unused Transmission Occasion / Configured grant type 2 | TS 38.321 5.8.2: Test Purpose 1: with { UE in RRC_Connected state with DRB established and configured UL grant type 2 } ensure that { when { the UE determines that buffered data can be transmitted using N CG occasion (N>0, N<nrofBitsInUTO-UCI-r18) and UE transmits for the first time in CG occasion m } then { UE transmits UTO-UCI with at least one bit set to 1 (unused) for the first time in CG occasion m+X (0≤X≤N). The first N-X-1 bits of UTO-UCI are set to 0 (used) and bits from N-X to nrofBitsInUTO-UCI-r18 set to 1 (unused) } } | Nokia | RAN5#107 (May-25) |  |  | 1 | 0% | 0% |  | 0% | 0%
TBD | Y | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
RRC
|  | 38.523-1 | 8.1.5.10 | UE Assistance Information | Existing clause, added just for clarity here. |  | TBD |  |  | 0
14 | Y | 38.523-1 | 8.1.5.10.7 | UE Assistance Information/ UL Traffic Information | TS 38.331 5.7.4: Test Purpose 1: with { UE in NR RRC_CONNECTED state } ensure that { when { UE configured to provide XR traffic information and the traffic information has changed with respect to the last reporting (UE determines that the information has been updated) and timer T346X is not running } then { the UE transmits a UEAssistanceInformation message } } Test Purpose 2: with { UE in NR RRC_CONNECTED state } ensure that { when { UE configured to provide XR traffic information and the traffic information has changed with respect to the last reporting (UE determines that the information has been updated) and timer T346X is running } then { the UE does not transmit a UEAssistanceInformation message } } | Huawei, HiSilicon | RAN5#106 (Feb-25) |  |  | 1 | 0% | 0% |  | 0% | 0%
TBD | Y | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
NAS
TBD |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD | Y | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TS 38.523-2: Applicability for Protocol test cases
TBD |  | 38.523-2 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0.1 | 0% | 0% |  | 0% | 0%
30 |  | 38.523-2 | 4.1 | Protocol conformance test cases applicability | Add test case applicability statements for the new test cases introduced in 38.523-1 |  | RAN5#107 (May-25) | R5-245605, R5-245618, R5-247632, R5-247670 | R5-245618 sent for email agreement. => Agreed | 0.1 | 65% (+25%) | 65% (+25%) |  | 65% | 65%
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.