## Cover sheet
3GPP TSG-RAN WG5 Meeting #105 | [10 empty] | R5-247512
Orlando, United States, 18th Nov 2024 - 22nd Nov 2024
Agenda Item: | 5.3.30
Source: | China Telecom
Title: | UE Conformance - Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR(UID - 1030061)
Work item code: | NR_DualTxRx_MUSIM-UEConTest
Release: | Rel-18
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
The objective of this work item is to define the UE conformance requirements corresponding to the WI Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR to improve the performance of MUSIM UEs, including protocol and RRM test cases.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 72% (+72%) | 5 (+5) | 10 (+10)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 72.3% (+72.3%) | 5 (+5) | 10 (+10)
FR1 |  | 75.1% (+75.1%) | 5 (+5) | 8 (+8)
FR2 |  | 69.8% (+69.8%) | 5 (+5) | 9 (+9)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508
UE specific test functions | 36.509
LTE RF/RRM
RF common parts | 36.521-1
RF Rx test cases | 36.521-1 Rx
RF Tx test cases | 36.521-1 Tx
RF Demod test cases | 36.521-1 Demod
Applicability RF. Demod/QSI and RRM test cases | 36.521-2
RRM test cases | 36.521-3
Test Tolerances analysis RRM test cases | 36.903
Test Tolerances analysis receiver test cases | 36.904
Test Point analysis receiver and transmitter test cases | 36.905
LTE RAN and CN protocols
Protocol test cases | 36.523-1
Applicability Protocol test cases | 36.523-2
Test suites (TTCN) | 36.523-3
5GS
5GS Common
Common test environment | 38.508-1 | 100% (+100%) |  |  | 100% (+100%) |  |  | 100% (+100%)
Common ICS | 38.508-2 | 100% (+100%) |  |  | 100% (+100%) |  |  | 100% (+100%)
UE specific test functions | 38.509
NR RF/RRM
FR1 RF common parts | 38.521-1
FR1 RF Tx test cases | 38.521-1 Tx
FR1 RF Rx test cases | 38.521-1 Rx
FR2 RF common parts | 38.521-2
FR2 RF Tx test cases | 38.521-2 Tx
FR2 RF Rx test cases | 38.521-2 Rx
FR1 and FR2 Interworking operation with other radios RF common parts | 38.521-3
FR1 and FR2 Interworking operation with other radios RF Tx test cases | 38.521-3 Tx
FR1 and FR2 Interworking operation with other radios RF Rx test cases | 38.521-3 Rx
RF Demod/QSI test cases | 38.521-4
RRM test cases | 38.533 | 46.3% (+46.3%) | 1 (+1) | 6 (+6) | 51.1% (+51.1%) | 1 (+1) | 4 (+4) | 41.8% (+41.8%) | 1 (+1) | 5 (+5)
Applicability RF. Demod/QSI and RRM test cases | 38.522 | 100% (+100%) |  |  | 100% (+100%) |  |  | 100% (+100%)
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 0% |  |  | 0% |  |  | 0%
Test Point analysis receiver and transmitter test cases | 38.905
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 100% (+100%) | 4 (+4) | 4 (+4) | 100% (+100%) | 4 (+4) | 4 (+4) | 100% (+100%) | 4 (+4) | 4 (+4)
Applicability Protocol test cases | 38.523-2 | 100% (+100%) |  |  | 100% (+100%) |  |  | 100% (+100%)
Test suites (TTCN) | 38.523-3
UE Positioning
UE Positioning Min. Performance test cases | 37.571-1
UE Positioning Protocol test cases | 37.571-2
Applicability and ICS UE Positioning test cases | 37.571-3
UE Positioning Test sutes (TTCN) | 37.571-4
UE Positioning test scenarios and assistance data | 37.571-5
IMS
IMS over LTE protocol test cases | 34.229-1
IMS over 5GS protocol test cases | 34.229-5
Applicability and ICS IMS test cases | 34.229-2
IMS Test suite (TTCN) | 34.229-3
Mission Critical Services
MC Common test environment | 36.579-1
MCPTT UE test cases | 36.579-2
MC Server Application test cases | 36.579-3
Applicability and ICS MC test cases | 36.579-4
MC Test suite (TTCN) | 36.579-5
MC Video UE test cases | 36.579-6
MC Data UE test cases | 36.579-7
5 References
[1] RP-240045 | New WID on UE Conformance - Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance - Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_DualTxRx_MUSIM-UEConTest
WP Scope: |  | UE conformance requirements corresponding to the WI Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR to improve the performance of MUSIM UEs, including protocol and RRM | [12 empty] | vs Area
WP Resp: |  | Jing Zhao (China Telecom) |  |  | zhaoj16@chinatelecom.cn | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | N/A |  |  | N/A
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1 | FR2
[14 empty] | 75.1% (+75.1%) | 69.8% (+69.8%)
[14 empty] | 15 (+15) | 16 (+16)
[14 empty] | 12.2 (+12.2) | 13.2 (+13.2)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
1 |  | 38.508-1 | 4.6 | Default NG-RAN RRC message and information elements contents | To add default configuration of RRC messages and IEs for MUSIM RRM and protocol tests | All contributers | RAN5#107 (May-25) | R5-245622 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | 0% | 0% |  | 0% | 0%
2 |  | 38.508-2 | Annex A | ICS proforma for NR/5GS Generation User Equipment | To add ICS as needed for the test case applicability statements for the new test cases introduced in MUSIM RRM and protocol test cases. | All contributers | RAN5#107 (May-25) | R5-245623，R5-247651 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
TS 38.509: UE specific testing functions
|  | 38.509 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
|  | 38.509 | <Clause> | Void | Void | China telecom | RAN5#104 (Aug-24) |  |  | 0
NR RF/RRM
TS 38.522: Applicability for RF, Demod/CSI reporting and RRM test cases
|  | 38.522 | <Clause> | <Title> | Add new ICS statements.
17 |  | 38.522 | 4.0 & 4.2 | Test case conditions and selection criteria | Add test case applicability statements for the new MUSIM test cases introduced for 38.533. | All contributers | RAN5#107 (May-25) | R5-246885 |  | 0.5 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
TS 38.533: RRM test cases
|  | 38.533 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
6 | Y | 38.533 | 6.6.1.0.6 | Minimum conformance requirements for event-triggered measurement with MUSIM gap configured | Ref: 38.133 A.6.6.2.X1 | Huawei, Hisilicon | RAN5#107 (May-25) | R5-246881 | cedar.wang@hisilicon.com | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
5 | Y | 38.533 | 6.6.1.9 | NR SA FR1 event triggered reporting with MUSIM gap | Ref: 38.133 A.6.6.1.X1 | Huawei, Hisilicon | RAN5#107 (May-25) | R5-246882 | cedar.wang@hisilicon.com | 1 | 50% (+50%) | 50% (+50%) |  | 50% | 50%
6 | Y | 38.533 | 6.6.2.13 | NR SA FR1-FR1 event triggered reporting using MUSIM gap with lower and higher priority | Ref: 38.133 A.6.6.2.X1 | Huawei, Hisilicon | RAN5#107 (May-25) | R5-246883 | cedar.wang@hisilicon.com | 1 | 70% (+70%) | 70% (+70%) |  | 70% | 70%
7 | Y | 38.533 | 6.6.2.14 | NR SA FR1-FR1 event triggered reporting using MUSIM gap with shorter MGRP | Ref: 38.133 A.6.6.2.X2 | Huawei, Hisilicon | RAN5#107 (May-25) |  | cedar.wang@hisilicon.com | 1 | 0% | 0% |  | 0%
8 | Y | 38.533 | 7.6.2.20 | NR SA FR2-FR2 event triggered reporting using MUSIM gap with higher priority | Ref: 38.133 A.7.6.2.X1 | Huawei, Hisilicon | RAN5#107 (May-25) |  | cedar.wang@hisilicon.com | 1 | 0% | 0% |  |  | 0%
9 | Y | 38.533 | 7.6.2.21 | NR SA FR2-FR2 event triggered reporting using MUSIM gap with shorter MGRP | Ref: 38.133 A.7.6.2.X2 | Huawei, Hisilicon | RAN5#107 (May-25) |  | cedar.wang@hisilicon.com | 1 | 0% | 0% |  |  | 0%
10 |  | 38.533 | Annexes | RRM test configurations, Cell configuration mapping & Measurement uncertainties and test tolerances | To add RRM test configurations, Cell configuration mapping & Measurement uncertainties and test tolerances for MUSIM RRM test cases | Huawei, Hisilicon | RAN5#107 (May-25) | R5-246884 | cedar.wang@hisilicon.com | 0.5 | 20% (+20%) | 20% (+20%) |  | 20% | 20%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
|  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
11 |  | 38.903 | 8 & attachments | Grouping table | To add TT analysis for MUSIM RRM test cases. | Huawei, Hisilicon | RAN5#107 (May-25) |  |  | 1 | 0% | 0% |  | 0% | 0%
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
RRC
|  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
12 | Y | 38.523-1 | 8.1.1.2.5 | RRC connection establishment / MUSIM / early indication | ****TP1: [TS 38.331: 5.3.3.4]**** WITH: UE received SIB1 containing musim-CapRestrictionAllowed, and is in RRC_CONNECTED state in network A. WHEN: UE capability is restricted for MUSIM operation and it is going on RRC Setup procedure on network B. THEN: UE includes the musim-CapRestrictionInd in the RRCSetupComplete message | China Telecom | RAN5#107 (May-25) | R5-245749 | zhaoj16@chinatelecom.cn | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
13 | Y | 38.523-1 | 8.1.1.4.10 | RRC resume / MUSIM / early indication | ****TP1: [TS 38.331: 5.3.13.4]**** WITH: UE received SIB1 containing musim-CapRestrictionAllowed and UE is in RRC_CONNECTED state in network A and received RRCRelease message containing suspendConfig IE from network B and enters into RRC_INACTIVE state in network B. WHEN: UE capability is restricted for MUSIM operation and it is going on RRC Resume procedure on network B. THEN: UE include the musim-CapRestrictionInd in the RRCResumeComplete message | China Telecom | RAN5#107 (May-25) | R5-247654 | zhaoj16@chinatelecom.cn | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
14 | Y | 38.523-1 | 8.1.5.10.5 | UE Assistance Information / MUSIM / musim-cellToAffectList | ****TP1: [TS 38.331: 5.7.4.2]**** WITH: UE in NR RRC_CONNECTED state WHEN: UE configured to provide MUSIM assistance information for temporary capability restriction and it has temporary capability restriction on the current configuration and timer T348 is not running THEN：The UE transmits a UEAssistanceInformation message including musim-CellToAffectList and start the timer 348 with the timer value set to the musim-WaitTimer ****TP2: [TS 38.331: 5.7.4.2]**** WITH: UE in NR RRC_CONNECTED state WHEN: UE configured to provide MUSIM assistance information for temporary capability restriction and it has temporary capability restriction on the current configuration and timer T348 is running then {the UE Does NOT transmit a UEAssistanceInformation message including musim-CellToAffectList} | CATT | RAN5#107 (May-25) | R5-247652 | chenxiaozhong@CATT.CN | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
15 | Y | 38.523-1 | 8.1.5.10.6 | UE Assistance Information / MUSIM / musim-AffectedBandsList / musim-AvoidedBandsList / musim-MaxCC | ****TP1: [TS 38.331: 5.7.4.2]**** WITH: UE in NR RRC_CONNECTED state WHEN: UE configured to provide MUSIM assistance information for temporary capability restriction and it has temporary capability restriction on the combination(s) of bands comprising of band(s) included in musim-CandidateBandList and it did not transmit a UEAssistanceInformation message with musim-AffectedBandsList and/or musim-AvoidedBandsList and/or musim-MaxCC since it was configured to provide MUSIM assistance information for temporary capability restriction and the timer T346n is not running THEN：The UE transmits a UEAssistanceInformation message including current musim-AffectedBandsList and/or musim-AvoidedBandsList and/or musim-MaxCC and start or restart the timer 346n with the timer value set to the musim-ProhibitTimer. ****TP2: [TS 38.331: 5.7.4.2]**** WITH: UE in NR RRC_CONNECTED state WHEN: UE configured to provide MUSIM assistance information for temporary capability restriction and the current musim-AffectedBandsList and/or musim-AvoidedBandsList and/or musim-MaxCC is different from the one indicated in the last transmission of the UEAssistanceInformation message including musim-CapRestriction and the timer T346n is not running THEN: The UE transmits a UEAssistanceInformation message including current musim-AffectedBandsList and/or musim-AvoidedBandsList and/or musim-MaxCC and start or restart the timer T346n with the timer value set to the musim-ProhibitTimer. ****TP3: [TS 38.331: 5.7.4.2]**** WITH: UE in NR RRC_CONNECTED state WHEN: UE configured to provide MUSIM assistance information for temporary capability restriction and it has temporary capability restriction on the current configuration and timer T346n is running then {the UE Does NOT transmit a UEAssistanceInformation message including musim-AffectedBandsList and/or musim-AvoidedBandsList and/or musim-MaxCC} | CATT | RAN5#107 (May-25) | R5-247653 | chenxiaozhong@CATT.CN | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
TS 38.523-2: Applicability for Protocol test cases
|  | 38.523-2 | <Clause> | <Title> | Add new ICS statements.
16 |  | 38.523-2 | <Clause> | <Title> | Add test case applicability statements for the new MUSIM test cases introduced in 38.523-1 | China Telecom,CATT | RAN5#106 (Feb-25) | R5-245669，R5-247676 |  | 0.2 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.