## Slide 1
Frank Mademann, outgoing SA2 Chairman (Huawei)
Maurice Pope, SA2 Support (MCC)
TSG SA WG2 Report and Questions for Advice at TSG SA#84 (agenda item 7.2)

## Slide 2: Contents
1) General aspects (events since SA#83, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2) Rel-15 Maintenance and Work and Work
  2.3) Rel-16 and later Work
  2.4) New and Updated WIDs/SIDs and Exceptions
  2.5) IETF Dependency Update
3) Action Items
4) Documents for Information and Approval
5) Collected Items requiring action from SA
Explicit requests for TSG SA are highlighted in RED

## Slide 3: Contents
1) General aspects (events since SA#83, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2) Rel-15 Maintenance and Work
  2.3) Rel-16 and later Work and Maintenance
  2.4) New and Updated WIDs/SIDs and Exceptions
  2.5) IETF Dependency Update
3) Action Items
4) Documents for Information and Approval
5) Collected Items requiring action from SA
è

## Slide 4: 1) General Aspects (1/8)
SA2 meetings held since SA#83
  SA2#132: April 2019, Xi’an, China
  SA2#133: May 2019, Reno, Nevada, USA
Future SA2 meetings
  SA2#134: June 2019, Sapporo, Japan

## Slide 5: 1) General Aspects (2/8)
SA2 WG leadership
  Chairman: Puneet Jain
  Vice Chairmen: Tao Sun, Andrew Bennett
  Secretary: Maurice Pope (MCC)
Parallel sessions held in the last plenary cycle
  Many thanks to Maurice Pope and the parallel session chairs Irfan Ali, Andrew Bennett, Puneet Jain, LaeYoung Kim, Krisztian Kiss, Yannick Lair and Tao Sun for their outstanding support!

## Slide 6: 1) General Aspects (3/8)
New SA2 leadership elected during SA2#133:
  Puneet Jain (Intel), Chairman
  Tao Sun (China Mobile), Vice Chairman
  Andrew Bennett (Samsung), Vice Chairman

## Slide 7: 1) General Aspects (4/8)
Statistics at SA WG2 #132:
279 delegates ‘attended’ (checked-in) SA WG2 #132
  1650 documents, 1450 Tdocs handled (including revisions), including
    1097 CRs (including revisions)
    76 Incoming LSs, of which 19 were postponed
    25 Outgoing LSs Approved
  159 Tdocs postponed / not handled
Total CRs agreed: 213 (+61 revised at SA WG2#133)
Statistics at SA WG2 #133:
276 delegates ‘attended’ (checked-in) SA WG2 #133
  1758 documents, 1626 Tdocs handled (including revisions), including
    1093 CRs (including revisions)
    67 Incoming LSs, of which 10 were postponed
    25 Outgoing LSs Approved
  171 Tdocs postponed / not handled
Total CRs agreed: 309
754 people registered on the SA WG2 e-mail reflector on 31 May 2019

## Slide 8: 1) General Aspects (5/8)
Chart: SA2 meeting attendance
| 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 113AH | 114 | 115 | 116 | 116bis | 117 | 118 | 118bis | 119 | 120 | 121 | 122 | 122bis | 123 | 124 | 125 | 126 | 127 | 127bis | 128 | 128bis | 129 | 129bis | 130 | 131 | 132 | 133
attended | 157 | 139 | 133 | 162 | 135 | 142 | 139 | 173 | 181 | 165 | 158 | 153 | 189 | 146 | 133 | 145 | 142 | 144 | 195 | 159 | 175 | 182 | 113 | 137 | 200 | 137 | 107 | 157 | 168 | 169 | 143 | 157 | 233 | 182 | 175 | 191 | 188 | 156 | 154 | 156 | 222 | 196 | 174 | 149 | 140 | 152 | 149 | 165 | 191 | 153 | 178 | 279 | 280

## Slide 9: 1) General Aspects (6/8) Resource usage
SA2 meetings
Number of Sessions
Chart: 
| #118bis Jan | #119 Feb | #120 Mar | #121 May | #122 Jun | #122bis Aug | #123 Oct | #124 Nov | #125 Jan | #126 Feb | #127 Apr | #127bis May | #128 Jul | #128bis Aug | #129 Oct | #129bis Nov | #130 Jan | #131 Feb | #132 Apr | #133 May
maintenance | 5 | 6 | 6.7 | 6.5 | 6 | 3.4 | 5 | 3 | 4.5 | 3.8 | 4 | 4 | 1.5 | 1.2 | 3 | 1.5 | 0.9 | 0.9 | 2 | 0.9
R15 5GS / maintenance | 18 | 23 | 24 | 27 | 31 | 32.5 | 36 | 37 | 24 | 25 | 19 | 19 | 15 | 15 | 13.7 | 11.5 | 9 | 9.3 | 8.2 | 7.2
R15 other | 2.5 | 8.5 | 12.3 | 11.5 | 8.3 | 6.3 | 4 | 3
R16 work | 3.7 | 13.5 | 12 | 19.5 | 20 | 26.4 | 28.6 | 31.2 | 34.9 | 34.9 | 34.4 | 35.3 | 37.7
R15 exceptions | 1 | 1.3 | 1 | 0.2

## Slide 10: 1) General Aspects (7/8) Document Handling / Meeting
Number of Tdocs
Rel-12
Rel-11
Rel-13
Rel-14
Rel-15
Rel-16
Chart: 

## Slide 11: 1) General Aspects (8/8) SA2 Agreed CRs by Release / Meeting
Rel-12
Rel-11
Rel-14
Number of CRs
Rel-13
Note: for 5GS (draft) TSs agreed pCRs and for #125 also agreed/endorsed draft CRs are shown
Rel-15
Rel-16
Chart: 
| 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107+E | 108 | 109 | 110 | 110AH | 111 | 112 | 113 | 113AH | 114 | 115 | 116 | 116bis | 117 | 118 | 118bis | 119 | 120 | 121 | 122 | 122bis | 122e | 123 | 124 | 125 | 126 | 127 | 127bis | 128 | 128bis | 129 | 129bis | 130 | 131 | 132 | 133
r10 CR | 52 | 41 | 54 | 38 | 38 | 21 | 21 | 17 | 3 | 3 | 9 | 1 | 6 | 2 | 3 | 3 | 4 | 0 | 0 | 2 | 3 | 6 | 3 | 1 | 3 | 1 | 0 | 1 | 1 | 1
r11 CR | 2 | 3 | 12 | 16 | 7 | 31 | 26 | 23 | 105 | 71 | 53 | 45 | 18 | 27 | 20 | 20 | 19 | 17 | 10 | 7 | 4 | 5 | 5 | 0 | 6 | 3 | 1 | 1 | 1
r12 CR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 4 | 11 | 8 | 19 | 21 | 35 | 50 | 38 | 64 | 55 | 39 | 35 | 34 | 21 | 11 | 10 | 9 | 1 | 9 | 3 | 3 | 3 | 1
r13 CR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 10 | 19 | 13 | 14 | 6 | 9 | 56 | 25 | 58 | 73 | 41 | 11 | 35 | 29 | 25 | 25 | 9 | 11 | 2 | 5 | 2 | 4 | 2 | 5 | 3 | 1 | 1 | 1 | 1
r14 CR | 4 | 21 | 69 | 81 | 33 | 56 | 23 | 13 | 17 | 18 | 20 | 10 | 8 | 10 | 8 | 1 | 7 | 2 | 1 | 2 | 5 | 1
r15 PCR/draftCR | 63 | 126 | 117 | 121 | 171 | 214 | 62 | 287 | 328 | 182
r15 CR | 19 | 19 | 27 | 27 | 12 | 351 | 201 | 213 | 119 | 159 | 100 | 102 | 78 | 74 | 50 | 40
r16 CR | 2 | 3 | 66 | 133 | 117 | 233

## Slide 12: Contents
1) General aspects (events since SA#83, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2) Rel-15 Maintenance and Work
  2.3) Rel-16 and later Work and Maintenance
  2.4) New and Updated WIDs/SIDs and Exceptions
  2.5) IETF Dependency Update
3) Action Items
4) Documents for Information and Approval
5) Collected Items requiring action from SA
è

## Slide 13: 2.1) Rel-14 and before Maintenance (1/1)
Work Progress on Corrections (Category A CRs are not counted)
  R12: none
  R13: none
  R14: none

## Slide 14: Contents
1) General aspects (events since SA#83, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2 Rel-15 Maintenance and Work
  2.3) Rel-16 and later Work and Maintenance
  2.4) New and Updated WIDs/SIDs and Exceptions
  2.5) IETF Dependency Update
3) Action Items
4) Documents for Information and Approval
5) Collected Items requiring action from SA
è

## Slide 15: 2.2) Rel-15 Maintenance and Work (1/2)
WI | Work Item | WP | CRs approved
VoWLAN | Complementary Features for Voice services over WLAN | 100% | 
ProSe_WLAN_DD_Stage2 | Inclusion of WLAN direct discovery technologies as an alternative for ProSe direct discovery | 100% | 
NAPS | Northbound APIs for SCEF – SCS/AS Interworking | 100% | 2
eVoLP | enhanced VoLTE performance | 100% | 
USOS | Unlicensed spectrum offloading system enhancements | 100% | 
EDCE5 | EPC enhancements to support 5G New Radio via Dual Connectivity | 100% | 3
PS_Data_Off_Phase2 | PS Data Off Feature Phase 2 | 100% | 
EPS_URLLC | EPC support for E-UTRAN Ultra Reliable Low Latency Comm. | 100% | 
TEI15 | Maintenance for pre-Rel-15 features in Rel-15 |  | 4
TEI15 | Rel-15 Cat B/C alignments with other WGs or specifically required |  | 2

## Slide 16: 2.2) Rel-15 Maintenance and Work (2/2)
Progress since SA#83
  CRs agreed for TS 23.501 (20+10 CRs), TS 23.502 (20+23 CRs), TS 23.503 (3+3 CRs)
  (compare with Q1: CRs agreed for TS 23.501 (27+27 CRs), TS 23.502 (39+36 CRs), TS 23.503 (11+9 CRs))
  1 CR agreed for TS 23.401
  Maintenance effort decreases further. See also SA2 work planning sheet.
Next steps:
  Essential corrections, further aligning with the work from other WGs
WI | Work Item | WP |  | 
5GS_Ph1 | 5G System – Phase 1 | 100% |  | 

## Slide 17: Contents
1) General aspects (events since SA#83, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2) Rel-15 Maintenance and Work
  2.3) Rel-16 and later Work and Maintenance
  2.4) New and Updated WIDs/SIDs and Exceptions
  2.5) IETF Dependency Update
3) Action Items
4) Documents for Information and Approval
5) Collected Items requiring action from SA
è

## Slide 18: 2.3) Rel-16 and later Work and Maint. (1/23)
WI | Work Item | WP |  | 
PARLOS_SA2 | System enhancements for Provision of Access to Restricted Local Operator Services by Unauthenticated UEs | 95 > 100% |  | 
Progress since SA#83
  Concluded from SA2 perspective
  Some final question to RAN (WGs) on whether it is feasible to add an indicator for RLOS in RRC
RAN impacts or dependencies
  LS to RAN, RAN2/3 on feasibility of an RLOS indicator in RRC (S2-1906806 containing a CR that SA can approve if RAN answer is positive)
Next steps:
  Maintenance
  potential stage 2 update based on RAN feedback

## Slide 19: 2.3) Rel-16 and later Work and Maint. (2/23)
WI | Work Item | WP |  | 
FS_5WWC | Study on the Wireless and Wireline Convergence for the 5G system architecture | 100 > 100% |  | 
5WWC | Wireless and Wireline Convergence for the 5G system architecture | 50 > 85% |  | 
Progress since SA#83
  Specification of Trusted N3GPP network in TS23.501 and TS 23.502
  For W-5GAN specification (Registration and Connection Management, Session management, Identifiers, Protocol stack, Connection, Registration and Mobility Management procedures, Session Management procedures, User Profile management procedures)
  TS 23.316 provided for approval
  Exception requested for non-3GPP device and W-5GAN
RAN impact/dependency
  None identified
Next steps:
  Complete outstanding normative issues, when the requested exception is granted
  maintenance

## Slide 20
Progress since SA#83
  CRs on performance measurement to TS 23.50/23.502/23.503 were agreed
  CRs on MA-PDU Session establishment/modification and release call flow were agreed
  CRs on MA PDU QoS Aspect were agreed
  Traffic switching for GBR QoS flow was discussed, the agreed CRs may need further discussion
  Exception request on EPC IWK for MA-PDU session and Network based be-activation of UP for Non-3GPP
RAN impacts or dependencies
  None identified
Next steps
  Finalize outstanding aspects, when the exception is granted.
  Maintenance
2.3) Rel-16 and later Work and Maint. (3/23)
WI | Work Item | WP |  | 
FS_ATSSS | Study on Access Traffic Steering, Switch and Splitting support in the 5G system architecture | 100 > 100% |  | 
ATSSS | Study on Access Traffic Steering, Switch and Splitting support in the 5G system architecture | 45 > 85% |  | 

## Slide 21: 2.3) Rel-16 and later Work and Maint. (4/23)
WI | Work Item | WP |  | 
FS_eV2XARC | Study on architecture enhancements for 3GPP support of advanced V2X services (FS_eV2XARC) | 95 > 100% |  | 
eV2XARC | Architecture enhancements for 3GPP support of advanced V2X services (eV2XARC) | 30 > 75% |  | 
Progress since SA#83
  Last remaining study key issue, KI#15 (Enhancements to assist Application Adjustment) concluded.
  New TS 23.287 progressed and is provided for information
  CRs to TS 23.501/23.503 and pCR to TS 23.288 agreed.
  Exception requested for finalizing normative work.
RAN impacts or dependencies
  RAN: NR PC5 unicast/groupcast/broadcast (e.g. PC5 QoS details, PC5 Signalling for unicast), Cross-RAT PC5 control authorization in EPS, Combinations of Uu QoS characteristics values – One LS ask RAN1 for feedback
  SA3: PC5 unicast and groupcast security protection
Next steps
  Finalize normative work, when the requested exception is granted.
  Maintenance

## Slide 22: 2.3) Rel-16 and later Work and Maint. (5/23)
WI | Work Item | WP |  | 
FS_eNA | Study of enablers for Network Automation for 5G | 94 > 100% |  | 
eNA | enablers for Network Automation for 5G | 65 > 85% |  | 
Progress since SA#83
  Last remaining study KI#14 concluded
  Controversial normative issues resolved
  New TS 23.288 progressed and provided for approval
RAN impacts or dependences:
  Feedback from RAN3 on input data on Performance Measurements relevant to determine User Data Congestion Analytics
Next steps:
  Finalise normative work by resolve the open issues, which are mostly related to alignment between SA2 and SA5/RAN3
  maintenance

## Slide 23: 2.3) Rel-16 and later Work and Maint. (6/23)
WI | Work Item | WP |  | 
FS_CIoT_5G | Study on Cellular IoT support and evolution for the 5G System | 95 > 100% |  | 
CIoT_5G | Cellular IoT support and evolution for the 5G System | 50 > 95% |  | 
Progress since SA#83
  Concluded last remaining study key issue 2 (Frequent small data communication)
  Almost all features normatively documented in both TS 23.501 and TS 23.502
  Outstanding issues (see also work item exception): support of EDT for 5GS UP optimization and support of LTE-M identification in 5GC
RAN impacts or dependencies
  Support of NB-IoT/eMTC connected to 5GC: impacts due to Data over NAS and UP optimization, MO/MT EDT, eDRX, Inter-UE QoS for DoNAS, Enhanced Coverage, Expected UE behavior signaling to RAN, signaling of CIoT feature support, LTE-M identification
Next steps
  Complete outstanding issues, if exception is granted
  maintenance

## Slide 24: 2.3) Rel-16 and later Work and Maint. (7/23)
WI | Work Item | WP |  | 
FS_ETSUN | Study on Enhancing Topology of SMF and UPF in 5G Networks | 100 > 100% |  | 
ETSUN | Enhancing Topology of SMF and UPF in 5G Networks | 45 > 90% |  | 
Progress since SA#83
  Set of CR(s) to 23.501/502 agreed. No impact to 23.503 / charging / security
  No specific issue identified
RAN impacts or dependencies
  None identified
Next steps:
  Maintenance

## Slide 25: 2.3) Rel-16 and later Work and Maint. (8/23)
WI | Work Item | WP |  | 
FS_eLCS | Study on Enhancement to Service Based Architecture for Location Services | 100 > 100% |  | 
5G_eLCS | Enhancement to Service Based Architecture for Location Services | 45 > 85% |  | 
Progress since SA#83:
  Normative Work progressed (NF services, Procedures, Information Storages, GMLC selection, UE privacy, Bulk operation, EPS-5GC interconnection for common interface, …)
  New TS 23.273 reaches 85% and is provided for one step approval
  Exception requested
RAN impacts or dependencies:
  LS from RAN WG2 on “broadcast assistance data delivery” received. No progress in SA2.
Next steps:
  Completion of the work described in the exception request, if granted.
  Work on “broadcast assistance data delivery” and reply to RAN WGs
  Maintenance

## Slide 26: 2.3) Rel-16 and later Work and Maint. (9/23)
WI | Work Item | WP |  | 
FS_RACS | Study on optimisations on UE radio capability signalling | 100 > 100% |  | 
RACS | Optimisations on UE radio capability signalling | 0 > 90% |  | 
Progress since SA#83
  CRs to TS 23.501, TS 23.401 and TS 23.502 approved by SA2 document most RACS functionality and procedures for 5GS and EPS
  Some outstanding issues. (no WG agreed exception request version after email approval)
RAN impacts or dependencies
  As per SA2 agreed CRs
Next steps:
  Complete outstanding issues (also depending on exception request, which is expected as company input to SA)
  Maintenance

## Slide 27: 2.3) Rel-16 and later Work and Maint. (10/23)
WI | Work Item | WP |  | 
FS_Vertical_LAN | Study on 5GS Enh. support of Vertical and LAN Services | 92 > 100% |  | 
Vertical_LAN | 5GS Enhanced support of Vertical and LAN Services | 43 > 90% |  | 
Progress since SA#83
  Last remaining aspect of the study concluded.
  5G-LAN (100%) – progressed with DNN to 5G VN Group mapping, 5G VN group management, optimized data routing between UEs via UPFs (without DNN), …
  NPN (100%) - progressed with network (RAN) sharing by NPN/PLMN, emergency services support in Public Network integrated NPN, UAC related aspects, …
  TSC (70%) - progressed with concept level agreements on Time Sync, QoS assistance information, 5GS Bridge delay estimation, Bridge management with CNC, parameters exchanged with the UE and concepts related to integration of 5GS with IEEE TSN network. Main pending items (exception requested) are updates to procedures and policy specification based on agreed concepts.
RAN impacts or dependencies (following items may lead to impacts/dependencies)
  potential interaction with RAN and handling impacts due to potential LS from RAN
Next steps
  Finalize normative TSC work described in the exception request, if granted
  Maintenance

## Slide 28: 2.3) Rel-16 and later Work and Maint. (11/23)
WI | Work Item | WP |  | 
FS_5G_URLLC | Study on enhancement of URLLC supporting in 5GC | 90 > 95% |  | 
5G_URLLC | Enhancement of URLLC supporting in 5GC | 50 > 80% |  | 
Progress since SA#83
  Concluded remaining study key issue (KI#2): Supporting low latency and low jitter during handover
  Progressed normative work by refining/endorsing solutions for the concluded key issues to TSs 23.501/502/503
RAN impacts or dependencies (following items may lead to impacts/dependencies)
  Remaining study KI#7: Automated GBR service recovery; LS replies from RAN2/RAN3 has been discussed in SA2 but no agreement achieved yet on the conclusion, further analysis and potentially exchange with RAN are expected.
Next steps
  Finalize work as described in exception request, if granted :
    Conclude remaining open KI#7. Automatic GBR service recovery after handover”. Conduct related normative work.
    Finalize endorsed CRs on key issue “QoS monitoring” depending on LS reply from RAN WG3.
  Maintenance

## Slide 29: 2.3) Rel-16 and later Work and Maint. (12/23)
WI | Work Item | WP |  | 
FS_eSBA | Study on Enhancements to the Service-Based 5G System Architecture | 100 > 100% |  | 
5G_eSBA | Enhancements to the Service-Based 5G System Architecture | 50 > 80% |  | 
Progress since SA#83
  CRs agreed on aspects such as further completion & clarification on direct/indirect communication and NF/NF Service Set, update of network reliability, descriptions of context transfer, implementation of SCF
  Exception request as potential company contribution
RAN impacts or dependencies
  None identified
Next steps:
  Completion of NF Service context transfer and/or delegated SMF discovery based on SCP, depending on any potential exception
  Maintenance

## Slide 30: 2.3) Rel-16 and later Work and Maint. (13/23)
WI | Work Item | WP |  | 
FS_eNS | Study on Enhancement of Network Slicing | 100 > 100% |  | 
eNS | Enhancement of Network Slicing | 60 > 100% |  | 
Progress since SA#83
  Introduction of Slice-Specific Authentication and Authorization
  Finalization of the feature specification
  Some maintenance CRs
RAN impacts or dependencies
  None identified
Next steps:
  maintenance

## Slide 31: 2.3) Rel-16 and later Work and Maint. (14/23)
WI | Work Item | WP |  | 
FS_UDICoM | Study on User data interworking, Coexistence and Migration | 100 > 100% |  | 
UDICoM | User data interworking, Coexistence and Migration | 100 > 100% |  | 
Progress since SA#83
  Based on the updated SID and with the relevant content from TR 23.732 a new TR 23.973 containing all aspects that are suitable as deployment guidelines
  Potential company input for approving TR 23.973
RAN impacts or dependencies
  None identified
Next steps:
  maintenance

## Slide 32: 2.3) Rel-16 and later Work and Maint. (15/23)
WI | Work Item | WP |  | 
FS_5GSAT_ARCH | Study on architecture aspects for using satellite access in 5G | 50 > ?% |  | 
Progress since SA#83
  5 P-CRs on updating key issues, solutions an evaluations
RAN impacts or dependencies:
  To be determined
Next steps:
  The study is scheduled for completion next quarter.

## Slide 33: 2.3) Rel-16 and later Work and Maint. (16/23)
WI | Work Item | WP |  | 
FS_ENTRADE | Study on encrypted traffic detection and verification | 70 > 70% |  | 
Progress since SA#83
  For a few quarters no work conducted as not determined as focus area by TSG SA
  SID updated to reduce the scope and extending the timeline to June 2019.
Next steps:
  to be determined by TSG SA
  no continuation with a SID update or otherwise proposed
  proposed to be stopped

## Slide 34: 2.3) Rel-16 and later Work and Maint. (17/23)
WI | Work Item | WP |  | 
xBDT | 5GS Transfer of Policies for Background Data Transfer | 0 > 100% |  | 
Progress since SA#83
  Normative work completed with 5 CRs:
    TS 23.503 – Validation Condition and PDU session management for Validation Condition
    TS 23.502 – New service operation (Nnef_ApplyPolicy) defined and related procedures updated
    TS 23.501 - Alignment with TS 23.502 added
RAN impacts or dependencies
  None identified
Next steps:
  maintenance

## Slide 35: 2.3) Rel-16 and later Work and Maint. (18/23)
WI | Work Item | WP |  | 
FS_eIMS5G | Study on Enhanced IMS to 5GC Integration | 70 > 70% |  | 
eIMS5G_SBA | Enhanced IMS to 5GC Integration | 0 > 100% |  | 
Progress Since SA#83
  The objective related to service-based interfaces was prioritized at SA #82; Conclusions reached for Key Issues 5, 6 and 7 (presented at SA #83) and no further work expected to these Key Issues.
  Revised FS_eIMS5G provided for approval for work on the other key issues in Rel-17.
  The work resulting from the Rel-16 study conclusions was conducted under eIMS5G_SBA and completed at SA2 #133. The related CRs are provided for approval.
RAN Impacts or Dependencies
  No RAN dependencies identified.
Next Steps
  maintenance

## Slide 36: 2.3) Rel-16 and later Work and Maint. (19/23)
WI | Work Item | WP |  | 
FS_LLC_Mob | Study on EPC support for Mobility with Low Latency Communication | 75 > 75% |  | 
Progress since SA#83
  For a few quarters no work conducted as not determined as focus area by TSG SA
RAN impacts or dependencies
  None identified
Next steps:
  to be determined by TSG SA
  no continuation with a SID update or otherwise proposed
  proposed to be stopped

## Slide 37: 2.3) Rel-16 and later Work and Maint. (20/23)
WI | Work Item | WP |  | 
FS_AAI_LTE_NR | Study on Application Awareness Interworking between LTE and NR | 30 > 30% |  | 
Progress since SA#83
  For a few quarters no work conducted as not determined as focus area by TSG SA
  A SID update for Rel-17 timeframe is WG approved with an objection to one of the objectives
Next steps:
  Revised SID is submitted for approval by TSG SA

## Slide 38: 2.3) Rel-16 and later Work and Maint. (21/23)
WI | Work Item | WP |  | 
FS_EPS_URACE | Study on enhancement of systems using EPS for Ultra Reliability and Availability using commodity equipment | 10 > 10% |  | 
Progress since SA#83
  No work conducted as not determined as focus area by TSG SA
RAN impacts or dependencies
  High availability by redundant transmission in UP between UE/RAN and CN (may impact cell reselection and handover target selection)
  Notification control for GBR bearers
Next steps:
  to be determined by TSG SA
  no continuation with a SID update or otherwise proposed
  proposed to be stopped

## Slide 39: 2.3) Rel-16 and later Work and Maint. (22/23)
WI | Work Item | WP |  | 
TEI16 | Technical Enhancements and Improvements Rel-16, small Rel-16 work items (WI & CRs approved together) | n.a. |  | 
  WID on Reliable Data Service Serialization Indication. WG-approved. Normative Work also completed with 3 CRs for TS 23.682, TS 23.501 and TS 23.502.
  WID on S6b Optional for ePDG connected to 5GS. WG-approved. Normative Work also completed with 2 CRs for TS 23.501 and TS 23.502.
  TEI16 Dedicated Bearers for Ethernet in EPC, WG-approved with 5 CRs for 23.060, 23.401, 23.221 and 23.502
  TEI16 Support of multiple EATF instances in Emergency SRVCC procedures, WG-approved with 1 CR for 23.237
  TEI16 Enhancement of Monitoring Event configuration, WG-approved with 1 CR for 23.682
  TEI16 PCF selection for PDU sessions with same DNN and S-NSSAI, WG-approved with 2 CRs for 23.501 and 23.503
Next steps:
  maintenance

## Slide 40: 2.3) Rel-16 and later Work and Maint. (23/23)
WI | Work Item | WP | CRs approved
TEI16 | Maintenance for pre-Rel-16 features in Rel-16 specs only |  | 53
TEI16 | Rel-16 Cat B/C for alignments with other WG’s work |  | 9

## Slide 41: Contents
1) General aspects (events since SA#83, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2) Rel-15 Maintenance and Work
  2.3) Rel-16 and later Work and Maintenance
  2.4) New and Updated WIDs/SIDs and Exceptions
  2.5) IETF Dependency Update
3) Action Items
4) Documents for Information and Approval
5) Collected Items requiring action from SA
è

## Slide 42: 2.4) New and Updated WIDs/SIDs and Exceptions - 1
New and revised SID/WID:
  Rel-16 New Work Item on Reliable Data Service Serialization Indication
  Rel-16 New WID on S6b Optional for ePDG connected 5GS
  Revised SID on System enhancement for Proximity based Services in 5GS
  Revised SID on Application Awareness Interworking between LTE and NR
  Revised SID on system architecture for next generation real time communication services
  Revised SID on Enhanced IMS to 5GC Integration
  New WID on supporting Flexible Local Area Data Network
  New WID on 5G System Enhancement for Advanced Interactive Services
  New SID on the Usage of User Identifiers in the 5G System
  New SID on Enablers for Network Automation for 5G - phase 2
  New SID on Enhancement to the 5GC LoCation Services - Phase 2
  New SID on Enhancement of 5G UE Policy
  New SID on Architectural enhancements for 5G multicast-broadcast services
  New SID on enhanced support of Non-Public Networks
  New SID on enhancement of support for 5G LAN-type service

## Slide 43: 2.4) New and Updated WIDs/SIDs and Exceptions - 2
Exception requests:
  Exception request for Vertical_LAN
  Exception request for ATSSS
  Exception request for eV2XARC
  Exception request for eLCS
  Exception request for 5WWC
  Exception request for 5G_CIoT
  Exception request for 5G_URLLC

## Slide 44: Contents
1) General aspects (events since SA#83, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2) Rel-15 Maintenance and Work
  2.3) Rel-16 and later Work and Maintenance
  2.4) New and Updated WIDs and SIDs
  2.5) IETF and External SDO Normative Reference Update
3) Action Items
4) Documents for Information and Approval
5) Collected Items requiring action from SA
è

## Slide 45: 2.5) IETF and External SDO Normative Reference Update (1/1)

## Slide 46: Contents
1) General aspects (events since SA#83, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2) Rel-15 Maintenance and Work
  2.3) Rel-16 and later Work and Maintenance
  2.4) New and Updated WIDs and SIDs
  2.5) IETF Dependency Update
3) Action Items
4) Documents for Information and Approval
5) Collected Items requiring action from SA
è

## Slide 47: Contents
1) General aspects (events since SA#83, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2) Rel-15 Maintenance and Work
  2.3) Rel-16 and later Work and Maintenance
  2.4) New and Updated WIDs and SIDs
  2.5) IETF Dependency Update
3) Action Items
4) Documents for Information and Approval
5) Collected Items requiring action from SA
è

## Slide 48: 4) Documents for Information and Approval
Presentation for Information
  TS 23.287 "Architecture enhancements for 5G System (5GS) to support Vehicle-to-Everything (V2X) services"
Presentation for Approval
  TS 23.273 "5G System Location Services (LCS)"
  TS 23.316 "Wireless and wireline convergence access support for the 5G System (5GS)"
  TS 23.288 "Architecture enhancements for 5G System (5GS) to support network data analytics services"

## Slide 49: Contents
1) General aspects (events since SA#83, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2) Rel-15 Maintenance and Work
  2.3) Rel-16 and later Work and Maintenance
  2.4) New and Updated WIDs and SIDs
  2.5) IETF Dependency Update
3) Action Items
4) Documents for Information and Approval
5) Collected Items requiring action from SA
è

## Slide 50: 5) Collected Items requiring action from SA
    Approval of proposed/updated WIDs
    Approval of provided TSs
    Approval of exception requests
    Consider stopping studies: FS_LLC_Mob, FS_EPS_URACE, FS_ENTRADE
    In addition FS_FLADN should be stopped. It never started as a study. And is now provided as a work item.

## Slide 51
Thank You!