## Slide 1: Initial views on Rel-18
MediaTek Inc.
3GPP TSG SA Workshop on Rel-18 TDOC SP-210650
September 2021 Agenda Item 3

## Slide 2: Outline
Timeline
Priorities for Rel-18

## Slide 3: Timeline [1/2]
3GPP to deliver stable releases in a timely predictable manner
Careful release planning required for:
  Content
  Timing
  Release transition: often overlooked
Stabilizing Rel-17 is of utmost priority before 3GPP resources shift to Rel-18
Proposal 1: Stage 2 Rel-18 technical work to start in Q1
Proposal 2: 15 months* Stage 2 from start to freeze (not from freeze to freeze) **18 months otherwise
 | Rel-17 | Rel-18 “normal” | Proposal Rel-18 “+3mo”
Stage 2 (SA2) | Jun 2021** | Dec 2022 | Jan 2022 – Mar 2023
PHY | Dec 2021 | Jun 2023 | Mar 2022 – Sep 2023
L3/Core | Mar 2022 | Sep 2023 | Jun 2022 – Dec 2023
ASN.1 | Jun 2022 | Dec 2023 | Mar 2024
RAN4 perf | Sep 2022 | Mar 2024 | Jun 2024
** 14 exception sheets. Q3/Q4 full with Rel-17 |  |  | 
2021 | 2022 |  |  |  | 2023 |  |  |  | 2024 | 
Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
Buffer | System Architecture Stage 2 |  |  |  |  |  |  |  |  | 
 | Buffer | Stage 3 PHY |  |  |  |  |  |  |  | 
 |  | buffer | Stage 3 Others |  |  |  |  |  | ASN.1 | Perf

## Slide 4: Timeline [2/2]
2021 | 2022 |  |  |  | 2023 |  |  |  | 2024 | 
Q4 #94 | Q1 #95 | Q2 #96 | Q3 #97 | Q4 #98 | Q1 #99 | Q2 #100 | Q3 #101 | Q4 #102 | Q1 #103 | Q2 #104
Rel-17 PHY |  |  |  |  |  |  |  |  |  | 
Rel-17 Stage 3 Others |  | Rel-17 ASN.1 | Rel-17 Perf |  |  |  |  |  |  | 
 |  | No Rel-18 interference |  |  |  |  |  |  |  | 
6mo buffer | Rel-18 System Architecture Stage 2 [15 months] |  |  |  |  |  |  |  |  | 
 | 3mo buffer | Rel-18 Stage 3 PHY [18 months] |  |  |  |  |  |  |  | 
 |  | 3mo buffer | Rel-18 Stage 3 Others [18 months] |  |  |  |  |  | Rel-18 ASN.1 | Rel-18 Perf.
Rel-18 Package (SA2/RAN)
9 months

## Slide 5
IIoT
Distributed config model for TSN
RedCap enh.
eDRX>10.24s in RRC Inactive
(RAN alignment if needed)
NTN IoT
Mobility (RAN alignment)
5GC connectivity (if needed)
R17 leftovers
NTN NR
Regenerative arch.
MBS
R17 leftovers
Sidelink Relay
U2U relay
mPath, mHop
Full Mobility (Remote, Relay)
AI/ML traffic
Function of Stage 1 requirements (QoS, Arch)
(NR) MBS
TV (ATSC3.0 ref)
QoS+ (Tput, reliab.)
XR/CG (LLeMBB)
QoS enhancements (frame-based)
Mutual awareness App/5GS
X-layer optimization
Congestion handling e.g. L4S
eMBB consumer
NW Topology
NTN Evolution
Long-term explor.
Common tech.
Verticals
UE Policy
URSP provisioning w/V-PCF (roaming)
URSP enforcement
Misc. enh. incl. provisioning triggers (e.g. UE req), distribution
3GPP TSG SA#93e Rel-18 Workshop – MediaTek Inc.
eNPN 2
Equivalent SNPNs
Localized services

## Slide 6: Thank You!