## Slide 1: FS_SOBOT Status Update Study on Network of Service Robots with Ambient Intelligence
Ki-Dong Lee
LG Electronics
FS_SOBOT Rapporteur
3GPP TSG-SA WG1 Meeting #100
Electronic Meeting, Nov 14 – Nov 18, 2022
Notes: 1

## Slide 2: FS_SOBOT Progress
Progress made at this meeting
  Use case template
  Two use cases
Study Item Completion: 40%
Controversial issues
  None
Notes: 1

## Slide 3: FS_SOBOT Planning
Planning for subsequent meetings
  SA1#101e (Feb 2023): 70%
    Overview section, etc.
    Collect Use cases that are and/or are not covered by the existing robot-communication related requirements
    Updated/Additional Use cases and potential requirements
    Send TR to SA for information
  SA1#102e (May 2023): 100%
    Conclusions, TR corrections/clean-up
    Send TR to SA for Approval
Notes: 1

## Slide 4: Work plan between meetings
Email coordination
  Coordination among interested/contributing companies, about planned inputs, use cases, etc.
  Before each SA1 meeting
  To be moderated by the rapporteur
Conference calls
  TBD (upon need)
Notes: 1

## Slide 5: FS_SOBOT Completion Date
Current expected completion dates:
  For information: SA#99 (03/2023)
  For approval: SA#100 (06/2023)
Have these dates been changed at this meeting? n
  If yes, previous target completion dates:
    N/A
Notes: 1

## Slide 6: FS_SOBOT History
SI agreed at SA1#98e, approved at SA#96
  Approved SID is in Tdoc SP-220447
History of completion rates
  SA1#99e: 10%
  SA1#100: 40%
Notes: 1